## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate |  |  |  | FINANCIAL CLOSE CERTIFICATE
Project Name: | 1 Bolt Ave
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Certificate - Planning
Emergent Energy – Planning Phase Completion Certificate |  |  |  | PLANNING CERTIFICATE
Project Name: | 1 Bolt Ave
Client Representative:
Programme Manager: | Roedolph Venter
Project Manager: | Peet Verreynne
Project Engineer:
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Project Introduction Presentation
Project Brief
Engineering Pack
BOQ
PO – Material & Equipment
PO - Contractors
HSE – NOC
HSE – EE File
HSE – Contractor File
SSEG Application
Risks / Notes
Acknowledgement and Acceptance:
Role | Name | Signature | Date

## Change Register
Change Register
ID | Description | Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## BOQ
Item | Supplier | Description | Quantity | Comments
PV Module
Mounting Structure
DC Cable Red & Black
Inverters
Current Transformers (Production)
Current Transformers (Consumption)
Solar Production Meter
Solar Consumption Meter
Wi-Fi Router & Sim
Switch
Back Up Battery
PVDB
Supplier List
Accuenergy
Krannich
Menlo
Red Pole
Schletter
Switchboard
Techsitter

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW |  |  |  | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 3283810.55 |  | 3377404.75 |  |  |  | Start Date |  |  |  | 3283810.5496 | 2217962.1719 | 3192804.2084 | 2169914.54
2 | Planned Expenditure | 2763016.5281 |  | 2217962.1719 | VO PM Limit | Current VO Total
3 | Planned Profit | 520794.0219 |  | 1159442.5781 | 26039.7011 | 0 |  | End Date - PC
4 | Planned Margin | 15.86% |  | 34.33%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE REQUIREMENTS & COMMENTS | MILESTONE DOCUMENTS RECEIVED
1 | Acceptance and Initial Deposit |  | 35% | 1149333.6925 |  | 2025-09-08 | 004830 | 2025-09-04 | 2025-09-05 |  | TRUE |  |  |  |  | 1900-01-06
2 | Delivery of Panels |  | 30% | 985143.165 |  | 2025-10-21 | 004853 | 2025-10-20 | 2025-10-21 |  | TRUE
3 | Delivery of Inverters |  | 20% | 656762.11 |  | 2025-10-21 | 004853 | 2025-10-20 | 2025-11-10 |  | TRUE
4 | Practical Completion |  | 10% | 328381.055 |  | 2025-11-25 | 004907 | 2025-12-24 | 16/01/2026 |  | TRUE
5 | Handover |  | 5% | 164190.5275 |  | 2025-12-04 |  |  | 2026-02-18 | awaiting HO meeting date | TRUE
6 | Client VO - Walkways |  | 0% | 93594.2 |  | 2025-11-25 | 004908 | 2025-12-24 | 16/01/2026 |  | TRUE
7 | - |  | 0% | 0 | [6 empty] | FALSE
|  |  | 100% | 3377404.75
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 1182091.6625
2 | Delivery of Panels |  | 30% | 1013221.425
3 | Delivery of Inverters |  | 20% | 675480.95
4 | Practical Completion |  | 10% | 337740.475
5 | Handover |  | 5% | 168870.2375
| Total |  | 100% | 3377404.75
|  |  | 100% | 3377404.75
Note on P17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Johannes Potgieter is a soft handover not an option here, so we able to move the payment date up?

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC | Approved | DOL
7.1 Agreement | Approved | EE
13.2 Agreement | Approved | EE
EE File | Approved | Client
Subbie File | Approved | Client
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application | In Process |  |  | Awaiting signed BQ, ESA, LPU from client
PTI | In Process |  |  | NERSA letter from ESKOM
Commissioning Approval
NERSA Registration

## Project Plan
[9 empty] | 2026-02-03 | 2026-02-03
| PROJECT PLAN | 1 Bolt Ave |  |  | Net Work Days |  | 71 |  | 0 | 1
| PROJECT SIZE (kWp) | 366 |  |  | Total Weeks |  | 14.2
| PROJECT DEVELOPER | Peet Verreynne |  |  | kW/Week Installation Rate |  | 25.7746
| PROJECT MANAGERS | Peet Verreynne
| CONTRACT VALUE | 3283810.55
| Phase: | Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Status | Comment
|  |  | 35 |  |  | 101 |  | 96% | 95.4%
1 | Project Initiation | 2025-09-09 | 30 | 2025-10-09 | 2025-09-09 | 43 | 2025-10-22 | 100% | 100%
1.1 | BD Handover | 2025-09-09 | 1 | 2025-09-10 | 2025-09-09 | 1 | 2025-09-10 | 100% | 100% |  | Milestone | Start Date | Duration | End Date | 2026-02-03 | 2026-02-03
1.2 | Project Introduction | 2025-09-30 | 1 | 2025-10-01 | 2025-09-30 | 1 | 2025-10-01 | 100% | 100% |  | Project Initiation | 2025-09-09 | 43 | 2025-10-22 | 1 | 0
1.3 | HSE | 2025-09-30 | 7 | 2025-10-09 | 2025-10-16 | 7 | 2025-10-22 | 100% | 100% | Meeting with Client HSE was today 22/10/2025 | Site Establishment | 2025-10-14 | 1 | 2025-10-15
1.4 | Installer Kick Off | 2025-09-30 | 1 | 2025-10-01 | 2025-09-30 | 1 | 2025-10-01 | 100% | 100% |  | AC Installation | 2025-09-30 | 62 | 2025-12-01
1.5 | Project Review | 2025-10-07 | 1 | 2025-10-08 | 2025-10-07 | 1 | 2025-10-08 | 100% | 100% |  | DC Works | 2025-10-14 | 62 | 2025-12-15
[11 empty] | Module installation | 2025-10-14 | 62 | 2025-12-15
2 | Site Establishment | 2025-10-14 | 1 | 2025-10-15 | 2025-10-14 | 1 | 2025-10-15 | 100% | 100% |  | Commissioning | 2025-12-15 | 39 | 2026-01-23
2.1 | Solar Contractor Establishment | 2025-10-14 | 1 | 2025-10-15 | 2025-10-14 | 1 | 2025-10-15 | 100% | 100% |  | QA Inspections | 2026-01-21 | 1 | 2026-01-22
[11 empty] | Project Closure | 2026-01-22 | 22 | 2026-02-13
3 | AC Installation | 2025-09-30 | 42 | 2025-11-11 | 2025-09-30 | 62 | 2025-12-01 | 100% | 100%
3.1 | Inverters delivered | 2025-10-14 | 1 | 2025-10-15 | 2025-10-14 | 1 | 2025-10-15 | 100% | 100%
3.2 | Inverters Mounted | 2025-10-22 | 2 | 2025-10-24 | 2025-10-29 | 2 | 2025-10-31 | 100% | 100% | Waiting on iverter rack + 7
3.3 | Solar DB Lead Time | 2025-09-30 | 25 | 2025-11-04 | 2025-09-30 | 33 | 2025-11-14 | 100% | 100%
3.4 | AC Works | 2025-11-04 | 5 | 2025-11-11 | 2025-11-09 | 15 | 2025-11-28 | 100% | 100%
3.5 | AC Tie-In | 2025-11-04 | 1 | 2025-11-05 | 2025-11-28 | 1 | 2025-12-01 | 100% | 100%
4 | DC Works | 2025-10-14 | 31 | 2025-11-14 | 2025-10-14 | 62 | 2025-12-15 | 96.55% | 96.55%
4.1 | Mounting Structure delivered | 2025-10-14 | 1 | 2025-10-15 | 2025-10-14 | 1 | 2025-10-15 | 100% | 100%
4.2 | Mounting Structure installation | 2025-10-15 | 6 | 2025-10-23 | 2025-10-15 | 19 | 2025-11-11 | 100% | 100% | Roof inspection and fixes caused + 3 days
4.3 | DC Cable delivered | 2025-10-14 | 1 | 2025-10-15 | 2025-10-14 | 1 | 2025-10-15 | 100% | 100%
4.4 | DC Stringing | 2025-11-02 | 10 | 2025-11-14 | 2025-12-04 | 8 | 2025-12-15 | 100% | 100%
5 | Module installation | 2025-10-14 | 22 | 2025-11-05 | 2025-10-14 | 62 | 2025-12-15 | 100% | 100%
5.1 | Module delivery | 2025-10-14 | 1 | 2025-10-15 | 2025-10-14 | 1 | 2025-10-15 | 100% | 100%
5.2 | Module mounting | 2025-10-23 | 9 | 2025-11-05 | 2025-12-02 | 9 | 2025-12-15 | 100% | 100%
6 | Commissioning | 2025-11-14 | 4 | 2025-11-18 | 2025-12-15 | 39 | 2026-01-23 | 100% | 100%
6.1 | Commissioning | 2025-11-14 | 1 | 2025-11-17 | 2025-12-15 | 5 | 2025-12-23 | 100% | 100%
6.2 | Practical Completion | 2025-11-17 | 1 | 2025-11-18 | 2026-01-22 | 1 | 2026-01-23 | 100% | 100%
7 | QA Inspections | 2025-11-14 | 5 | 2025-11-19 | 2026-01-21 | 1 | 2026-01-22 | 100% | 100%
7.1 | Red-Team Inspection | 2025-11-14 | 3 | 2025-11-19 | 2026-01-21 | 1 | 2026-01-22 | 100% | 100%
8 | Project Closure | 2025-11-18 | 16 | 2025-12-04 | 2026-01-22 | 22 | 2026-02-13 | 71.43% | 66.66%
8.1 | Equipment serial numbers | 2025-11-19 | 1 | 2025-11-20 | 2026-01-27 | 2 | 2026-01-29 | 100% | 100%
8.2 | Snags completion | 2025-11-19 | 5 | 2025-11-26 | 2026-01-22 | 3 | 2026-01-27 | 100% | 100%
8.3 | System Performance Monitoring | 2025-11-18 | 5 | 2025-11-25 | 2026-01-23 | 3 | 2026-01-28 | 100% | 100%
8.4 | Handover documentation | 2025-11-26 | 1 | 2025-11-27 | 2026-01-27 | 2 | 2026-01-29 | 100% | 100%
8.5 | Handover to Client | 2025-11-27 | 1 | 2025-11-28 | 2026-02-10 | 1 | 2026-02-11 | 0% | 0%
8.6 | Handover to Matriarch | 2025-11-27 | 5 | 2025-12-04 | 2026-02-10 | 3 | 2026-02-13 | 0% | 0% | Date TBC
Formulas:
Planned Start = MIN([Planned Start, row below]:E16)
Planned Start = [Planned Start, row above]
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = WORKDAY.INTL([Actual End, row above],0,1,Data!$C3:C14)+7+7
Actual End = MAX([Actual End, row below]:K16)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C14)
Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 2763016.5281 |  | 2217962.1719 | 545054.3562
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 838063 |  | 706622.74 | 131440.26
2 | 2. Inverters | 210000 |  | 195738 | 14262
3 | 3. Mounting Structures | 146400 |  | 69250 | 77150
4 | 4. DC Equipment | 286300 |  | 257154.9 | 29145.1
5 | 5. Monitoring | 49000 |  | 44864.75 | 4135.25
6 | 6. AC Equipment | 497053.5957 |  | 247722.28 | 249331.3157
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 208000 |  | 226006.5 | -18006.5
9 | 9. AC & DC installation | 291000 |  | 321250 | -30250
10 | 10. Site Logistics | 76945.4667 |  | 92395.69 | -15450.2233
11 | 11. Due Dilligence | 109300 |  | 14750 | 94550
12 | 12. BDP Commission | 13353.69 |  | 0 | 13353.69
13 | 13. Engineering | 31300.7758 |  | 41047.6319 | -9746.8561
14 | 14. General Expenses | 6300 |  | 1159.68 | 5140.32
15 | 15. Service Add On | 0 |  | 0 | 0
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 2763016.5281 | 3283810.5522 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 2217962.1719
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FORECASTED PAYMENT DATE | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 838063 | 2025-12-13 | 838063 | 1022028.0488 |  | 1 | 1. Panels | Panels Budget - Assume 610W - Longi 610 (Krannich) | 600 | 1128.5 | 677100 |  | Krannich - 15-10014113 | 2025-10-31 | 982465.7171 | 0 | 2025-12-18 | 706622.74
1 |  | Delivery Budget | [7 empty] | 1 | 1. Panels | EPR Fees |  |  | 14365.74 |  | Krannich - 15-10014113 | 2025-10-31 | 20844.5533 |  | 2025-12-18
1 | [9 empty] | 1 | 1. Panels | Delivery |  |  | 12900 |  | Krannich - 15-10014113 | 2025-10-31 | 18717.7784 |  | 2025-12-18
1 | [9 empty] | 1 | 1. Panels | Panels from stock (Ziegler) | 2 | 1128.5 | 2257 |  | Allocated from Cpt Storeroom | 2025-12-31 | 0 |  | 2025-12-31
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 497053.5957
2 | Inverters | Inverter Budget |  |  | 210000 | 2025-12-13 | 210000 | 256097.561 |  | 2 | 2. Inverters | Huawei 100KTL (Krannich) | 3 | 65246 | 195738 |  | Krannich - 15-10014113 | 2025-10-31 | 256097.561 | 0 | 2025-12-18 | 195738 | DC Equipment | 169260
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | AC Labour | 91500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 199500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 22285.4667
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 2960
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 146400 | 2025-11-13 | 146400 | 178536.5854 |  | 3 | 3. Mounting Structures | Schletter Structure |  |  | 69250 | PO4324-BOLT-20250925 - RV Approved | Schletter - INV2244 | 2025-09-30 | 178536.5854 | 0 | 2025-10-30 | 69250 | Other | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Total | 991059.0623
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Less 15% | 842400.203
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | R/Wp | 2.3016
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL | Installer Price
[23 empty] | AC Equipment | 116890.33
4 | DC Equipment | DC Cable Budget | 9614 |  | 117040 | 2025-12-13 | 286300 | 349146.3415 |  | 4 | 4. DC Equipment | DC Cable - Menlo SO0003713 | 8000 | 13.65 | 109200 |  | Menlo - INV0003329 | 2025-10-31 | 148263.8693 | 0 | 2025-12-12 | 257154.9 | DC Equipment | 147954.9
4 |  | DC Equipment Budget |  |  | 169260 | 2025-12-13 |  |  |  | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | AC Labour | 93937.5
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | DC Labour | 227312.5
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | OffLoading | 12000
4 | [9 empty] | 4 | 4. DC Equipment | Project Kick Off | 147954.9 | 15% | 22193.235 | PO4349-BOLT-20251001 - RV Approved | Leading Edge - INV-0158 | 2025-10-31 | 30132.3708 |  | 2025-10-09 |  | Storage | 11440
4 | [9 empty] | 4 | 4. DC Equipment | Site Establishment |  | 15% | 22193.235 |  | Leading Edge - INV-0159 | 2025-10-31 | 30132.3708 |  | 2025-10-09 |  | Geda | 37455.8
4 | [9 empty] | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 29590.98 |  | Leading Edge - INV-0172 | 2025-11-30 | 40176.4944 |  | 2025-12-08 |  | Travel | 19549.89
4 | [9 empty] | 4 | 4. DC Equipment | DC Installation Complete |  | 20% | 29590.98 |  | Leading Edge - INV-0176 | 2025-12-31 | 40176.4944 |  | 2025-12-24 |  | COC's | 4000
4 | [9 empty] | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 14795.49 |  | Leading Edge - INV-0177 | 2025-12-31 | 20088.2472 |  | 2025-12-24 |  | HSE | 7950
4 | [9 empty] | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 14795.49 |  | Leading Edge - INV-0178 | 2025-12-31 | 20088.2472 |  | 2026-01-30 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 7397.745 |  | Leading Edge - INV-0179 | 2025-12-31 | 10044.1236 |  | 2026-02-05 |  | Total | 678490.92
4 | [9 empty] | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 7397.745 |  | Leading Edge - INV-0180 | 2025-12-31 | 10044.1236 |  | 2026-03-28 |  | R/Wp | 1.8538
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 34000 | 2025-12-13 | 49000 | 59756.0976 |  | 5 | 5. Monitoring | Smartlogger - Menlo SO0003713 |  |  | 8598.34 |  | Menlo - INV0003329 | 2025-10-31 | 11639.5934 | 0.0019764 | 2025-12-13 | 44864.75
5 |  | Revenue Metering |  |  | 15000 | 2025-10-31 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 22615.5 | PO4325-BOLT-20250925 - RV Approved | Accuenergy - ASAI-006478 | 2025-09-30 | 31168.8503 |  | 2025-10-30
5 | [9 empty] | 5 | 5. Monitoring | Techsitter |  |  | 11169 |  | Matriarch - INV-5207 | 2025-10-31 | 15320.0891 |  | 2025-11-13
[10 empty] | 5 | 5. Monitoring | Courier of Techsitter |  |  | 206.91 |  | DSV Inv: 180150385 | 2025-10-31 | 283.8105 |  | 2025-11-30
5 | [9 empty] | 5 | 5. Monitoring | Lithium Battery |  |  | 975 |  | Red Pole - SO-35912 | 2025-09-30 | 1343.7523 |  | 2025-10-09
5 | [9 empty] | 5 | 5. Monitoring | Power Supply |  |  | 1300 |  | Allocated from Cpt Storeroom | 2025-12-31 | 0 |  | 2025-12-31
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 497053.5957 | 2025-10-31 | 497053.5957 | 606162.9215 |  | 6 | 6. AC Equipment | [7 empty] | 0 | 0 |  | 247722.28
6 | [9 empty] | 6 | 6. AC Equipment | PVDB |  |  | 130831.95 | PO4329-BOLT-20250925 - MI Approved | Switchboard - 2-SOI002605 | 2025-11-30 | 320138.653 |  | 2025-12-30
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | Project Kick Off | 116890.33 | 15% | 17533.5495 | PO4349-BOLT-20251001 - RV Approved | Leading Edge - INV-0158 | 2025-10-31 | 42903.6403 |  | 2025-10-09
6 | [9 empty] | 6 | 6. AC Equipment | Site Establishment |  | 15% | 17533.5495 |  | Leading Edge - INV-0159 | 2025-10-31 | 42903.6403 |  | 2025-10-09
6 | [9 empty] | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 23378.066 |  | Leading Edge - INV-0172 | 2025-11-30 | 57204.8537 |  | 2025-12-08
6 | [9 empty] | 6 | 6. AC Equipment | DC Installation Complete |  | 20% | 23378.066 |  | Leading Edge - INV-0176 | 2025-12-31 | 57204.8537 |  | 2025-12-24
6 | [9 empty] | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 11689.033 |  | Leading Edge - INV-0177 | 2025-12-31 | 28602.4269 |  | 2025-12-24
6 | [9 empty] | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 11689.033 |  | Leading Edge - INV-0178 | 2025-12-31 | 28602.4269 |  | 2026-01-30
6 | [9 empty] | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 5844.5165 |  | Leading Edge - INV-0179 | 2025-12-31 | 14301.2134 |  | 2026-02-05
6 | [9 empty] | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 5844.5165 |  | Leading Edge - INV-0180 | 2025-12-31 | 14301.2134 |  | 2026-03-28
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 208000 | 239241.1924 |  | 8 | 8. Product Add On | [7 empty] | 0 | 0 |  | 226006.5
8 |  | Inverter Rack |  |  | 48000 | 2025-10-07 |  |  |  | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | APEX & Emulator |  |  | 44000 | PO4326-BOLT-20250925 - RV Approved | Rbicon - INVWCRE-0070990 | 2025-09-30 | 87904.9058 |  | 2025-10-30
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 |  | MV Metering Emulator |  |  | 85000 | 2025-10-07 |  |  |  | 8 | 8. Product Add On | Catladder & Inverter Rack | 75750 | 50% | 37875 | PO4347-BOLT-20250930 - RV Approved | Barrier Projects - 497 | 2025-10-31 | 75668.1433 |  | 2025-10-09
8 | [9 empty] | 8 | 8. Product Add On |  |  | 50% | 37875 |  | Barrier Projects - 497 | 2025-10-31 | 75668.1433 |  | 2025-11-13
8 | [9 empty] | 8 | 8. Product Add On | Walkway Installation |  |  | 29500 | PO4465-BOLT-20251111 - RV Approved | Leading Edge - INV-0169 | 2025-11-30 | 0 |  | 2025-11-19
8 |  | Catladder |  |  | 75000 | 2025-10-07 |  |  |  | 8 | 8. Product Add On | Walkway Material |  |  | 71592.3 | PO4462-BOLT-20251111 - RV Approved | Onvlee Engineering PO4662-Bolt-20251111 | 2025-11-30 | 0 |  | 2025-11-13
[10 empty] | 8 | 8. Product Add On | Walkway Clamps |  |  | -5272.5 |  | Onvlee Engineering - CN 01001981 | 2026-01-31 |  |  | 2026-01-21
8 | [9 empty] | 8 | 8. Product Add On | Walkway Clamps |  |  | 10436.7 |  | Onvlee Engineering - ONV1702 | 2026-01-31 | 0 |  | 2026-01-09
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 91500 | 2025-10-07 | 291000 | 323333.3333 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0 |  | 321250
9 |  | DC Installation Budget |  |  | 199500 | 2025-10-07 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 321250 | 15% | 48187.5 | PO4349-BOLT-20251001 - RV Approved | Leading Edge - INV-0158 | 2025-10-31 | 48500 |  | 2025-10-09
9 | [9 empty] | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 48187.5 |  | Leading Edge - INV-0159 | 2025-10-31 | 48500 |  | 2025-10-09
9 | [9 empty] | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 64250 |  | Leading Edge - INV-0172 | 2025-11-30 | 64666.6667 |  | 2025-12-08
9 | [9 empty] | 9 | 9. AC & DC installation | DC Installation Complete |  | 20% | 64250 |  | Leading Edge - INV-0176 | 2025-12-31 | 64666.6667 |  | 2025-12-24
9 | [9 empty] | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 32125 |  | Leading Edge - INV-0177 | 2025-12-31 | 32333.3333 |  | 2025-12-24
9 | [9 empty] | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 32125 |  | Leading Edge - INV-0178 | 2025-12-31 | 32333.3333 |  | 2026-01-30
9 | [9 empty] | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 16062.5 |  | Leading Edge - INV-0179 | 2025-12-31 | 16166.6667 |  | 2026-02-05
9 | [9 empty] | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 16062.5 |  | Leading Edge - INV-0180 | 2025-12-31 | 16166.6667 |  | 2026-03-28
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-11-30 | 76945.4667 | 85494.963 |  | 10 | 10. Site Logistics | [7 empty] | 0 | 0 |  | 92395.69
10 |  | Scaffolding |  |  | 22285.4667 | 2025-11-30 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Security |  |  | 43200 | 2025-11-30 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 2960 | 2025-11-30 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | Project Kick Off | 92395.69 | 15% | 13859.3535 | PO4349-BOLT-20251001 - RV Approved | Leading Edge - INV-0158 | 2025-10-31 | 12824.2444 |  | 2025-10-09
10 | [9 empty] | 10 | 10. Site Logistics | Site Establishment |  | 15% | 13859.3535 |  | Leading Edge - INV-0159 | 2025-10-31 | 12824.2444 |  | 2025-10-09
10 | [9 empty] | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 18479.138 |  | Leading Edge - INV-0172 | 2025-11-30 | 17098.9926 |  | 2025-12-08
10 | [9 empty] | 10 | 10. Site Logistics | DC Installation Complete |  | 20% | 18479.138 |  | Leading Edge - INV-0176 | 2025-12-31 | 17098.9926 |  | 2025-12-24
10 | [9 empty] | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 9239.569 |  | Leading Edge - INV-0177 | 2025-12-31 | 8549.4963 |  | 2025-12-24
10 | [9 empty] | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 9239.569 |  | Leading Edge - INV-0178 | 2025-12-31 | 8549.4963 |  | 2026-01-30
10 | [9 empty] | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 4619.7845 |  | Leading Edge - INV-0179 | 2025-12-31 | 4274.7481 |  | 2026-02-05
10 | [9 empty] | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 4619.7845 |  | Leading Edge - INV-0180 | 2025-12-31 | 4274.7481 |  | 2026-03-28
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2025-09-16 | 109300 | 121444.4444 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 8750 |  | Sunspot E040 | 2026-01-31 | 72043.3145 | 0 | 2026-02-07 | 14750
11 |  | Structural sign off |  |  | 18300 | 2025-09-16 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 0 |  | New roof, not required | 2025-11-30 | 0 |  | 2025-11-30
11 |  | Grid Study |  |  | 80000 | 2025-10-07 |  |  |  | 11 | 11. Due Dilligence | Grid Study |  |  | 0 |  |  |  | 0
11 | [9 empty] | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 |  |  | 2026-02-28 | 49401.1299 |  | 2026-03-30
11 | [9 empty] | 11 | 11. Due Dilligence | [7 empty] | 0
12 | BDP Commission | PD Fee |  |  | 13353.69 | 2025-11-30 | 13353.69 | 0 |  | 12 | 12. BDP Commission | PD Fee |  |  | 0 | [6 empty] | 0
12 | BDP Commission | [8 empty] | 12 | 12. BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 31300.7758 | 2025-11-30 | 31300.7758 | 35569.0634 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 41047.6319 |  |  | 2026-02-28 | 35569.0634 | 0 | 2026-03-31 | 41047.6319
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 6300 | 2025-09-30 | 6300 | 7000 |  | 14 | 14. General Expenses | Travel |  |  | 28.56 |  | Expense Claims | 2025-09-30 | 62.8964 | 0.00058632 | 2025-10-10 | 1159.68
14 | [5 empty] | 2025-10-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 37 |  | Expense Claims | 2025-10-31 | 299.7225 |  | 2025-11-06
14 | [5 empty] | 2025-11-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 37 |  | Expense Claims | 2025-11-30 | 234.9079 |  | 2025-12-05
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 57.12 |  | Expense Claims | 2025-12-31 | 366.3248 |  | 2026-01-08
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 500 |  |  | 2026-01-31 | 3018.074 |  | 2026-01-31
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 500 |  |  | 2026-02-28 | 3018.074 |  | 2026-03-05
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | [8 empty] | 0 |  | 0
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 16 | 16. VO - XXX
| Panel Procurement Budget | 838063 |  | 1022028.0488
| Inverter Procurement Budget | 210000 |  | 256097.561
| Mounting Structure Budget | 146400 |  | 178536.5854
| DC Equipment Budget | 286300 |  | 349146.3415
| AC Equipment Budget | 497053.5957 |  | 606162.9215
| Monitoring Budget | 49000 |  | 59756.0976
| Optional Extras Budget | 75000 |  | 91463.4146
| MV Equipment Budget | 0 |  | 0
| ADD ON | 133000 |  | 147777.7778
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 91500 |  | 101666.6667
| DC Installer Budget | 199500 |  | 221666.6667
| In-House Expense Budget | 31300.7758 |  | 35569.0634
| Compliance Budget | 109300 |  | 121444.4444
| Offloading Budget | 8500 |  | 9444.4444
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 2960 |  | 3288.8889
| On Site Security | 43200 |  | 48000
| Roof Access Budget for Installers | 22285.4667 |  | 24761.6296
| EPC Management Fee | 0 |  | 0
| ADD ON | 0 |  | 0
Expenses
| Total EE Expense Budget | 6300 |  | 7000
Note on Q9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Peet Verreynne why did we install 2 additional panels? Reply: There was a small mistake on the Engineering Pack

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-07-07 to 2051-06-12
PLANNED |  | CHECK | CHECK
| Planned Revenue | 3283810.55 | 3377404.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149333.6925 | 0 | 0 | 0 | 0 | 0 | 1641905.275 | 0 | 0 | 0 | 0 | 421975.255 | 164190.5275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149333.6925 | 1149333.6925 | 1149333.6925 | 1149333.6925 | 1149333.6925 | 1149333.6925 | 2791238.9675 | 2791238.9675 | 2791238.9675 | 2791238.9675 | 2791238.9675 | 3213214.2225 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75 | 3377404.75
| Planned Expenditure | 2763016.5281 | 2763016.5281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29300 | 0 | 6300 | 579000 | 0 | 0 | 512053.5957 | 0 | 146400 | 0 | 121599.9324 | 0 | 1368363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29300 | 29300 | 35600 | 614600 | 614600 | 614600 | 1126653.5957 | 1126653.5957 | 1273053.5957 | 1273053.5957 | 1394653.5281 | 1394653.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281 | 2763016.5281
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149333.6925 | 1120033.6925 | 1120033.6925 | 1113733.6925 | 534733.6925 | 534733.6925 | 2176638.9675 | 1664585.3718 | 1664585.3718 | 1518185.3718 | 1518185.3718 | 1818560.6944 | 1982751.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219 | 614388.2219
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 3377404.75 | 2955429.495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149333.6925 | 0 | 0 | 0 | 0 | 0 | 0 | 985143.165 | 0 | 0 | 656762.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164190.5275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149333.6925 | 1149333.6925 | 1149333.6925 | 1149333.6925 | 1149333.6925 | 1149333.6925 | 1149333.6925 | 2134476.8575 | 2134476.8575 | 2134476.8575 | 2791238.9675 | 2791238.9675 | 2791238.9675 | 2791238.9675 | 2791238.9675 | 2791238.9675 | 2791238.9675 | 2791238.9675 | 2791238.9675 | 2791238.9675 | 2791238.9675 | 2791238.9675 | 2791238.9675 | 2791238.9675 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495 | 2955429.495
| Actual + Planned Expenditure | 2217962.1719 | 2217962.1719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242425.836 | 0 | 0 | 135865.5 | 37 | 120636.3 | 29500 | 206.91 | 37 | 253496.524 | 900103.74 | 203547.276 | 134388.95 | 10493.82 | 0 | -5272.5 | 68349.092 | 42674.546 | 0 | 0 | 0 | 500 | 0 | 0 | 33924.546 | 47047.6319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242425.836 | 242425.836 | 242425.836 | 378291.336 | 378328.336 | 498964.636 | 528464.636 | 528671.546 | 528708.546 | 782205.07 | 1682308.81 | 1885856.086 | 2020245.036 | 2030738.856 | 2030738.856 | 2025466.356 | 2093815.448 | 2136489.994 | 2136489.994 | 2136489.994 | 2136489.994 | 2136989.994 | 2136989.994 | 2136989.994 | 2170914.54 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719 | 2217962.1719
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149333.6925 | 1149333.6925 | 1149333.6925 | 1149333.6925 | 1149333.6925 | 906907.8565 | 906907.8565 | 1892051.0215 | 1756185.5215 | 1756148.5215 | 2292274.3315 | 2262774.3315 | 2262567.4215 | 2262530.4215 | 2009033.8975 | 1108930.1575 | 905382.8815 | 770993.9315 | 760500.1115 | 760500.1115 | 765772.6115 | 697423.5195 | 654748.9735 | 654748.9735 | 818939.501 | 818939.501 | 818439.501 | 818439.501 | 818439.501 | 784514.955 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231 | 737467.3231
|  | CHECK | CHECK
| Revenue Recognition | 0.00035145 | 3283810.5496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299016.9901 | 0 | 0 | 0 | 1873989.4923 | 0 | 0 | 0 | 499520.5683 | 0 | 0 | 0 | 0 | 448233.8432 | 0 | 0 | 0 | 75061.3885 | 0 | 0 | 0 | 87988.2673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 3283810.5496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299016.9901 | 299016.9901 | 299016.9901 | 299016.9901 | 2173006.4824 | 2173006.4824 | 2173006.4824 | 2173006.4824 | 2672527.0507 | 2672527.0507 | 2672527.0507 | 2672527.0507 | 2672527.0507 | 3120760.8939 | 3120760.8939 | 3120760.8939 | 3120760.8939 | 3195822.2824 | 3195822.2824 | 3195822.2824 | 3195822.2824 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496 | 3283810.5496

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | Grand Total
(blank)
1. Panels |  |  | 1022028.0488 |  | 0 | 0 |  |  | 1022028.0488
2. Inverters |  |  | 256097.561 |  |  | 0 |  |  | 256097.561
3. Mounting Structures |  | 178536.5854 |  |  |  | 0 |  |  | 178536.5854
4. DC Equipment |  |  | 208528.611 | 40176.4944 | 100441.2361 | 0 |  |  | 349146.3415
5. Monitoring |  | 32512.6026 | 27243.493 |  | 0 | 0 |  |  | 59756.0956
6. AC Equipment |  |  | 85807.2806 | 377343.5067 | 143012.1343 | 0 |  |  | 606162.9215
8. Product Add On | 0 | 87904.9058 | 151336.2866 | 0 |  |  | 0 |  | 239241.1924
9. AC & DC installation | 0 |  | 97000 | 64666.6667 | 161666.6667 | 0 |  |  | 323333.3333
10. Site Logistics | 0 |  | 25648.4889 | 17098.9926 | 42747.4815 | 0 |  |  | 85494.963
11. Due Dilligence | 0 |  |  | 0 |  | 0 | 121444.4444 |  | 121444.4444
13. Engineering | 0 | [5 empty] | 35569.0634 |  | 35569.0634
14. General Expenses |  | 62.8964 | 299.7225 | 234.9079 | 366.3248 | 0 | 3018.074 | 3018.074 | 6999.9994
15. Service Add On
12. BDP Commission
7.BESS
16. VO - XXX
Grand Total | 0 | 299016.9901 | 1873989.4923 | 499520.5683 | 448233.8432 | 0 | 160031.5818 | 3018.074 | 3283810.5496

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | Grand Total
(blank)
1. Panels |  |  | 704365.74 |  | 2257 |  |  | 706622.74
2. Inverters |  |  | 195738 |  |  |  |  | 195738
3. Mounting Structures |  | 69250 | [5 empty] | 69250
4. DC Equipment |  |  | 153586.47 | 29590.98 | 73977.45 |  |  | 257154.9
5. Monitoring |  | 23590.5 | 19974.25 |  | 1300 |  |  | 44864.75
6. AC Equipment |  |  | 35067.099 | 154210.016 | 58445.165 |  |  | 247722.28
8. Product Add On |  | 44000 | 75750 | 101092.3 |  | 10436.7 |  | 231279
9. AC & DC installation |  |  | 96375 | 64250 | 160625 |  |  | 321250
10. Site Logistics |  |  | 27718.707 | 18479.138 | 46197.845 |  |  | 92395.69
11. Due Dilligence | 0 |  |  | 0 |  | 18577.5 |  | 18577.5
13. Engineering | [5 empty] | 41047.6319 |  | 41047.6319
14. General Expenses |  | 28.56 | 37 | 37 | 57.12 | 500 | 500 | 1159.68
15. Service Add On
12. BDP Commission | 0 | [6 empty] | 0
7.BESS
16. VO - XXX
Grand Total | 0 | 136869.06 | 1308612.266 | 367659.434 | 342859.58 | 70561.8319 | 500 | 2227062.1719

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 0.75927 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.38841 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.26277 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 0.62885 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
1 Bolt Ave |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | 1 Bolt Ave | 0 | 0 | 0