## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[9 empty] | 2026-02-02 | 2026-02-02
| PROJECT PLAN | IconSA_KZN | [7 empty] | 1
| PROJECT SIZE (kWp) | 71
| PROJECT DEVELOPER | Peet Verenney
| PROJECT MANAGERS | Eon Van Rensburg
| CONTRACT VALUE | 1027136
| Phase: | Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Expected Status | Comment | Milestone | Start Date | Total Duration | End Date | Progress Percentage
|  |  | 26 |  |  | 34 |  | 94.68% | 100% |  | Project Initiation | 2025-08-04 | 24 | 2025-08-28 | 100%
[11 empty] | Site Establishment | 2025-09-10 | 1 | 2025-09-11 | 100% | 2026-02-02 | 2026-02-02
1 | Project Initiation | 2025-08-04 | 32 | 2025-09-05 | 2025-08-04 | 24 | 2025-08-28 | 100% | 100% |  | AC Installation | 2025-09-04 | 36 | 2025-10-10 | 100% | 1 | 0
1.1 | BD Handover | 2025-08-04 | 1 | 2025-08-05 | 2025-08-04 | 1 | 2025-08-05 | 100% | 100% |  | DC Works | 2025-09-04 | 32 | 2025-10-06 | 100%
1.2 | Project Introduction | 2025-09-04 | 1 | 2025-09-05 | 2025-08-27 | 1 | 2025-08-28 | 100% | 100% |  | Module installation | 2025-09-18 | 15 | 2025-10-03 | 100%
1.3 | HSE | 2025-08-21 | 8 | 2025-09-02 | 2025-08-13 | 4 | 2025-08-19 | 100% | 100% |  | Commissioning | 2025-10-10 | 4 | 2025-10-14 | 100%
1.4 | Installer Kick Off | 2025-09-04 | 1 | 2025-09-05 | 2025-08-19 | 1 | 2025-08-20 | 100% | 100% |  | QA Inspections | 2025-10-13 | 1 | 2025-10-14 | 100%
1.5 | Project Review | 2025-08-25 | 1 | 2025-08-26 | 2025-08-25 | 1 | 2025-08-26 | 100% | 100% |  | Project Closure | 2025-10-14 | 106 | 2026-01-28 | 57.47%
2 | Site Establishment | 2025-09-18 | 1 | 2025-09-19 | 2025-09-10 | 1 | 2025-09-11 | 100% | 100%
2.1 | Solar Contractor Establishment | 2025-09-18 | 1 | 2025-09-19 | 2025-09-10 | 1 | 2025-09-11 | 100% | 100%
3 | AC Installation | 2025-08-28 | 43 | 2025-10-10 | 2025-09-04 | 36 | 2025-10-10 | 100% | 100%
3.1 | Inverters delivered | 2025-08-28 | 1 | 2025-08-29 | 2025-08-28 | 1 | 2025-08-29 | 100% | 100%
3.2 | Inverters Mounted | 2025-09-19 | 2 | 2025-09-23 | 2025-09-28 | 2 | 2025-09-30 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-09-04 | 20 | 2025-10-03 | 2025-09-04 | 20 | 2025-10-03 | 100% | 100%
3.4 | AC Works | 2025-10-03 | 5 | 2025-10-10 | 2025-10-03 | 5 | 2025-10-10 | 100% | 100%
3.5 | AC Tie-In | 2025-10-03 | 1 | 2025-10-06 | 2025-10-03 | 1 | 2025-10-06 | 100% | 100%
4 | DC Works | 2025-08-28 | 42 | 2025-10-09 | 2025-09-04 | 32 | 2025-10-06 | 100% | 100%
4.1 | [7 empty] | 0% | 0%
4.1 | Mounting Structure delivered | 2025-08-28 | 1 | 2025-08-29 | 2025-09-04 | 1 | 2025-09-05 | 100% | 100%
4.2 | Mounting Structure installation | 2025-09-18 | 3 | 2025-09-23 | 2025-09-10 | 6 | 2025-09-18 | 100% | 100%
4.7 | DC Cable delivered | 2025-08-28 | 1 | 2025-08-29 | 2025-09-04 | 1 | 2025-09-05 | 100% | 100%
4.8 | DC Stringing | 2025-10-05 | 4 | 2025-10-09 | 2025-09-30 | 4 | 2025-10-06 | 100% | 100%
5 | Module installation | 2025-08-28 | 41 | 2025-10-08 | 2025-09-18 | 15 | 2025-10-03 | 100% | 100%
5.1 | Module delivery | 2025-08-28 | 1 | 2025-08-29 | 2025-08-28 | 1 | 2025-08-29 | 100% | 100%
5.2 | Module mounting | 2025-09-23 | 10 | 2025-10-08 | 2025-09-18 | 10 | 2025-10-03 | 100% | 100%
6 | Commissioning | 2025-10-10 | 4 | 2025-10-14 | 2025-10-10 | 4 | 2025-10-14 | 100% | 100%
6.1 | Commissioning | 2025-10-10 | 1 | 2025-10-13 | 2025-10-10 | 1 | 2025-10-13 | 100% | 100%
6.2 | Practical Completion | 2025-10-13 | 1 | 2025-10-14 | 2025-10-13 | 1 | 2025-10-14 | 100% | 100%
7 | QA Inspections | 2025-10-10 | 3 | 2025-10-13 | 2025-10-13 | 1 | 2025-10-14 | 100% | 100%
7.1 | Red-Team Inspection | 2025-10-10 | 1 | 2025-10-13 | 2025-10-13 | 1 | 2025-10-14 | 100% | 100%
8 | Project Closure | 2025-10-13 | 17 | 2025-10-30 | 2025-10-14 | 106 | 2026-01-28 | 57.47% | 100%
8.1 | Equipment serial numbers | 2025-10-13 | 1 | 2025-10-14 | 2025-10-14 | 1 | 2025-10-15 | 100% | 100%
8.2 | Snags completion - Gen Intg Outstanding | 2025-10-13 | 5 | 2025-10-20 | 2025-10-14 | 74 | 2026-01-28 | 50% | 100% | Still outstanding
8.3 | System Performance Monitoring | 2025-10-14 | 5 | 2025-10-21 | 2025-10-14 | 5 | 2025-10-21 | 100% | 100%
8.4 | Handover documentation | 2025-10-20 | 1 | 2025-10-21 | 2025-11-08 | 1 | 2025-11-10 | 100% | 100%
8.5 | Handover to Client | 2025-10-21 | 1 | 2025-10-22 | 2025-11-12 | 1 | 2025-11-13 | 100% | 100%
8.6 | Handover to Matriarch | 2025-10-23 | 5 | 2025-10-30 | 2025-11-24 | 5 | 2025-12-01 | 100% | 100%
Formulas:
Planned Start = MIN([Planned Start, row below]:E16)
Planned Start = [Planned Start, row above]-14
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = [Actual Start, row above]-14
Actual End = MAX([Actual End, row below]:K16)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C14)
Expected Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )
Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  | FINANCIAL REVIEW | TIMELINE REVIEW |  |  | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 1027136 |  | 1027136 |  | 1027136 | Start Date |  |  | 665572.3774 | 542298.3 | 364591.7378 | 228208.97 | 364591.7378 | 228208.97
2 | Planned Expenditure | 817052.62 |  | 770507.27 |  | 780286.29 | 2025-09-18
3 | Planned Profit | 210083.38 |  | 256628.73 |  | 246849.71 | End Date - PC
4 | Planned Margin | 20.45% |  | 24.98% |  | 24.03% | 2025-10-14
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Acceptance and Initial Deposit |  | 50% | 513568 | 2025-08-21 | 004800 | 2025-07-29 | 2025-08-05 | [7 empty] | 1900-01-06
2 | Delivery of Panels |  | 25% | 256784 | 2025-09-04 | 004828 | 2025-08-31 | 2025-09-05
3 | Delivery of Inverters |  | 10% | 102713.6 | 2025-09-04 | 004828 | 2025-08-31 | 2025-09-05
4 | Practical Completion |  | 10% | 102713.6 | 2025-10-21 | 004854 | 2025-10-20 | 2025-11-18
5 | Handover |  | 5% | 51356.8 | 2025-10-28 | 004878 | 2025-11-13 | 2025-11-18
6 | - |  | 0% | 0
7 | - |  | 0% | 0
|  |  | 100% | 1027136
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 359497.6
2 | Delivery of Panels |  | 30% | 308140.8
3 | Delivery of Inverters |  | 20% | 205427.2
4 | Practical Completion |  | 10% | 102713.6
5 | Handover |  | 5% | 51356.8
| Total |  | 100% | 1027136
|  |  | 100% | 1027136
Note on R14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Thami Cambalele please invoice these for us

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 817052.62 |  | 770507.27 | 46545.35
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 160883.16 |  | 149174 | 11709.16
2 | 2. Inverters | 74130 |  | 74130.34 | -0.34
3 | 3. Mounting Structures | 97648.8 |  | 101652.61 | -4003.81
4 | 4. DC Equipment | 61800.6 |  | 100367 | -38566.4
5 | 5. Monitoring | 166000 |  | 89397.71 | 76602.29
6 | 6. AC Equipment | 135950.84 |  | 126812.12 | 9138.72
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 0 |  | 0 | 0
9 | 9. AC & DC installation | 54230 |  | 59310 | -5080
10 | 10. Site Logistics | 26112.27 |  | 34792 | -8679.73
11 | 11. Due Dilligence | 29000 |  | 18575 | 10425
12 | 12. BDP Commission | 0 |  | 0 | 0
13 | 13. Engineering | 10071.95 |  | 12839.2 | -2767.25
14 | 14. General Expenses | 1225 |  | 3159.05 | -1934.05
15 | 15. Service Add On | 0 |  | 298.24 | -298.24
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 817052.62 | 1027135 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 770507.27
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | ERROR on REV |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 160883.16 | 2025-10-25 | 160883.16 | 206260 |  | 1 | 1. Panels | Jinko 620W modules - 66HL4M-BDV - Menlo | 114.5161 | 1227.6 | 141174 | PO4273-IKZN-20250825 - RV Approved | Menlo INV0003176 | 2025-08-31 | 195198.555 | 0 | 2025-10-24 | 149174
1 |  | Delivery Budget |  |  |  | 2025-10-25 |  |  |  | 1 | 1. Panels | Delivery |  |  | 8000 |  | Menlo INV0003176 | 2025-08-31 | 11061.445 |  | 2025-10-24
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 135950.84
2 | Inverters | Inverter Budget |  |  | 74130 | 2025-10-25 | 74130 | 95038 |  | 2 | 2. Inverters | Huawei 36KTL - Menlo | 2 | 37065.17 | 74130.34 | PO4273-IKZN-20250825 - RV Approved | Menlo INV003176 | 2025-08-31 | 95038 | 0 | 2025-10-24 | 74130.34 | DC Equipment | 48780.6
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | AC Labour | 17690
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 36540
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 9212.27
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 0
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 97648.8 | 2025-09-10 | 97648.8 | 125191 |  | 3 | 3. Mounting Structures | Schletter Structure |  |  | 83929.11 | PO4272-IKZN-20250825 - RV Approved | Schletter Inv: INV2149 | 2025-09-30 | 103363.4966 | 0 | 2025-10-30 | 101652.61 | Other | 0
3 | [5 empty] | 2025-09-11 |  |  |  | 3 | 3. Mounting Structures | Lintels |  |  | 17723.5 | PO4293-IKZN-20250902 - RV Approved | Precast Structural - IN44436 | 2025-09-30 | 21827.5034 |  | 2025-09-11 |  | Total | 256673.71
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Less 15% | 218172.6535
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | R/Wp | 3.0729
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL - Thula Moya | Installer Price
[23 empty] | AC Equipment | 126812.1
4 | DC Equipment | DC Cable Budget | 1069.5 |  | 13020 | 2025-09-30 | 61800.6 | 79232 |  | 4 | 4. DC Equipment | DC Cable - Rubicon | 4000 | 13.5 | 54000 | PO4273-IKZN-20250825 - RV Approved | Rubicon - INVWCRE-0070283 | 2025-08-31 | 42628.8322 | 0 | 2025-09-30 | 100367 | DC Equipment | 46367
4 |  | DC Equipment Budget |  |  | 48780.6 | 2025-10-01 |  |  |  | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | AC Labour | 12365
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | DC Labour | 46945
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Site Logistics & Material Handling | 12000
4 | [9 empty] | 4 | 4. DC Equipment | Project Kick Off | 46367 | 10% | 4636.7 | PO4270-IKZN-20250825 - RV Approved | Thula Moya IN04863 | 2025-08-31 | 3660.3168 |  | 2025-09-04 |  | Forklift | 0
4 | [9 empty] | 4 | 4. DC Equipment | Site Establishment |  | 15% | 6955.05 |  | Thula Moya IN04864 | 2025-08-31 | 5490.4752 |  | 2025-09-11 |  | Geda | 0
4 | [9 empty] | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 9273.4 |  | Thula Moya IN04865 | 2025-08-31 | 7320.6336 |  | 2025-10-16 |  | Logistics | 0
4 | [9 empty] | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 11591.75 |  | Thula Moya IN04866 | 2025-08-31 | 9150.792 |  | 2025-10-16 |  | HSE | 0
4 | [9 empty] | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 4636.7 |  | Thula Moya IN04867 | 2025-08-31 | 3660.3168 |  | 2026-01-29 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 4636.7 |  | Thula Moya IN04868 | 2025-08-31 | 3660.3168 |  | 2026-01-29 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 2318.35 |  | Thula Moya IN04869 | 2025-08-31 | 1830.1584 |  | 2026-01-15 |  | Total | 244489.1
4 | [9 empty] | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 2318.35 |  | Thula Moya IN04870 | 2025-08-31 | 1830.1584 |  | 2026-01-15 |  | R/Wp | 3.4435
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 151000 | 2025-10-25 | 166000 | 212821 |  | 5 | 5. Monitoring | Smartlogger |  |  | 8598.34 | PO4273-IKZN-20250825 - RV Approved | Menlo INV003176 | 2025-08-31 | 13585.528 | 12.1651 | 2025-10-24 | 89397.71
5 |  | Revenue Metering |  |  | 15000 | 2025-10-25 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 22428 | PO4271-IKZN-20250825 - RV Approved | AccuEnergy ASAI-006226 | 2025-08-31 | 35436.6334 |  | 2025-09-30
5 | [5 empty] | 2025-10-25 |  |  |  | 5 | 5. Monitoring | Techsitter |  |  | 11169 |  | Matriarch - INV-4999 | 2025-08-31 | 17647.2159 |  | 2025-08-31
5 | [5 empty] | 2025-10-25 |  |  |  | 5 | 5. Monitoring | Apex - Allocated from Corporate Park |  |  | 44000 | PO4176-DCP-20250728 - RV Approved | Allocated from Corporate PArk | 2025-10-31 | 139319.3469 |  | 2025-10-31
[10 empty] | 5 | 5. Monitoring | Delivery of Apex & Techsitter + Power Supply |  |  | 577.37 |  | DSV Inv: 180150385 | 2025-10-31 | 1379.8947 |  | 2025-11-30
5 | [5 empty] | 2025-10-25 |  |  |  | 5 | 5. Monitoring | Battery & Power Supply |  | 3500 | 975 |  | Red Pole - SO-35912 | 2025-09-30 | 2345.4242 |  | 2025-10-09
5 | [5 empty] | 2025-10-25 |  |  |  | 5 | 5. Monitoring | Battery & Power Supply |  |  | 1300 |  | Allocated from Cpt Storeroom | 2025-10-31 | 3094.7918 |  | 2025-10-31
5 | [5 empty] | 2025-10-25 |  |  |  | 5 | 5. Monitoring | Antenna |  |  | 350 | PO4472-IKZN-20251114 - RV Approved | Accuenergy - ASAI-006874 | 2025-11-30 |  |  | 2026-01-07
2025-10-25
6 | AC Equipment | AC Equipment Budget |  |  | 135950.84 | 2025-10-25 | 135950.84 | 174296 |  | 6 | 6. AC Equipment | [7 empty] | 0 | 0 |  | 126812.12
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [5 empty] | 2025-09-04 |  |  |  | 6 | 6. AC Equipment | Project Kick Off | 126812.1 | 10% | 12681.21 | PO4270-IKZN-20250825 - RV Approved | Thula Moya IN04863 | 2025-08-31 | 17429.5973 |  | 2025-09-04
6 | [5 empty] | 2025-09-11 |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 19021.82 |  | Thula Moya IN04864 | 2025-08-31 | 26144.4027 |  | 2025-09-11
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 25362.42 |  | Thula Moya IN04865 | 2025-08-31 | 34859.1945 |  | 2025-10-16
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 31703.03 |  | Thula Moya IN04866 | 2025-08-31 | 43574 |  | 2025-10-16
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 12681.21 |  | Thula Moya IN04867 | 2025-08-31 | 17429.5973 |  | 2026-01-29
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 12681.21 |  | Thula Moya IN04868 | 2025-08-31 | 17429.5973 |  | 2026-01-29
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 6340.61 |  | Thula Moya IN04869 | 2025-08-31 | 8714.8055 |  | 2026-01-15
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 6340.61 |  | Thula Moya IN04870 | 2025-08-31 | 8714.8055 |  | 2026-01-15
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 0 | 0 |  | 8 | 8. Product Add On | [8 empty] | 0 |  | 0
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 17690 | 2025-09-04 | 54230 | 60256 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0 |  | 59310
9 |  | DC Installation Budget |  |  | 36540 | 2025-09-04 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 59310 | 10% | 5931 | PO4270-IKZN-20250825 - RV Approved | Thula Moya IN04863 | 2025-08-31 | 6025.6 |  | 2025-09-04
9 | [5 empty] | 2025-09-11 |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 8896.5 |  | Thula Moya IN04864 | 2025-08-31 | 9038.4 |  | 2025-09-11
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 11862 |  | Thula Moya IN04921 | 2025-10-31 | 12051.2 |  | 2025-10-16
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 14827.5 |  | Thula Moya IN04921 | 2025-10-31 | 15064 |  | 2025-10-16
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 5931 |  | Thula Moya IN04921 | 2025-10-31 | 6025.6 |  | 2026-01-29
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 5931 |  | Thula Moya IN04921 | 2025-10-31 | 6025.6 |  | 2026-01-29
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 2965.5 |  | Thula Moya IN04921 | 2025-10-31 | 3012.8 |  | 2026-01-29
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 2965.5 |  | Thula Moya IN04921 | 2025-10-31 | 3012.8 |  | 2026-01-29
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-08-28 | 26112.27 | 29013 |  | 10 | 10. Site Logistics | [7 empty] | 0 | 0 |  | 34792
10 |  | Scaffolding |  |  | 9212.27 | 2025-08-29 |  |  |  | 10 | 10. Site Logistics | Security |  |  | 22792 | PO42788-IKZN-20250828 - RV Approved | Excellerate Inv 442934 | 2025-08-31 | 19006.2168 |  | 2025-08-29
10 |  | Security |  |  | 8400 | 2025-08-30 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 0 | 2025-08-31 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [5 empty] | 2025-09-01 |  |  |  | 10 | 10. Site Logistics | Project Kick Off | 12000 | 10% | 1200 | PO4270-IKZN-20250825 - RV Approved | Thula Moya IN04863 | 2025-08-31 | 1000.6783 |  | 2025-09-04
10 | [5 empty] | 2025-09-02 |  |  |  | 10 | 10. Site Logistics | Site Establishment |  | 15% | 1800 |  | Thula Moya IN04864 | 2025-08-31 | 1501.0175 |  | 2025-09-11
10 | [5 empty] | 2025-09-03 |  |  |  | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 2400 |  | Thula Moya IN04865 | 2025-08-31 | 2001.3566 |  | 2025-10-16
10 | [5 empty] | 2025-09-04 |  |  |  | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 3000 |  | Thula Moya IN04866 | 2025-08-31 | 2501.6958 |  | 2025-10-16
10 | [5 empty] | 2025-09-05 |  |  |  | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 1200 |  | Thula Moya IN04867 | 2025-08-31 | 1000.6783 |  | 2026-01-29
10 | [5 empty] | 2025-09-06 |  |  |  | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 1200 |  | Thula Moya IN04868 | 2025-08-31 | 1000.6783 |  | 2026-01-29
10 | [5 empty] | 2025-09-07 |  |  |  | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 600 |  | Thula Moya IN04869 | 2025-08-31 | 500.3392 |  | 2026-01-29
10 | [5 empty] | 2025-09-08 |  |  |  | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 600 |  | Thula Moya IN04870 | 2025-08-31 | 500.3392 |  | 2026-01-29
10 | [5 empty] | 2025-09-09 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [5 empty] | 2025-09-10 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [5 empty] | 2025-09-11 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
2025-09-12
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2025-09-13 | 29000 | 32222 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 12575 |  | SunSpot - E039 | 2026-01-31 | 21813.817 | -3041.2803 | 2026-01-29 | 18575
11 |  | Structural sign off |  |  | 18000 | 2025-09-14 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 0 |  |  |  | 0
11 | [5 empty] | 2025-09-15 |  |  |  | 11 | 11. Due Dilligence | [7 empty] | 0
11 | [5 empty] | 2025-09-16 |  |  |  | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 |  | Matriarch - INV-5370 | 2025-10-31 | 13449.4633 |  | 2025-11-30
11 | [5 empty] | 2025-09-17 |  |  |  | 11 | 11. Due Dilligence | [7 empty] | 0
2025-09-18
12 | BDP Commission |  |  |  |  | 2025-09-19 | 0 | 0 |  | 12 | 12. BDP Commission | [10 empty] | 0
12 | BDP Commission |  |  |  |  | 2025-09-20 |  |  |  | 12 | 12. BDP Commission
2025-09-21
13 | Engineering | Matriarch Defects Period |  |  | 10071.95 | 2025-09-22 | 10071.95 | 11445 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 12839.2 |  | Matriarch - INV-5369 | 2025-10-31 | 11445 | 0 | 2025-11-30 | 12839.2
13 | [9 empty] | 13 | 13. Engineering | Management | [6 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | Project manager |  |  | 0 |  |  |  | 0
13 | [9 empty] | 13 | 13. Engineering | Planner time |  |  | 0 |  |  |  | 0
13 | [9 empty] | 13 | 13. Engineering | De Snagging |  |  | 0 |  |  |  | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 1225 | 2025-08-31 | 1225 | 1361 |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  | 2025-08-31 | 0 | 0 | 2025-08-31 | 3159.05
14 | [5 empty] | 2025-09-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  | 2025-09-30 | 0 |  | 2025-09-30
14 | [5 empty] | 2025-10-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  | 2025-10-31 | 0 |  | 2025-10-31
14 | [5 empty] | 2025-11-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 3159.05 |  | Expense Claim | 2025-11-30 | 1361 |  | 2025-12-05
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | Courier of Sonnel Meter |  |  | 298.24 |  | DSV Inv: 180154233 | 2025-11-30 |  | 0 | 2025-12-31 | 298.24
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
| Panel Procurement Budget | 160883.16 |  | 206260
| Inverter Procurement Budget | 74130 |  | 95038
| Mounting Structure Budget | 97648.8 |  | 125191
| DC Equipment Budget | 61800.6 |  | 79232
| AC Equipment Budget | 135950.84 |  | 174296
| Monitoring Budget | 166000 |  | 212821
Optional Extras Budget
MV Equipment Budget
ADD ON
Battery System
Generator
Services
| AC Installer Budget | 17690 |  | 19656
| DC Installer Budget | 36540 |  | 40600
| In-House Expense Budget | 10071.95 |  | 11445
| Compliance Budget | 29000 |  | 32222
| Offloading Budget | 8500 |  | 9444
Roof Access Budget for Equipment
Site storage
| On Site Security | 8400 |  | 9333
| Roof Access Budget for Installers | 9212.27 |  | 10236
EPC Management Fee
ADD ON
Expenses
| Total EE Expense Budget | 1225 |  | 1361

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 1027136 | 1027136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 513568 | 0 | 359497.6 | 0 | 0 | 0 | 0 | 0 | 0 | 102713.6 | 51356.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 513568 | 513568 | 873065.6 | 873065.6 | 873065.6 | 873065.6 | 873065.6 | 873065.6 | 873065.6 | 975779.2 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136
| Planned Expenditure | 817052.62 | 817052.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27337.27 | 54230 | 126648.8 | 0 | 10071.95 | 61800.6 | 0 | 0 | 536964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27337.27 | 81567.27 | 208216.07 | 208216.07 | 218288.02 | 280088.62 | 280088.62 | 280088.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62 | 817052.62
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 513568 | 486230.73 | 791498.33 | 664849.53 | 664849.53 | 654777.58 | 592976.98 | 592976.98 | 592976.98 | 158726.58 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38 | 210083.38
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 1027136 | 1027136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 513568 | 0 | 0 | 0 | 359497.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154070.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 513568 | 513568 | 513568 | 513568 | 873065.6 | 873065.6 | 873065.6 | 873065.6 | 873065.6 | 873065.6 | 873065.6 | 873065.6 | 873065.6 | 873065.6 | 873065.6 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136 | 1027136
| Actual + Planned Expenditure | 770507.27 | 770507.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33961 | 24448.91 | 54396.87 | 0 | 0 | 76428 | 975 | 110020.1 | 231902.68 | 129229.11 | 0 | 0 | 0 | 19416.57 | 3159.05 | 0 | 0 | 0 | 298.24 | 350 | 17317.92 | 0 | 68603.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33961 | 58409.91 | 112806.78 | 112806.78 | 112806.78 | 189234.78 | 190209.78 | 300229.88 | 532132.56 | 661361.67 | 661361.67 | 661361.67 | 661361.67 | 680778.24 | 683937.29 | 683937.29 | 683937.29 | 683937.29 | 684235.53 | 684585.53 | 701903.45 | 701903.45 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27 | 770507.27
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 513568 | 513568 | 513568 | 479607 | 814655.69 | 760258.82 | 760258.82 | 760258.82 | 683830.82 | 682855.82 | 572835.72 | 340933.04 | 211703.93 | 211703.93 | 211703.93 | 365774.33 | 346357.76 | 343198.71 | 343198.71 | 343198.71 | 343198.71 | 342900.47 | 342550.47 | 325232.55 | 325232.55 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73 | 256628.73
|  | CHECK | CHECK
| Revenue Recognition | -3028.1152 | 1030164.1152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 665572.3774 | 0 | 0 | 0 | 0 | 127536.4242 | 0 | 0 | 0 | 213880.4966 | 0 | 0 | 0 | 1361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21813.817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 1030164.1152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 665572.3774 | 665572.3774 | 665572.3774 | 665572.3774 | 665572.3774 | 793108.8016 | 793108.8016 | 793108.8016 | 793108.8016 | 1006989.2982 | 1006989.2982 | 1006989.2982 | 1006989.2982 | 1008350.2982 | 1008350.2982 | 1008350.2982 | 1008350.2982 | 1008350.2982 | 1008350.2982 | 1008350.2982 | 1008350.2982 | 1008350.2982 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152 | 1030164.1152

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 |  | 2026-01-31 | Grand Total
(blank)
1. Panels |  | 206260 |  |  |  | 0 |  | 206260
2. Inverters | 0 | 95038 |  |  |  | 0 |  | 95038
3. Mounting Structures |  |  | 125191 |  |  | 0 |  | 125191
4. DC Equipment | 0 | 79232 |  |  |  | 0 |  | 79232
5. Monitoring |  | 66669.3774 | 2345.4242 | 143794.0333 |  |  |  | 212808.8349
6. AC Equipment | 0 | 174296 |  |  |  | 0 |  | 174296
8. Product Add On
9. AC & DC installation | 0 | 15064 |  | 45192 |  | 0 |  | 60256
10. Site Logistics | 0 | 29013 |  |  |  | 0 |  | 29013
11. Due Dilligence | 0 |  |  | 13449.4633 |  | 0 | 18772.5367 | 32222
13. Engineering | 0 |  |  | 11445 |  | 0 |  | 11445
14. General Expenses |  | 0 | 0 | 0 | 1361 | 0 |  | 1361
15. Service Add On
12. BDP Commission
7.BESS
Grand Total | 0 | 665572.3774 | 127536.4242 | 213880.4966 | 1361 | 0 | 18772.5367 | 1027122.8349

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2026-01-31 | Grand Total
(blank)
1. Panels |  | 149174 |  |  |  |  | 149174
2. Inverters |  | 74130.34 |  |  |  |  | 74130.34
3. Mounting Structures |  |  | 101652.61 |  |  |  | 101652.61
4. DC Equipment |  | 100367 |  |  |  |  | 100367
5. Monitoring |  | 42195.34 | 975 | 45877.37 | 350 |  | 89397.71
6. AC Equipment |  | 126812.12 |  |  |  |  | 126812.12
8. Product Add On
9. AC & DC installation |  | 14827.5 |  | 44482.5 |  |  | 59310
10. Site Logistics |  | 34792 |  |  |  |  | 34792
11. Due Dilligence | 0 |  |  | 6000 |  | 8374.7 | 14374.7
13. Engineering | 0 |  |  | 12839.2 |  |  | 12839.2
14. General Expenses |  | 0 | 0 | 0 | 3159.05 |  | 3159.05
15. Service Add On |  |  |  |  | 298.24 |  | 298.24
12. BDP Commission
7.BESS
Grand Total | 0 | 542298.3 | 102627.61 | 109199.07 | 3807.29 | 8374.7 | 766306.97

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate | [5 empty] | FINANCIAL CLOSE CERTIFICATE
Project Name: | IconSA_KZN
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion: |  |  |  | 1. Financial Close | 1. Financial Close
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 3.914 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 2.0022 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 1.3546 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 3.2417 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
IconSA_KZN |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | IconSA_KZN | 0 | 0 | 0