## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate | [5 empty] | FINANCIAL CLOSE CERTIFICATE
Project Name: | Northpoint Industrial
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion: |  |  |  | 1. Financial Close | 1. Financial Close
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[9 empty] | 2026-01-20 | 2026-01-20
| PROJECT PLAN | Northpoint Industrial | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 260
| PROJECT DEVELOPER | Natasha Watkins-Baker |  |  |  | Target Month | 2025-07-31
| PROJECT MANAGERS | Justin Franke
| CONTRACT VALUE | 2566596.3061
| Phase: | Compliance Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Expected Status | Comment
|  |  | 23 |  |  | 64 |  | 100% | 100%
1 | Project Initiation | 2025-06-17 | 16 | 2025-07-03 | 2025-06-17 | 23 | 2025-07-10 | 100% | 100%
1.1 | BD Handover | 2025-06-17 | 5 | 2025-06-24 | 2025-06-17 | 5 | 2025-06-24 | 100% | 100%
1.2 | Project Introduction | 2025-06-23 | 1 | 2025-06-24 | 2025-06-30 | 1 | 2025-07-01 | 100% | 100%
1.3 | HSE | 2025-06-23 | 8 | 2025-07-03 | 2025-06-30 | 8 | 2025-07-10 | 100% | 100%
1.4 | Installer Kick Off | 2025-06-23 | 1 | 2025-06-24 | 2025-06-30 | 1 | 2025-07-01 | 100% | 100%
1.5 | Project Review | 2025-06-23 | 1 | 2025-06-24 | 2025-06-30 | 1 | 2025-07-01 | 100% | 100%
2 | Site Establishment | 2025-07-07 | 1 | 2025-07-08 | 2025-07-14 | 1 | 2025-07-15 | 100% | 100%
2.1 | Solar Contractor Establishment | 2025-07-07 | 1 | 2025-07-08 | 2025-07-14 | 1 | 2025-07-15 | 100% | 100% |  | 47 | Net Work Days
3 | AC Installation | 2025-06-23 | 35 | 2025-07-28 | 2025-06-30 | 67 | 2025-09-05 | 100% | 100% |  | 9.4 | Total Weeks
3.1 | Inverters delivered | 2025-07-08 | 1 | 2025-07-09 | 2025-06-30 | 1 | 2025-07-01 | 100% | 100% |  | 27.6596 | kW/Week Installation Rate
3.2 | Inverters Mounted | 2025-07-09 | 2 | 2025-07-11 | 2025-07-29 | 0 | 2025-07-29 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-06-23 | 20 | 2025-07-21 | 2025-07-21 | 25 | 2025-08-25 | 100% | 100%
3.4 | AC Works | 2025-07-21 | 5 | 2025-07-28 | 2025-07-29 | 27 | 2025-09-04 | 100% | 100%
3.5 | AC Tie-In | 2025-07-21 | 1 | 2025-07-22 | 2025-09-04 | 1 | 2025-09-05 | 100% | 100%
4 | DC Works | 2025-07-07 | 17 | 2025-07-24 | 2025-06-30 | 73 | 2025-09-11 | 100% | 100%
4.1 | Lifeline Installation (If Applicable) | [6 empty] | 0% | 0%
4.1 | Mounting Structure delivered | 2025-07-07 | 1 | 2025-07-08 | 2025-06-30 | 1 | 2025-07-01 | 100% | 100%
4.2 | Mounting Structure installation | 2025-07-08 | 3 | 2025-07-11 | 2025-07-23 | 1 | 2025-07-24 | 100% | 100%
4.3 | DC Cable delivered | 2025-07-07 | 1 | 2025-07-08 | 2025-07-24 | 1 | 2025-07-25 | 100% | 100%
4.3 | DC Stringing | 2025-07-18 | 4 | 2025-07-24 | 2025-08-26 | 12 | 2025-09-11 | 100% | 100%
5 | Module installation | 2025-07-11 | 10 | 2025-07-21 | 2025-06-30 | 42 | 2025-08-11 | 100% | 100%
5.1 | Module delivery | 2025-07-11 | 1 | 2025-07-14 | 2025-06-30 | 1 | 2025-07-01 | 100% | 100%
5.2 | Module mounting | 2025-07-14 | 5 | 2025-07-21 | 2025-08-01 | 6 | 2025-08-11 | 100% | 100%
6 | Commissioning | 2025-07-28 | 2 | 2025-07-30 | 2025-09-12 | 4 | 2025-09-16 | 100% | 100%
6.1 | Commissioning | 2025-07-28 | 1 | 2025-07-29 | 2025-09-12 | 1 | 2025-09-15 | 100% | 100%
6.2 | Practical Completion | 2025-07-29 | 1 | 2025-07-30 | 2025-09-15 | 1 | 2025-09-16 | 100% | 100%
7 | QA Inspections | 2025-07-28 | 1 | 2025-07-29 | 2025-09-12 | 3 | 2025-09-15 | 100% | 100%
7.1 | Red-Team Inspection | 2025-07-28 | 1 | 2025-07-29 | 2025-09-12 | 1 | 2025-09-15 | 100% | 100%
8 | Project Closure | 2025-07-29 | 10 | 2025-08-08 | 2025-09-15 | 45 | 2025-10-30 | 100% | 100%
8.1 | Equipment serial numbers | 2025-07-29 | 1 | 2025-07-30 | 2025-09-15 | 1 | 2025-09-16 | 100% | 100%
8.2 | Snags completion | 2025-07-29 | 2 | 2025-07-31 | 2025-09-15 | 3 | 2025-09-18 | 100% | 100%
8.3 | System Performance Monitoring | 2025-07-30 | 5 | 2025-08-06 | 2025-09-16 | 5 | 2025-09-23 | 100% | 100%
8.4 | Handover documentation | 2025-07-31 | 1 | 2025-08-01 | 2025-10-15 | 1 | 2025-10-16 | 100% | 100%
8.5 | Handover to Client | 2025-08-01 | 1 | 2025-08-04 | 2025-10-23 | 1 | 2025-10-24 | 100% | 100%
8.6 | Handover to Matriarch | 2025-08-03 | 5 | 2025-08-08 | 2025-10-23 | 5 | 2025-10-30 | 100% | 100% | Justin when is this scheduled?
Formulas:
Natasha Watkins-Baker = MIN([Natasha Watkins-Baker, row below]:E16)
Natasha Watkins-Baker = [Natasha Watkins-Baker, row above]
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Natasha Watkins-Baker],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = [Actual Start, row above]
Actual End = MAX([Actual End, row below]:K16)
Actual End = WORKDAY.INTL([Actual Start],[Target Month],1,Data!$C3:C14)
Expected Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  | FINANCIAL REVIEW | TIMELINE REVIEW | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 2566596.3061 |  | 2566596.3061 |  | 2566596.3061 | Start Date | 2566316.4175 | 1550723.4438 | 0 | -9306.02 | 0 | -11156.52
2 | Planned Expenditure | 2272424.1252 |  | 1541417.4238 |  | 1868123.0238 | 2025-07-14
3 | Planned Profit | 294172.1809 |  | 1025178.8823 |  | 698473.2823 | End Date - PC
4 | Planned Margin | 11.46% |  | 39.94% |  | 27.21% | 2025-08-06
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE |  | MILESTONE NOTES & COMMENTS
1 | Acceptance and Initial Deposit |  | 50% | 1283298.153 | 2025-06-27 | 004773 | 2025-06-23 | 2025-06-25
2 | Delivery of Panels |  | 10% | 256659.6306 | 2025-07-18 | 004787 | 2025-07-21 | 2025-07-25
3 | Delivery of Inverters |  | 25% | 641649.0765 | 2025-07-15 | 004787 | 2025-07-21 | 2025-07-25
4 | Practical Completion |  | 10% | 256659.6306 | 2025-08-06 | 004841 | 2025-09-19 | 2025-10-31
5 | Handover |  | 5% | 128329.8153 | 2025-08-08 | 004861 | 2025-10-28 | 2025-11-25
6 | - |  | 0% | 0
7 | - |  | 0% | 0
|  |  | 100% | 2566596.3061
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 898308.7071
2 | Delivery of Panels |  | 30% | 769978.8918
3 | Delivery of Inverters |  | 20% | 513319.2612
4 | Practical Completion |  | 10% | 256659.6306
5 | Handover |  | 5% | 128329.8153
| Total |  | 100% | 2566596.3061
|  |  | 100% | 2566596.3061

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 2272424.1252 |  | 1541417.4238 | 731006.7013
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 698586.14 |  | 516326.7 | 182259.44
2 | 2. Inverters | 157796 |  | 137740.7 | 20055.3
3 | 3. Mounting Structures | 116964 |  | 40716.32 | 76247.68
4 | 4. DC Equipment | 264529.6 |  | 168174.76 | 96354.84
5 | 5. Monitoring | 174000 |  | 89789.33 | 84210.67
6 | 6. AC Equipment | 274566.9478 |  | 158795.42 | 115771.5278
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 4000 |  | 4814.1 | -814.1
9 | 9. AC & DC installation | 216600 |  | 316500 | -99900
10 | 10. Site Logistics | 100574.1667 |  | 43752.49 | 56821.6767
11 | 11. Due Dilligence | 89000 |  | 26807.91 | 62192.09
12 | 12. BDP Commission | 0 |  | 0 | 0
13 | 13. Engineering | 171432.2707 |  | 32082.4538 | 139349.8169
14 | 14. General Expenses | 4375 |  | 542.64 | 3832.36
15 | 15. Service Add On | 0 |  | 5374.6 | -5374.6
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 2272424.1252 | 2566596.3061 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 1541417.4238
620
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | ERROR on REV |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 698586.14 | 2025-09-01 | 698586.14 | 780543.1732 |  | 1 | 1. Panels | Jinko 590W | 441 | 1168.2 | 515176.2 | PO4057-SNP-20250628 - RV Approved | Menlo INV0003046 | 2025-06-30 | 780543.1732 | 0 | 2025-09-01 | 516326.7
1 |  | Delivery Budget |  |  |  | 2025-10-26 |  |  |  | 1 | 1. Panels |  |  |  | 1150.5 |  | Menlo - INV0003187 | 2025-08-31 | 0 |  | 2025-10-24
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 274566.9478
2 | Inverters | Inverter Budget |  |  | 157796 | 2025-09-01 | 157796 | 176308.3799 |  | 2 | 2. Inverters | Huawei 100KTL | 2 | 68870.35 | 137740.7 | PO4057-SNP-20250628 - RV Approved | Menlo INV0003046 | 2025-06-30 | 176308.3799 | 0 | 2025-09-01 | 137740.7 | DC Equipment | 153169.6
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | AC Labour | 64980
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 151620
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 30532.5
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 1541.6667
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 116964 | 2025-07-29 | 116964 | 130686.0335 |  | 3 | 3. Mounting Structures | Schletter Structure |  |  | 56772 |  | Schletter INV1907 | 2025-06-30 | 130686.0335 | 0 | 2025-07-29 | 40716.32 | Other | 0
3 | [9 empty] | 3 | 3. Mounting Structures | Seam Clamps | 300 | -27.2 | -8160 |  | Allocated to Cpt Storeroom | 2025-09-30 | 0 |  | 2025-09-30 |  | Total | 684910.7145
3 | [9 empty] | 3 | 3. Mounting Structures | Mid Clamps | 648 | -10.95 | -7095.6 |  | Allocated to Cpt Storeroom | 2025-09-30 | 0 |  | 2025-09-30 |  | Less 15% | 582174.1073
3 | [9 empty] | 3 | 3. Mounting Structures | End Clapms | 73 | -10.96 | -800.08 |  | Allocated to Cpt Storeroom | 2025-09-30 | 0 |  | 2025-09-30 |  | R/Wp | 2.2391
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL - Matthews Group | Installer Price
[23 empty] | AC Equipment | 74201.35
4 | DC Equipment | DC Cable Budget | 9147.4286 |  | 111360 | 2025-07-31 | 264529.6 | 295563.7989 |  | 4 | 4. DC Equipment | DC Cable - black from stock (CPT) | 3000 | 13.5 | 40500 | PO4057-SNP-20250628 - RV Approved | Allocated from Cpt Storeroom | 2025-07-31 | 81086.2206 | 0.0004528 | 2025-07-31 | 168174.76 | DC Equipment | 63124.76
4 |  | DC Equipment Budget |  |  | 153169.6 | 2025-07-31 |  |  |  | 4 | 4. DC Equipment | DC Cable - red | 3000 | 13.5 | 40500 |  | Allocated from Cpt Storeroom | 2025-07-31 | 81086.2206 |  | 2025-07-31 |  | AC Labour | 62600
4 | [5 empty] | 2025-08-07 |  |  |  | 4 | 4. DC Equipment | Transport |  |  | 3500 |  | ABL Transport INV0175 | 2025-08-31 | 6151.1805 |  | 2025-08-07 |  | DC Labour | 221000
[6 empty] | 2025-08-31 |  |  |  |  | 4. DC Equipment | DC Cable - from stock (CPT) - black | 1000 | 13.5 | 13500 |  | Allocated from Cpt Storeroom | 2025-08-31 | 48.5817 |  | 2025-08-31
4 | [5 empty] | 2025-10-26 |  |  |  | 4 | 4. DC Equipment | DC Cable - Menlo - Red | 500 | 13.5 | 6750 |  | Menlo - INV0003187 | 2025-08-31 | 11862.9909 |  | 2025-10-26 |  | Offloading
4 | [5 empty] | 2025-07-11 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 63124.76 | 10% | 6312.476 | PO4110-SNP-20250709-MI approved | Matthews Group INV1499 | 2025-07-31 | 12638.3907 |  | 2025-07-11 |  | Scaffolding
4 | [5 empty] | 2025-07-24 |  |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 9468.714 |  | Matthews Group INV1500 | 2025-07-31 | 18957.586 |  | 2025-07-24 |  | Storage
4 | [5 empty] | 2025-09-25 |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 12624.952 |  | Matthews Group INV1515 | 2025-08-31 | 22188.1023 |  | 2025-09-25 |  | Logistics | 24212.5
4 | [5 empty] | 2025-09-04 |  |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 15781.19 |  | Matthews Group INV1515 | 2025-08-31 | 27735.1278 |  | 2025-09-04 |  | HSE | 11500
4 | [5 empty] | 2025-09-25 |  |  |  | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 6312.476 |  | Matthews Group INV1515 | 2025-08-31 | 11094.0511 |  | 2025-09-25 |  | Other | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 6312.476 |  | Matthews Group INV1515 | 2025-08-31 | 11094.0511 |  | 2025-09-25 |  | Other | 0
4 | [5 empty] | 2025-10-02 |  |  |  | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 3156.238 |  | Matthews Group INV1515 | 2025-08-31 | 5547.0256 |  | 2025-11-19 |  | Total | 456638.61
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 3156.238 |  | Matthews Group INV1515 | 2025-08-31 | 5547.0256 |  | 2025-12-04 |  | R/Wp | 1.7563
4 | [5 empty] | 2025-10-26 |  |  |  | 4 | 4. DC Equipment |  |  |  | 300 |  | Menlo - INV0003187 | 2025-08-31 | 527.244 |  | 2025-10-24
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 159000 | 2025-09-01 | 174000 | 194413.4078 |  | 5 | 5. Monitoring | Smartlogger |  |  | 8598.34 | PO4057-SNP-20250628 - RV Approved | Menlo INV0003046 | 2025-06-30 | 13032.5117 | 0.0047163 | 2025-09-01 | 89789.33
5 |  | Revenue Metering |  |  | 15000 | 2025-07-29 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 14668 | PO4065-SNP-20250630 - RV Approved | AccuEnergy - ASAI-005844 | 2025-06-30 | 22232.3009 |  | 2025-07-29
[10 empty] | 5 | 5. Monitoring | Delivery of CT's |  |  | 172 |  | Uber: C/C DS 100902 | 2025-09-30 | 0 |  | 2025-09-10
5 | [5 empty] | 2025-07-31 |  |  |  | 5 | 5. Monitoring | Techsitter |  |  | 11169 |  | Matriarch - INV-4742 | 2025-07-31 | 24496.2351 |  | 2025-07-31
5 | [5 empty] | 2025-08-31 |  |  |  | 5 | 5. Monitoring | APEX DNP3 |  |  | 54000 | PO4128-SNP-20250717 - RV Approved | Rubicon INVWCRE-0069476 | 2025-07-31 | 134198.3778 |  | 2025-08-31
5 | [5 empty] | 2025-08-29 |  |  |  | 5 | 5. Monitoring | Delivery of Techsitter |  |  | 206.99 |  | DSV Inv: 180138260 | 2025-07-31 | 453.9776 |  | 2025-08-29
5 | [5 empty] | 2025-08-30 |  |  |  | 5 | 5. Monitoring | Battery |  |  | 975 |  | Red Pole Energy: SO-35689 | 2025-08-31 | 0 |  | 2025-08-30
[6 empty] | 2025-08-30 |  |  |  | 5 | 5. Monitoring | Powersupply |  |  | 850 |  | Mantech-SOR1007853 | 2025-08-31 | 0 |  | 2025-08-30
[6 empty] | 2025-09-30 |  |  |  | 5 | 5. Monitoring |  |  |  | -850 |  | Mantech-CRN949171 | 2025-09-30 | 0 |  | 2025-09-30
5 | [5 empty] | 2025-10-01 |  |  |  | 5 | 5. Monitoring | [7 empty] | 0
2025-10-02
6 | AC Equipment | AC Equipment Budget |  |  | 274566.9478 | 2025-10-03 | 274566.9478 | 306778.7127 |  | 6 | 6. AC Equipment | [7 empty] | 0 | 0 |  | 158795.42
6 | [5 empty] | 1900-01-29 |  |  |  | 6 | 6. AC Equipment | PVDB |  |  | 84594.07 |  | Switchboard 2-SOI002241 | 2025-08-31 | 163428.2644 |  | 2025-09-30
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [5 empty] | 2025-07-11 |  |  |  | 6 | 6. AC Equipment | Project Kick Off | 74201.35 | 10% | 7420.135 | PO4110-SNP-20250709-MI approved | Matthews Group INV1499 | 2025-07-31 | 14335.0448 |  | 2025-07-11
6 | [5 empty] | 2025-07-24 |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 11130.2025 |  | Matthews Group INV1500 | 2025-07-31 | 21502.5672 |  | 2025-07-24
6 | [5 empty] | 2025-09-25 |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 14840.27 |  | Matthews Group INV1515 | 2025-08-31 | 28670.0896 |  | 2025-09-25
6 | [5 empty] | 2025-09-04 |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 18550.3375 |  | Matthews Group INV1515 | 2025-08-31 | 35837.6121 |  | 2025-09-04
6 | [5 empty] | 2025-09-25 |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 7420.135 |  | Matthews Group INV1515 | 2025-08-31 | 14335.0448 |  | 2025-09-25
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 7420.135 |  | Matthews Group INV1515 | 2025-08-31 | 14335.0448 |  | 2025-09-25
6 | [5 empty] | 2025-10-02 |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 3710.0675 |  | Matthews Group INV1515 | 2025-08-31 | 7167.5224 |  | 2025-11-19
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 3710.0675 |  | Matthews Group INV1515 | 2025-08-31 | 7167.5224 |  | 2025-12-04
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 4000 | 4494.382 |  | 8 | 8. Product Add On | [8 empty] | 0 |  | 4814.1
8 |  | Check Meter |  |  | 4000 | 2025-09-10 |  |  |  | 8 | 8. Product Add On
8 | [5 empty] | 2025-09-11 |  |  |  | 8 | 8. Product Add On | Check Meter |  |  | 3600 | PO4240-ARIM-20250819 - RV Approved | CBB - CBB-5722 | 2025-08-31 | 4494.382 |  | 2025-09-11
8 | [5 empty] | 2025-09-10 |  |  |  | 8 | 8. Product Add On | Battery |  |  | 1214.1 |  | Current Automotion - SOQ324142 | 2025-09-30 |  |  | 2025-09-10
8 | [5 empty] | 2025-09-30 |  |  |  | 8 | 8. Product Add On | [6 empty] | 2025-09-30 |  |  | 2025-09-30
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 64980 | 2025-07-10 | 216600 | 254823.5294 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | -0.002149 |  | 316500
9 |  | DC Installation Budget |  |  | 151620 | 2025-07-11 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 283600 | 10% | 28360 | PO4110-SNP-20250709-MI approved | Matthews Group INV1499 | 2025-07-31 | 22682.9733 |  | 2025-07-11
9 | [5 empty] | 2025-07-24 |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 42540 |  | Matthews Group INV1500 | 2025-07-31 | 34024.46 |  | 2025-07-24
9 | [5 empty] | 2025-09-25 |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 56720 |  | Matthews Group INV1515 | 2025-08-31 | 46043.2129 |  | 2025-09-25
9 | [5 empty] | 2025-09-04 |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 70900 |  | Matthews Group INV1515 | 2025-08-31 | 57083.6911 |  | 2025-09-04
9 | [5 empty] | 2025-09-25 |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 28360 |  | Matthews Group INV1515 | 2025-08-31 | 22833.4764 |  | 2025-09-25
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 28360 |  | Matthews Group INV1515 | 2025-08-31 | 22833.4764 |  | 2025-09-25
9 | [5 empty] | 2025-10-02 |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 14180 |  | Matthews Group INV1515 | 2025-08-31 | 11416.7382 |  | 2025-11-19
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 14180 |  | Matthews Group INV1515 | 2025-08-31 | 11416.7382 |  | 2025-12-04
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [5 empty] | 2025-08-21 |  |  |  | 9 | 9. AC & DC installation | DC Run Trenching | 50% | 32900 | 16450 | PO2916-SNP-20250819 - RV Approved | Ask Fritz - 2508_013 | 2025-08-31 | 13244.3825 |  | 2025-08-21
9 | [5 empty] | 2025-09-11 |  |  |  | 9 | 9. AC & DC installation |  | 50% |  | 16450 |  | Ask Fritz - 2508_013 | 2025-08-31 | 13244.3825 |  | 2025-09-11
10 | Site Logistics | Offloading |  |  | 8500 | 2025-06-26 | 100574.1667 | 118322.549 |  | 10 | 10. Site Logistics | [7 empty] | 0 | 279.8874 |  | 43752.49
10 |  | Scaffolding |  |  | 30532.5 | 2025-06-27 |  |  |  | 10 | 10. Site Logistics | Container Rental |  |  | 6100 |  | Container World PFC02315 | 2025-06-30 | 7082.2279 |  | 2025-06-27
10 |  | Security |  |  | 60000 | 2025-08-07 |  |  |  | 10 | 10. Site Logistics |  |  |  | 100 |  | Container World - C581577 | 2025-06-30 | 116.1021 |  | 2025-08-07
[6 empty] | 2025-08-21 |  |  |  | 10 | 10. Site Logistics |  |  |  | 4900 |  | Container World - CM19731 | 2025-07-31 | 12018.435 |  | 2025-08-21
10 |  | Storage |  |  | 1541.6667 | 2025-09-01 |  |  |  | 10 | 10. Site Logistics | Container Rental - August |  |  | 620 |  | Container World - C585035 | 2025-07-31 | 1546.6185 |  | 2025-09-01
[6 empty] | 2025-09-30 |  |  |  | 10 | 10. Site Logistics | Container Rental - September |  |  | 6600 |  | Container World - C580804 | 2025-08-31 | 17848.7858 |  | 2025-09-30
[6 empty] | 2025-09-30 |  |  |  | 10 | 10. Site Logistics |  |  |  | 600 |  | Container World - C588470 | 2025-08-31 | 1622.6169 |  | 2025-09-30
[6 empty] | 2025-10-30 |  |  |  | 10 | 10. Site Logistics |  |  |  | 620 |  | Container World - C591998 | 2025-09-30 |  |  | 2025-09-30
[6 empty] | 2025-09-30 |  |  |  | 10 | 10. Site Logistics |  |  |  | -5400 |  | Container World - CCM13068 | 2025-08-31 | 0 |  | 2025-09-30
[6 empty] | 2025-09-30 |  |  |  | 10 | 10. Site Logistics |  |  |  | -6100 |  | Container World - PFC02315 | 2025-08-31 | 0 |  | 2025-09-30
[10 empty] | 10 | 10. Site Logistics
10 | [5 empty] | 2025-07-11 |  |  |  | 10 | 10. Site Logistics | Project Kick Off | 35712.5 | 10% | 3571.25 | PO4110-SNP-20250709-MI approved | Matthews Group INV1499 | 2025-07-31 | 8908.649 |  | 2025-07-11
10 | [5 empty] | 2025-07-24 |  |  |  | 10 | 10. Site Logistics | Site Establishment |  | 15% | 5356.875 |  | Matthews Group INV1500 | 2025-07-31 | 13362.9735 |  | 2025-07-24
10 | [5 empty] | 2025-09-25 |  |  |  | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 7142.5 |  | Matthews Group INV1515 | 2025-08-31 | 19593.5548 |  | 2025-09-25
10 | [5 empty] | 2025-09-04 |  |  |  | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 8928.125 |  | Matthews Group INV1515 | 2025-08-31 | 6552.3835 |  | 2025-09-04
10 | [5 empty] | 2025-09-25 |  |  |  | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 3571.25 |  | Matthews Group INV1515 | 2025-08-31 | 9796.7774 |  | 2025-09-25
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 3571.24 |  | Matthews Group INV1515 | 2025-08-31 | 9796.76 |  | 2025-09-25
10 | [5 empty] | 2025-10-02 |  |  |  | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 1785.625 |  | Matthews Group INV1515 | 2025-08-31 | 4898.3887 |  | 2025-11-19
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 1785.625 |  | Matthews Group INV1515 | 2025-08-31 | 4898.3887 |  | 2025-12-04
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2025-08-28 | 89000 | 104705.8824 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 13117 |  | Sunspot Inv: E028 | 2025-07-31 | 48656.6072 | 0.0021971 | 2025-11-28 | 26807.91
11 |  | Structural Sign Off |  |  | 18000 | 2025-08-29 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 7690.91 |  | L&B Inv 1701 | 2025-06-30 | 32614.5743 |  | 2024-08-22
11 |  | SCADA |  |  | 60000 | 2025-08-30 |  |  |  | 11 | 11. Due Dilligence | [7 empty] | 0
11 | [5 empty] | 2025-08-31 |  |  |  | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 |  | Matriarch - INV-4987 | 2025-08-31 | 23434.6987 |  | 2025-08-31
11 | [9 empty] | 11 | 11. Due Dilligence | [7 empty] | 0
12 | BDP Commission | [5 empty] | 0 | 0 |  | 12 | 12. BDP Commission | [10 empty] | 0
12 | BDP Commission | [8 empty] | 12 | 12. BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 26157.7107 | 2025-08-31 | 171432.2707 | 194809.3985 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 32082.4538 |  | Matriarch - INV-4986 | 2025-08-31 | 194809.3985 | 0 | 2025-08-31 | 32082.4538
13 |  | Management |  |  | 20000 | 2025-09-01 |  |  |  | 13 | 13. Engineering | Management |  |  | 0 |  |  |  | 0
13 |  | Project manager |  |  | 68000 | 2025-09-02 |  |  |  | 13 | 13. Engineering | Project manager |  |  | 0 |  |  |  | 0
13 |  | Planner time |  |  | 26000 | 2025-09-03 |  |  |  | 13 | 13. Engineering | Planner time |  |  | 0 |  |  |  | 0
13 |  | De Snagging |  |  | 31274.56 | 2025-09-04 |  |  |  | 13 | 13. Engineering | De Snagging |  |  | 0 |  |  |  | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 4375 | 2025-07-04 | 4375 | 5147.0588 |  | 14 | 14. General Expenses | Travel |  |  | 323.68 |  | Expense Claim | 2025-06-30 | 663.4328 | -0.0040247 | 2025-07-04 | 542.64
14 | [5 empty] | 2025-07-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-07-31 | 0 |  | 2025-07-31
14 | [5 empty] | 2025-08-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-08-31 | 4483.63 |  | 2025-09-05
14 | [5 empty] | 2025-09-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-09-30 | 0 |  | 2025-09-30
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 218.96 |  | Expense Claim | 2025-10-31 | 0 |  | 2025-11-06
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On |  |  |  |  | 2025-09-30 | 0 | 0 |  | 15 | 15. Service Add On | [8 empty] | 0 |  | 5374.6
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On | PLS - Meter Installation |  |  | 3524.1 | PO4493-20251126 - RV Approved | PLS - IN106336 | 2025-12-31 |  |  | 2025-12-12
15 | [9 empty] | 15 | 15. Service Add On | Metronomic - Meter Commissioning |  |  | 1850.5 | PO4494-20251126 - RV Approved |  | 2026-01-31 |  |  | 2026-01-22
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
| Panel Procurement Budget | 698586.14 |  | 780543.1732
| Inverter Procurement Budget | 157796 |  | 176308.3799
| Mounting Structure Budget | 116964 |  | 130686.0335
| DC Equipment Budget | 264529.6 |  | 295563.7989
| AC Equipment Budget | 274566.9478 |  | 306778.7127
| Monitoring Budget | 174000 |  | 194413.4078
| Optional Extras Budget | 0 |  | 0
| MV Metering Budget | 0 |  | 0
| ADD ON | 4000 |  | 4494.382
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 64980 |  | 76447.0588
| DC Installer Budget | 151620 |  | 178376.4706
| In-House Expense Budget | 171432.2707 |  | 194809.3985
| Compliance Budget | 89000 |  | 104705.8824
| Offloading Budget | 8500 |  | 10000
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 1541.6667 |  | 1813.7255
| On Site Security | 60000 |  | 70588.2353
| Roof Access Budget for Installers | 30532.5 |  | 35920.5882
| EPC Management Fee | 0 |  | 0
| ADD ON | 0 |  | 0
Expenses
| Total EE Expense Budget | 4375 |  | 5147.0588
Note on H34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date
Note on W34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date
Note on H108: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment dte
Note on W108: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment dte

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 2566596.3061 | 2566596.3061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1283298.153 | 0 | 0 | 898308.7071 | 0 | 0 | 384989.4459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1283298.153 | 1283298.153 | 1283298.153 | 2181606.8602 | 2181606.8602 | 2181606.8602 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061
| Planned Expenditure | 2272424.1252 | 2272424.1252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39032.5 | 4375 | 216600 | 0 | 0 | 396493.6 | 60000 | 0 | 0 | 115157.7107 | 1162198.3667 | 4000 | 0 | 0 | 274566.9478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39032.5 | 43407.5 | 260007.5 | 260007.5 | 260007.5 | 656501.1 | 716501.1 | 716501.1 | 716501.1 | 831658.8107 | 1993857.1773 | 1997857.1773 | 1997857.1773 | 1997857.1773 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252 | 2272424.1252
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1244265.653 | 1239890.653 | 1023290.653 | 1921599.3602 | 1921599.3602 | 1525105.7602 | 1850095.2061 | 1850095.2061 | 1850095.2061 | 1734937.4954 | 572739.1287 | 568739.1287 | 568739.1287 | 568739.1287 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809 | 294172.1809
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 2566596.3061 | 2566596.3061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1283298.153 | 0 | 0 | 0 | 898308.7071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256659.6306 | 0 | 0 | 0 | 128329.8153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1283298.153 | 1283298.153 | 1283298.153 | 1283298.153 | 2181606.8602 | 2181606.8602 | 2181606.8602 | 2181606.8602 | 2181606.8602 | 2181606.8602 | 2181606.8602 | 2181606.8602 | 2181606.8602 | 2181606.8602 | 2181606.8602 | 2181606.8602 | 2181606.8602 | 2181606.8602 | 2438266.4908 | 2438266.4908 | 2438266.4908 | 2438266.4908 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061 | 2566596.3061
| Actual + Planned Expenditure | 1541417.4238 | 1533726.5138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6100 | 323.68 | 45663.861 | 0 | 68495.7915 | 163609 | 3600 | 0 | 21350 | 107614.4438 | 776294.8925 | 21436.1 | 0 | 182655.434 | 64008.39 | 0 | 0 | 8200.5 | 0 | 218.96 | 0 | 22831.9305 | 13117 | 22831.9305 | 3524.1 | 0 | 0 | 0 | 0 | 0 | 1850.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6100 | 6423.68 | 52087.541 | 52087.541 | 120583.3325 | 284192.3325 | 287792.3325 | 287792.3325 | 309142.3325 | 416756.7763 | 1193051.6688 | 1214487.7688 | 1214487.7688 | 1397143.2028 | 1461151.5928 | 1461151.5928 | 1461151.5928 | 1469352.0928 | 1469352.0928 | 1469571.0528 | 1469571.0528 | 1492402.9833 | 1505519.9833 | 1528351.9138 | 1531876.0138 | 1531876.0138 | 1531876.0138 | 1531876.0138 | 1531876.0138 | 1531876.0138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138 | 1533726.5138
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1277198.153 | 1276874.473 | 1231210.612 | 1231210.612 | 2061023.5277 | 1897414.5277 | 1893814.5277 | 1893814.5277 | 1872464.5277 | 1764850.0838 | 988555.1913 | 967119.0913 | 967119.0913 | 784463.6573 | 720455.2673 | 720455.2673 | 720455.2673 | 712254.7673 | 968914.398 | 968695.438 | 968695.438 | 945863.5075 | 1061076.3228 | 1038244.3923 | 1034720.2923 | 1034720.2923 | 1034720.2923 | 1034720.2923 | 1034720.2923 | 1034720.2923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923 | 1032869.7923
|  | CHECK | CHECK
| Revenue Recognition | 279.8886 | 2566316.4175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1163278.7363 | 0 | 0 | 0 | 529955.3367 | 0 | 0 | 0 | 873082.3445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 2566316.4175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1163278.7363 | 1163278.7363 | 1163278.7363 | 1163278.7363 | 1693234.073 | 1693234.073 | 1693234.073 | 1693234.073 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175 | 2566316.4175

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-12-31 |  | 2026-01-31 | Grand Total
(blank)
1. Panels |  | 780543.1732 |  | 0 |  |  |  | 0 |  | 780543.1732
2. Inverters |  | 176308.3799 | [5 empty] | 0 |  | 176308.3799
3. Mounting Structures |  | 130686.0335 |  |  | 0 |  |  | 0 |  | 130686.0335
4. DC Equipment |  |  | 193768.4178 | 101795.3806 |  |  |  | 0 |  | 295563.7984
5. Monitoring | 0 | 35264.8126 | 159148.5905 | 0 | 0 |  |  |  |  | 194413.4031
6. AC Equipment |  |  | 35837.6121 | 270941.1006 |  |  |  | 0 |  | 306778.7127
8. Product Add On |  |  |  | 4494.382 | [5 empty] | 4494.382
9. AC & DC installation |  |  | 56707.4333 | 198116.0983 |  |  |  | 0 |  | 254823.5316
10. Site Logistics | 0 | 7198.33 | 35836.6759 | 75007.6558 |  |  |  | 0 |  | 118042.6616
11. Due Dilligence |  | 32614.5743 | 48656.6072 | 23434.6987 |  |  |  | 0 |  | 104705.8802
13. Engineering | 0 |  |  | 194809.3985 |  |  |  | 0 |  | 194809.3985
14. General Expenses |  | 663.4328 | 0 | 4483.63 | 0 | 0 |  | 0 |  | 5147.0628
15. Service Add On
12. BDP Commission
7.BESS
Grand Total | 0 | 1163278.7363 | 529955.3367 | 873082.3445 | 0 | 0 |  | 0 |  | 2566316.4175

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-12-31 | 2026-01-31 | Grand Total
(blank)
1. Panels |  | 515176.2 |  | 1150.5 |  |  |  |  | 516326.7
2. Inverters |  | 137740.7 | [6 empty] | 137740.7
3. Mounting Structures |  | 56772 |  |  | -16055.68 |  |  |  | 40716.32
4. DC Equipment |  |  | 96781.19 | 71393.57 |  |  |  |  | 168174.76
5. Monitoring |  | 23266.34 | 65375.99 | 1825 | -678 |  |  |  | 89789.33
6. AC Equipment |  |  | 18550.3375 | 140245.0825 |  |  |  |  | 158795.42
8. Product Add On |  |  |  | 3600 | 1214.1 |  |  |  | 4814.1
9. AC & DC installation |  |  | 70900 | 245600 |  |  |  |  | 316500
10. Site Logistics |  | 6200 | 14448.125 | 22484.365 | 620 |  |  |  | 43752.49
11. Due Dilligence |  | 7690.91 | 13117 | 6000 |  |  |  |  | 26807.91
13. Engineering | 0 |  |  | 32082.4538 |  |  |  |  | 32082.4538
14. General Expenses |  | 323.68 | 0 | 0 | 0 | 218.96 |  |  | 542.64
15. Service Add On | [6 empty] | 3524.1 | 1850.5 | 5374.6
12. BDP Commission
7.BESS
Grand Total | 0 | 747169.83 | 279172.6425 | 524380.9713 | -14899.58 | 218.96 | 3524.1 | 1850.5 | 1541417.4238

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 1.0688 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.54676 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.3699 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 0.88523 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
Northpoint Industrial |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Northpoint Industrial | 0 | 0 | 0