## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate |  |  |  | FINANCIAL CLOSE CERTIFICATE
Project Name: | Topsteel
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Product Agreement
EPC Agreement
O&M Agreeement
Cost Proposal
Deposit Received
Risks / Notes
Acknowledgement and Acceptance:
Role | Name | Signature | Date

## Certificate - Planning
Emergent Energy – Planning Phase Completion Certificate |  |  |  | PLANNING CERTIFICATE
Project Name: | Topsteel
Client Representative:
Programme Manager: | Roedolph Venter
Project Manager: | Justin Franke
Project Engineer:
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Project Introduction Presentation | Y
Project Brief | Y
Engineering Pack
BOQ | Y
PO – Material & Equipment | Y
PO - Contractors | Y
HSE – NOC | Y
HSE – EE File
HSE – Contractor File
SSEG Application | Y
Risks / Notes | PVDB Board lead time
Acknowledgement and Acceptance:
Role | Name | Signature | Date

## Change Register
Change Register
ID | Description | Supporting Image (If Applicable) | Impact | Proposed Date | Proposed By | Status | Approved By | Approved Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
DEC011
DEC012
DEC013
DEC014
DEC015
DEC016
DEC017
DEC018
DEC019
DEC020
DEC021
DEC022
DEC023
DEC024
DEC025
DEC026
DEC027
DEC028
DEC029
DEC030

## BOQ
Item | Supplier | Description | Quantity | Comments
PV Module | MSA | 610W Jinko Solar | 448
DC Cable Red & Black | MSA |  | 6000
Inverters | MSA | Huawei 100KTL | 2
Mounting Structure | Schletter | Kliplok Seamclamp | 273kWp
Current Transformers (Production) | Accuenergy | AcuCT-2031-600/5A | 3
Current Transformers (Consumption)
Solar Production Meter (Techistter) | Techsitter | Revenue Grade Meter | 1
Grid Consumption Meter
Wi-Fi Router & Sim | Accuenergy | Teltonika RTU241 | 1
Switch | Accuenergy | TSW200 5 port Ethernet | 1
Back Up Battery | Red Pole | RP-12V-18AH LiFePo4 | 1
PVDB | Switchboard |  | 1
Supplier List
Accuenergy
Krannich
Menlo
Red Pole
Schletter
Switchboard
Techsitter
MSA

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC |  |  |  | In progress
7.1 Agreement |  |  |  | In progress
13.2 Agreement |  |  |  | In progress
EE File |  |  |  | In progress
Subbie File |  |  |  | Not appointed yet
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[9 empty] | 2026-02-02 | 2026-02-02
| PROJECT PLAN | Topsteel |  |  | Net Work Days |  | 36 |  | 0 | 1
| PROJECT SIZE (kWp) | 273 |  |  | Total Weeks |  | 7.2
| PROJECT DEVELOPER | Cole Bisset |  |  | kW/Week Installation Rate |  | 37.9167
| PROJECT MANAGERS | Justin Franke
| CONTRACT VALUE | 2345835.8965
| Phase: | Construction
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration | Planned End | Actual Start | Duration | Actual End | Status | Expected Status | Comment
|  |  | 42 |  |  | 49 |  | 32.09% | 39.48% |  | 2026-02-02 | 2026-02-02
[11 empty] | 1 | 0
1 | Project Initiation | 2026-01-14 | 16 | 2026-01-30 | 2026-01-14 | 16 | 2026-01-30 | 100% | 100%
1.1 | Project Charter Handover | 2026-01-14 | 1 | 2026-01-15 | 2026-01-14 | 1 | 2026-01-15 | 100% | 100% |  | Milestone | Start Date | Duration | End Date
1.2 | HSE Readiness and Signoff | 2026-01-15 | 8 | 2026-01-27 | 2026-01-15 | 8 | 2026-01-27 | 100% | 100% |  | Project Initiation | 2026-01-14 | 16 | 2026-01-30
1.3 | Project Introduction | 2026-01-27 | 1 | 2026-01-28 | 2026-01-27 | 1 | 2026-01-28 | 100% | 100% |  | Site Establishment | 2026-01-27 | 1 | 2026-01-28
1.4 | Installer Kick Off | 2026-01-29 | 1 | 2026-01-30 | 2026-01-29 | 1 | 2026-01-30 | 100% | 100% |  | AC Installation | 2026-01-13 | 44 | 2026-02-26
1.5 | Project Review | 2026-01-25 | 1 | 2026-01-26 | 2026-01-25 | 1 | 2026-01-26 | 100% | 100% |  | DC Works | 2026-01-27 | 38 | 2026-03-06
[11 empty] | Module installation | 2026-01-27 | 27 | 2026-02-23
2 | Site Establishment | 2026-01-27 | 1 | 2026-01-28 | 2026-01-27 | 1 | 2026-01-28 | 100% | 100% |  | Commissioning | 2026-03-06 | 11 | 2026-03-17
2.1 | Solar Contractor Establishment | 2026-01-27 | 1 | 2026-01-28 | 2026-01-27 | 1 | 2026-01-28 | 100% | 100% |  | QA Inspections | 2026-03-10 | 8 | 2026-03-18
[11 empty] | Project Closure | 2026-03-13 | 18 | 2026-03-31
3 | AC Installation | 2026-01-13 | 36 | 2026-02-18 | 2026-01-13 | 44 | 2026-02-26 | 40.97% | 40.86%
3.1 | Inverters delivered | 2026-01-28 | 1 | 2026-01-29 | 2026-01-28 | 1 | 2026-01-29 | 100% | 100%
3.2 | Inverters Mounted | 2026-01-29 | 1 | 2026-01-30 | 2026-02-10 | 1 | 2026-02-11 | 0% | 0%
3.3 | Solar DB Lead Time | 2026-01-13 | 25 | 2026-02-17 | 2026-01-13 | 24 | 2026-02-16 | 59% | 58.82%
3.4 | AC Works | 2026-01-28 | 15 | 2026-02-18 | 2026-02-12 | 10 | 2026-02-26 | 0% | 0%
3.5 | AC Tie-In | 2026-01-28 | 1 | 2026-01-29 | 2026-02-12 | 1 | 2026-02-13 | 0% | 0%
4 | DC Works | 2026-01-27 | 31 | 2026-02-27 | 2026-01-27 | 38 | 2026-03-06 | 6.667% | 24.99%
4.1 | Mounting Structure delivered | 2026-01-27 | 1 | 2026-01-28 | 2026-01-27 | 1 | 2026-01-28 | 100% | 100%
4.2 | Mounting Structure installation | 2026-01-28 | 3 | 2026-02-02 | 2026-02-04 | 3 | 2026-02-09 | 0% | 0%
4.3 | DC Cable delivered | 2026-02-04 | 1 | 2026-02-05 | 2026-01-29 | 1 | 2026-01-30 | 100% | 100%
4.4 | DC Stringing | 2026-02-13 | 10 | 2026-02-27 | 2026-02-20 | 10 | 2026-03-06 | 0% | 0%
5 | Module installation | 2026-01-27 | 20 | 2026-02-16 | 2026-01-27 | 27 | 2026-02-23 | 9.091% | 49.99%
5.1 | Module delivery | 2026-01-27 | 1 | 2026-01-28 | 2026-01-27 | 1 | 2026-01-28 | 100% | 100%
5.2 | Module mounting | 2026-02-02 | 10 | 2026-02-16 | 2026-02-09 | 10 | 2026-02-23 | 0% | 0%
6 | Commissioning | 2026-02-27 | 11 | 2026-03-10 | 2026-03-06 | 11 | 2026-03-17 | 0% | 0%
6.1 | Commissioning | 2026-02-27 | 1 | 2026-03-02 | 2026-03-06 | 1 | 2026-03-09 | 0% | 0%
6.2 | Practical Completion | 2026-03-02 | 1 | 2026-03-03 | 2026-03-09 | 1 | 2026-03-10 | 0% | 0%
6.3 | System Performance Monitoring | 2026-03-03 | 5 | 2026-03-10 | 2026-03-10 | 5 | 2026-03-17 | 0% | 0%
7 | QA Inspections | 2026-03-03 | 8 | 2026-03-11 | 2026-03-10 | 8 | 2026-03-18 | 0% | 0%
7.1 | Red-Team Inspection | 2026-03-03 | 3 | 2026-03-06 | 2026-03-10 | 3 | 2026-03-13 | 0% | 0%
7.2 | Snags completion | 2026-03-06 | 3 | 2026-03-11 | 2026-03-13 | 3 | 2026-03-18 | 0% | 0%
8 | Project Closure | 2026-03-06 | 18 | 2026-03-24 | 2026-03-13 | 18 | 2026-03-31 | 0% | 0%
8.1 | Handover documentation | 2026-03-06 | 7 | 2026-03-17 | 2026-03-13 | 7 | 2026-03-24 | 0% | 0%
8.2 | Handover to Client | 2026-03-17 | 1 | 2026-03-18 | 2026-03-24 | 1 | 2026-03-25 | 0% | 0%
8.3 | Handover to Matriarch | 2026-03-17 | 5 | 2026-03-24 | 2026-03-24 | 5 | 2026-03-31 | 0% | 0%
Formulas:
Planned Start = MIN([Planned Start, row below]:E17)
Planned Start = [Planned End, row above]
Planned End = MAX([Planned End, row below]:G17)
Planned End = WORKDAY.INTL([Planned Start],[Duration],1,Data!$C3:C60)
Actual Start = MIN([Actual Start, row below]:I17)
Actual Start = [Actual End, row above]
Actual End = MAX([Actual End, row below]:K17)
Actual End = WORKDAY.INTL([Actual Start],[Duration],1,Data!$C3:C60)
Expected Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING | [11 empty] | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
|  | COSTED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW |  |  |  | 2345835.8965 | 1713981.6787 | 1430350.9937 | 1068855.525
1 | Planned Revenue | 2345835.8965 |  | 2345835.8965 |  |  |  | Start Date
2 | Planned Expenditure | 1920067.6241 |  | 1713981.6787 | VO PM LIMIT | CURRENT VO Total
3 | Planned Profit | 425768.2724 |  | 631854.2178 | 21288.4136 | 0 |  | End Date - PC
4 | Planned Margin | 18.15% |  | 26.94%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE REQUIREMENTS & COMMENTS | MILESTONE DOCUMENTS RECEIVED
1 | Acceptance and Initial Deposit |  | 50% | 1172917.9483 |  | 2025-12-31 | 004890 | 2025-12-02 | 2025-12-18 |  | FALSE |  |  |  |  | 1900-01-06
2 | Delivery of Panels |  | 25% | 586458.9741 |  | 2026-02-04 |  |  | 2026-02-18 |  | FALSE
3 | Delivery of Inverters |  | 10% | 234583.5897 |  | 2026-02-05 |  |  | 2026-02-19 |  | FALSE
4 | Practical Completion |  | 10% | 234583.5897 |  | 2026-03-17 |  |  | 2026-04-07 |  | FALSE
5 | Handover |  | 5% | 117291.7948 |  | 2026-03-25 |  |  | 2026-04-15 |  | FALSE
6 | - |  | 0% | 0 | [6 empty] | FALSE
7 | - |  | 0% | 0 | [6 empty] | FALSE
|  |  | 100% | 2345835.8965
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 821042.5638
2 | Delivery of Panels |  | 30% | 703750.769
3 | Delivery of Inverters |  | 20% | 469167.1793
4 | Practical Completion |  | 10% | 234583.5897
5 | Handover |  | 5% | 117291.7948
| Total |  | 100% | 2345835.8965
|  |  | 100% | 2345835.8965

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from Costed
EXPENDITURE |  | 1920067.6241 |  | 1713981.6787 | 206085.9454
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 597474.8 |  | 586950 | 10524.8
2 | 2. Inverters | 210000 |  | 206611.05 | 3388.95
3 | 3. Mounting Structures | 109312 |  | 45028 | 64284
4 | 4. DC Equipment | 209866.8 |  | 218112.78 | -8245.98
5 | 5. Monitoring | 49000 |  | 37582.84 | 11417.16
6 | 6. AC Equipment | 349524.5522 |  | 162851.62 | 186672.9322
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 0 |  | 0 | 0
9 | 9. AC & DC installation | 217280 |  | 286650 | -69370
10 | 10. Site Logistics | 60238.2667 |  | 51200 | 9038.2667
11 | 11. Due Dilligence | 89000 |  | 84500 | 4500
12 | 12. BDP Commission | 0 |  | 0 | 0
13 | 13. Engineering | 23646.2052 |  | 29322.9487 | -5676.7435
14 | 14. General Expenses | 4725 |  | 5172.44 | -447.44
15 | 15. Service Add On | 0 |  | 0 | 0
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 1920067.6241 | 2345835.8965 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 1713981.6787
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FORECASTED PAYMENT DATE | Total COS | ERROR on REV |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 597474.8 | 2026-03-28 | 597474.8 | 746843.5 |  | 1 | 1. Panels | Panel Size -- 610W a | 447.541 | 1311.5 | 586950 |  | MSA Energy INV0003560 | 2026-01-31 | 746843.5 | 0 | 2026-03-26 | 586950
1 |  | Delivery Budget | [7 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 349524.5522 | Includes the PVDB price, see price below in actual excluding DB price. This is what the contractor can quote us for.
2 | Inverters | Inverter Budget |  |  | 210000 | 2026-03-29 | 210000 | 262500 |  | 2 | 2. Inverters | [7 empty] | 0 | 0 |  | 206611.05 | DC Equipment | 130066.8
2 | [9 empty] | 2 | 2. Inverters | Huawei 100KTL | 3 | 68870.35 | 206611.05 |  | MSA Energy INV0003560 | 2026-01-31 | 262500 |  | 2026-03-26 |  | AC Labour | 68320
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 148960
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 18228.2667
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 1110
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
[23 empty] | Trenching | 0
3 | Mounting Structures | Structure Budget |  |  | 109312 | 2026-02-26 | 109312 | 136640 |  | 3 | 3. Mounting Structures | Schletter Structure |  |  | 45028 | PO4564-TPS-20260121 - RV Approved | Schletter Inv: INV002586 | 2026-01-31 | 136640 | 0 | 2026-02-27 | 45028 | Other | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Total | 724709.6188
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Less 15% | 616003.176
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | R/Wp | 2.2564
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL | Installer Price Cosmic Sun
[23 empty] | AC Equipment | 79500
4 | DC Equipment | DC Cable Budget | 5700 |  | 79800 | 2026-04-05 | 209866.8 | 262333.5 |  | 4 | 4. DC Equipment | DC Cable | 6000 | 13.99 | 83940 |  | MSA Energy INV0003560 | 2026-01-31 | 100958.2015 | 0 | 2026-03-26 | 218112.78 | DC Equipment | 134172.78
4 |  | DC Equipment Budget |  |  | 130066.8 | 2026-02-27 |  |  |  | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | AC Labour | 90090
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | DC Labour | 196560
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Offloading | 2750
4 | [9 empty] | 4 | 4. DC Equipment | Project Kick Off | 134172.78 | 10% | 13417.278 |  | Cosmic Sun - CS_TPS_001 | 2026-01-31 | 16137.5299 |  | 2026-01-29 |  | Roof Access (Geda Lift) | 11550
4 | [9 empty] | 4 | 4. DC Equipment | Site Establishment |  | 15% | 20125.917 |  | Cosmic Sun - CS_TPS_002 | 2026-01-31 | 24206.2948 |  | 2026-02-05 |  | HSE | 4500
4 | [9 empty] | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 26834.556 |  |  | 2026-03-31 | 32275.0597 |  | 2026-03-05 |  | Logistics | 0
4 | [9 empty] | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 33543.195 |  |  | 2026-03-31 | 40343.8246 |  | 2026-03-13 |  | Trenching | 0
4 | [9 empty] | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 13417.278 |  |  | 2026-03-31 | 16137.5299 |  | 2026-03-24 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 13417.278 |  |  | 2026-03-31 | 16137.5299 |  | 2026-03-25 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 6708.639 |  |  | 2026-03-31 | 8068.7649 |  | 2026-03-25 |  | Total | 519122.78
4 | [9 empty] | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 6708.639 |  |  | 2026-04-30 | 8068.7649 |  | 2026-04-17 |  | R/Wp | 1.9015
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Smartlogger 3000 |  |  | 26000 | 2026-03-19 | 49000 | 61250 |  | 5 | 5. Monitoring | Smartlogger 3000 |  |  | 8598.34 |  | MSA Energy INV0003560 | 2026-01-31 | 14012.9997 | 0 | 2026-03-26 | 37582.84
5 |  | Comms DB |  |  | 8000 | 2026-03-19 |  |  |  | 5 | 5. Monitoring | Comms DB |  |  | 13984.5 | PO4576-TPS-20260126 - RV Approved |  | 2026-02-28 | 22791.0032 |  | 2026-03-30
5 |  | Revenue Grade Meter |  |  | 15000 | 2026-03-19 |  |  |  | 5 | 5. Monitoring | Revenue Grade Meter |  |  | 15000 |  |  | 2026-02-28 | 24445.9972 |  | 2026-03-30
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 349524.5522 | 2026-03-19 | 349524.5522 | 436905.6902 |  | 6 | 6. AC Equipment | [7 empty] | 0 | 0 |  | 162851.62
6 | [9 empty] | 6 | 6. AC Equipment | PVDB |  |  | 83351.62 | PO4591-TPS-20260129 - RV Approved |  | 2026-02-28 | 223619.4953 |  | 2026-03-30
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | Project Kick Off | 79500 | 10% | 7950 |  | Cosmic Sun - CS_TPS_001 | 2026-01-31 | 21328.6195 |  | 2026-01-29
6 | [9 empty] | 6 | 6. AC Equipment | Site Establishment |  | 15% | 11925 |  | Cosmic Sun - CS_TPS_002 | 2026-01-31 | 31992.9292 |  | 2026-02-05
6 | [9 empty] | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 15900 |  |  | 2026-03-31 | 42657.239 |  | 2026-03-05
6 | [9 empty] | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 19875 |  |  | 2026-03-31 | 53321.5487 |  | 2026-03-13
6 | [9 empty] | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 7950 |  |  | 2026-03-31 | 21328.6195 |  | 2026-03-24
6 | [9 empty] | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 7950 |  |  | 2026-03-31 | 21328.6195 |  | 2026-03-25
6 | [9 empty] | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 3975 |  |  | 2026-03-31 | 10664.3097 |  | 2026-03-25
6 | [9 empty] | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 3975 |  |  | 2026-04-30 | 10664.3097 |  | 2026-04-17
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 0 | 0 |  | 8 | 8. Product Add On | [7 empty] | 0 |  |  | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 68320 | 2026-02-25 | 217280 | 241422.2222 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0 |  | 286650
9 |  | DC Installation Budget |  |  | 148960 | 2026-03-06 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 286650 | 10% | 28665 |  | Cosmic Sun - CS_TPS_001 | 2026-01-31 | 24142.2222 |  | 2026-01-29
9 | [9 empty] | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 42997.5 |  | Cosmic Sun - CS_TPS_002 | 2026-01-31 | 36213.3333 |  | 2026-02-05
9 | [9 empty] | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 57330 |  |  | 2026-03-31 | 48284.4444 |  | 2026-03-05
9 | [9 empty] | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 71662.5 |  |  | 2026-03-31 | 60355.5556 |  | 2026-03-13
9 | [9 empty] | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 28665 |  |  | 2026-03-31 | 24142.2222 |  | 2026-03-24
9 | [9 empty] | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 28665 |  |  | 2026-03-31 | 24142.2222 |  | 2026-03-25
9 | [9 empty] | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 14332.5 |  |  | 2026-03-31 | 12071.1111 |  | 2026-03-25
9 | [9 empty] | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 14332.5 |  |  | 2026-04-30 | 12071.1111 |  | 2026-04-17
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2026-02-25 | 60238.2667 | 66931.4074 |  | 10 | 10. Site Logistics | Security |  |  | 32400 |  |  | 2026-03-31 | 42355.0312 | 0 | 2026-03-05 | 51200
10 |  | Scaffolding |  |  | 18228.2667 | 2026-02-25 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Security |  |  | 32400 | 2026-02-25 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 1110 | 2026-02-25 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | Project Kick Off | 18800 | 10% | 1880 |  | Cosmic Sun - CS_TPS_001 | 2026-01-31 | 2457.6376 |  | 2026-01-29
10 | [9 empty] | 10 | 10. Site Logistics | Site Establishment |  | 15% | 2820 |  | Cosmic Sun - CS_TPS_002 | 2026-01-31 | 3686.4564 |  | 2026-02-05
10 | [9 empty] | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 3760 |  |  | 2026-03-31 | 4915.2752 |  | 2026-03-05
10 | [9 empty] | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 4700 |  |  | 2026-03-31 | 6144.094 |  | 2026-03-13
10 | [9 empty] | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 1880 |  |  | 2026-03-31 | 2457.6376 |  | 2026-03-24
10 | [9 empty] | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 1880 |  |  | 2026-03-31 | 2457.6376 |  | 2026-03-25
10 | [9 empty] | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 940 |  |  | 2026-03-31 | 1228.8188 |  | 2026-03-25
10 | [9 empty] | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 940 |  |  | 2026-04-30 | 1228.8188 |  | 2026-04-17
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2026-03-10 | 89000 | 98888.8889 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 11000 |  |  | 2026-03-31 | 12873.1098 | 0 | 2026-03-31 | 84500
11 |  | Structural sign off |  |  | 18000 | 2026-03-10 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 7500 |  | L&B Consulting - Inv 2039 | 2025-12-31 | 8777.1203 |  | 2025-09-04
11 |  | Scada for CoCT |  |  | 60000 | 2026-03-10 |  |  |  | 11 | 11. Due Dilligence | SCADA for CoCT |  |  | 60000 |  |  | 2026-04-30 | 70216.9625 |  | 2026-05-30
11 | [9 empty] | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 |  |  | 2026-03-31 | 7021.6963 |  | 2026-03-31
11 | [9 empty] | 11 | 11. Due Dilligence | [7 empty] | 0
12 | BDP Commission | PD Fee |  |  | 0 |  | 0 | 0 |  | 12 | 12. BDP Commission | PD Fee |  |  | 0 | [6 empty] | 0
12 | BDP Commission | [8 empty] | 12 | 12. BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 23646.2052 | 2026-03-24 | 23646.2052 | 26870.6878 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 29322.9487 |  |  | 2026-03-31 | 26870.6878 | 0 | 2026-03-17 | 29322.9487
13 | [9 empty] | 13 | 13. Engineering | Management | [5 empty] | 2026-03-31 | 0 |  | 2026-03-17
13 | [9 empty] | 13 | 13. Engineering | Project manager | [5 empty] | 2026-03-31 | 0 |  | 2026-03-17
13 | [9 empty] | 13 | 13. Engineering | Planner time | [5 empty] | 2026-03-31 | 0 |  | 2026-03-17
13 | [9 empty] | 13 | 13. Engineering | De Snagging | [5 empty] | 2026-03-31 | 0 |  | 2026-03-17
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 4725 | 2026-03-24 | 4725 | 5250 |  | 14 | 14. General Expenses | Travel |  |  | 447.44 |  | Exepnse Claim | 2025-12-31 | 454.1493 | 0 | 2026-01-08 | 5172.44
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 1181.25 |  |  | 2026-01-31 | 1198.9627 |  | 2026-02-07
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 1181.25 |  |  | 2026-02-28 | 1198.9627 |  | 2026-03-07
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 1181.25 |  |  | 2026-03-31 | 1198.9627 |  | 2026-04-07
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 1181.25 |  |  | 2026-04-30 | 1198.9627 |  | 2026-05-07
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | [8 empty] | 0 |  | 0
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
| Panel Procurement Budget | 597474.8 |  | 746843.5
| Inverter Procurement Budget | 210000 |  | 262500
| Mounting Structure Budget | 109312 |  | 136640
| DC Equipment Budget | 209866.8 |  | 262333.5
| AC Equipment Budget | 349524.5522 |  | 436905.6902
| Monitoring Budget | 49000 |  | 61250
| Optional Extras Budget | 0 |  | 0
| MV Equipment Budget | 0 |  | 0
| ADD ON | 0 |  | 0
| Check Meter | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 68320 |  | 75911.1111
| DC Installer Budget | 148960 |  | 165511.1111
| In-House Expense Budget | 23646.2052 |  | 26870.6878
| Compliance Budget | 89000 |  | 98888.8889
| Offloading Budget | 8500 |  | 9444.4444
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 1110 |  | 1233.3333
| On Site Security | 32400 |  | 36000
| Roof Access Budget for Installers | 18228.2667 |  | 20253.6296
| EPC Management Fee | 0 |  | 0
| ADD ON | 0 |  | 0
Expenses
| Total EE Expense Budget | 4725 |  | 5250

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-11-03 to 2031-04-21
PLANNED |  | CHECK | CHECK
| Planned Revenue | 2345835.8965 | 2345835.8965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1172917.9483 | 0 | 0 | 0 | 0 | 821042.5638 | 0 | 0 | 0 | 0 | 0 | 234583.5897 | 117291.7948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1172917.9483 | 1172917.9483 | 1172917.9483 | 1172917.9483 | 1172917.9483 | 1993960.512 | 1993960.512 | 1993960.512 | 1993960.512 | 1993960.512 | 1993960.512 | 2228544.1017 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965
| Planned Expenditure | 1920067.6241 | 1920067.6241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 367937.0667 | 148960 | 89000 | 398524.5522 | 835846.0052 | 79800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 367937.0667 | 516897.0667 | 605897.0667 | 1004421.6188 | 1840267.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241 | 1920067.6241
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1172917.9483 | 1172917.9483 | 1172917.9483 | 1172917.9483 | 1172917.9483 | 1993960.512 | 1993960.512 | 1993960.512 | 1626023.4454 | 1477063.4454 | 1388063.4454 | 1224122.4828 | 505568.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724 | 425768.2724
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 2345835.8965 | 2345835.8965 | 0 | 0 | 0 | 0 | 0 | 0 | 1172917.9483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 821042.5638 | 0 | 0 | 0 | 0 | 0 | 0 | 234583.5897 | 117291.7948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1172917.9483 | 1172917.9483 | 1172917.9483 | 1172917.9483 | 1172917.9483 | 1172917.9483 | 1172917.9483 | 1172917.9483 | 1172917.9483 | 1993960.512 | 1993960.512 | 1993960.512 | 1993960.512 | 1993960.512 | 1993960.512 | 1993960.512 | 2228544.1017 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965
| Actual + Planned Expenditure | 1713981.6787 | 1706481.6787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447.44 | 0 | 0 | 51912.278 | 79049.667 | 0 | 0 | 45028 | 137405.806 | 129780.695 | 29322.9487 | 1015880.085 | 129336.12 | 1181.25 | 25956.139 | 0 | 0 | 1181.25 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447.44 | 447.44 | 447.44 | 52359.718 | 131409.385 | 131409.385 | 131409.385 | 176437.385 | 313843.191 | 443623.886 | 472946.8347 | 1488826.9197 | 1618163.0397 | 1619344.2897 | 1645300.4287 | 1645300.4287 | 1645300.4287 | 1646481.6787 | 1646481.6787 | 1646481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787 | 1706481.6787
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1172917.9483 | 1172917.9483 | 1172917.9483 | 1172470.5083 | 1172470.5083 | 1172470.5083 | 1120558.2303 | 1041508.5633 | 1041508.5633 | 1862551.127 | 1817523.127 | 1680117.321 | 1550336.626 | 1521013.6773 | 505133.5923 | 375797.4723 | 609199.812 | 700535.4678 | 700535.4678 | 700535.4678 | 699354.2178 | 699354.2178 | 699354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178 | 639354.2178
|  | CHECK | CHECK
| Revenue Recognition | 0 | 2345835.8965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9231.2696 | 0 | 0 | 0 | 1422318.6868 | 0 | 0 | 0 | 272055.4583 | 0 | 0 | 0 | 0 | 538781.552 | 0 | 0 | 0 | 103448.9298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 2345835.8965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9231.2696 | 9231.2696 | 9231.2696 | 9231.2696 | 1431549.9564 | 1431549.9564 | 1431549.9564 | 1431549.9564 | 1703605.4147 | 1703605.4147 | 1703605.4147 | 1703605.4147 | 1703605.4147 | 2242386.9667 | 2242386.9667 | 2242386.9667 | 2242386.9667 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965 | 2345835.8965

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | Grand Total
(blank)
1. Panels |  |  | 0 | 746843.5 |  |  |  | 746843.5
2. Inverters | 0 |  | 0 | 262500 |  |  |  | 262500
3. Mounting Structures |  |  | 0 | 136640 |  |  |  | 136640
4. DC Equipment |  |  | 0 | 37267.7157 | 143076.8098 | 74535.4314 | 7453.5431 | 262333.5
5. Monitoring |  |  | 0 |  | 50732.3232 | 10517.6768 |  | 61250
6. AC Equipment |  |  | 0 | 45860.4746 | 290152.1715 | 91720.9492 | 9172.0949 | 436905.6902
8. Product Add On
9. AC & DC installation |  |  | 0 | 60355.5556 | 48284.4444 | 120711.1111 | 12071.1111 | 241422.2222
10. Site Logistics |  |  | 0 | 7062.4993 | 44331.4098 | 14124.9985 | 1412.4999 | 66931.4074
11. Due Dilligence |  | 8777.1203 | 0 |  |  | 19894.806 | 70216.9625 | 98888.8889
13. Engineering |  |  | 0 |  |  | 26870.6878 |  | 26870.6878
14. General Expenses |  | 454.1493 | 0 | 1198.9627 | 1198.9627 | 1198.9627 | 1198.9627 | 5250
15. Service Add On
12. BDP Commission
7.BESS
Grand Total | 0 | 9231.2696 | 0 | 1297728.7078 | 577776.1214 | 359574.6235 | 101525.1742 | 2345835.8965

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | Grand Total
(blank)
1. Panels |  |  |  | 586950 |  |  |  | 586950
2. Inverters |  |  |  | 204000 |  |  |  | 204000
3. Mounting Structures |  |  |  | 80000 |  |  |  | 80000
4. DC Equipment |  |  |  | 27639.195 | 106111.356 | 55278.39 | 5527.839 | 194556.78
5. Monitoring |  |  |  |  | 41000 | 8500 |  | 49500
6. AC Equipment |  |  |  | 12815.9798 | 81084.7339 | 25631.9597 | 2563.196 | 122095.8693
8. Product Add On
9. AC & DC installation |  |  |  | 46172 | 36937.6 | 92344 | 9234.4 | 184688
10. Site Logistics |  |  |  | 5915.6317 | 37132.5053 | 11831.2633 | 1183.1263 | 56062.5267
11. Due Dilligence |  | 7500 |  |  |  | 17000 | 60000 | 84500
13. Engineering | [5 empty] | 29322.9487 |  | 29322.9487
14. General Expenses |  | 447.44 |  | 1181.25 | 1181.25 | 1181.25 | 1181.25 | 5172.44
15. Service Add On
12. BDP Commission |  |  | 0 |  |  |  |  | 0
7.BESS
Grand Total |  | 7947.44 | 0 | 964674.0565 | 303447.4452 | 241089.8117 | 79689.8113 | 1596848.5647

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill
2025-12-15 | Builders Break
2025-12-16 | Builders Break
2025-12-17 | Builders Break
2025-12-18 | Builders Break
2025-12-19 | Builders Break
2025-12-20 | Builders Break
2025-12-21 | Builders Break
2025-12-22 | Builders Break
2025-12-23 | Builders Break
2025-12-24 | Builders Break
2025-12-25 | Builders Break
2025-12-26 | Builders Break
2025-12-27 | Builders Break
2025-12-28 | Builders Break
2025-12-29 | Builders Break
2025-12-30 | Builders Break
2025-12-31 | Builders Break
2026-01-01 | Builders Break
2026-01-02 | Builders Break
2026-01-03 | Builders Break
2026-01-04 | Builders Break
2026-01-05 | Builders Break
2026-01-06 | Builders Break
2026-01-07 | Builders Break
2026-01-08 | Builders Break
Builders Break
Builders Break
Builders Break
Builders Break
Builders Break
Builders Break
Builders Break
Builders Break
2026-03-21 | Human Rights day
2026-04-03 | Good Friday
2026-04-06 | Family Day
2026-04-27 | Freedom Day
2026-05-01 | Workers day
2026-06-16 | Youth Day Holiday
2026-08-09 | Womens Day
2026-08-10 | Womens Day Observerd
2026-09-24 | Heritage Day
2026-12-16 | Day of Reconciliation
2026-12-25 | Christmas Day
2026-12-26 | Day of Goodwill