# SOP — Cost Proposal (CP)

Acronyms as per internal sheet (PD, PoD, HoPD, HoD, OE). Fill [TBC] items.

# Purpose

Convert FA into a priced, sign-off ready proposal pack.

Lock technical intent, yield basis, scope, assumptions, risks, and price for client approval.

# Scope & Triggers

In scope:

PVSOL yield & losses analysis

SLD (level 0/1)

Roof Quality Report (RQR)

High-level BoM & price; options; allowances; exclusions; risks; preliminary program

Out of scope:

Detailed EP and construction method statements

Final network protection studies

Procurement placement

Trigger (UPDATED):

PD posts a CP request on MS Teams (Engineering intake channel [TBC]).

Automation creates the CP task on ClickUp for Engineering to track.

The Teams thread is the anchor for inputs and approvals (no SharePoint link required in ClickUp).

# Definitions & DoR/DoD

DoR (ready to start CP):

From FA: FA Summary, Helioscope layout, constraints & risks, FA Costing sheet.

FA Decision = Go present in Teams/ClickUp (or exec bypass approval [TBC]).

Client/PD inputs in Teams: funding model (self-funded / Fedgroup), required options (PV / PV+Gen / PV+BESS), any scope adds/drops since FA.

Site visuals available (photos/drone) OR site visit/logging booked if required [rule TBC].

ClickUp fields set: Priority; Complexity (Std/Complex/BESS); Due/SLA.

DoD (complete CP):

PVSOL model + report (key losses, shading, performance ratio).

SLD (L0/1) signed by HoD then HoPD.

Roof Quality Report signed by OE (with photos/notes).

Costing sheet (EE template v[TBC]) signed by HoD then HoPD; funding model set.

CP Summary (client-ready): scope, assumptions, inclusions/exclusions, options, allowances, risks (RAG), prelim program, price (ex VAT), validity [TBC days].

All artefacts stored (SharePoint [TBC path]) OR posted into the Teams thread.

ClickUp Decision = Ready for PD (handover to PD for client issuance).

# Roles (RACI)

R — OE

A — HoD

C — PD, PoD, HoPD

I — (PM not involved at CP stage)

Prioritisation: PoD & HoPD

Workload assigning: PoD

SLD sign-off: HoD → HoPD

RQR sign-off: OE

Costing sheet sign-off: HoD → HoPD

Escalation: OE → PD → HoD → MD

# Inputs / Tools / Artefacts

Tools: PVSOL; AutoCAD; EE Costing Sheet; Power Logger [if required]; Drone/Photos; Teams (anchor); ClickUp (tracking); Google Earth; SLD template [TBC].

Created: PVSOL report; SLD (PDF/DWG); RQR; Costing sheet; CP Summary (client-ready); Options table; Risk register update.

# SLAs

HoD triage/assignment: [TBC] hours.

CP build (Std): [TBC] business days from triage.

CP build (BESS/Complex): [TBC].

HoD review: [TBC] hours.

HoPD review: [TBC] hours.

# Steps (Who / What / Tool / Output)

| # | Who | What | Tool | Output |
| --- | --- | --- | --- | --- |
| 1 | Automation | Create CP task; carry Teams link & FA meta | ClickUp | CP task “New” |
| 2 | HoD | Triage; set priority/complexity; assign OE | ClickUp | Assignee + SLA |
| 3 | OE | DoR check; if missing items, post DoR-Fail and pause | Teams | Gaps list |
| 4 | OE | Confirm funding model & options with PD (single source) | Teams | Options list (locked) |
| 5 | OE | Assess visuals; decide if site visit/logging needed [rule TBC]; book if needed | Teams | Visit/log plan |
| 6 | OE | Build PVSOL (EE default libraries [TBC]; losses; shading) | PVSOL | Report (PDF) |
| 7 | OE | Draft SLD L0/1 (topology, PCC, ATS/protection placeholders, metering) | AutoCAD | SLD v1 |
| 8 | OE | Prepare RQR (roof types, access, walkways, penetrations; photos) | Template | RQR v1 |
| 9 | OE | Price using EE Costing Sheet (rates/date; funding model; options; allowances) | XLSX | Costing v1 |
| 10 | OE | Compile CP Summary incl. options/alternates | Template | CP Summary v1 |
| 11 | OE | Self-check against Quality Gate | Checklist | Ready for review |
| 12 | HoD | Technical review; approve PVSOL/SLD/Costing (HoD sign-off) | Teams/ClickUp | HoD sign-off |
| 13 | HoPD | Commercial/departmental review; sign-off SLD & Costing | Teams/ClickUp | HoPD sign-off |
| 14 | OE | Finalise pack; store to SP [TBC] or post to Teams; update ClickUp | SP/Teams | CP Pack (current) |
| 15 | OE | Set ClickUp Decision = Ready for PD; tag PD in thread | ClickUp/Teams | Handover to PD |

# Quality gates (control points)

Inputs locked: FA constraints; options/funding model confirmed in Teams.

PVSOL: correct EE defaults; shading loss stated; PR & specific yield consistent with FA area; DC/AC within [TBC range].

SLD: correct topology; PCC identified; ATS/protection placeholders; export status; genset/BESS interfaces; revision & sign-off block present.

RQR: roof types, penetrations, cable routes, tray strategy, walkways/fall-arrest notes; access constraints; photos.

Costing: rates/date; FX [if any]; contingency [TBC %]; prelims; compliance items; delivery/cranage; long-lead items flagged (lead time [TBC]).

CP Summary: inclusions/exclusions; assumptions; risks (RAG + owners); prelim program; options pricing; validity [TBC days]; VAT excluded.

Sign-offs captured: HoD → HoPD; files stamped/signed [TBC method].

# Artefacts (forms, logs, file paths)

CP Summary (client-ready) — headings:

System intent & size (kWp DC / kVA AC), DC/AC; PVSOL yield (kWh/yr; PR; losses).

Scope summary (PV / PV+Gen / PV+BESS; metering & control overview).

Inclusions (high-level BoM) & Exclusions.

Assumptions (export status; structural by others; network approvals; access).

Options & Alternates (add/deduct).

Allowances (cable routes, cranage, protection studies, compliance).

Risks (RAG + owner/mitigation).

Preliminary program / lead times.

Commercials (price ex VAT; validity; payment basis [TBC]).

RQR — sections: roof types; condition; penetrations; fall-risk; trays/walkways; photos & annotations.

SLD — contents: topology; PCC; breakers/fuses/CT/VT placeholders; gens/BESS tie; comms blocks; revision history.

File path: [TBC Root]/Engineering/02_CP/Client_Site/YYYY-MM-DD

Subfolders: 01_Inputs | 02_PVSOL | 03_SLD | 04_RQR | 05_Costing | 06_CP_Summary | _Archive

# ClickUp mapping

List: Engineering » CP

Statuses: New → Triaged → In-Progress → For-HoD → For-HoPD → Ready for PD → Done/Rework

Fields: Priority; Complexity; Due/SLA; Funding model; Options (multi-select); Scope Change (Y/N); Decision.

Required at “For-HoD”: PVSOL PDF, SLD v1, RQR v1, Costing v1, CP Summary v1.

Required at “For-HoPD”: Updated pack post-HoD comments.

Automation: On “Ready for PD” → notify PD in Teams; add CP Pack link.

# KPIs & reporting (CP)

Lead time: triage → Ready for PD.

On-time delivery: % within SLA.

First-pass sign-off: % passing HoD without rework; % passing HoPD without rework.

Rework drivers: top 3 causes (design, pricing, missing inputs).

Price delta vs FA: |CP price – FA estimate| / FA estimate.

Long-lead exposure: # CPs with flagged long-lead items.

# Change control

Scope changes during CP: set Scope Change = Yes, note in Teams; version bump (CP_v{n+1}); reset SLA [rule TBC] if material.

Options add/deduct tracked as separate lines; base scope remains stable.

Archive prior versions; mark the latest CURRENT.

# Standard messages (ready to paste)

DoR-Fail (Teams): CP paused — missing: {items}. Please attach here. SLA resumes once complete. (Ref: ClickUp {task})

For-HoD review (Teams): CP ready for HoD review: PVSOL v__, SLD v__, RQR v__, Costing v__, CP Summary v__. Files stored here: {path or thread}.

For-HoPD review (Teams): HoD comments addressed. Please review & sign-off SLD and Costing.

Generated: 2025-08-21