## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[10 empty] | 2026-02-23 | 2026-02-23
| PROJECT PLAN | Pretoria North | [5 empty] | all docs ready |  | 0 | 1
| PROJECT SIZE (kWp) | 509
| PROJECT DEVELOPER | Natasha Watkins-Baker
| PROJECT MANAGERS | Eon Van Rensburg
| CONTRACT VALUE | 4761473
| Phase: | Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Expected Status |  | Comment
|  |  | 63 |  |  | 70 |  | 98.28% | 95.47%
1 | Project Initiation | 2025-04-22 | 80 | 2025-07-11 | 2025-04-29 | 17 | 2025-05-16 | 100% | 100% | 17
1.1 | BD Handover | 2025-04-22 | 1 | 2025-04-23 | 2025-05-13 | 1 | 2025-05-14 | 100% | 100%
1.2 | Project Introduction | 2025-07-10 | 1 | 2025-07-11 | 2025-05-15 | 1 | 2025-05-16 | 100% | 100%
1.3 | HSE | 2025-04-22 | 10 | 2025-05-07 | 2025-04-29 | 10 | 2025-05-14 | 100% | 100%
1.4 | Installer Kick Off | 2025-07-03 | 1 | 2025-07-04 | 2025-05-14 | 1 | 2025-05-15 | 100% | 100%
1.5 | Project Review | 2025-07-03 | 1 | 2025-07-04 | 2025-05-08 | 1 | 2025-05-09 | 100% | 100%
2 | Site Establishment | 2025-07-17 | 1 | 2025-07-18 | 2025-09-29 | 1 | 2025-09-30 | 100% | 100% | 1
2.1 | Solar Contractor Establishment | 2025-07-17 | 1 | 2025-07-18 | 2025-09-29 | 1 | 2025-09-30 | 100% | 100% | 1 | Client delay on roof works | 51 | Net Work Days
3 | AC Installation | 2025-06-26 | 70 | 2025-09-04 | 2025-06-26 | 139 | 2025-11-12 | 100% | 100% | 139 |  | 10.2 | Total Weeks
3.1 | Inverters delivered | 2025-07-18 | 1 | 2025-07-21 | 2025-06-26 | 1 | 2025-06-27 | 100% | 100% |  |  | 49.902 | kW/Week Installation Rate
3.2 | Inverters Mounted | 2025-07-21 | 5 | 2025-07-28 | 2025-10-22 | 5 | 2025-10-29 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-06-26 | 25 | 2025-07-31 | 2025-07-31 | 2 | 2025-08-04 | 100% | 100%
3.4 | AC Works | 2025-07-31 | 25 | 2025-09-04 | 2025-10-22 | 15 | 2025-11-12 | 100% | 100%
3.5 | AC Tie-In | 2025-07-31 | 3 | 2025-08-05 | 2025-10-22 | 3 | 2025-10-27 | 100% | 100%
4 | DC Works | 2025-07-17 | 55 | 2025-09-10 | 2025-06-26 | 155 | 2025-11-28 | 93.75% | 93.75% | 145.3125
4.1 | Lifeline Installation (If Applicable) | [6 empty] | 0% | 0%
4.1 | Mounting Structure delivered | 2025-07-17 | 1 | 2025-07-18 | 2025-06-26 | 1 | 2025-06-27 | 100% | 100%
4.2 | Mounting Structure installation | 2025-07-18 | 10 | 2025-08-01 | 2025-10-15 | 5 | 2025-10-22 | 100% | 100%
4.3 | DC Cable delivered | 2025-07-17 | 1 | 2025-07-18 | 2025-06-26 | 1 | 2025-06-27 | 100% | 100%
4.3 | DC Stringing | 2025-08-25 | 12 | 2025-09-10 | 2025-11-17 | 9 | 2025-11-28 | 100% | 100%
5 | Module installation | 2025-07-30 | 29 | 2025-08-28 | 2025-06-26 | 147 | 2025-11-20 | 100% | 100% | 1900-05-26
5.1 | Module delivery | 2025-07-30 | 1 | 2025-07-31 | 2025-06-26 | 1 | 2025-06-27 | 100% | 100%
5.2 | Module mounting | 2025-07-31 | 20 | 2025-08-28 | 2025-10-22 | 21 | 2025-11-20 | 100% | 100%
6 | Commissioning | 2025-09-10 | 8 | 2025-09-18 | 2025-12-02 | 6 | 2025-12-08 | 100% | 100% | 6
6.1 | Commissioning | 2025-09-10 | 1 | 2025-09-11 | 2025-12-02 | 2 | 2025-12-04 | 100% | 100%
6.2 | Practical Completion | 2025-09-11 | 5 | 2025-09-18 | 2025-12-04 | 2 | 2025-12-08 | 100% | 100%
7 | QA Inspections | 2025-09-18 | 1 | 2025-09-19 | 2025-12-08 | 3 | 2025-12-11 | 100% | 100% | 1900-01-02
7.1 | Red-Team Inspection | 2025-09-18 | 1 | 2025-09-19 | 2025-12-08 | 3 | 2025-12-11 | 100% | 100%
8 | Project Closure | 2025-09-19 | 17 | 2025-10-06 | 2025-12-11 | 85 | 2026-03-06 | 92.5% | 69.98% | 1900-03-18 15:00
8.1 | Equipment serial numbers | 2025-09-19 | 2 | 2025-09-23 | 2025-12-11 | 2 | 2025-12-15 | 100% | 100%
8.2 | Snags completion | 2025-09-19 | 5 | 2025-09-29 | 2025-12-11 | 32 | 2026-01-28 | 100% | 100% |  | Anderson consulting snags to be completed
8.3 | System Performance Monitoring | 2025-09-29 | 5 | 2025-10-06 | 2025-12-15 | 15 | 2026-01-07 | 100% | 100%
8.4 | Handover documentation | 2025-09-19 | 3 | 2025-09-25 | 2025-12-24 | 25 | 2026-01-29 | 100% | 100%
8.5 | Handover to Client | 2025-09-25 | 1 | 2025-09-26 | 2026-03-05 | 1 | 2026-03-06 | 0% | 0% |  | Portfolio handover
8.6 | Handover to Matriarch | 2025-09-21 | 5 | 2025-09-29 | 2026-02-22 | 5 | 2026-02-27 | 0% | 20%
Formulas:
Planned Start = MIN([Planned Start, row below]:E16)
Planned Start = WORKDAY.INTL([Planned End, row above],0,1,Data!$C3:C14)
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = WORKDAY.INTL([Actual Start, row above],0,1,Data!$C3:C14)
Actual End = MAX([Actual End, row below]:K16)
Actual End = MAX([Actual End, row below])
Expected Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 4761473 |  | 4761473 |  |  |  | Start Date | 4406260.8841 | 3366094.35 | 355211.9226 | 570508.3025 | 166296.0092 | 431289.89
2 | Planned Expenditure | 4406841.0025 |  | 3936602.6525 | VO PM Limit | Current VO Total
3 | Planned Profit | 354631.9975 |  | 824870.3475 | 17731.5999 | 45501.4 |  | End Date - PC
4 | Planned Margin | 7.448% |  | 17.32%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE |  | MILESTONE NOTES & COMMENTS
1 | Deposit |  | 20% | 952294.6 |  | 2025-05-23 | 004737 | 2025-05-01 | 2025-04-30
2 | Delivery of Panels |  | 20% | 952294.6 |  | 2025-08-06 | 004737 | 2025-05-01 | 2025-07-03
3 | Delivery of Inverters |  | 15% | 714220.95 |  | 2025-07-25 | 004737 | 2025-05-01 | 2025-07-03
4 | Commissioning Complete |  | 15% | 714220.95 |  | 2025-09-25 | 004737 | 2025-05-01 | 2026-01-03
5 | Final Completion Issued |  | 25% | 1190368.25 |  | 2025-09-26 | 004737 | 2025-05-01 | 2026-01-03
6 | Handover |  | 5% | 238073.65 |  | 2026-03-13 | 004737 | 2025-05-01 | 2026-01-03
7 | - |  | 0% | 0
|  |  | 100% | 4761473
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 1666515.55
2 | Delivery of Panels |  | 30% | 1428441.9
3 | Delivery of Inverters |  | 20% | 952294.6
4 | Practical Completion |  | 10% | 476147.3
5 | Handover |  | 5% | 238073.65
| Total |  | 100% | 4761473
|  |  | 100% | 4761473

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 4406841.0025 |  | 3936602.6525 | 470238.35
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 1110081.32 |  | 1017651.2 | 92430.12
2 | 2. Inverters | 280000 |  | 275481.4 | 4518.6
3 | 3. Mounting Structures | 229194 |  | 147784.22 | 81409.78
4 | 4. DC Equipment | 407489.6 |  | 374718.25 | 32771.35
5 | 5. Monitoring | 49000 |  | 35927.13 | 13072.87
6 | 6. AC Equipment | 673981.4609 |  | 292269.32 | 381712.1409
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 0 |  | 152060 | -152060
9 | 9. AC & DC installation | 411950 |  | 508999.99 | -97049.99
10 | 10. Site Logistics | 106291.6667 |  | 217870 | -111578.3333
11 | 11. Due Dilligence | 125199 |  | 114589.71 | 10609.29
12 | 12. BDP Commission | 88657.9512 |  | 0 | 88657.9512
13 | 13. Engineering | 166246.0038 |  | 59518.4125 | 106727.5913
14 | 14. General Expenses | 8750 |  | 13433.02 | -4683.02
15 | 15. Service Add On | 750000 |  | 726300 | 23700
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 4406841.0025 | 4761472.8072 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 3936602.6525
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | ERROR on REV |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 1110081.32 | 2025-07-24 | 1110081.32 | 1233423.6889 |  | 1 | 1. Panels | Jinko 620W - Menlo | 821 | 1233.8 | 1012949.8 | PO3899-DIP-PH2-SHP-20250514 | Menlo - INV0002942 | 2025-05-31 | 1233423.6889 | 0 | 2025-07-24 | 1017651.2
1 |  | Delivery Budget | [7 empty] | 1 | 1. Panels | Jinko 620W - Replacement of broken modules - VO | 3 | 1233.8 | 3701.4 |  | Menlo - INV0003424 | 2025-11-30 | 0 |  | 2026-01-15
1 | [9 empty] | 1 | 1. Panels | Delivery |  |  | 1000 |  | Menlo - INV0003424 | 2025-11-30 | 0 |  | 2026-01-15
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 673981.4609
2 | Inverters | Inverter Budget |  |  | 280000 | 2025-07-24 | 280000 | 311111.1111 |  | 2 | 2. Inverters | Huawei 100KTL - Menlo | 4 | 68870 | 275481.4 | PO3899-DIP-PH2-SHP-20250514 | Menlo - INV0002942 | 2025-05-31 | 311111.1111 | 0 | 2025-07-24 | 275481.4 | DC Equipment | 241169.6
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | AC Labour | 127330
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 284620
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 31625
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 6166.6667
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 229194 | 2025-07-29 | 229194 | 254660 |  | 3 | 3. Mounting Structures | Schletter Structure |  |  | 74458.2 | PO3918-DIP-Ph2-Shoprite-20250515 - RV Approved | Schletter - INV1897 | 2025-06-30 | 166046.598 | 0.0020001 | 2025-07-29 | 147784.22 | Other | 0
3 | [5 empty] | 2025-09-30 |  |  |  | 3 | 3. Mounting Structures |  |  |  | 7278.8 |  | Schletter - INV2028 | 2025-08-31 | 88613.4 |  | 2025-09-30 |  | Total | 1373392.7275
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Less 15% | 1167383.8184
[10 empty] | 3 | 3. Mounting Structures | Return Scheltter Stock |  |  | -40497.6 |  | Schletter - CRN0278 | 2025-10-31 | 0 |  | 2025-10-31
[10 empty] | 3 | 3. Mounting Structures | Return Scheltter Stock |  |  | 616.92 |  | DSV Inv: 180155155 & 180154233 | 2025-11-30 | 0 |  | 2025-12-31
3 | [9 empty] | 3 | 3. Mounting Structures | New Scheltter Stock |  |  | 83015.5 | PO4369-DIP-Ph2-Shoprite-20251015 - RV Approved | Schletter - INV2301 | 2025-10-31 | 0 |  | 2025-11-28 |  | R/Wp | 2.2935
3 | [9 empty] | 3 | 3. Mounting Structures |  |  |  | 22912.4 |  | Schletter - INV2356 | 2025-10-31 | 0 |  | 2025-11-28
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL - Cosmic Sun | Installer Price
[23 empty] | AC Equipment | 121839
4 | DC Equipment | DC Cable Budget | 13662 |  | 166320 | 2025-07-29 | 407489.6 | 452766.2222 |  | 4 | 4. DC Equipment | DC Cable | 10000 | 13.89 | 138900 | PO3934-DIP-Ph2-Pretoria N-20250519 - RV Approved | Krannich - Inv 15-10013107 | 2025-06-30 | 182172.3743 | 0 | 2025-07-29 | 374718.25 | DC Equipment | 195918.25
4 |  | DC Equipment Budget |  |  | 241169.6 | 2025-07-29 |  |  |  | 4 | 4. DC Equipment | Freight |  |  | 10400 |  | Krannich - Inv 15-10013107 | 2025-06-30 | 13639.9762 |  | 2025-07-29 |  | AC Labour | 152700
4 | [9 empty] | 4 | 4. DC Equipment | DC Cable - Rubicon - VO |  |  | 29500 | PO4496-DIP-PH2-SPN-20251126 - RV Approved | Rubicon - INVRED-0136040 | 2025-12-31 | 0 |  | 2026-01-30 |  | DC Labour | 356300
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Offloading | 4950
4 | [5 empty] | 2025-05-15 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 195918.25 | 10% | 19591.825 | PO3869-DIP-Ph2-Shoprite-20250512 - RV Approved | Cosmic Sun: CS_PTN_001 | 2025-05-31 | 25695.3872 |  | 2025-05-15 |  | Scaffolding | 28270
4 | [5 empty] | 2025-06-26 |  |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 29387.7375 |  | Cosmic Sun: CS_PTN_002 | 2025-06-30 | 38543.0808 |  | 2025-06-26 |  | Storage | 6600
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 39183.65 |  | CS_PTN_004 | 2025-08-31 | 51390.7743 |  | 2025-11-13 |  | Telehandler | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 30766.06 |  | CS_PTN_003 | 2025-08-31 | 64238.4679 |  | 2025-11-30 |  | HSE | 4500
[10 empty] | 4 | 4. DC Equipment | DC Installation Complete |  |  | 18213.5025 |  | CS_PTN_003 | 2025-08-31 | 0 |  | 2025-12-12
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 19591.825 |  | CS_PTN_005 | 2025-08-31 | 25695.3872 |  | 2025-12-18 |  | Other | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 19591.825 |  | CS_PTN_006 A | 2025-08-31 | 25695.3872 |  | 2025-12-24 |  | Other | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 9795.9125 |  | CS_PTN_007 A | 2025-08-31 | 12847.6936 |  | 2026-12-30 |  | Total | 871077.25
4 | [5 empty] | 2025-10-31 |  |  |  | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 9795.9125 |  | CS_PTN_008 A | 2025-08-31 | 12847.6936 |  | 2026-02-25 |  | R/Wp | 1.7114
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 34000 | 2025-07-17 | 49000 | 54444.4444 |  | 5 | 5. Monitoring | Smartlogger - Menlo |  |  | 8598.35 | PO3899-DIP-PH2-SHP-20250514 | Menlo - INV0002931 | 2025-05-31 | 9210.3317 | -0.0014822 | 2025-07-17 | 35927.13
5 |  | Revenue Metering |  |  | 15000 | 2025-05-27 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 13695 | PO3831-DIP-Ph2-Shoprite-20250429 - RV Approved | Accuenergy - INV ASAI-005357 | 2025-04-30 | 18689.4765 |  | 2025-05-27
[6 empty] | 2025-07-29 |  |  |  | 5 | 5. Monitoring |  |  |  | 214.28 |  | Accuenergy - Inv ASAI-005800 | 2025-06-30 | 3769.3927 |  | 2025-07-29
5 | [5 empty] | 2025-06-30 |  |  |  | 5 | 5. Monitoring | Techsitter |  |  | 11169 |  | Matriarch Inv: 4451 | 2025-06-30 | 21003.9292 |  | 2025-06-30
5 | [5 empty] | 2025-05-22 |  |  |  | 5 | 5. Monitoring | UPS |  |  | 2250.5 | PO3863-DIP Ph2-20250509 - RV Approved | Frontline INV725690 | 2025-05-31 | 2816.4685 |  | 2025-05-22
5 | [5 empty] | 2025-06-27 |  |  |  | 5 | 5. Monitoring | CTs |  |  | 3960 | PO3959-DIP-Ph2-Pretoria N-20250524 - RV Approved | Accuenergy - Inv ASAI-005581 | 2025-05-31 | 4955.8832 |  | 2025-06-27
5 | [5 empty] | 2025-06-30 |  |  |  | 5 | 5. Monitoring |  |  |  | -3960 |  | Accuenergy - CN-00188 | 2025-06-30 | -6001.036 |  | 2025-06-30
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 673981.4609 | 2025-07-28 | 673981.4609 | 748868.2899 |  | 6 | 6. AC Equipment | [7 empty] | 0 | 0.0028627 |  | 292269.32
6 | [5 empty] | 2025-07-29 |  |  |  | 6 | 6. AC Equipment | PVDB - Request a wall mount unit |  |  | 170430.32 | PO3931-DIP-Ph2-Pretoria N-20250519 - RV Approved | Switchboard Inv: 2-SOI002099 | 2025-06-30 | 436685.8016 |  | 2025-07-29
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [5 empty] | 2025-05-15 |  |  |  | 6 | 6. AC Equipment | Project Kick Off | 121839 | 10% | 12183.9 | PO3869-DIP-Ph2-Shoprite-20250512 - RV Approved | Cosmic Sun: CS_PTN_001 | 2025-05-31 | 31674.726 |  | 2025-05-15
6 | [5 empty] | 2025-06-26 |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 18275.85 |  | Cosmic Sun: CS_PTN_002 | 2025-06-30 | 46370.8932 |  | 2025-06-26
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 24367.8 |  | CS_PTN_004 | 2025-08-31 | 62436.4977 |  | 2025-10-30
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 30459.75 |  | CS_PTN_003 | 2025-08-31 | 78045.6221 |  | 2025-12-15
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 12183.9 |  | CS_PTN_005 | 2025-08-31 | 31218.2488 |  | 2025-12-18
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 12183.9 |  | CS_PTN_006 A | 2025-08-31 | 31218.2488 |  | 2025-12-24
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 6091.95 |  | CS_PTN_007 A | 2025-08-31 | 15609.1244 |  | 2026-12-30
6 | [5 empty] | 2025-10-31 |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 6091.95 |  | CS_PTN_008 A | 2025-08-31 | 15609.1244 |  | 2026-02-05
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 0 | 0 |  | 8 | 8. Product Add On | [8 empty] | 0 |  | 152060
8 | [9 empty] | 8 | 8. Product Add On
8 | [5 empty] | 2025-07-31 |  |  |  | 8 | 8. Product Add On | Inverter Cage with roof |  |  | 64865 | PO4020-DIP-Ph2-Shoprite-20250623 - RV Approved | The Engineering Hub INV/2025/06/0573 | 2025-06-30 |  |  | 2025-07-31
8 | [9 empty] | 8 | 8. Product Add On | Inverter landing area and walkway |  |  | 22639 | PO4522-DIP-Ph2-Shoprite-20251204 - RV Approved | The Engineering Hub - INV/2025/12/0065 | 2025-12-31 |  |  | 2026-01-30
8 | [5 empty] | 0 |  |  |  | 8 | 8. Product Add On | Waterpoint |  |  | 14332 | PO4340-DIP-Ph2-Shoprite-20250929 - RV Approved | Ndawonga Trading - 1484 | 2025-11-30 |  |  | 2025-12-12
8 | [9 empty] | 8 | 8. Product Add On | Estops |  |  | 6000 | PO4392-DIP-Ph2-Shoprite-20251023 - RV Approved | Cosmic Sun - CS_PTN_009 | 2025-11-30 |  |  | 2025-12-04
8 | [5 empty] | 0 |  |  |  | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On | Inverter cage modification |  |  | 44224 | PO4580-DIP-Ph2-SPN-20260127 - RV Approved | The Engineering Hub INV/2026/01/0249 | 2026-01-31 |  |  | 2026-02-28
8 | [9 empty] | 8 | 8. Product Add On
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 127330 | 2025-05-14 | 411950 | 484647.0588 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | -0.0019043 |  | 508999.99
9 |  | DC Installation Budget |  |  | 284620 | 2025-05-15 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 509000 | 10% | 50900 | PO3869-DIP-Ph2-Shoprite-20250512 - RV Approved | Cosmic Sun: CS_PTN_001 | 2025-05-31 | 48464.7059 |  | 2025-05-15
9 | [5 empty] | 2025-06-26 |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 76350 |  | Cosmic Sun: CS_PTN_002 | 2025-06-30 | 72697.0588 |  | 2025-06-26
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 101800 |  | CS_PTN_004 | 2025-08-31 | 96929.4118 |  | 2025-11-13
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 127250 |  | CS_PTN_003 | 2025-08-31 | 121161.7647 |  | 2025-12-18
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 50900 |  | CS_PTN_005 | 2025-08-31 | 48464.7059 |  | 2025-12-15
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 21054.3043 |  | CS_PTN_006 B | 2025-10-31 | 48464.7068 |  | 2025-12-24
[10 empty] | 9 | 9. AC & DC installation | Site De-establisment |  |  | 29845.6957 |  | CS_PTN_006 B | 2025-10-31 | 0 |  | 2025-12-24
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 25450 |  | CS_PTN_007 B | 2025-10-31 | 24232.3534 |  | 2025-12-18
9 | [5 empty] | 2025-10-31 |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 25450 |  | CS_PTN_008 B | 2025-10-31 | 24232.3534 |  | 2026-02-05
9 | [9 empty] | 9 | 9. AC & DC installation | Rounding Difference |  |  | -0.01 |  | CS_PTN_006 B | 2025-10-31 | 0 |  | 2026-02-05
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-07-29 | 106291.6667 | 125049.0196 |  | 10 | 10. Site Logistics | [7 empty] | 0 | -0.0041727 |  | 217870
10 |  | Scaffolding |  |  | 31625 | 2025-07-30 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
[6 empty] | 2025-07-31 |  |  |  | 10 | 10. Site Logistics | Security - July |  |  | 32400 | PO4031-DIP-Ph2-Shoprite-20250625 - RV Approved | GSG Tactical INV000013575 | 2025-06-30 | 25852.4007 |  | 2025-07-31
[6 empty] | 2025-09-11 |  |  |  | 10 | 10. Site Logistics | Security - August |  |  | 27900 |  | GSG Tactical INV000013791 | 2025-08-31 | 26751.0171 |  | 2025-09-11
[6 empty] | 0 |  |  |  | 10 | 10. Site Logistics | Crane Hire |  |  | 22800 | PO4283-DIP-Ph2-Shoprite-20250827 - RV Approved | Supply Chain - SCO05262 | 2025-09-30 | 17311.8503 |  | 2025-11-06
[6 empty] | 2025-09-30 |  |  |  | 10 | 10. Site Logistics | Security - September |  |  | 27900 |  | GSG Tactical - INV000013885 | 2025-09-30 | 14421.7694 |  | 2025-10-09
10 |  | Security |  |  | 60000 | 2025-10-01 |  |  |  | 10 | 10. Site Logistics | Security - October |  |  | 27900 |  | GSG Tactical - INV000013973 | 2025-10-31 | 0 |  | 2025-11-06
[10 empty] | 10 | 10. Site Logistics | Security - November |  |  | 27900 |  | GSG Tactical - INV000014095 | 2025-11-30 | 0 |  | 2025-12-12
[10 empty] | 10 | 10. Site Logistics | Security - December |  |  | 6750 |  | GSG Tactical - INV000014166 | 2025-12-31 | 0 |  | 2026-01-29
10 |  | Storage |  |  | 6166.6667 | 2025-10-02 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [5 empty] | 2025-05-15 |  |  |  | 10 | 10. Site Logistics | Project Kick Off | 44320 | 10% | 4432 | PO3869-DIP-Ph2-Shoprite-20250512 - RV Approved | Cosmic Sun: CS_PTN_001 | 2025-05-31 | 3372.7924 |  | 2025-05-15
10 | [5 empty] | 2025-06-26 |  |  |  | 10 | 10. Site Logistics | Site Establishment |  | 15% | 6648 |  | Cosmic Sun: CS_PTN_002 | 2025-06-30 | 5468.0896 |  | 2025-06-26
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 8864 |  | CS_PTN_004 | 2025-08-31 | 8498.9611 |  | 2025-11-13
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 11080 |  | CS_PTN_003 | 2025-08-31 | 10623.7014 |  | 2025-12-15
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 4432 |  | CS_PTN_005 | 2025-08-31 | 4249.4806 |  | 2025-12-18
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 4432 |  | CS_PTN_006 A | 2025-08-31 | 4249.4806 |  | 2025-12-24
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 2216 |  | CS_PTN_007 A | 2025-08-31 | 2124.7403 |  | 2025-12-24
10 | [5 empty] | 2025-10-31 |  |  |  | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 2216 |  | CS_PTN_008 A | 2025-08-31 | 2124.7403 |  | 2026-02-05
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 12733 | 2025-09-30 | 125199 | 147292.9412 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 13977.96 |  | Sunspot - E027 | 2025-07-31 | 56993.3641 | 0.0012807 | 2026-02-05 | 114589.71
11 |  | Structural Sign Off |  |  | 25466 | 2025-10-01 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 7811.75 | PO3745-DIP-Ph2-20250313 - RV Approved | L&B Consulting - Invoice 1934 | 2025-04-30 | 34198.9652 |  | 2025-04-10
11 |  | Grid Study |  |  | 80000 | 2025-10-02 |  |  |  | 11 | 11. Due Dilligence | Grid Impact Study |  |  | 79700 | PO4447-DIP-Ph2-Shoprite-20251106 - RV Approved |  | 2026-02-28 | 0 |  | 2026-03-31
11 |  | Lightning Risk Assessment |  |  | 7000 | 2025-10-03 |  |  |  | 11 | 11. Due Dilligence | Lightning Risk Assessment |  |  | 5100 | PO3844-Dipula Ph2-20250430 - RV Approved | LPS Inv: IN306837 | 2025-04-30 | 22327.2279 |  | 2025-06-26
11 | [5 empty] | 2025-10-04 |  |  |  | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 8000 |  | Matriarch - INV-5975 | 2025-12-31 | 33773.3827 |  | 2026-01-30
2025-10-05
12 | BDP Commission | Referral Fee |  |  | 66493.4634 | 2025-10-06 | 88657.9512 | 0 |  | 12 | 12. BDP Commission | Referral Fee | [9 empty] | 0
12 | BDP Commission | PD Fee |  |  | 22164.4878 | 2025-10-07 |  |  |  | 12 | 12. BDP Commission | PD Fee
2025-10-08
13 | Engineering | Matriarch Defects Period |  |  | 42414.8381 | 2025-10-09 | 166246.0038 | 188915.9134 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 59518.4125 |  |  | 2026-02-28 | 188915.9134 | 0 | 2026-03-31 | 59518.4125
13 |  | Management |  |  | 28571.4286 | 2025-10-10 |  |  |  | 13 | 13. Engineering | Management |  |  | 0 |  |  |  | 0
13 |  | Project manager |  |  | 34000 | 2025-10-11 |  |  |  | 13 | 13. Engineering | Project manager |  |  | 0 |  |  |  | 0
13 |  | Planner time |  |  | 37142.8571 | 2025-10-12 |  |  |  | 13 | 13. Engineering | Planner time |  |  | 0 |  |  |  | 0
13 |  | De Snagging |  |  | 24116.88 | 2025-10-13 |  |  |  | 13 | 13. Engineering | De Snagging |  |  | 0 |  |  |  | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 8750 | 2025-05-08 | 8750 | 10294.1176 |  | 14 | 14. General Expenses | Travel |  |  | 1182.26 |  | Expense Claim | 2025-04-30 | 1343.7092 | 0.0019271 | 2025-05-08 | 13433.02
14 | [5 empty] | 2025-05-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-05-31 | 0 |  | 2025-05-31
14 | [5 empty] | 2025-07-04 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 3211.84 |  | Expense Claim | 2025-06-30 | 4165.4796 |  | 2025-07-04
14 | [5 empty] | 2025-08-07 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-07-31 | 0 |  | 2025-08-07
14 | [5 empty] | 2025-09-05 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 542.64 |  | Expense Claim | 2025-08-31 | 925.3339 |  | 2025-09-05
14 | [5 empty] | 2025-09-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 1085.28 |  | Expense Claim | 2025-09-30 | 1983.8277 |  | 2025-09-30
14 | [5 empty] | 2025-10-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 3791.54 |  | Expense Claim | 2025-10-31 | 1080.8053 |  | 2025-11-06
14 | [5 empty] | 2025-11-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 2115.3 |  | Expense Claim | 2025-11-30 | 794.96 |  | 2025-12-05
14 | [5 empty] | 2025-12-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 533.12 |  | Expense Claim | 2025-12-31 | 0 |  | 2026-01-08
14 | [5 empty] | 2026-01-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 971.04 |  | Expense Claim | 2026-01-31 | 0 |  | 2026-02-05
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 0 |  |  |  | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | Welcome Bonus |  |  | 750000 | 2025-07-11 | 750000 | 750000 |  | 15 | 15. Service Add On | Welcome Bonus - Site Establishment |  |  | 357000 |  | Luxanio Trading - 23403/202506/274900/I | 2025-06-30 | 375000 | 0 | 2025-07-11 | 726300
15 | [5 empty] | #REF! |  |  |  | 15 | 15. Service Add On | Welcome Bonus - Commissioning |  |  | 357000 |  | Luxanio Trading - 23403/202506/274900/I | 2025-06-30 | 375000 |  | 2026-01-15
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | Community Engagement | [6 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | Scaffolding - Cosmic Sun - VO |  |  | 7350 | PO4352-DIP-Ph2-Shoprite-20251006 - RV Approved | Cosmic Sun - CS_PTN_010 | 2025-11-30 | 0 |  | 2025-10-31
15 | [9 empty] | 15 | 15. Service Add On | Client Electrician Labour - VO |  |  | 4950 | PO4501-DIP-Ph2-Shoprite-20251127 - RV Approved | Ecom Electrical INV2892 | 2025-11-30 | 0 |  | 2025-11-28
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
| Panel Procurement Budget | 1110081.32 |  | 1233423.6889
| Inverter Procurement Budget | 280000 |  | 311111.1111
| Mounting Structure Budget | 229194 |  | 254660
| DC Equipment Budget | 407489.6 |  | 452766.2222
| AC Equipment Budget | 673981.4609 |  | 748868.2899
| Monitoring Budget | 49000 |  | 54444.4444
| Optional Extras Budget | 0 |  | 0
| MV Metering Budget | 0 |  | 0
| ADD ON | 0 |  | 0
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 127330 |  | 149800
| DC Installer Budget | 284620 |  | 334847.0588
| In-House Expense Budget | 166246.0038 |  | 188915.9134
| Compliance Budget | 125199 |  | 147292.9412
| Offloading Budget | 8500 |  | 10000
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 6166.6667 |  | 7254.902
| On Site Security | 60000 |  | 70588.2353
| Roof Access Budget for Installers | 31625 |  | 37205.8824
| EPC Management Fee | 0 |  | 0
| ADD ON | 750000 |  | 750000
Expenses
| Total EE Expense Budget | 8750 |  | 10294.1176
Note on Q23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs dont forget to clarify with Roedolph Reply: @Roedolph Venter , can I have a breakdown of the stock returned for PTN?
Note on W36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs pleae update the payment date
Note on H109: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs , please update the payment date
Note on W109: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs , please update the payment date
Note on W129: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 4761473 | 4761473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 952294.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 714220.95 | 0 | 952294.6 | 0 | 0 | 0 | 0 | 0 | 0 | 1904589.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238073.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 952294.6 | 952294.6 | 952294.6 | 952294.6 | 952294.6 | 952294.6 | 952294.6 | 952294.6 | 952294.6 | 1666515.55 | 1666515.55 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 4523399.35 | 4523399.35 | 4523399.35 | 4523399.35 | 4523399.35 | 4523399.35 | 4523399.35 | 4523399.35 | 4523399.35 | 4523399.35 | 4523399.35 | 4523399.35 | 4523399.35 | 4523399.35 | 4523399.35 | 4523399.35 | 4523399.35 | 4523399.35 | 4523399.35 | 4523399.35 | 4523399.35 | 4523399.35 | 4523399.35 | 4523399.35 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473
| Planned Expenditure | 4406841.0025 | 4406841.0025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8750 | 411950 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 750000 | 34000 | 1390081.32 | 1350790.0609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191365.6667 | 230787.075 | 24116.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8750 | 420700 | 420700 | 435700 | 435700 | 435700 | 435700 | 435700 | 435700 | 1185700 | 1219700 | 2609781.32 | 3960571.3809 | 3960571.3809 | 3960571.3809 | 3960571.3809 | 3960571.3809 | 3960571.3809 | 3960571.3809 | 3960571.3809 | 3960571.3809 | 4151937.0475 | 4382724.1225 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025 | 4406841.0025
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8750 | -420700 | 531594.6 | 516594.6 | 516594.6 | 516594.6 | 516594.6 | 516594.6 | 516594.6 | -233405.4 | -267405.4 | -943265.77 | -2294055.8309 | -1341761.2309 | -1341761.2309 | -1341761.2309 | -1341761.2309 | -1341761.2309 | -1341761.2309 | -1341761.2309 | 562827.9691 | 371462.3025 | 140675.2275 | 116558.3475 | 116558.3475 | 116558.3475 | 116558.3475 | 116558.3475 | 116558.3475 | 116558.3475 | 116558.3475 | 116558.3475 | 116558.3475 | 116558.3475 | 116558.3475 | 116558.3475 | 116558.3475 | 116558.3475 | 116558.3475 | 116558.3475 | 116558.3475 | 116558.3475 | 116558.3475 | 116558.3475 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975 | 354631.9975
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 4761473 | 4761473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 952294.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1666515.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2142662.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 952294.6 | 952294.6 | 952294.6 | 952294.6 | 952294.6 | 952294.6 | 952294.6 | 952294.6 | 952294.6 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 2618810.15 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473 | 4761473
| Actual + Planned Expenditure | 3936602.6525 | 3936602.6525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7811.75 | 0 | 0 | 0 | 1182.26 | 87107.725 | 2250.5 | 13695 | 0 | 0 | 0 | 139721.5875 | 10420.84 | 357000 | 8598.35 | 1288431.2 | 491667.8 | 0 | 0 | 0 | 0 | 542.64 | 27900 | 0 | 0 | 8364.08 | 27900 | 0 | 0 | -8779.8 | 54491.54 | 149847.65 | 0 | 141643.96 | 8115.3 | 60445.5025 | 281347.475 | 89323.725 | 616.92 | 533.12 | 361701.4 | 0 | 66889 | 48706.94 | 0 | 0 | 54019.9125 | 0 | 0 | 0 | 0 | 139218.4125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15887.8625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7811.75 | 7811.75 | 7811.75 | 7811.75 | 8994.01 | 96101.735 | 98352.235 | 112047.235 | 112047.235 | 112047.235 | 112047.235 | 251768.8225 | 262189.6625 | 619189.6625 | 627788.0125 | 1916219.2125 | 2407887.0125 | 2407887.0125 | 2407887.0125 | 2407887.0125 | 2407887.0125 | 2408429.6525 | 2436329.6525 | 2436329.6525 | 2436329.6525 | 2444693.7325 | 2472593.7325 | 2472593.7325 | 2472593.7325 | 2463813.9325 | 2518305.4725 | 2668153.1225 | 2668153.1225 | 2809797.0825 | 2817912.3825 | 2878357.885 | 3159705.36 | 3249029.085 | 3249646.005 | 3250179.125 | 3611880.525 | 3611880.525 | 3678769.525 | 3727476.465 | 3727476.465 | 3727476.465 | 3781496.3775 | 3781496.3775 | 3781496.3775 | 3781496.3775 | 3781496.3775 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3920714.79 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525 | 3936602.6525
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7811.75 | -7811.75 | -7811.75 | 944482.85 | 943300.59 | 856192.865 | 853942.365 | 840247.365 | 840247.365 | 840247.365 | 840247.365 | 700525.7775 | 2356620.4875 | 1999620.4875 | 1991022.1375 | 702590.9375 | 210923.1375 | 210923.1375 | 210923.1375 | 210923.1375 | 210923.1375 | 210380.4975 | 182480.4975 | 182480.4975 | 182480.4975 | 174116.4175 | 146216.4175 | 146216.4175 | 146216.4175 | 154996.2175 | 100504.6775 | -49342.9725 | -49342.9725 | -190986.9325 | -199102.2325 | -259547.735 | -540895.21 | -630218.935 | 1511826.995 | 1511293.875 | 1149592.475 | 1149592.475 | 1082703.475 | 1033996.535 | 1033996.535 | 1033996.535 | 979976.6225 | 979976.6225 | 979976.6225 | 979976.6225 | 979976.6225 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 840758.21 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475 | 824870.3475
|  | CHECK | CHECK
| Revenue Recognition | 0.19332 | 4761472.8067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76559.3788 | 0 | 0 | 0 | 1670725.0949 | 0 | 0 | 0 | 0 | 1760414.0388 | 0 | 0 | 0 | 56993.3641 | 0 | 0 | 0 | 841569.0075 | 0 | 0 | 0 | 0 | 33717.4475 | 0 | 0 | 0 | 98010.2189 | 0 | 0 | 0 | 794.96 | 0 | 0 | 0 | 0 | 33773.3827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188915.9134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 4761472.8067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76559.3788 | 76559.3788 | 76559.3788 | 76559.3788 | 1747284.4737 | 1747284.4737 | 1747284.4737 | 1747284.4737 | 1747284.4737 | 3507698.5125 | 3507698.5125 | 3507698.5125 | 3507698.5125 | 3564691.8766 | 3564691.8766 | 3564691.8766 | 3564691.8766 | 4406260.8841 | 4406260.8841 | 4406260.8841 | 4406260.8841 | 4406260.8841 | 4439978.3316 | 4439978.3316 | 4439978.3316 | 4439978.3316 | 4537988.5505 | 4537988.5505 | 4537988.5505 | 4537988.5505 | 4538783.5105 | 4538783.5105 | 4538783.5105 | 4538783.5105 | 4538783.5105 | 4572556.8933 | 4572556.8933 | 4572556.8933 | 4572556.8933 | 4572556.8933 | 4572556.8933 | 4572556.8933 | 4572556.8933 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067 | 4761472.8067

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | Grand Total
(blank)
1. Panels |  |  | 1233423.6889 | [5 empty] | 0 |  | 0 |  |  | 1233423.6889
2. Inverters |  |  | 311111.1111 | [7 empty] | 0 |  |  | 311111.1111
3. Mounting Structures | 0 |  |  | 166046.598 |  | 88613.4 |  | 0 | 0 |  | 0 |  |  | 254659.998
4. DC Equipment |  |  | 25695.3872 | 234355.4313 |  | 192715.4038 |  |  |  | 0 | 0 |  |  | 452766.2222
5. Monitoring |  | 18689.4765 | 16982.6834 | 18772.286 | [6 empty] | 0 |  |  | 54444.4459
6. AC Equipment |  |  | 31674.726 | 483056.6948 |  | 234136.8662 |  |  |  |  | 0 |  |  | 748868.287
8. Product Add On
9. AC & DC installation |  |  | 48464.7059 | 72697.0588 |  | 266555.8824 |  | 96929.4137 |  |  | 0 |  |  | 484647.0607
10. Site Logistics |  |  | 3372.7924 | 31320.4903 |  | 58622.1213 | 31733.6197 | 0 | 0 | 0 | 0 |  |  | 125049.0238
11. Due Dilligence |  | 56526.193 |  |  | 56993.3641 |  |  |  |  | 33773.3827 |  |  | 0 | 147292.9399
13. Engineering | 0 | [9 empty] | 0 |  | 188915.9134 | 188915.9134
14. General Expenses |  | 1343.7092 | 0 | 4165.4796 | 0 | 925.3339 | 1983.8277 | 1080.8053 | 794.96 | 0 | 0 | 0 |  | 10294.1157
15. Service Add On | 0 |  |  | 750000 |  |  |  |  | 0 |  | 0 |  |  | 750000
12. BDP Commission
7.BESS
Grand Total | 0 | 76559.3788 | 1670725.0949 | 1760414.0388 | 56993.3641 | 841569.0075 | 33717.4475 | 98010.2189 | 794.96 | 33773.3827 | 0 | 0 | 188915.9134 | 4761472.8067
|  | 76559.38 | 1670725.09 | 1702274.5 | 145606.76 | 811095.15 | [6 empty] | 4406260.88
|  | -0.0012254 | 0.0048859 | 58139.5388 | -88613.3959 | 30473.8575 | [6 empty] | 0.0041142

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 |  | 2026-02-28 | Grand Total
(blank)
1. Panels |  |  | 1012949.8 | [5 empty] | 4701.4 |  |  |  |  | 1017651.2
2. Inverters |  |  | 275481.4 | [10 empty] | 275481.4
3. Mounting Structures |  |  |  | 74458.2 |  | 7278.8 |  | 65430.3 | 616.92 |  |  |  |  | 147784.22
4. DC Equipment |  |  | 19591.825 | 178687.7375 |  | 146938.6875 |  |  |  | 29500 |  |  |  | 374718.25
5. Monitoring |  | 13695 | 14808.85 | 7423.28 | [9 empty] | 35927.13
6. AC Equipment |  |  | 12183.9 | 188706.17 |  | 91379.25 | [7 empty] | 292269.32
8. Product Add On |  |  |  | 64865 |  |  |  |  | 20332 | 22639 | 44224 |  |  | 152060
9. AC & DC installation |  |  | 50900 | 76350 |  | 279950 |  | 101799.99 | [5 empty] | 508999.99
10. Site Logistics |  |  | 4432 | 39048 |  | 61140 | 50700 | 27900 | 27900 | 6750 |  |  |  | 217870
11. Due Dilligence |  | 12911.75 |  |  | 13977.96 |  |  |  |  | 8000 |  |  | 79700 | 114589.71
13. Engineering | 0 | [11 empty] | 59518.4125 | 59518.4125
14. General Expenses |  | 1182.26 | 0 | 3211.84 | 0 | 542.64 | 1085.28 | 3791.54 | 2115.3 | 533.12 | 971.04 | 0 |  | 13433.02
15. Service Add On |  |  |  | 714000 |  |  |  |  | 12300 |  |  |  |  | 726300
12. BDP Commission
7.BESS
Grand Total | 0 | 27789.01 | 1390347.775 | 1346750.2275 | 13977.96 | 587229.3775 | 51785.28 | 198921.83 | 67965.62 | 67422.12 | 45195.04 | 0 | 139218.4125 | 3936602.6525

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate | [5 empty] | FINANCIAL CLOSE CERTIFICATE
Project Name: | Pretoria North
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion: |  |  |  | 1. Financial Close | 1. Financial Close
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 0.54596 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.27929 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.18895 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 0.45218 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
Pretoria North |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Pretoria North | 0 | 0 | 0