## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[9 empty] | 2026-02-23 | 2026-02-23
| PROJECT PLAN | Marikana Shoprite | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 825
| PROJECT DEVELOPER | Natasha Watkins-Baker
| PROJECT MANAGERS | Lloyd Brown
| CONTRACT VALUE | 8906375
| Phase: | Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Excepted Status | Comment
|  |  | 90 |  |  | 117 |  | 97.6% | 100%
1 | Project Initiation | 2025-04-22 | 44 | 2025-06-05 | 2025-04-29 | 17 | 2025-05-16 | 100% | 100%
1.1 | BD Handover | 2025-04-22 | 1 | 2025-04-23 | 2025-05-13 | 1 | 2025-05-14 | 100% | 100%
1.2 | Project Introduction | 2025-06-04 | 1 | 2025-06-05 | 2025-05-15 | 1 | 2025-05-16 | 100% | 100%
1.3 | HSE | 2025-04-22 | 10 | 2025-05-07 | 2025-04-29 | 10 | 2025-05-14 | 100% | 100%
1.4 | Installer Kick Off | 2025-05-28 | 1 | 2025-05-29 | 2025-05-14 | 1 | 2025-05-15 | 100% | 100%
1.5 | Project Review | 2025-05-28 | 1 | 2025-05-29 | 2025-05-08 | 1 | 2025-05-09 | 100% | 100%
2 | Site Establishment | 2025-06-11 | 1 | 2025-06-12 | 2025-06-11 | 1 | 2025-06-12 | 100% | 100%
2.1 | Solar Contractor Establishment | 2025-06-11 | 1 | 2025-06-12 | 2025-06-11 | 1 | 2025-06-12 | 100% | 100% |  | 82 | Net Work Days
3 | AC Installation | 2025-05-21 | 71 | 2025-07-31 | 2025-05-21 | 105 | 2025-09-03 | 100% | 100% |  | 16.4 | Total Weeks
3.1 | Inverters delivered | 2025-06-12 | 1 | 2025-06-13 | 2025-06-12 | 1 | 2025-06-13 | 100% | 100% |  | 50.3049 | kW/Week Installation Rate
3.2 | Inverters Mounted | 2025-06-13 | 5 | 2025-06-23 | 2025-07-23 | 9 | 2025-08-05 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-05-21 | 25 | 2025-06-26 | 2025-05-21 | 40 | 2025-07-17 | 100% | 100%
3.4 | AC Works | 2025-06-26 | 25 | 2025-07-31 | 2025-08-05 | 19 | 2025-09-01 | 100% | 100%
3.5 | AC Tie-In | 2025-06-26 | 3 | 2025-07-01 | 2025-09-03 | 0 | 2025-09-03 | 100% | 100%
4 | DC Works | 2025-06-11 | 78 | 2025-08-28 | 2025-06-11 | 112 | 2025-10-01 | 100% | 100%
4.1 | Lifeline Installation (If Applicable) | [6 empty] | 0% | 0%
4.1 | Mounting Structure delivered | 2025-06-11 | 1 | 2025-06-12 | 2025-06-11 | 1 | 2025-06-12 | 100% | 100%
4.2 | Mounting Structure installation | 2025-06-12 | 25 | 2025-07-18 | 2025-06-12 | 52 | 2025-08-26 | 100% | 100%
4.4 | DC Cable delivered | 2025-06-11 | 1 | 2025-06-12 | 2025-08-19 | 1 | 2025-08-20 | 100% | 100%
4.5 | DC Stringing | 2025-08-08 | 14 | 2025-08-28 | 2025-09-15 | 11 | 2025-10-01 | 100% | 100% | 2: Cable Trays - ~60%;4: Earth Cable - ~30%
5 | Module installation | 2025-07-11 | 31 | 2025-08-11 | 2025-08-19 | 42 | 2025-09-30 | 100% | 100%
5.1 | Module delivery | 2025-07-11 | 1 | 2025-07-14 | 2025-08-19 | 1 | 2025-08-20 | 100% | 100%
5.2 | Module mounting | 2025-07-14 | 20 | 2025-08-11 | 2025-08-26 | 24 | 2025-09-30 | 100% | 100%
6 | Commissioning | 2025-08-28 | 12 | 2025-09-09 | 2025-10-01 | 5 | 2025-10-06 | 100% | 100%
6.1 | Commissioning | 2025-08-28 | 3 | 2025-09-02 | 2025-10-01 | 1 | 2025-10-02 | 100% | 100%
6.2 | Practical Completion | 2025-09-02 | 5 | 2025-09-09 | 2025-10-02 | 2 | 2025-10-06 | 100% | 100%
7 | QA Inspections | 2025-09-09 | 1 | 2025-09-10 | 2025-10-24 | 3 | 2025-10-27 | 100% | 100%
7.1 | Red-Team Inspection | 2025-09-09 | 1 | 2025-09-10 | 2025-10-24 | 1 | 2025-10-27 | 100% | 100%
8 | Project Closure | 2025-09-10 | 15 | 2025-09-25 | 2025-10-27 | 35 | 2025-12-01 | 80.77% | 100%
8.1 | Equipment serial numbers | 2025-09-10 | 2 | 2025-09-12 | 2025-10-27 | 2 | 2025-10-29 | 100% | 100%
8.2 | Snags completion | 2025-09-10 | 5 | 2025-09-17 | 2025-10-27 | 5 | 2025-11-03 | 100% | 100%
8.3 | System Performance Monitoring | 2025-09-17 | 5 | 2025-09-25 | 2025-11-03 | 5 | 2025-11-10 | 100% | 100%
8.4 | Handover documentation | 2025-09-10 | 4 | 2025-09-16 | 2025-10-27 | 4 | 2025-10-31 | 100% | 100%
8.5 | Handover to Client | 2025-09-16 | 1 | 2025-09-17 | 2025-11-24 | 5 | 2025-12-01 | 0% | 100% | Redo handover documentation
8.6 | Handover to Matriarch | 2025-09-12 | 5 | 2025-09-19 | 2025-10-29 | 5 | 2025-11-05 | 100% | 100%
Formulas:
Planned Start = MIN([Planned Start, row below]:E16)
Planned Start = WORKDAY.INTL([Planned End, row above],0,1,Data!$C3:C14)
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Excepted Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )
Actual Start = MIN([Actual Start, row below])
Actual Start = MIN([Actual Start, row below]:I52)
Actual End = MAX([Actual End, row below])
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C14)

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 8906375 |  | 8906375 |  |  |  | Start Date | 7814255.4141 | 5535818.6275 | 1092119.36 | 1080651.0675 | 780848.06 | 1080651.0675
2 | Planned Expenditure | 8264787.1907 |  | 6616469.695 | VO PM Limit | Current VO Total
3 | Planned Profit | 641587.8093 |  | 2289905.305 | 32079.3905 | 62927.5 |  | End Date - PC
4 | Planned Margin | 7.204% |  | 25.71%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE |  | MILESTONE NOTES & COMMENTS
1 | Deposit |  | 20% | 1781275 |  | 2025-04-30 | 004734 | 2025-05-01 | 2025-04-30
2 | Delivery of Panels |  | 20% | 1781275 |  | 2025-07-18 | 004734 | 2025-05-01 | 2025-07-04
3 | Delivery of Inverters |  | 15% | 1335956.25 |  | 2025-06-19 | 004734 | 2025-05-01 | 2025-06-20
4 | Commissioning Complete |  | 15% | 1335956.25 |  | 2025-09-16 | 004734 | 2025-05-01 | 2025-10-10
5 | Final Completion Issued |  | 25% | 2226593.75 |  | 2025-09-17 | 004734 | 2025-05-01 | 2025-11-14
6 | Handover |  | 5% | 445318.75 |  | 2025-12-08 | 004734 | 2025-05-01 | 2025-11-14
7 | - |  | 0% | 0
|  |  | 100% | 8906375
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
| [ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important] | [5 empty] | 1536349.6875
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 3117231.25
2 | Delivery of Panels |  | 30% | 2671912.5
3 | Delivery of Inverters |  | 20% | 1781275
4 | Practical Completion |  | 10% | 890637.5
5 | Handover |  | 5% | 445318.75
| Total |  | 100% | 8906375
|  |  | 100% | 8906375

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | PLANNED |  | ACTUAL | Difference from costed | Difference from planned
EXPENDITURE |  | 8264787.1907 |  | #REF! |  | 6616469.695 | #REF! | #REF!
No. | Item | Costed Expenditure |  | Planned Expenditure |  | Actual Expenditure | Saving / Overrun | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 1793009.85 |  | #REF! |  | 1872409.5 | #REF! | #REF!
2 | 2. Inverters | 480000 |  | #REF! |  | 483092.45 | #REF! | #REF!
3 | 3. Mounting Structures | 371182.5 |  | #REF! |  | 166868.6 | #REF! | #REF!
4 | 4. DC Equipment | 650651 |  | #REF! |  | 401319.8355 | #REF! | #REF!
5 | 5. Monitoring | 49000 |  | #REF! |  | 40802.14 | #REF! | #REF!
6 | 6. AC Equipment | 792658.713 |  | #REF! |  | 378370.86 | #REF! | #REF!
7 | 7.BESS | 0 |  | #REF! |  | 0 | #REF! | #REF!
8 | 8. Product Add On | 200000 |  | #REF! |  | 219457.9315 | #REF! | #REF!
9 | 9. AC & DC installation | 675037.5 |  | #REF! |  | 866748.6 | #REF! | #REF!
10 | 10. Site Logistics | 168120.6 |  | #REF! |  | 577581.1305 | #REF! | #REF!
11 | 11. Due Dilligence | 141863.75 |  | #REF! |  | 38467.58 | #REF! | #REF!
12 | 12. BDP Commission | 162449.3288 |  | #REF! |  | 0 | #REF! | #REF!
13 | 13. Engineering | 266463.9489 |  | #REF! |  | 111329.6875 | #REF! | #REF!
14 | 14. General Expenses | 14350 |  | #REF! |  | 10546.38 | #REF! | #REF!
15 | 15. Service Add On | 2500000 |  | #REF! |  | 1449475 | #REF! | #REF!
| check: | 0 | #REF! | #REF! | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 8264787.1907 | 8906374.7836 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 6616469.695
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | ERROR on REV |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 1793009.85 | 2025-07-25 | 1793009.85 | 2037511.1932 |  | 1 | 1. Panels | Jinko 585W - Menlo | 1262 | 1327.95 | 1675872.9 | po3911-dip-ph2-mari-20250514 | Menlo INV0002855 | 2025-04-30 | 1822352.3216 | -0.001545 | 2025-07-29 | 1872409.5
1 |  | Delivery Budget |  |  |  | 2025-07-26 |  |  |  | 1 | 1. Panels |  |  | 2.27 |  |  |  |  | 0
1 | [5 empty] | 2025-07-27 |  |  |  | 1 | 1. Panels | [7 empty] | 0
1 | [5 empty] | 2025-07-28 |  |  |  | 1 | 1. Panels | Jinko 585W | 148 | 1327.95 | 196536.6 |  | Menlo INV0002946 | 2025-05-31 | 215158.8731 |  | 2025-07-28
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 792658.713
2 | Inverters | Inverter Budget |  |  | 480000 | 2025-07-29 | 480000 | 545454.5455 |  | 2 | 2. Inverters | Huawei 100KTL - Menlo | 7 | 68870 | 482092.45 | PO3896-DIP-PH2-MARI=20250514 | Menlo Inv:INV0003031 | 2025-06-30 | 545454.5455 | 0 | 2025-07-29 | 483092.45 | DC Equipment | 377679
2 | [5 empty] | 2025-12-01 |  |  |  | 2 | 2. Inverters | Huawei 100KTL - Menlo |  |  | 68870.35 |  | Menlo - INV0003291 | 2025-10-31 | 0 |  | 2025-12-04 |  | AC Labour | 206212.5
2 | [5 empty] | 2025-12-01 |  |  |  | 2 | 2. Inverters |  |  |  | 1000 |  | Menlo - INV0003291 | 2025-10-31 | 0 |  | 2025-12-04 |  | DC Labour | 468825
2 | [9 empty] | 2 | 2. Inverters |  |  |  | -68870.35 |  | Menlo - CRN0000261 | 2025-10-31 | 0 |  | 2025-11-30 |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 46050.6
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 15170
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 371182.5 | 2025-07-29 | 371182.5 | 421798.2955 |  | 3 | 3. Mounting Structures | Schletter Structure |  |  | 161223.6 | PO3982-MARSR-20250604 - RV Approved | Schletter Inv: 1853 | 2025-06-30 | 391583.7266 | 0 | 2025-07-29 | 166868.6 | Other | 0
3 | [5 empty] | 2025-06-30 |  |  |  | 3 | 3. Mounting Structures | Seam Clamps (From PE Store) |  |  | 12440 |  | Allocated from PE Storeroom | 2025-06-30 | 30214.5688 |  | 2025-06-30 |  | Total | 1915095.813
3 | [5 empty] | 2025-07-31 |  |  |  | 3 | 3. Mounting Structures | Seam Clamps (Returned PE Store) |  |  | -12440 |  | Allocated to PE Storeroom | 2025-07-31 | 0 |  | 2025-07-31 |  | Less 15% | 1627831.4411
3 | [5 empty] | 2025-07-31 |  |  |  | 3 | 3. Mounting Structures | End Clamps |  |  | 5645 |  | Allocated from PE Storeroom | 2025-07-31 | 0 |  | 2025-07-31 |  | R/Wp | 1.9731
3 | [5 empty] | 2025-08-01 |  |  |  | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [5 empty] | 2025-08-02 |  |  |  | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL | Installer Price
[6 empty] | 2025-08-03 | [16 empty] | AC Equipment | 159695.79
4 | DC Equipment | DC Cable Budget | 22422.7 |  | 272972 | 2025-08-04 | 650651 | 739376.1364 |  | 4 | 4. DC Equipment | DC Cable - Menlo | 16000 | 13.3 | 212800 | PO3911-DIP-PH2-MARI-20250514 | Menlo INV0002855 | 2025-04-30 | 266460.3514 | 0.0041255 | 2025-07-29 | 401319.8355 | DC Equipment | 188519.83
4 |  | DC Equipment Budget |  |  | 377679 | 2025-08-05 |  |  |  | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | AC Labour | 84614.5 | 0.10256
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | DC Labour | 782134.1 | 0.94804
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Roof Access | 24640
4 | [5 empty] | 2025-06-05 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 188519.83 | 10% | 18851.983 | PO3937-DIP-Ph2-Mari-20250520 - RV Approved | Greenway Solar: INV0001377 | 2025-05-31 | 34732.1645 |  | 2025-06-05 |  | Offloading & Rigging | 35165.63
4 | [5 empty] | 2025-06-19 |  |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 28277.98 |  | Greenway Solar: INV0001389 | 2025-06-30 | 93962.9462 |  | 2025-06-19 |  | P&G | 154925.5
4 | [5 empty] | 2025-10-08 |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 37703.966 |  | Greenway Solar: INV0001425 | 2025-07-31 | 111329.0681 |  | 2025-10-16 |  | Telehandler | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 47129.9575 |  | Greenway Solar: INV0001425 | 2025-07-31 | 128695.1101 |  | 2025-10-16 |  | HSE | 10000
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 18851.983 |  | Greenway Solar: INV0001425 | 2025-07-31 | 34732.164 |  | 2025-10-16 |  | Other | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 18851.983 |  | Greenway Solar: INV0001425 | 2025-07-31 | 34732.164 |  | 2026-01-29 |  | Other | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 9425.9915 |  | Greenway Solar: INV0001425 | 2025-07-31 | 17366.082 |  | 2026-02-05 |  | Total | 1439695.35
4 | [5 empty] | 2025-11-30 |  |  |  | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 9425.9915 |  | Greenway Solar: INV0001425 | 2025-07-31 | 17366.082 |  | 2026-03-07 |  | R/Wp | 1.7451
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 34000 | 2025-07-17 | 49000 | 55681.8182 |  | 5 | 5. Monitoring | Smartlogger |  |  | 8598.35 | PO3896-DIP-PH2-MARI-20250514 | Menlo INV0002930 | 2025-05-31 | 11776.5377 | -0.00019466 | 2025-07-17 | 40802.14
5 |  | Revenue Metering |  |  | 15000 | 2025-05-29 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 14805 | PO3830-DIP-Ph2-Mari-20250429 - RV Approved | Accuenergy - INV ASAI-005356 | 2025-04-30 | 20104.117 |  | 2025-05-29
[6 empty] | 2025-07-29 |  |  |  | 5 | 5. Monitoring | DIN Rail |  |  | 214.29 |  | Accuenergy - Inv ASAI-005800 | 2025-06-30 | 349.577 |  | 2025-07-29
5 | [5 empty] | 2025-06-30 |  |  |  | 5 | 5. Monitoring | Techsitter |  |  | 14934 |  | Matriarch Inv: 4451 | 2025-06-30 | 20195.2742 |  | 2025-06-30
5 | [5 empty] | 2025-05-22 |  |  |  | 5 | 5. Monitoring | UPS |  |  | 2250.5 | PO3863-DIP Ph2-20250509 - RV Approved | Frontline Electrical: INV725690 | 2025-05-31 | 3256.3124 |  | 2025-05-22
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 792658.713 | 2025-08-29 | 792658.713 | 900748.5375 |  | 6 | 6. AC Equipment | [7 empty] | 0 | 0.0046744 |  | 378370.86
6 | [5 empty] | 2025-08-30 |  |  |  | 6 | 6. AC Equipment | PVDB |  |  | 218675.07 | PO3890-DIP-Ph2-Marikana-20250513 - RV Approved | Switchboard - Inv 2-SOI002190 | 2025-07-31 | 520577.2176 |  | 2025-08-30
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [5 empty] | 2025-06-05 |  |  |  | 6 | 6. AC Equipment | Project Kick Off | 159695.79 | 10% | 15969.579 | PO3937-DIP-Ph2-Mari-20250520 - RV Approved | Greenway Solar: INV0001377 | 2025-05-31 | 38574.4741 |  | 2025-06-05
6 | [5 empty] | 2025-06-19 |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 23954.3685 |  | Greenway Solar: INV0001389 | 2025-06-30 | 57861.7112 |  | 2025-06-19
6 | [5 empty] | 2025-10-08 |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 31939.158 |  | Greenway Solar: INV0001425 | 2025-07-31 | 74640.904 |  | 2025-10-16
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 39923.9475 |  | Greenway Solar: INV0001425 | 2025-07-31 | 95042.83 |  | 2025-10-16
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 15969.579 |  | Greenway Solar: INV0001425 | 2025-07-31 | 38017.132 |  | 2025-10-16
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 15969.579 |  | Greenway Solar: INV0001425 | 2025-07-31 | 38017.132 |  | 2026-01-29
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 7984.7895 |  | Greenway Solar: INV0001425 | 2025-07-31 | 19008.566 |  | 2026-02-05
6 | [5 empty] | 2025-11-30 |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 7984.7895 |  | Greenway Solar: INV0001425 | 2025-07-31 | 19008.566 |  | 2026-03-07
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 200000 | 227272.7273 |  | 8 | 8. Product Add On | Estop |  |  | 695 | PO4396-MARSR-20251023 - RV Approved | The Greenway - INV0001512 | 2025-10-31 | 0 | 0 | 2025-10-31 | 219457.9315
8 | [9 empty] | 8 | 8. Product Add On | Modification on inverter cage |  |  | 8375 | PO4573-MARSH-20260126 - RV Approved | The Engineering Hub Inv: INV/2026/01/0252 | 2026-01-31 | 0 |  | 2026-02-28
8 |  | MV Metering |  |  | 200000 | 2025-07-31 |  |  |  | 8 | 8. Product Add On | Inverter Cage with Roof |  |  | 94626.2715 |  | The Engineering Hub Inv: INV/2025/06/0572 | 2025-06-30 | 227272.7273 |  | 2025-07-31
8 | [9 empty] | 8 | 8. Product Add On | Replace Stolen Earth Cable |  |  | 8260 | PO4535-MARSR-20251210 - RV Approved | The Greenway Solar Inv: INV0001585 | 2025-12-31 |  |  | 2026-01-15
8 | [5 empty] | 2025-10-02 |  |  |  | 8 | 8. Product Add On | Inverter Room Budget | 75% | 81501 | 61125.75 | PO4322-MAR-SR-20250919 - RV Approved | Van Staden Three INV3001 | 2025-09-30 | 0 |  | 2025-10-02
8 | [5 empty] | 2025-10-31 |  |  |  | 8 | 8. Product Add On |  | 25% |  | 20375.25 |  | Van Staden Three INV3039 | 2025-10-31 | - |  | 2025-10-31
8 | [5 empty] | 2025-10-02 |  |  |  | 8 | 8. Product Add On | Waterpoints |  |  | 12966.66 | PO4326-MAR-OC-2025092 - RV Approved | Van Staden Group Inv: 1656 | 2025-09-30 | 0 |  | 2025-10-13
8 | [9 empty] | 8 | 8. Product Add On | Strapping of Trays |  |  | 6844 | PO4411-MARSR-20251027 - RV Approved | The Greenway - INV0001527 | 2025-10-31 | 0 |  | 2025-10-30
8 | [9 empty] | 8 | 8. Product Add On | Replacement of Earth Cable - VO |  |  | 6190 | PO4410-MARSR-20251027 - RV Approved | The Greenway - INV0001518 | 2025-10-31 | 0 |  | 2025-10-31
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 206212.5 | 2025-06-04 | 675037.5 | 794161.7647 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0 |  | 866748.6
9 |  | DC Installation Budget |  |  | 468825 | 2025-06-05 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 866748.6 | 10% | 86674.86 | PO3937-DIP-Ph2-Mari-20250520 - RV Approved | Greenway Solar: INV0001377 | 2025-05-31 | 79416.1765 |  | 2025-06-05
9 | [5 empty] | 2025-06-19 |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 130012.29 |  | Greenway Solar: INV0001389 | 2025-06-30 | 119124.2647 |  | 2025-06-19
9 | [5 empty] | 2025-10-08 |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 173349.72 |  | Greenway Solar: INV0001425 | 2025-08-31 | 158832.3529 |  | 2025-10-16
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 216687.15 |  | Greenway Solar: INV0001425 | 2025-09-30 | 198540.4412 |  | 2025-10-16
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 86674.86 |  | Greenway Solar: INV0001425 | 2025-09-30 | 79416.1765 |  | 2025-10-16
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 86674.86 |  | Greenway Solar: INV0001425 | 2025-10-31 | 79416.1765 |  | 2026-01-29
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 43337.43 |  | Greenway Solar: INV0001425 | 2025-10-31 | 39708.0882 |  | 2026-02-05
9 | [5 empty] | 2025-11-30 |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 43337.43 |  | Greenway Solar: INV0001425 | 2025-10-31 | 39708.0882 |  | 2026-03-07
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-07-01 | 168120.6 | 197788.9412 |  | 10 | 10. Site Logistics | Security | [6 empty] | 0 | 0.0027171 |  | 577581.1305
10 |  | Scaffolding |  |  | 46050.6 | 2025-07-02 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
[6 empty] | 2025-07-03 |  |  |  | 10 | 10. Site Logistics | Security - June |  |  | 25950 | PO4033-MAR-20250625 - RV Approved | JerryG & Sons INV6 | 2025-06-30 | 16228.0406 |  | 2025-07-03
[6 empty] | 2025-07-31 |  |  |  | 10 | 10. Site Logistics | Security - July |  |  | 41230 |  | JerryG & Sons INV9 | 2025-07-31 | 23780.6915 |  | 2025-07-31
[6 empty] | 2025-09-01 |  |  |  | 10 | 10. Site Logistics | Security - August |  |  | 41230 |  | JerryG & Sons INV10 | 2025-08-31 | 19979.22 |  | 2025-09-01
[6 empty] | 2025-10-02 |  |  |  | 10 | 10. Site Logistics | Security - September |  |  | 39900 |  | JerryG & Sons: INV14 | 2025-09-30 | 0 |  | 2025-10-02
[6 empty] | 2025-10-03 |  |  |  | 10 | 10. Site Logistics | Security - October |  |  | 65710 |  | JerryG & Sons: INV16 | 2025-10-31 | 0 |  | 2025-11-06
10 |  | Security |  |  | 98400 | 2025-10-04 |  |  |  | 10 | 10. Site Logistics | Security - November |  |  | 63700 |  | JerryG & Sons INV20 | 2025-11-30 |  |  | 2025-11-28
10 |  | Storage |  |  | 15170 | 2025-10-05 |  |  |  | 10 | 10. Site Logistics | Security - December |  |  | 41230 |  | JerryG & Sons INV23 | 2025-12-31 |  |  | 2026-01-09
[10 empty] | 10 | 10. Site Logistics | Security - January |  |  | 33900 |  | JerryG & Sons INV26 | 2026-01-31 |  |  | 2026-01-29
[10 empty] | 10 | 10. Site Logistics
[10 empty] | 10 | 10. Site Logistics
10 | [5 empty] | 2025-10-06 |  |  |  | 10 | 10. Site Logistics | Project Kick Off | 224731.13 | 10% | 22473.113 | PO3937-DIP-Ph2-Mari-20250520 - RV Approved | Greenway Solar: INV0001377 | 2025-05-31 | 13755.8187 |  | 2025-06-05
10 | [5 empty] | 2025-06-19 |  |  |  | 10 | 10. Site Logistics | Site Establishment |  | 15% | 33709.67 |  | Greenway Solar: INV0001389 | 2025-06-30 | 21378.5324 |  | 2025-06-19
10 | [5 empty] | 2025-10-08 |  |  |  | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 44946.226 |  | Greenway Solar: INV0001425 | 2025-07-31 | 27377.7694 |  | 2025-10-16
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 56182.7825 |  | Greenway Solar: INV0001425 | 2025-07-31 | 34222.2117 |  | 2025-10-16
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 22473.113 |  | Greenway Solar: INV0001425 | 2025-07-31 | 13688.8847 |  | 2025-10-16
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 22473.113 |  | Greenway Solar: INV0001425 | 2025-07-31 | 13688.8847 |  | 2026-01-29
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 11236.5565 |  | Greenway Solar: INV0001425 | 2025-07-31 | 6844.4423 |  | 2026-02-05
10 | [5 empty] | 2025-11-30 |  |  |  | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 11236.5565 |  | Greenway Solar: INV0001425 | 2025-07-31 | 6844.4423 |  | 2026-03-07
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 20621.25 | 2025-04-09 | 141863.75 | 166898.5294 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 22655.83 |  | Sunspot E027 | 2025-07-31 | 96403.6821 | 0.0024125 | 2025-11-27 | 38467.58
11 |  | Structural Sign Off |  |  | 41242.5 | 2025-04-10 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 7811.75 | PO3745-DIP-Ph2-20250313 - RV Approved | L&B Consulting - Invoice 1934 | 2025-04-30 | 35785.403 |  | 2025-04-10
11 |  | Grid Study |  |  | 80000 | 2025-04-11 |  |  |  | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 8000 |  | Matriarch - INV-5370 | 2025-10-31 | 34709.442 |  | 2025-11-28
11 | [5 empty] | 2025-04-12 |  |  |  | 11 | 11. Due Dilligence | [7 empty] | 0
11 | [5 empty] | 2025-04-13 |  |  |  | 11 | 11. Due Dilligence | [7 empty] | 0
2025-04-14
12 | BDP Commission | Referral Fee |  |  | 121836.9966 | 2025-04-15 | 162449.3288 | 0 |  | 12 | 12. BDP Commission | Referral Fee | [9 empty] | 0
12 | BDP Commission | PD Fee |  |  | 40612.3322 | 2025-04-16 |  |  |  | 12 | 12. BDP Commission | PD Fee
2025-04-17
13 | Engineering | Matriarch Defects Period |  |  | 64019.0489 | 2025-04-18 | 266463.9489 | 302799.9419 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 111329.6875 |  | Matriarch - INV-5369 | 2025-10-31 | 302799.9419 | 0 | 2025-11-30 | 111329.6875
13 |  | Management |  |  | 24000 | 2025-04-19 |  |  |  | 13 | 13. Engineering | Management |  |  | 0 |  |  |  | 0
13 |  | Project manager |  |  | 102000 | 2025-04-20 |  |  |  | 13 | 13. Engineering | Project manager |  |  | 0 |  |  |  | 0
13 |  | Planner time |  |  | 41600 | 2025-04-21 |  |  |  | 13 | 13. Engineering | Planner time |  |  | 0 |  |  |  | 0
13 |  | De Snagging |  |  | 34844.9 | 2025-04-22 |  |  |  | 13 | 13. Engineering | De Snagging |  |  | 0 |  |  |  | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 14350 | 2025-05-08 | 14350 | 16882.3529 |  | 14 | 14. General Expenses | Travel |  |  | 3414.34 |  | Site Visit | 2025-04-30 | 3870.0669 | -0.00011373 | 2025-05-08 | 10546.38
14 | [5 empty] | 2025-04-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  | 2025-04-30 | 0 |  | 2025-04-30
14 | [5 empty] | 2025-05-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-05-31 | 0 |  | 2025-05-31
14 | [5 empty] | 2025-07-04 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 4792.56 |  | Expense Claim | 2025-06-30 | 4968.4806 |  | 2025-07-04
14 | [5 empty] | 2025-07-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-07-31 | 0 |  | 2025-07-31
14 | [5 empty] | 2025-08-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 1476.49 |  | Expense Claim | 2025-08-31 | 1494.1 |  | 2025-08-31
14 | [5 empty] | 2025-09-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 862.99 |  | Expense Claim | 2025-09-30 | 2060.3555 |  | 2025-10-10
14 | [5 empty] | 2025-10-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-10-31 | 0 |  | 2025-10-31
14 | [5 empty] | 2025-11-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-11-30 | 4489.35 |  | 2025-12-05
14 | [5 empty] | 2025-12-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  |  | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | Welcome Bonus |  |  | 2500000 | 2025-07-03 | 2500000 | 2500000 |  | 15 | 15. Service Add On | Welcome Bonus - Site Establishsment |  |  | 668000 |  | Hynorex - Inv 23409/202506/274917/I | 2025-06-30 | 1094364.3512 | -0.0024902 | 2025-07-03 | 1449475
15 | [5 empty] | 2025-10-20 |  |  |  | 15 | 15. Service Add On | Welcome Bonus - Commissioning |  |  | 668000 |  | Hynorex - Inv 23409/202506/274917/I | 2025-06-30 | 1094364.3512 |  | 2025-10-24
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | Community Engagement | [6 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | New Installer Contigency fund |  |  | 0
15 | [9 empty] | 15 | 15. Service Add On | Delays and standing time - VO | 50% | 113475 | 56737.5 | PO4434-MARSR-20251031 - RV Approved | The Greenway - INV0001517 | 2025-10-31 |  |  | 2025-11-06
15 | [9 empty] | 15 | 15. Service Add On |  | 50% |  | 56737.5 |  | The Greenway - INV0001517 | 2025-10-31 | - |  | 2026-03-07
15 | [9 empty] | 15 | 15. Service Add On | [6 empty] | 2025-11-30 | 311271.3
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
| Panel Procurement Budget | 1793009.85 |  | 2037511.1932
| Inverter Procurement Budget | 480000 |  | 545454.5455
| Mounting Structure Budget | 371182.5 |  | 421798.2955
| DC Equipment Budget | 650651 |  | 739376.1364
| AC Equipment Budget | 792658.713 |  | 900748.5375
| Monitoring Budget | 49000 |  | 55681.8182
| Optional Extras Budget | 0 |  | 0
| MV Metering Budget | 200000 |  | 227272.7273
| ADD ON | 0 |  | 0
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 206212.5 |  | 242602.9412
| DC Installer Budget | 468825 |  | 551558.8235
| In-House Expense Budget | 266463.9489 |  | 302799.9419
| Compliance Budget | 141863.75 |  | 166898.5294
| Offloading Budget | 8500 |  | 10000
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 15170 |  | 17847.0588
| On Site Security | 98400 |  | 115764.7059
| Roof Access Budget for Installers | 46050.6 |  | 54177.1765
| EPC Management Fee | 0 |  | 0
| ADD ON | 2500000 |  | 2500000
Expenses
| Total EE Expense Budget | 14350 |  | 16882.3529
Note on W64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date
Note on W65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs Please update the payment date

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 8906375 | 8906375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1781275 | 0 | 0 | 0 | 0 | 0 | 0 | 1335956.25 | 0 | 0 | 0 | 1781275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3562550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 445318.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1781275 | 1781275 | 1781275 | 1781275 | 1781275 | 1781275 | 1781275 | 3117231.25 | 3117231.25 | 3117231.25 | 3117231.25 | 4898506.25 | 4898506.25 | 4898506.25 | 4898506.25 | 4898506.25 | 4898506.25 | 4898506.25 | 4898506.25 | 4898506.25 | 8461056.25 | 8461056.25 | 8461056.25 | 8461056.25 | 8461056.25 | 8461056.25 | 8461056.25 | 8461056.25 | 8461056.25 | 8461056.25 | 8461056.25 | 8461056.25 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375
| Planned Expenditure | 8264787.1907 | 8264787.1907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141863.75 | 352468.3777 | 76444.9 | 0 | 14350 | 0 | 0 | 15000 | 675037.5 | 0 | 0 | 0 | 2554550.6 | 0 | 34000 | 1793009.85 | 1051182.5 | 650651 | 0 | 0 | 792658.713 | 0 | 0 | 0 | 0 | 113570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141863.75 | 494332.1277 | 570777.0277 | 570777.0277 | 585127.0277 | 585127.0277 | 585127.0277 | 600127.0277 | 1275164.5277 | 1275164.5277 | 1275164.5277 | 1275164.5277 | 3829715.1277 | 3829715.1277 | 3863715.1277 | 5656724.9777 | 6707907.4777 | 7358558.4777 | 7358558.4777 | 7358558.4777 | 8151217.1907 | 8151217.1907 | 8151217.1907 | 8151217.1907 | 8151217.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907 | 8264787.1907
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -141863.75 | -494332.1277 | -570777.0277 | 1210497.9723 | 1196147.9723 | 1196147.9723 | 1196147.9723 | 1181147.9723 | 506110.4723 | 506110.4723 | 1842066.7223 | 1842066.7223 | -712483.8777 | -712483.8777 | 1034791.1223 | -758218.7277 | -1809401.2277 | -2460052.2277 | -2460052.2277 | -2460052.2277 | -3252710.9407 | -3252710.9407 | -3252710.9407 | 309839.0593 | 309839.0593 | 196269.0593 | 196269.0593 | 196269.0593 | 196269.0593 | 196269.0593 | 196269.0593 | 196269.0593 | 196269.0593 | 196269.0593 | 196269.0593 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093 | 641587.8093
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 8906375 | 8906375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1781275 | 0 | 0 | 0 | 0 | 0 | 0 | 1335956.25 | 0 | 1781275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1335956.25 | 0 | 0 | 0 | 0 | 2671912.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1781275 | 1781275 | 1781275 | 1781275 | 1781275 | 1781275 | 1781275 | 3117231.25 | 3117231.25 | 4898506.25 | 4898506.25 | 4898506.25 | 4898506.25 | 4898506.25 | 4898506.25 | 4898506.25 | 4898506.25 | 4898506.25 | 4898506.25 | 4898506.25 | 4898506.25 | 4898506.25 | 4898506.25 | 6234462.5 | 6234462.5 | 6234462.5 | 6234462.5 | 6234462.5 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375 | 8906375
| Actual + Planned Expenditure | 6616469.695 | 6616469.695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7811.75 | 0 | 0 | 0 | 3414.34 | 0 | 2250.5 | 14805 | 143969.535 | 0 | 215954.3085 | 0 | 726116.56 | 0 | 8598.35 | 0 | 2857801.1115 | 0 | 0 | 0 | 220151.56 | 41230 | 0 | 0 | 0 | 101025.75 | 862.99 | 804799.1025 | 668000 | 34104.25 | 122447.5 | 0 | 0 | 136815.1675 | 69870.35 | 0 | 0 | 0 | 0 | 41230 | 8260 | 0 | 177869.535 | 71984.7675 | 0 | 0 | 8375 | 128722.2675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7811.75 | 7811.75 | 7811.75 | 7811.75 | 11226.09 | 11226.09 | 13476.59 | 28281.59 | 172251.125 | 172251.125 | 388205.4335 | 388205.4335 | 1114321.9935 | 1114321.9935 | 1122920.3435 | 1122920.3435 | 3980721.455 | 3980721.455 | 3980721.455 | 3980721.455 | 4200873.015 | 4242103.015 | 4242103.015 | 4242103.015 | 4242103.015 | 4343128.765 | 4343991.755 | 5148790.8575 | 5816790.8575 | 5850895.1075 | 5973342.6075 | 5973342.6075 | 5973342.6075 | 6110157.775 | 6180028.125 | 6180028.125 | 6180028.125 | 6180028.125 | 6180028.125 | 6221258.125 | 6229518.125 | 6229518.125 | 6407387.66 | 6479372.4275 | 6479372.4275 | 6479372.4275 | 6487747.4275 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695 | 6616469.695
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7811.75 | -7811.75 | -7811.75 | 1773463.25 | 1770048.91 | 1770048.91 | 1767798.41 | 1752993.41 | 1609023.875 | 1609023.875 | 2729025.8165 | 2729025.8165 | 3784184.2565 | 3784184.2565 | 3775585.9065 | 3775585.9065 | 917784.795 | 917784.795 | 917784.795 | 917784.795 | 697633.235 | 656403.235 | 656403.235 | 656403.235 | 656403.235 | 555377.485 | 1890470.745 | 1085671.6425 | 417671.6425 | 383567.3925 | 261119.8925 | 2933032.3925 | 2933032.3925 | 2796217.225 | 2726346.875 | 2726346.875 | 2726346.875 | 2726346.875 | 2726346.875 | 2685116.875 | 2676856.875 | 2676856.875 | 2498987.34 | 2427002.5725 | 2427002.5725 | 2427002.5725 | 2418627.5725 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305 | 2289905.305
|  | CHECK | CHECK
| Revenue Recognition | 0.22595 | 8906374.7741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2148572.2599 | 0 | 0 | 0 | 396670.357 | 0 | 0 | 0 | 0 | 3717323.0976 | 0 | 0 | 0 | 1371384.0266 | 0 | 0 | 0 | 180305.6729 | 0 | 0 | 0 | 0 | 280016.9731 | 0 | 0 | 0 | 496341.7368 | 0 | 0 | 0 | 315760.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 8906374.7741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2148572.2599 | 2148572.2599 | 2148572.2599 | 2148572.2599 | 2545242.6169 | 2545242.6169 | 2545242.6169 | 2545242.6169 | 2545242.6169 | 6262565.7146 | 6262565.7146 | 6262565.7146 | 6262565.7146 | 7633949.7411 | 7633949.7411 | 7633949.7411 | 7633949.7411 | 7814255.4141 | 7814255.4141 | 7814255.4141 | 7814255.4141 | 7814255.4141 | 8094272.3872 | 8094272.3872 | 8094272.3872 | 8094272.3872 | 8590614.1241 | 8590614.1241 | 8590614.1241 | 8590614.1241 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741 | 8906374.7741

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | Grand Total
(blank)
1. Panels |  | 1675872.9 | 196536.6 | [8 empty] | 1872409.5
2. Inverters |  |  |  | 482092.45 |  |  |  | 1000 |  |  |  | 483092.45
3. Mounting Structures |  |  |  | 173663.6 | -6795 | [6 empty] | 166868.6
4. DC Equipment |  | 212800 | 18851.983 | 28277.98 | 141389.8725 | [6 empty] | 401319.8355
5. Monitoring |  | 14805 | 10848.85 | 15148.29 | [7 empty] | 40802.14
6. AC Equipment |  |  | 15969.579 | 23954.3685 | 338446.9125 | [6 empty] | 378370.86
8. Product Add On |  |  |  | 94626.2715 |  |  | 74092.41 | 34104.25 |  | 8260 | 8375 | 219457.9315
9. AC & DC installation |  |  | 86674.86 | 130012.29 |  | 173349.72 | 303362.01 | 173349.72 |  |  |  | 866748.6
10. Site Logistics |  |  | 22473.113 | 59659.67 | 209778.3475 | 41230 | 39900 | 65710 | 63700 | 41230 | 33900 | 577581.1305
11. Due Dilligence |  | 7811.75 |  |  | 22655.83 |  |  | 8000 |  |  |  | 38467.58
13. Engineering | 0 | [6 empty] | 111329.6875 |  |  |  | 111329.6875
14. General Expenses | 0 | 3414.34 | 0 | 4792.56 | 0 | 1476.49 | 862.99 | 0 | 0 |  |  | 10546.38
15. Service Add On | 0 |  |  | 1336000 |  |  |  | 113475 |  |  |  | 1449475
12. BDP Commission
7.BESS
Grand Total | 0 | 1914703.99 | 351354.985 | 2348227.48 | 705475.9625 | 216056.21 | 418217.41 | 506968.6575 | 63700 | 49490 | 42275 | 6616469.695

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | Grand Total
(blank)
1. Panels |  | 1822352.3216 | 215158.8731 | [7 empty] | 0 |  | 2037511.1947
2. Inverters |  |  |  | 545454.5455 |  |  |  | 0 |  |  | 0 |  | 545454.5455
3. Mounting Structures |  |  |  | 421798.2955 | 0 | [5 empty] | 0 |  | 421798.2955
4. DC Equipment |  | 266460.3514 | 34732.1645 | 93962.9462 | 344220.6702 | [5 empty] | 0 |  | 739376.1322
5. Monitoring |  | 20104.117 | 15032.8501 | 20544.8512 | [6 empty] | 0 |  | 55681.8184
6. AC Equipment | 0 |  | 38574.4741 | 57861.7112 | 804312.3475 | [5 empty] | 0 |  | 900748.5329
8. Product Add On |  |  |  | 227272.7273 |  |  | 0 | 0 |  |  |  | 0 | 227272.7273
9. AC & DC installation |  |  | 79416.1765 | 119124.2647 |  | 158832.3529 | 277956.6176 | 158832.3529 |  |  | 0 |  | 794161.7647
10. Site Logistics |  |  | 13755.8187 | 37606.573 | 126447.3268 | 19979.22 | 0 | 0 |  |  | 0 |  | 197788.9385
11. Due Dilligence |  | 35785.403 |  |  | 96403.6821 |  |  | 34709.442 |  |  | 0 |  | 166898.527
13. Engineering | 0 | [6 empty] | 302799.9419 |  |  | 0 |  | 302799.9419
14. General Expenses | 0 | 3870.0669 | 0 | 4968.4806 | 0 | 1494.1 | 2060.3555 | 0 | 4489.35 |  | 0 |  | 16882.3531
15. Service Add On | 0 |  |  | 2188728.7025 |  |  |  | 0 | 311271.3 |  | 0 |  | 2500000.0025
12. BDP Commission
7.BESS
Grand Total | 0 | 2148572.2599 | 396670.357 | 3717323.0976 | 1371384.0266 | 180305.6729 | 280016.9731 | 496341.7368 | 315760.65 |  | 0 | 0 | 8906374.7741

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate |  |  |  | FINANCIAL CLOSE CERTIFICATE
Project Name: | Marikana Shoprite
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 0.33684 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.17231 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.11657 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 0.27898 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
Marikana Shoprite |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Marikana Shoprite | 0 | 0 | 0