# SOP — Engineering Pack (EP)

Ownership: Engineering (inside Engineering department). System of record: ClickUp (tracking & gates), SharePoint (files). Note: Trigger is ClickUp — HoPE creates the EP ticket.

# 1) Purpose

Produce a constructible, compliant, and reviewed Engineering Pack to unlock procurement and construction.

Freeze technical scope, minimize rework, and deliver IFC (Issued for Construction) documents with zero ambiguity.

Provide clear interfaces to PM, CM, Procurement, and Compliance/HSE.

# 2) Scope & Trigger

In scope:

Basis of Design (BoD) and detailed design – acquire adequate information regarding the site layout, obstructions, challenges and electrical reticulation.

Drawings: Module layout, mounting details, stringing, DC/AC routing, earthing/LPS, SLDs DC/AC, General Assemblies (GA) signage.

Calculations & reports: yield, DC/AC sizing, earthing/LPS, structural checks, protection/co-ordination basis.

Schedules: cable, equipment, signage/labels.

Specifications & datasheets; approved equivalents.

Engineering inputs to method statements and QA/QC test plans.

Out of scope:

Placing POs; construction method statements (execution means/methods); commissioning procedures.

Client contractual communications (PM) and final CoCs (Compliance/HSE).

Original facility CoC to be acquired to allow our CoC to be completed.

Trigger:

Head of Project Engineering creates the EP task/ticket in ClickUp (manual creation).

No MS Teams post is made for the trigger. ClickUp is the single source of truth for EP tracking.

EP task includes links to SharePoint folders and required metadata (see DoR).

# 3) Definitions

DoR — Definition of Ready (to start EP):

EP ClickUp task exists and includes:

Links to SharePoint folders for Charter, RQR, SIR, and CP Pack.

Confirmed scope/option as per PD/DE→PM/EO Handover Charter (final).

Client rules/permits affecting design (or “None”).

Baseline survey inputs status (roof dims, penetrations, DB schedules, existing SLDs, earthing, PCC photo/coords) or booked survey date (Drone imagery recommended).

Dependencies list (surveys/logging/tests) with owners and target dates.

Gate targets set in fields: 30% BoD, 60% DD, 90% For Review, 100% IFC.

If any item missing: set task to Blocked and post a DoR-Fail comment listing the gaps.

DoD — Definition of Done (EP complete):

**TBC by Engineering Leadership** — to be filled in by the team. Use the template below to define the final acceptance criteria.

DoD Template — items to define:

IFC drawings list (exact) and required signatures (OE, HoD, Pr.Eng where applicable).

Calcs & reports (final list) and sign-off requirements.

Protection settings/coordination status (final settings or placeholders per utility).

Schedules (cables, equipment, signage) — completeness criteria.

Specifications & datasheets — approved ranges/equivalents policy.

Transmittal requirements (who receives, where filed, required references).

Open RFIs tolerance (zero or documented with owners/dates).

ClickUp status and fields to close EP (e.g., Gate = IFC – Done, “EP DoD Met” checkbox).

# 4) Roles (RACI)

| Function | Role in EP |
| --- | --- |
| OE (Design Owner) | Responsible for calculations, drawings, specs, schedules; drives gates. |
| Drafter/CAD | Prepares and updates drawings per OE markups. |
| Peer Reviewer | Independent internal reviewer at 60% and 90% gates. |
| HoPE / HoD | Accountable for technical sign-off and quality gates. |
| PM | Consulted for program and client comms. |
| CM | Consulted for buildability (access, trays, penetrations, install methods). |
| Procurement | Consulted for pre-RFQ and RFQ-ready schedules; LLIs/market input. |
| Compliance/HSE | Consulted for Safety File implications, signage, isolation/test requirements. |

# 5) Tools & Artefacts

CAD platform; PVSOL; Helioscope (reference only); Excel sizing sheets; Protection tool [TBC]; EE Drawing Library [TBC path]; EE Calculation Templates [TBC].

SharePoint path: [TBC Root]/Engineering/04_EP/Client_Site/YYYY-MM-DD with subfolders: 01_BoD | 02_Surveys | 03_Calcs | 04_Drawings | 05_Schedules | 06_Specs_Datasheets | 07_Protection | 08_QAQC | 09_Transmittals | _Archive.

ClickUp EP task custom fields: Gate dates, Complexity, Blocked (Y/N + reason), Scope Change (Y/N), Review status, DoD Met (Y/N).

# 6) SLAs (insert house numbers)

EP Kickoff from EP task creation: ≤ [3 h].

30% BoD from Kickoff: ≤ [2 days].

60% Design Development from 30%: ≤ [3 days].

90% For Review from 60%: ≤ [1 days].

100% IFC after review closure: ≤ [1 days].

Peer Review turnaround: ≤ [3 h].

HoD sign-off: ≤ [2 h].

# 7) Design Gates & Deliverables

30% – Basis of Design (BoD)

BoD document; SLD L1 (topology, PCC, metering/export).

Prelim GA (roof areas, walkways, keep-outs, penetrations).

Prelim DC/AC concept; assumptions & standards list.

Data gaps & survey/measurement plan.

60% – Design Development

GA complete; mounting typicals; stringing diagram.

DC routing & sizing calcs; inverter/combiner placements.

AC routes & tray sizes; earthing/LPS concept.

Draft cable/equipment/signage schedules.

90% – For Review

Full drawing set draft; full calcs pack.

Protection basis (draft settings/coordination or placeholders per utility).

Specs & datasheets; QA/QC test plan inputs; method inputs.

Signage schedule; RFI list (if any).

100% – IFC

Signed drawings & calcs; final schedules; protection basis; specs & datasheets; signage list; transmittal.

Update ClickUp gate to IFC – Done; file all in SharePoint.

# 8) IFC Drawing Set — minimum content

Cover & Index (project info, revision history, legend).

Mounting/Racking details — typicals per roof type; fixings; torque; sealing; corrosion control.

Stringing diagrams — string IDs, counts, MPPT groupings, pathways, JBs.

DC routing & schedule — tray/conduit sizes, penetrations, pull points, cable sizes/lengths, VD ref.

Inverter/Combiner layouts — footprints, clearances, anchoring.

AC routing & schedule — sizes/lengths; tray specs; terminations; VD & fault current ref.

Earthing & bonding — scheme, bars, bonding points, conductor sizes, test points, target resistance.

Lightning protection (if applicable) — zones, air terms, down conductors, bonding, separation.

SLD L1–L3 — topology; breakers/fuses/CT/VT placeholders; settings table; metering/export/gens/BESS interfaces.

Signage & labelling — location plans + schedule.

Details & notes — penetrations, seals, roof repairs, fire-stopping, segregation, EMC notes.

Energisation & test points — isolations, lock-outs, test links.

Site specific: GA — roof plans, blocks, walkways, keep-outs, penetrations, fall arrest interfaces, module orientation/tilt, grid/coords, inverter layout, cage.

# 9) Calculations & Reports — minimum set

Yield basis (PVSOL).

Structural checks for racking & fixings (Pr.Eng sign-off policy [TBC]).

DC sizing: string voltage window (min/max temp), Isc factors, VD %, fuse/ampacity, insulation levels.

AC sizing: ampacity, VD, fault levels, thermal constraints.

Earthing: conductor sizing; resistance target & method.

LPS: risk assessment & design (if applicable).

Protection & coordination: device selection, settings or placeholders; discrimination summary (where applicable).

Compliance checklist against SANS/NRS/client/utility standards.

# 10) Quality Gates (checklists)

30% BoD Gate:

Scope & topology consistent with Charter/CP.

Constraints & assumptions listed; data gaps & survey plan agreed.

Standards list & component families [EE defaults TBC] confirmed.

60% Gate:

Layout buildable (walkways, penetrations, access).

Stringing within component limits; DC/AC routes feasible; trays sized.

Earthing/LPS concepts fit constraints; draft schedules ≥80% complete.

90% Gate (For Review):

Full pack complete; peer review done; comments closed/logged.

Procurement RFQ-ready specs/schedules coherent.

PM/CM consulted for buildability; clashes resolved or RFIs raised.

Compliance/HSE reviewed signage, isolation points, Safety File implications.

100% Gate (IFC):

Drawings signed (OE + HoD; Pr.Eng where required).

Calcs pack signed.

Protection basis accepted or clearly marked pending utility settings.

Transmittal prepared; SharePoint filing complete; ClickUp updated.

# 11) Step-by-Step (Who / What / Tool / Output)

| Who | What | Tool | Output |
| --- | --- | --- | --- |
| HoPE | Create EP task in ClickUp; set gate dates/owners; add SP links; set Complexity. (No Teams post.) | ClickUp | EP plan (gates) live |
| OE | Produce 30% BoD (SLD L1, GA concept, assumptions, standards). | CAD/Templates | BoD pack |
| OE + CM/PM | Buildability pass (access, trays, penetrations); update BoD. | ClickUp comments/quick huddle | Closed BoD issues |
| OE/Drafter | Develop 60%: GA, mounting details, stringing, DC/AC routes & sizing drafts, earthing/LPS concept, draft schedules. | CAD/Excel | 60% pack |
| Peer Reviewer | Review 60%; mark-ups; OE closes comments. | ClickUp/Markup PDF | Closed 60% review |
| OE | Compile 90% For Review: full drawings, calcs, protection basis, specs, QA/QC inputs, method inputs, signage schedule. | CAD/Excel | 90% pack |
| PM/CM/Proc/HSE | Multi-discipline review; consolidate comments; raise RFIs if needed. | ClickUp comments (Teams optional) | Consolidated comments |
| OE | Close comments; finalise protection basis; calcs/schedules/specs clean. | CAD/Excel | Clean set |
| HoD/Pr.Eng | Technical sign-off. | ClickUp/Signing method [TBC] | Signed IFC drawings & calcs |
| OE/HoPE | Issue IFC: upload to SharePoint; attach transmittal; update ClickUp gate to IFC – Done. | SharePoint/ClickUp | IFC transmittal + links |

# 12) Interfaces

Procurement:

At 60% provide pre-RFQ schedules/specs for market scans (no commitment).

At 90% provide RFQ-ready schedules/specs + drawings; note approved equivalents policy.

At IFC confirm any pending utility settings do not block orders; flag LLIs.

Compliance/HSE:

Confirm isolation points, labels, signage, and test requirements (IV curve, insulation, earth resistance, torque).

Provide Engineering inputs to Safety File (datasheets, certificates templates, test sheets).

Construction (CM):

Validate buildability: tray sizes vs bends, cable pulls, penetrations, fixings, hot-work constraints.

Provide installation maps: string maps, routing, equipment locations, earthing bonding points.

# 13) Document Control

Naming: Client_Site_EP_{DocType}_{Discipline}_{Rev}.ext (e.g., ACME_Pretoria_EP_SLD_ELEC_RevC.pdf).

Revisions: 1.1/1.2/1.3… during design; IFC with date stamp for issue, and within construction version of changes will be V2/V3/V4....

Transmittals: include file list, revs, purpose, recipients; store in 09_Transmittals.

# 14) Change Control

Any scope/intent change during EP: set Scope Change = Yes in ClickUp; comment with reason; bump Rev; adjust gates/dates; inform PM/Procurement/CM.

Archive superseded in _Archive; mark latest CURRENT.

# 15) KPIs

Gate adherence: % gates met on time.

First-pass sign-off: % passing HoD without rework.

Rework drivers: top 3 (data gap, buildability, protection).

IFC vs CP variance: design-driven cost impact flagged pre-IFC.

RFI count & closure time.

Install NCRs attributable to design (target zero).

# 16) Common Failure Modes & Controls

Inadequate survey data → hold at 30% until resolved; run targeted survey; avoid assumptions.

Tray space clashes → check bend radius & fill; coordinate with CM early.

String voltage breaches → verify min/max temp window and add EE safety margin [TBC].

Earthing/LPS ambiguity → agree resistance targets and LPS scope; document method.

Protection TBD → clearly label placeholders; confirm procurement can proceed; book utility settings review.

Standards drift → lock EE libraries; peer check against standards list.

# 17) Templates (ready to paste into ClickUp)

Gate Checklists:

30% BoD: Topology fixed ☐ / Constraints listed ☐ / Standards listed ☐ / Survey plan ☐ / Assumptions ☐

60%: GA done ☐ / Stringing done ☐ / DC sizes calc ☐ / AC routes & tray sizes calc ☐ / Earthing/LPS concept ☐ / Draft schedules ☐

90%: Full pack ☐ / Calcs complete ☐ / Protection basis ☐ / Specs & datasheets ☐ / QA/QC inputs ☐ / Method inputs ☐ / Signage ☐ / Peer review closed ☐

IFC: Drawings signed ☐ / Calcs signed ☐ / Transmittal ☐ / SharePoint filed ☐ / ClickUp updated ☐

ClickUp Comment Templates:

DoR-Fail: EP blocked — missing {items}. Please attach to this task. SLA resumes once complete.

For Review (90%): EP 90% ready — please comment by {date}. Attach markups to this task.

IFC Issued: EP IFC issued — transmittal & SP link attached. Gate set to IFC – Done.