## NEW
| Tel: | +27 21 828 4202 +27 11 028 8060
| E-mail: | info@emergy.co.za
| Physical: | Brickfield Canvas, 35 Brickfield Road, Salt River, Cape Town
89 Bute Lane, Sandton, Johannesburg
| Postal: | PO Box 23877, Claremont 7735
Internal Project Kick-off
1 | Project Details |  |  | 2 | Emergent Energy Team Details
1.1 | Project name: | China Town Ottery |  | 2.1 | Business developer: | Maxime Eon
1.2 | Size (kWp): | 200 kWp |  | 2.2 | PV Sol Designer: | Issac Olayiwola
1.3 | Value (R's): | 2141434.01 |  | 2.3 | Project Manager: | LeChloe Clegg
1.4 | Site address: | Woodlands Road, Ottery |  | 2.4 | Project Coordinator | Simon Muller
3 | Project Checklist | Action | Y | N | Comments
3.1 | Signed cost proposal | Maxime Eon |  |  | Check payment milestones
3.2 | Signed contract | Maxime Eon
3.3 | Client deposit paid | Tasneema van Harte | X
3.4 | PV Sol design finalised | Issac Olayiwola
3.5 | SSEG application | Issac Olayiwola
3.6 | NERSA resigstration | Issac Olayiwola
3.7 | SLD design | Dayne Sage
3.8 | Structural inspection | LeChloe Clegg
3.9 | Site visits (EE / Installer) | LeChloe Clegg
3.10 | Project description | LeChloe Clegg
3.11 | Department of labour | LeChloe Clegg
3.12 | Safety file (EE) | LeChloe Clegg
3.13 | Internet connection | LeChloe Clegg
3.14 | O&M contract | Maxime / Natheera
3.15 | Installer appointed | LeChloe / Simon
4 | Technical information |  |  | 5 | Client details
4.1 | Modules: | Longi 440 W (456) |  | 5.1 | Client: | Steve Kruger
4.2 | Inverters: | SolarEdge 82.8 |  | 5.2 | Client rep on site:
4.3 | MS brief: |  |  | 5.3 | Site access:
4.4 | Metering: | Solar Edge |  | 5.4 | Security information:
4.5 | Generator integration: | No |  | 5.5 | Tenant pack required? | Yes / Action
4.6 | Scada: |  |  | 5.6 | Project start date: | 2021-01-18
4.7 | Roof type: | IBR |  | 5.7 | Project end date: | 2021-02-05
6 | Comments |  |  | 7 | Next meetings
6.1 |  |  |  | 7.1 | Client kick off
6.2 |  |  |  | 7.2 | Project readiness
6.3
6.4
6.5

## Sheet1
| Tel: | +27 21 828 4202 +27 11 028 8060
| E-mail: | info@emergy.co.za
| Physical: | Brickfield Canvas, 35 Brickfield Road, Salt River, Cape Town
89 Bute Lane, Sandton, Johannesburg
| Postal: | PO Box 23877, Claremont 7735
Internal Project Kick-off
| Project: | 0 |  |  | Cost Proposal: | 0 | Physical Address:
| Date: |  |  |  | Signature Date: | 0
Present at Kick-Off
| Salesperson |  | 0 |  | Project Manager |  | 0
| Project Sponsor |  | 0 |  | Project Planner |  | 0
| Other |  |  |  | Installer |  | 0
| Check List |  | Y/N | Action |  |  | Due Date | Closed
| Proposal Signed | [7 empty] | Creation of project folder
| Contract Signed | [8 empty] | set up PM, ACC and PRE folder
PV Sol 3rd Party Review
Deposit Invoiced/Received
Site Visit
Structural Sign-Off
Internet Connection
Project Description
SSEG Application Submitted
O&M Contract
Dept. of Labour Informed
Project Value
Cost Proposal Margin
| What's exciting about this project? What's our biggest worry? What's 1 thing we want to do better? | [8 empty] | Start date
Order placement date
Handover Date
Anticipated planning
| Project Planning | [8 empty] | Start date
Order placement date
Handover Date
info for PM and Ops Manager before site visit
| Site / Project / Client Specifics |  | Tenant Pack Required? | [6 empty] | Location of site, km from office
|  |  | Client Requirements | [6 empty] | Access, roof height, site info
Generator Integration
Metering
downpayment status
| High-Level Technical Information |  | Panels | [6 empty] | preferred suppliers
|  |  | Inverters | [6 empty] | preferred installers
Roof Type
|  |  | Generator Integration | [6 empty] | cCS / SCS completed?
| Actions | [5 empty] | Due Date | Closed
1.
2.
3.
4.
5.
Project Manager:
|  |  |  | Name | Signature |  | Date
Note on C10: Robert: Project Name + peak power