## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[9 empty] | 2026-02-26 | 2026-02-26
| PROJECT PLAN | Umzimkhulu Mall | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 838
| PROJECT DEVELOPER | Natasha Watkins-Baker
| PROJECT MANAGERS | Lloyd Brown
| CONTRACT VALUE | 8147396
| Phase: | Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Expected Status | Comment
|  |  | 80 |  |  | 148 |  | 99.6% | 99.6%
1 | Project Initiation | 2025-04-22 | 22 | 2025-05-14 | 2025-04-29 | 17 | 2025-05-16 | 100% | 100%
1.1 | BD Handover | 2025-04-22 | 1 | 2025-04-23 | 2025-05-13 | 1 | 2025-05-14 | 100% | 100%
1.2 | Project Introduction | 2025-05-13 | 1 | 2025-05-14 | 2025-05-15 | 1 | 2025-05-16 | 100% | 100%
1.3 | HSE | 2025-04-22 | 10 | 2025-05-07 | 2025-04-29 | 10 | 2025-05-14 | 100% | 100%
1.4 | Installer Kick Off | 2025-05-06 | 1 | 2025-05-07 | 2025-05-14 | 1 | 2025-05-15 | 100% | 100%
1.5 | Project Review | 2025-05-06 | 1 | 2025-05-07 | 2025-05-08 | 1 | 2025-05-09 | 100% | 100%
2 | Site Establishment | 2025-05-20 | 1 | 2025-05-21 | 2025-05-20 | 1 | 2025-05-21 | 100% | 100%
2.1 | Solar Contractor Establishment | 2025-05-20 | 1 | 2025-05-21 | 2025-05-20 | 1 | 2025-05-21 | 100% | 100% |  | 105 | Net Work Days
3 | AC Installation | 2025-04-29 | 72 | 2025-07-10 | 2025-04-29 | 129 | 2025-09-05 | 100% | 100% |  | 21 | Total Weeks
3.1 | Inverters delivered | 2025-05-21 | 1 | 2025-05-22 | 2025-05-29 | 1 | 2025-05-30 | 100% | 100% |  | 39.9048 | kW/Week Installation Rate
3.2 | Inverters Mounted | 2025-05-22 | 5 | 2025-05-29 | 2025-07-29 | 5 | 2025-08-05 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-04-29 | 25 | 2025-06-04 | 2025-04-29 | 40 | 2025-06-26 | 100% | 100%
3.4 | AC Works | 2025-06-04 | 25 | 2025-07-10 | 2025-07-29 | 28 | 2025-09-05 | 100% | 100%
3.5 | AC Tie-In | 2025-06-04 | 3 | 2025-06-09 | 2025-08-24 | 0 | 2025-08-24 | 100% | 100%
4 | DC Works | 2025-05-20 | 66 | 2025-07-25 | 2025-05-20 | 104 | 2025-09-01 | 100% | 100%
4.1 | Lifeline Installation (If Applicable) | [6 empty] | 0% | 0%
4.1 | Mounting Structure delivered | 2025-05-20 | 1 | 2025-05-21 | 2025-05-20 | 1 | 2025-05-21 | 100% | 100%
4.2 | Mounting Structure installation | 2025-05-21 | 13 | 2025-06-09 | 2025-05-21 | 13 | 2025-06-09 | 100% | 100%
4.3 | DC Cable delivered | 2025-05-20 | 1 | 2025-05-21 | 2025-05-29 | 1 | 2025-05-30 | 100% | 100%
4.3 | DC Stringing | 2025-06-29 | 20 | 2025-07-25 | 2025-06-06 | 60 | 2025-09-01 | 100% | 100%
5 | Module installation | 2025-06-02 | 30 | 2025-07-02 | 2025-05-29 | 125 | 2025-10-01 | 100% | 100%
5.1 | Module delivery | 2025-06-02 | 1 | 2025-06-03 | 2025-05-29 | 1 | 2025-05-30 | 100% | 100%
5.2 | Module mounting | 2025-06-03 | 20 | 2025-07-02 | 2025-05-30 | 86 | 2025-10-01 | 100% | 100% | There was a bit of delay as it was a windy day
6 | Commissioning | 2025-07-25 | 14 | 2025-08-08 | 2025-10-09 | 6 | 2025-10-15 | 100% | 100%
6.1 | Commissioning | 2025-07-25 | 5 | 2025-08-01 | 2025-10-09 | 1 | 2025-10-10 | 100% | 100%
6.2 | Practical Completion | 2025-08-01 | 5 | 2025-08-08 | 2025-10-10 | 3 | 2025-10-15 | 100% | 100%
7 | QA Inspections | 2025-08-08 | 3 | 2025-08-11 | 2025-10-13 | 1 | 2025-10-14 | 100% | 100%
7.1 | Red-Team Inspection | 2025-08-08 | 1 | 2025-08-11 | 2025-10-13 | 1 | 2025-10-14 | 100% | 100%
8 | Project Closure | 2025-08-11 | 14 | 2025-08-25 | 2025-10-14 | 146 | 2026-03-09 | 96.77% | 96.77%
8.1 | Equipment serial numbers | 2025-08-11 | 2 | 2025-08-13 | 2025-10-14 | 2 | 2025-10-16 | 100% | 100%
8.2 | Snags completion | 2025-08-11 | 5 | 2025-08-18 | 2025-11-11 | 5 | 2025-11-18 | 100% | 100%
8.3 | System Performance Monitoring | 2025-08-18 | 5 | 2025-08-25 | 2025-11-18 | 3 | 2025-11-21 | 100% | 100%
8.4 | Handover documentation | 2025-08-11 | 5 | 2025-08-18 | 2025-10-31 | 15 | 2025-11-21 | 100% | 100%
8.5 | Handover to Client | 2025-08-18 | 1 | 2025-08-19 | 2026-03-06 | 1 | 2026-03-09 | 0% | 0%
8.6 | Handover to Matriarch | 2025-08-13 | 1 | 2025-08-14 | 2025-11-24 | 5 | 2025-12-01 | 100% | 100%
plus one day for winds delay on 12 September
plus one day for winds delay on 16 September
Formulas:
Planned Start = MIN([Planned Start, row below]:E16)
Planned Start = WORKDAY.INTL([Planned End, row above],0,1,Data!$C3:C14)
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = WORKDAY.INTL([Actual End, row above],0,1,Data!$C3:C14)
Actual End = MAX([Actual End, row below]:K16)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C14)
Expected Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 8147396 |  | 8155733.5 |  |  |  | Start Date | 7908674.9326 | 6052351.3014 | 161772.5134 | 254161.6105 | 161772.5134 | 250689.0505
2 | Planned Expenditure | 7645523.4259 |  | 6306512.9119 | VO PM LIMIT | CURRENT VO Total
3 | Planned Profit | 501872.5741 |  | 1849220.5881 | 25093.6287 | 16439 |  | End Date - PC
4 | Planned Margin | 6.16% |  | 22.67%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE |  | MILESTONE NOTES & COMMENTS
1 | Deposit |  | 20% | 1629479.2 |  | 2025-04-30 | 004740 | 2025-05-01 | 2025-04-30
2 | Delivery of Panels |  | 20% | 1629479.2 |  | 2025-06-09 | 004740 | 2025-05-01 | 2025-06-13
3 | Delivery of Inverters |  | 15% | 1222109.4 |  | 2025-05-28 | 004740 | 2025-05-01 | 2025-06-13
4 | Commissioning Complete |  | 15% | 1222109.4 |  | 2025-08-15 | 004740 | 2025-05-01 | 2025-10-17
5 | Final Completion Issued |  | 25% | 2036849 |  | 2025-08-18 | 004740 | 2025-05-01 | 2025-10-24
6 | Handover |  | 5% | 407369.8 |  | 2026-03-16 | 004740 | 2025-05-01 | 2025-10-24
7 | VO - Relocation of Crane |  | 0% | 8337.5 |  | 2025-08-07 | 004807 | 2025-08-07 | 2025-08-08
|  |  | 100% | 8155733.5
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 2854506.725
2 | Delivery of Panels |  | 30% | 2446720.05
3 | Delivery of Inverters |  | 20% | 1631146.7
4 | Practical Completion |  | 10% | 815573.35
5 | Handover |  | 5% | 407786.675
| Total |  | 100% | 8155733.5
|  |  | 100% | 8155733.5

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 7645523.4259 |  | 6306512.9119 | 1339010.514
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 1820133.76 |  | 1672199 | 147934.76
2 | 2. Inverters | 490000 |  | 482092.45 | 7907.55
3 | 3. Mounting Structures | 376992 |  | 171482 | 205510
4 | 4. DC Equipment | 671877.8 |  | 708174.85 | -36297.05
5 | 5. Monitoring | 49000 |  | 99501.22 | -50501.22
6 | 6. AC Equipment | 1125717.3174 |  | 429563.8399 | 696153.4775
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 200000 |  | 139900.5 | 60099.5
9 | 9. AC & DC installation | 677600 |  | 1079213.0072 | -401613.0072
10 | 10. Site Logistics | 169956.4 |  | 129095.2548 | 40861.1452
11 | 11. Due Dilligence | 142832 |  | 42015.83 | 100816.17
12 | 12. BDP Commission | 125468.2282 |  | 0 | 125468.2282
13 | 13. Engineering | 281420.9203 |  | 101946.67 | 179474.2503
14 | 14. General Expenses | 14525 |  | 25855.73 | -11330.73
15 | 15. Service Add On | 1500000 |  | 1225472.56 | 274527.44
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 7645523.4259 | 8147396.3389 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 6306512.9119
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 1820133.76 | 2025-06-26 | 1820133.76 | 1978406.2609 |  | 1 | 1. Panels | Jinko 620W - MENLO | 1352 | 1233.8 | 1668097.6 | PO3912-DIP-PH2-UMZI=20250514 | Menlo INV0002863 | 2025-04-30 | 1978406.2609 | 0 | 2025-06-26 | 1672199
1 |  | Delivery Budget | [7 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [5 empty] | 2025-11-22 |  |  |  | 1 | 1. Panels |  |  |  | 4101.4 |  | Menlo - INV0003277 | 2025-09-30 | 0 |  | 2025-11-19
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 1125717.3174
2 | Inverters | Inverter Budget |  |  | 490000 | 2025-11-22 | 490000 | 532608.6957 |  | 2 | 2. Inverters | Huawei 100KTL - MENLO | 7 | 68870.35 | 482092.45 | PO3895-DIP-PH2-UMZI=20250514 | Menlo - INV0002962 | 2025-05-31 | 532608.6957 | 0 | 2025-07-28 | 482092.45 | DC Equipment | 399297.8
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | AC Labour | 209440
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 468160
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 46501.4
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 15355
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 376992 | 2025-06-27 | 376992 | 409773.913 |  | 3 | 3. Mounting Structures | Schletter Structure |  |  | 160486.6 | PO3920-DIP2UMZ-20250515 - RV Approved | SCHLETTER - INV1764 | 2025-05-31 | 369382.8422 | -0.0034676 | 2025-06-27 | 171482 | Other | 0
3 | [5 empty] | 0 |  |  |  | 3 | 3. Mounting Structures | Kliplok brackets (Kliplok551 - PE store) | 400 | 24.88 | 9952 |  | Allocated from PE Stockroom | 2025-05-31 | 22905.9501 |  | 2025-05-31 |  | Total | 2272971.5174
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Less 15% | 1932025.7898
3 | [5 empty] | 2025-06-27 |  |  |  | 3 | 3. Mounting Structures | Delivery |  |  | 1043.4 |  | DSV Inv: 180133248 | 2025-05-31 | 2401.5342 |  | 2025-06-27 |  | R/Wp | 2.3055
3 | [9 empty] | 3 | 3. Mounting Structures | [6 empty] | 2025-07-31 | 15083.59
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL - Thula Moya | Installer Price
[23 empty] | AC Equipment | 206394.5438
4 | DC Equipment | DC Cable Budget | 22390.5 |  | 272580 | 2025-07-29 | 671877.8 | 730301.9565 |  | 4 | 4. DC Equipment | DC Cable - MENLO | 22000 | 13.4 | 294800 | PO3895-DIP-PH2-UMZI=20250514 | Menlo - INV0002962 | 2025-05-31 | 304011.1041 | -0.002483 | 2025-07-29 | 708174.85 | DC Equipment | 413374.8457
4 |  | DC Equipment Budget |  |  | 399297.8 | 2025-07-29 |  |  |  | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | AC Labour | 333574.9281
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | DC Labour | 745638.0745
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Offloading | 20306.9153
4 | [5 empty] | 2025-05-15 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 413374.8457 | 10% | 41337.4846 | PO3886-DIP2UMZ-20250513 - RV Approved | Thula Moya Inv: IN04718 | 2025-05-31 | 42629.0852 |  | 2025-05-15 |  | Scaffolding | 74062.7443
4 | [5 empty] | 2025-05-29 |  |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 62006.2269 |  | Thula Moya Inv: IN04718 | 2025-05-31 | 63943.6279 |  | 2025-05-29 |  | Storage | 12227.9484
4 | [5 empty] | 2025-08-30 |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 82674.9691 |  | Thula Moya Inv: IN04798 | 2025-07-31 | 85258.17 |  | 2025-08-30 |  | Telehandler | 0
4 | [5 empty] | 2025-07-11 |  |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 12.5% | 51671.86 |  | Thula Moya IN04776 | 2025-07-31 | 53286.3606 |  | 2025-07-11 |  | HSE | 4500
[6 empty] | 2025-10-07 |  |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 12.5% | 51671.8557 |  | Thula Moya IN04835 | 2025-08-31 | 53286.3562 |  | 2025-10-02
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 41337.4846 |  | Thula Moya IN04836 | 2025-08-31 | 42629.085 |  | 2025-10-16 |  | Other | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 41337.4846 |  | Thula Moya IN04837 | 2025-08-31 | 42629.085 |  | 2025-12-12 |  | Other | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 20668.7423 |  | Thula Moya IN04838 | 2025-08-31 | 21314.5425 |  | 2026-03-05 |  | Total | 1810080
4 | [5 empty] | 2025-11-30 |  |  |  | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 20668.7423 |  | Thula Moya IN04839 | 2025-08-31 | 21314.5425 |  | 2026-04-04 |  | R/Wp | 2.16
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 34000 | 2025-07-17 | 49000 | 53260.8696 |  | 5 | 5. Monitoring | Smartlogger - MENLO |  |  | 8598.35 |  | Menlo - INV0002929 | 2025-05-31 | 4835.1492 | 0.0018587 | 2025-07-17 | 99501.22
5 |  | Revenue Metering |  |  | 15000 | 2025-05-29 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 14805 | PO3829-DIP-Ph2-Umzi-20250429 - RV Approved | Accuenergy - INV ASAI-005355 | 2025-04-30 | 19230.025 |  | 2025-05-29
[6 empty] | 2025-07-29 |  |  |  | 5 | 5. Monitoring | Din Rail Kit |  |  | 214.28 |  | Accuenergy - Inv ASAI-005800 | 2025-06-30 | 115.441 |  | 2025-07-29
5 | [5 empty] | 2025-06-30 |  |  |  | 5 | 5. Monitoring | Techsitter |  |  | 14934 |  | Matriarch Inv: 4451 | 2025-06-30 | 7108.4459 |  | 2025-06-30
[6 empty] | 2025-09-30 |  |  |  | 5 | 5. Monitoring | Delivery of Techsitter Meter |  |  | 334.29 |  | DSV Inv: 180143171 | 2025-08-31 | 0 |  | 2025-09-30
5 | [5 empty] | 2025-05-22 |  |  |  | 5 | 5. Monitoring | UPS |  |  | 2250.5 | PO3863-DIP Ph2-20250509 - RV Approved | Frontline Inv725690 | 2025-05-31 | 1265.5339 |  | 2025-05-22
5 | [5 empty] | 2025-06-27 |  |  |  | 5 | 5. Monitoring | CTs |  |  | 14060 | PO3957-DIP-Ph2-Umzi-20250527 - RV Approved | Accuenergy - Inv ASAI-005580 | 2025-05-31 | 7906.4237 |  | 2025-06-27
[10 empty] | 5 | 5. Monitoring | Courier of Simcard |  |  | 304.8 |  | DSV Inv: 180150385 | 2025-10-31 | 0 |  | 2025-11-30
5 | [5 empty] | 2025-07-29 |  |  |  | 5 | 5. Monitoring | Apex Device |  |  | 40000 | PO3967-DIP-PH2-Umzi-20250529 - RV Approved | Rubicon INVWCRE-0068505 | 2025-06-30 | 10644.8937 |  | 2025-07-29
5 | [5 empty] | 2025-07-29 |  |  |  | 5 | 5. Monitoring | Apex Edge Device |  |  | 4000 | PO3987-DIP-Ph2-Umzi-20250609 - RV Approved | rubicon Inv: INVWCRE-0068578 | 2025-06-30 | 2154.9554 |  | 2025-07-29
6 | AC Equipment | AC Equipment Budget |  |  | 1125717.3174 | 2025-07-29 | 1125717.3174 | 1223605.7798 |  | 6 | 6. AC Equipment | [7 empty] | 0 | 0.0048541 |  | 429563.8399
6 | [5 empty] | 2025-07-29 |  |  |  | 6 | 6. AC Equipment | PVDB |  |  | 223169.3 |  | SwitchBoard - Inv 2-SOI002090 | 2025-06-30 | 633760.1819 |  | 2025-07-29
6 | [9 empty] | 7 | 6. AC Equipment | Supply and Install SPDs |  |  | 4825.5 | PO4438-UMZ-20251104 - RV Approved | Thula Moya Inv - IN04962 | 2025-12-31 |  |  | 2025-12-12
6 | [9 empty] | 8 | 6. AC Equipment | Supply and Install SPDs - Recover cost from SWB |  |  | -4825.5 |  | Switchboard - 2-ARI001536 | 2026-02-28 |  |  | 2026-02-28
6 | [9 empty] | 9 | 6. AC Equipment | [7 empty] | 0
6 | [5 empty] | 2025-05-15 |  |  |  | 6 | 6. AC Equipment | Project Kick Off | 206394.5438 | 10% | 20639.45 | PO3886-DIP2UMZ-20250513 - RV Approved | Thula Moya Inv: IN04718 | 2025-05-31 | 59564.7585 |  | 2025-05-15
6 | [5 empty] | 2025-05-29 |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 30959.18 |  | Thula Moya Inv: IN04718 | 2025-05-31 | 89347.1522 |  | 2025-05-29
6 | [5 empty] | 2025-08-30 |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 41278.9088 |  | Thula Moya Inv: IN04798 | 2025-07-31 | 117582.3164 |  | 2025-08-30
6 | [5 empty] | 2025-07-11 |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 12.5% | 25799.32 |  | Thula Moya IN04776 | 2025-07-31 | 73488.9435 |  | 2025-07-11
[6 empty] | 2025-10-07 |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 12.5% | 25799.318 |  | Thula Moya IN04835 | 2025-08-31 | 73488.9478 |  | 2025-10-02
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 20639.4544 |  | Thula Moya IN04836 | 2025-08-31 | 58791.1582 |  | 2025-10-16
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 20639.4544 |  | Thula Moya IN04837 | 2025-08-31 | 58791.1582 |  | 2025-12-12
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 10319.7272 |  | Thula Moya IN04838 | 2025-08-31 | 29395.5791 |  | 2026-03-05
6 | [5 empty] | 2025-11-30 |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 10319.7272 |  | Thula Moya IN04839 | 2025-08-31 | 29395.5791 |  | 2026-04-04
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On |  |  |  |  | 2025-09-30 | 200000 | 217391.3043 |  | 8 | 8. Product Add On | Waterpoints |  |  | 4430 | PO4320-UMZ-20250918 - RV Approved | Justin & Joann Construction | 2025-10-31 | 0 | -8337.5 | 2025-10-16 | 139900.5
8 | [9 empty] | 8 | 8. Product Add On | SPD
8 |  | MV Metering Budget |  |  | 200000 | 2025-07-31 |  |  |  | 8 | 8. Product Add On | Manufacture & Installation of Cage |  |  | 91969 | PO3963-UMZ-20250527 - RV Approved | The Engineering Hub Inv: INV/2025/06/0571 | 2025-06-30 | 217391.3043 |  | 2025-07-31
8 | [5 empty] | 2025-08-07 |  |  |  | 8 | 8. Product Add On | Relocation of Containers |  |  | 16675 | PO4161-UMZ-20250725 - RV Approved | Thula Moya: IN04809 | 2025-08-31 | 8337.5 |  | 2025-08-07
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [5 empty] | 2025-09-25 |  |  |  | 8 | 8. Product Add On | Crane Truck |  |  | 8337.5 |  | Luxinio Trading - Inv 87151 | 2025-07-31 | 0 |  | 2025-09-25
8 | [9 empty] | 8 | 8. Product Add On | Estop |  |  | 2050 | PO4388-UMZ-20251021 - RV Approved | Thula Moya - IN04932 | 2025-10-31 | 0 |  | 2025-10-31
8 | [9 empty] | 8 | 8. Product Add On | Install Extra Palisade Fencing - VO |  |  | 16439 | PO4408-UMZ-20251027 - RV Approved | The Engineering Hub Inv: INV/2025/10/0526 | 2025-10-31 | 0 |  | 2025-11-28
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 209440 | 2025-05-15 | 677600 | 797176.4706 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | -0.00086441 |  | 1079213.0072
9 |  | DC Installation Budget |  |  | 468160 | 2025-05-15 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 1079213.0026 | 10% | 107921.3003 | PO3886-DIP2UMZ-20250513 - RV Approved | Thula Moya Inv: IN04718 | 2025-05-31 | 79717.6471 |  | 2025-05-15
9 | [5 empty] | 2025-05-29 |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 161881.9504 |  | Thula Moya Inv: IN04718 | 2025-05-31 | 119576.4706 |  | 2025-05-29
9 | [5 empty] | 2025-08-30 |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 215842.6005 |  | Thula Moya Inv: IN04798 | 2025-07-31 | 159435.2934 |  | 2025-08-30
9 | [5 empty] | 2025-07-11 |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 12.5% | 134901.63 |  | Thula Moya IN04776 | 2025-07-31 | 99647.0618 |  | 2025-07-11
[6 empty] | 2025-10-07 |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 12.5% | 134901.6253 |  | Thula Moya IN04835 | 2025-08-31 | 99647.0584 |  | 2025-10-02
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 107921.3003 |  | Thula Moya IN04836 | 2025-08-31 | 79717.6467 |  | 2025-10-16
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 107921.3003 |  | Thula Moya IN04939 | 2025-10-31 | 79717.6467 |  | 2025-12-12
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 53960.6501 |  | Thula Moya IN04940 | 2025-10-31 | 39858.8234 |  | 2026-03-05
9 | [5 empty] | 2025-11-30 |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 53960.6501 |  | Thula Moya IN04945 | 2025-10-31 | 39858.8234 |  | 2026-04-04
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-09-01 | 169956.4 | 199948.7059 |  | 10 | 10. Site Logistics | [7 empty] | 0 | -0.0049512 |  | 129095.2548
[6 empty] | 2025-09-01 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
[6 empty] | 2025-09-01 |  |  |  | 10 | 10. Site Logistics | Security - June |  |  | 17637.6 | PO3966-UMZ-20250528 - RV Approved | Bidvest ProteaCoin - 743752 | 2025-08-31 | 45792.9713 |  | 2025-09-01
[6 empty] | 2025-09-01 |  |  |  | 10 | 10. Site Logistics | Security - July |  |  | 0 |  |  |  | 0
[6 empty] | 2025-09-01 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Scaffolding |  |  | 46501.4 | 2025-09-01 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Security |  |  | 99600 | 2025-09-01 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 15355 | 2025-09-01 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [5 empty] | 2025-05-15 |  |  |  | 10 | 10. Site Logistics | Project Kick Off | 111097.6079 | 10% | 11109.7608 | PO3886-DIP2UMZ-20250513 - RV Approved | Thula Moya Inv: IN04718 | 2025-05-31 | 13994.2625 |  | 2025-05-15
10 | [5 empty] | 2025-05-29 |  |  |  | 10 | 10. Site Logistics | Site Establishment |  | 15% | 16664.65 |  | Thula Moya Inv: IN04718 | 2025-05-31 | 20991.4049 |  | 2025-05-29
10 | [5 empty] | 2025-08-30 |  |  |  | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 22219.5216 |  | Thula Moya Inv: IN04798 | 2025-07-31 | 27988.5252 |  | 2025-08-30
10 | [5 empty] | 2025-07-11 |  |  |  | 10 | 10. Site Logistics | DC Installation Complete |  | 12.5% | 13887.2 |  | Thula Moya IN04776 | 2025-07-31 | 17492.827 |  | 2025-07-11
[6 empty] | 2025-10-07 |  |  |  | 10 | 10. Site Logistics | DC Installation Complete |  | 12.5% | 14247.2 |  | Thula Moya IN04835 | 2025-08-31 | 22066.7228 |  | 2025-10-02
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 11109.7608 |  | Thula Moya IN04836 | 2025-08-31 | 17207.3117 |  | 2025-10-16
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 11109.7608 |  | Thula Moya IN04837 | 2025-08-31 | 17207.3117 |  | 2025-12-12
[6 empty] | #REF! |  |  |  | 10 | 10. Site Logistics |  |  |  | 0.04 |  | Thula Moya IN04837 | 2025-08-31 | 0.061954 |  | 2025-12-12
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 5554.8804 |  | Thula Moya IN04838 | 2025-08-31 | 8603.6559 |  | 2026-02-26
10 | [5 empty] | 2025-11-30 |  |  |  | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 5554.8804 |  | Thula Moya IN04839 | 2025-08-31 | 8603.6559 |  | 2026-02-26
10 | [5 empty] | 0 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [5 empty] | 0 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [5 empty] | 0 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 20944 | 2025-09-01 | 142832 | 168037.6471 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 23015.83 |  | Sunspot E027 | 2025-07-31 | 89767.3966 | 0.00053319 | 2026-01-29 | 42015.83
11 |  | Structural Sign Off |  |  | 41888 | 2025-09-01 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 11000 | PO3745-DIP-Ph2-20250313 - RV Approved | L&B Consulting - Invoice 1934 | 2025-04-30 | 46275.1381 |  | 2025-04-10
11 |  | Grid Study |  |  | 80000 | 2025-09-01 |  |  |  | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 8000 |  | Matriarch - INV-4987 | 2025-08-31 | 31995.1118 |  | 2025-08-31
11 | [5 empty] | 2025-09-01 |  |  |  | 11 | 11. Due Dilligence | [7 empty] | 0
11 | [5 empty] | 2025-09-01 |  |  |  | 11 | 11. Due Dilligence | [7 empty] | 0
2025-09-01
12 | BDP Commission | Referral Fee |  |  | 94101.1712 | 2025-09-01 | 125468.2282 | 0 |  | 12 | 12. BDP Commission | Referral Fee | [9 empty] | 0
12 | BDP Commission | PD Fee |  |  | 31367.0571 | 2025-09-01 |  |  |  | 12 | 12. BDP Commission | PD Fee
2025-05-15
13 | Engineering | Matriarch Defects Period |  |  | 69051.366 | 2025-05-29 | 281420.9203 | 319796.5003 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 101946.67 |  | Matriarch - INV-4986 | 2025-08-31 | 319796.5003 | 0 | 2025-08-31 | 101946.67
13 |  | Management |  |  | 47428.5714 | 2025-08-30 |  |  |  | 13 | 13. Engineering | Management |  |  | 0 |  |  |  | 0
13 |  | Project manager |  |  | 68000 | 2025-07-11 |  |  |  | 13 | 13. Engineering | Project manager |  |  | 0 |  |  |  | 0
13 |  | Planner time |  |  | 61657.1429 | 2025-10-07 |  |  |  | 13 | 13. Engineering | Planner time |  |  | 0 |  |  |  | 0
13 |  | De Snagging |  |  | 35283.84 | #REF! |  |  |  | 13 | 13. Engineering | De Snagging |  |  | 0 |  |  |  | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 14525 | 2025-04-30 | 14525 | 17088.2353 |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  | 2025-04-30 | 0 | -0.00077521 | 2025-04-30 | 25855.73
14 | [5 empty] | 2025-06-09 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 7491.4 |  | Expense Claim | 2025-05-31 | 10803.9401 |  | 2025-06-09
14 | [5 empty] | 2025-07-04 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 10843.08 |  | Expense Claim | 2025-06-30 | 3947.076 |  | 2025-07-04
14 | [5 empty] | 2025-07-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-07-31 | 0 |  | 2025-07-30
14 | [5 empty] | 2025-08-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-08-31 | 0 |  | 2025-08-30
14 | [5 empty] | 2025-09-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-09-30 | 0 |  | 2025-09-30
14 | [5 empty] | 2025-10-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-10-31 | 2337.22 |  | 2025-10-30
14 | [5 empty] | 2025-11-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 5134.76 |  | Expense Claim | 2025-11-30 | 0 |  | 2025-12-05
14 | [5 empty] | 2025-12-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 2386.49 |  | Expense Claim | 2025-12-31 | 0 |  | 2026-01-08
14 | [5 empty] | 2026-01-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2026-01-31 | 0 |  | 2026-01-30
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | Welcome Bonus - Site Establishment |  |  | 1500000 | 2025-07-11 | 1500000 | 1500000 |  | 15 | 15. Service Add On | Welcome Bonus - Site Establishment |  |  | 611000 |  | Luxanio Trading - 23405/202506/274902/I | 2025-06-30 | 714898.5959 | 0 | 2025-07-11 | 1225472.56
15 | [5 empty] | 2025-10-23 |  |  |  | 15 | 15. Service Add On | Welcome Bonus - Commissioning |  |  | 611000 |  | Luxanio Trading - 23405/202506/274902/I | 2025-06-30 | 714898.5959 |  | 2025-10-30
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [5 empty] | 2025-08-31 |  |  |  | 15 | 15. Service Add On | Community Engagement |  |  | 0 |  |  | 2025-08-31 | 70202.8081 |  | 2025-08-31
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | Call Out Metering |  |  | 3472.56 |  |  | 2026-02-28 |  |  | 2026-03-05
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
| Panel Procurement Budget | 1820133.76 |  | 1978406.2609
| Inverter Procurement Budget | 490000 |  | 532608.6957
| Mounting Structure Budget | 376992 |  | 409773.913
| DC Equipment Budget | 671877.8 |  | 730301.9565
| AC Equipment Budget | 1125717.3174 |  | 1223605.7798
| Monitoring Budget | 49000 |  | 53260.8696
| Optional Extras Budget | 0 |  | 0
| MV Metering Budget | 200000 |  | 217391.3043
| ADD ON | 0 |  | 0
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 209440 |  | 246400
| DC Installer Budget | 468160 |  | 550776.4706
| In-House Expense Budget | 281420.9203 |  | 319796.5003
| Compliance Budget | 142832 |  | 168037.6471
| Offloading Budget | 8500 |  | 10000
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 15355 |  | 18064.7059
| On Site Security | 99600 |  | 117176.4706
| Roof Access Budget for Installers | 46501.4 |  | 54707.5294
| EPC Management Fee | 0 |  | 0
| ADD ON | 1500000 |  | 1500000
Expenses
| Total EE Expense Budget | 14525 |  | 17088.2353
Note on H36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date
Note on W36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date
Note on Q57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Mizelda Isaacs I changed the amount - from 217590.23
Note on W83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please add the payment date
Note on H88: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date
Note on W88: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date
Note on W128: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 8147396 | 8155733.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629479.2 | 0 | 0 | 0 | 1222109.4 | 0 | 1629479.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8337.5 | 1222109.4 | 2036849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407369.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629479.2 | 1629479.2 | 1629479.2 | 1629479.2 | 2851588.6 | 2851588.6 | 4481067.8 | 4481067.8 | 4481067.8 | 4481067.8 | 4481067.8 | 4481067.8 | 4481067.8 | 4481067.8 | 4489405.3 | 5711514.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 7748363.7 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5
| Planned Expenditure | 7645523.4259 | 7610239.5859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14525 | 0 | 677600 | 0 | 84051.366 | 0 | 0 | 0 | 2197125.76 | 0 | 1568000 | 34000 | 0 | 1997595.1174 | 0 | 0 | 0 | 47428.5714 | 438256.6282 | 0 | 0 | 0 | 0 | 61657.1429 | 0 | 0 | 0 | 0 | 0 | 490000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14525 | 14525 | 692125 | 692125 | 776176.366 | 776176.366 | 776176.366 | 776176.366 | 2973302.126 | 2973302.126 | 4541302.126 | 4575302.126 | 4575302.126 | 6572897.2434 | 6572897.2434 | 6572897.2434 | 6572897.2434 | 6620325.8148 | 7058582.443 | 7058582.443 | 7058582.443 | 7058582.443 | 7058582.443 | 7120239.5859 | 7120239.5859 | 7120239.5859 | 7120239.5859 | 7120239.5859 | 7120239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859 | 7610239.5859
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1614954.2 | 1614954.2 | 937354.2 | 937354.2 | 2075412.234 | 2075412.234 | 3704891.434 | 3704891.434 | 1507765.674 | 1507765.674 | -60234.326 | -94234.326 | -94234.326 | -2091829.4434 | -2083491.9434 | -861382.5434 | 1175466.4566 | 1128037.8852 | 689781.257 | 689781.257 | 689781.257 | 689781.257 | 689781.257 | 628124.1141 | 628124.1141 | 628124.1141 | 628124.1141 | 628124.1141 | 628124.1141 | 138124.1141 | 138124.1141 | 138124.1141 | 138124.1141 | 138124.1141 | 138124.1141 | 138124.1141 | 138124.1141 | 138124.1141 | 138124.1141 | 138124.1141 | 138124.1141 | 138124.1141 | 138124.1141 | 138124.1141 | 138124.1141 | 138124.1141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141 | 545493.9141
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 8155733.5 | 8155733.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629479.2 | 0 | 0 | 0 | 0 | 0 | 2851588.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8337.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1222109.4 | 2444218.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629479.2 | 1629479.2 | 1629479.2 | 1629479.2 | 1629479.2 | 1629479.2 | 4481067.8 | 4481067.8 | 4481067.8 | 4481067.8 | 4481067.8 | 4481067.8 | 4481067.8 | 4481067.8 | 4489405.3 | 4489405.3 | 4489405.3 | 4489405.3 | 4489405.3 | 4489405.3 | 4489405.3 | 4489405.3 | 4489405.3 | 4489405.3 | 5711514.7 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5 | 8155733.5
| Actual + Planned Expenditure | 6306512.9119 | 6306512.9119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 | 0 | 0 | 0 | 0 | 181007.9956 | 2250.5 | 296269.0072 | 0 | 7491.4 | 0 | 1843687.6 | 25777.08 | 837260.01 | 8598.35 | 0 | 1136245.03 | 16675 | 0 | 0 | 471962.67 | 17637.6 | 0 | 0 | 8337.5 | 226954.289 | 0 | 185438 | 0 | 613050 | 0 | 0 | 4101.4 | 16743.8 | 5134.76 | 185833.54 | 0 | 0 | 0 | 2386.49 | 0 | 0 | 23015.83 | 0 | 0 | 0 | 6284.2608 | 88421.6796 | 0 | 0 | 0 | 84949.1196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 | 11000 | 11000 | 11000 | 11000 | 192007.9956 | 194258.4956 | 490527.5029 | 490527.5029 | 498018.9029 | 498018.9029 | 2341706.5029 | 2367483.5829 | 3204743.5929 | 3213341.9429 | 3213341.9429 | 4349586.9729 | 4366261.9729 | 4366261.9729 | 4366261.9729 | 4838224.6429 | 4855862.2429 | 4855862.2429 | 4855862.2429 | 4864199.7429 | 5091154.0319 | 5091154.0319 | 5276592.0319 | 5276592.0319 | 5889642.0319 | 5889642.0319 | 5889642.0319 | 5893743.4319 | 5910487.2319 | 5915621.9919 | 6101455.5319 | 6101455.5319 | 6101455.5319 | 6101455.5319 | 6103842.0219 | 6103842.0219 | 6103842.0219 | 6126857.8519 | 6126857.8519 | 6126857.8519 | 6126857.8519 | 6133142.1127 | 6221563.7923 | 6221563.7923 | 6221563.7923 | 6221563.7923 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119 | 6306512.9119
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11000 | -11000 | -11000 | 1618479.2 | 1618479.2 | 1437471.2044 | 1435220.7044 | 1138951.6971 | 1138951.6971 | 3983048.8971 | 3983048.8971 | 2139361.2971 | 2113584.2171 | 1276324.2071 | 1267725.8571 | 1267725.8571 | 131480.8271 | 123143.3271 | 123143.3271 | 123143.3271 | -348819.3429 | -366456.9429 | -366456.9429 | -366456.9429 | -374794.4429 | -601748.7319 | -601748.7319 | 434922.6681 | 2879141.4681 | 2266091.4681 | 2266091.4681 | 2266091.4681 | 2261990.0681 | 2245246.2681 | 2240111.5081 | 2054277.9681 | 2054277.9681 | 2054277.9681 | 2054277.9681 | 2051891.4781 | 2051891.4781 | 2051891.4781 | 2028875.6481 | 2028875.6481 | 2028875.6481 | 2028875.6481 | 2022591.3873 | 1934169.7077 | 1934169.7077 | 1934169.7077 | 1934169.7077 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881 | 1849220.5881
|  | CHECK | CHECK
| Revenue Recognition | -8337.8442 | 8155733.8442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2043911.424 | 0 | 0 | 0 | 1745885.582 | 0 | 0 | 0 | 0 | 2304919.49 | 0 | 0 | 0 | 739030.4847 | 0 | 0 | 0 | 1160214.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161772.5134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 8155733.8442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2043911.424 | 2043911.424 | 2043911.424 | 2043911.424 | 3789797.006 | 3789797.006 | 3789797.006 | 3789797.006 | 3789797.006 | 6094716.496 | 6094716.496 | 6094716.496 | 6094716.496 | 6833746.9807 | 6833746.9807 | 6833746.9807 | 6833746.9807 | 7993961.3308 | 7993961.3308 | 7993961.3308 | 7993961.3308 | 7993961.3308 | 7993961.3308 | 7993961.3308 | 7993961.3308 | 7993961.3308 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442 | 8155733.8442

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | Grand Total
(blank)
1. Panels |  | 1978406.2609 |  |  |  |  | 0 |  |  |  | 0 |  |  | 1978406.2609
2. Inverters |  |  | 532608.6957 | [7 empty] | 0 |  |  | 532608.6957
3. Mounting Structures | 0 |  | 394690.3265 |  | 15083.59 | [5 empty] | 0 |  |  | 409773.9165
4. DC Equipment |  |  | 410583.8172 |  | 138544.5306 | 181173.6112 |  |  |  |  | 0 |  |  | 730301.959
5. Monitoring |  | 19230.025 | 14007.1068 | 20023.736 |  | 0 |  | 0 | [5 empty] | 53260.8677
6. AC Equipment |  |  | 148911.9107 | 633760.1819 | 191071.2599 | 249862.4224 |  |  |  |  | 0 |  |  | 1223605.7749
8. Product Add On |  |  |  | 217391.3043 | 0 | 8337.5 |  | 0 |  |  | 0 |  |  | 225728.8043
9. AC & DC installation |  |  | 199294.1176 |  | 259082.3553 | 179364.7051 |  | 159435.2934 |  |  | 0 |  |  | 797176.4715
10. Site Logistics | 0 |  | 34985.6674 |  | 45481.3522 | 119481.6912 |  |  |  |  | 0 |  |  | 199948.7108
11. Due Dilligence |  | 46275.1381 |  |  | 89767.3966 | 31995.1118 |  |  |  |  | 0 |  |  | 168037.6465
13. Engineering | 0 |  |  |  |  | 319796.5003 |  |  |  |  | 0 |  |  | 319796.5003
14. General Expenses |  | 0 | 10803.9401 | 3947.076 | 0 | 0 | 0 | 2337.22 | 0 | 0 | 0 | 0 |  | 17088.2361
15. Service Add On |  |  |  | 1429797.1919 |  | 70202.8081 |  |  |  |  | 0 |  |  | 1500000
12. BDP Commission
7.BESS
Grand Total | 0 | 2043911.424 | 1745885.582 | 2304919.49 | 739030.4847 | 1160214.35 | 0 | 161772.5134 | 0 | 0 | 0 | 0 |  | 8155733.8442

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | Grand Total
(blank)
1. Panels |  | 1668097.6 |  |  |  |  | 4101.4 | [5 empty] | 1672199
2. Inverters |  |  | 482092.45 | [9 empty] | 482092.45
3. Mounting Structures |  |  | 171482 | [9 empty] | 171482
4. DC Equipment |  |  | 398143.7114 |  | 134346.8291 | 175684.3094 | [6 empty] | 708174.85
5. Monitoring |  | 14805 | 24908.85 | 59148.28 |  | 334.29 |  | 304.8 |  |  |  |  | 99501.22
6. AC Equipment |  |  | 51598.63 | 223169.3 | 67078.2288 | 87717.6811 |  |  |  | 4825.5 |  | -4825.5 | 429563.8399
8. Product Add On |  |  |  | 91969 | 8337.5 | 16675 |  | 22919 |  |  |  |  | 139900.5
9. AC & DC installation |  |  | 269803.2506 |  | 350744.2305 | 242822.9256 |  | 215842.6005 |  |  |  |  | 1079213.0072
10. Site Logistics | 0 |  | 27774.4108 |  | 36106.7216 | 65214.1224 | [6 empty] | 129095.2548
11. Due Dilligence |  | 11000 |  |  | 23015.83 | 8000 | [6 empty] | 42015.83
13. Engineering | 0 |  |  |  |  | 101946.67 | [6 empty] | 101946.67
14. General Expenses |  | 0 | 7491.4 | 10843.08 | 0 | 0 | 0 | 0 | 5134.76 | 2386.49 | 0 |  | 25855.73
15. Service Add On |  |  |  | 1222000 |  | 0 | [6 empty] | 1222000
12. BDP Commission
7.BESS
Grand Total | 0 | 1693902.6 | 1433294.7029 | 1607129.66 | 619629.34 | 698394.9985 | 4101.4 | 239066.4005 | 5134.76 | 7211.99 | 0 | -4825.5 | 6303040.3519

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate | [5 empty] | FINANCIAL CLOSE CERTIFICATE
Project Name: | Umzimkhulu Mall
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion: |  |  |  | 1. Financial Close | 1. Financial Close
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 0.33161 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.16964 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.11477 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 0.27465 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
Umzimkhulu Mall |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Umzimkhulu Mall | 0 | 0 | 0