## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | PLANNED |  | ACTUAL | FR - Date | 2023 Rev & COS RECOGNISED | PLANNED | ACTUAL
1 | Planned Revenue | 20939008.7697 |  | 20939008.7697 | 20939008.7697 | 12809925.7154 | 8129083.0543 | 8129083.0543
2 | Planned Expenditure | 18682949.9513 |  | 19234297.2704 | 18820454.021 | 11843152.7427 | 6186351.0683 | 7391144.5278
3 | Planned Profit | 2256058.8184 |  | 1704711.4993 | 2118554.7487 | 966772.9727 | 1942731.986 | 737938.5266
4 | Planned Margin | 10.77% |  | 8.141% | 10.12%
CONTRACT |  | 11.9656
[Finance only]
No. | PAYMENT MILESTONE |  | % | VALUE | PLANNED PAYMENT DATE | ACTUAL PAYMENT DATE |  | INVOICE RAISED DATE | MILESTONE NOTES
1 | Initial deposit |  | 30% | 465855.8022 | 2023-02-14 | 2024-04-04 |  | 004359 | Add notes relating to the payment / assessment of milestone, draw from EPC contract or CP
|  |  |  | 1739130.4348 | 2023-02-14 | 2024-04-05 |  | 004359
|  |  |  | 1739130.4348 | 2023-02-14 | 2024-04-10 |  | 004359
|  |  |  | 1739130.4348 | 2023-02-14 | 2024-04-15 |  | 004359
|  |  |  | 598455.5244 | 2023-02-14 | 2024-04-16 |  | 004359
2 | Delivery of Main Equipment(Inverters & BOS) |  | 20% | 1140674.9104 | 2023-02-13 | 2024-04-16 |  | 004359
|  |  |  | 1739130.4348 | 2023-02-13 | 2024-04-17 |  | 004359
|  |  |  | 1307996.4088 | 2023-02-13 | 2024-04-19 |  | 004359
3 | Delivery of Main Equipment(Solar Panels) |  | 25% | 431134.026 | 2023-08-10 | 2024-04-19 |  | 004359
|  |  |  | 1739130.4348 | 2023-08-10 | 2024-04-25 |  | 004359
|  |  |  | 1739130.4348 | 2023-08-10 | 2024-04-26 |  | 004359
|  |  |  | 869565.2174 | 2023-08-10 | 2024-04-29 |  | 004359
|  |  |  | 455792.0795 | 2023-08-10 | 2024-04-30 |  | 004359
4 | Installation Complete(Physical Completion) |  | 10% | 2093900.877 | 2023-10-06 | 2024-06-30 |  | 004409
5 | Commissioing Complete(Testing and Checks Complete) |  | 10% | 2093900.877 | 2024-01-27 | 2024-06-30 |  | 004409
6 | Handover complete |  | 5% | 1046950.4385 | 2024-03-04 | 2024-06-30 |  | 004409
6 |  |  | 0% | 0
7 | - |  | 0% | 0
|  |  | 100% | 20939008.7697
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 7328653.0694
2 | Delivery of Panels |  | 30% | 6281702.6309
3 | Delivery of Inverters |  | 20% | 4187801.7539
4 | Practical Completion |  | 10% | 2093900.877
5 | Handover |  | 5% | 1046950.4385
| Total |  | 100% | 20939008.7697
|  |  | 100% | 20939008.7697
Formulas:
FR - Date = +[FR - Date, row above]+7+30

## Project Plan
| PROJECT PLAN | Mega Park Extension
| PROJECT SIZE (kWp) | 1749.93
| SITE ADDRESS | 17 Mill Rd, Unclear, Cape Town, 7530
| BUSINESS DEVELOPER | Natasha Watkins Baker
| PROJECT MANAGERS | Roedolph/Simon
| PROJECT COORDINATOR | Refiloe Mohohlo
| INSTALLER | Smart Solar
| CONTRACT VALUE | 20939008.7697
| Phase: | DLP
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Comment
|  |  | 185 |  |  | 234 |  | 100%
1 | Project Initiation | 2022-08-25 | 3 | 2023-05-16 | 2022-08-25 | 3 | 2023-05-16 | 100%
1.1 | Internal Handover | 2022-08-25 | 1 | 2022-08-26 | 2022-08-25 | 1 | 2022-08-26 | 100%
1.2 | Internal kick off | 2023-02-06 | 1 | 2023-02-07 | 2023-02-06 | 1 | 2023-02-07 | 100%
1.3 | Client kick off | 2023-05-15 | 1 | 2023-05-16 | 2023-05-15 | 1 | 2023-05-16 | 100%
2 | Site Establishment | 2023-06-19 | 2 | 2023-06-21 | 2023-06-19 | 3 | 2023-06-22 | 100%
2.1 | Installer on site and roof assessment | 2023-06-19 | 2 | 2023-06-21 | 2023-06-19 | 3 | 2023-06-22 | 100%
3 | AC Installation | 2023-06-14 | 90 | 2023-10-05 | 2023-06-15 | 179 | 2024-02-13 | 100%
3.1 | Inverters delivered | 2023-07-03 | 1 | 2023-07-04 | 2023-08-15 | 1 | 2023-08-16 | 100%
3.2 | Inverters Mounted | 2023-07-04 | 8 | 2023-07-14 | 2023-12-01 | 4 | 2023-12-07 | 100%
3.3 | Solar DB lead time | 2023-06-14 | 40 | 2023-08-09 | 2023-06-15 | 73 | 2023-09-26 | 100%
3.4 | AC Works | 2023-08-09 | 40 | 2023-10-04 | 2023-09-26 | 100 | 2024-02-13 | 100% | RT: too long need to push
3.5 | AC Tie - in | 2023-10-04 | 1 | 2023-10-05 | 2023-10-24 | 1 | 2023-10-25 | 100% | RV: Schedule PrEng
4 | DC Works | 2023-06-19 | 103 | 2023-11-09 | 2023-06-22 | 155 | 2023-12-13 | 100%
4.1 | Mounting Structure delivered | 2023-06-19 | 1 | 2023-06-20 | 2023-06-22 | 1 | 2023-06-23 | 100%
4.2 | Mounting Structure installation | 2023-06-20 | 50 | 2023-08-29 | 2023-06-23 | 50 | 2023-09-01 | 100%
4.3 | DC Cable delivered | 2023-08-29 | 1 | 2023-08-30 | 2023-09-01 | 1 | 2023-09-04 | 100%
4.4 | DC Cable Trays installation | 2023-08-30 | 30 | 2023-10-11 | 2023-09-04 | 72 | 2023-12-13 | 100%
4.5 | DC Cabling | 2023-10-11 | 21 | 2023-11-09 | 2023-08-07 | 31 | 2023-09-19 | 100%
5 | Module installation | 2023-08-29 | 73 | 2023-12-07 | 2023-09-01 | 51 | 2023-11-10 | 100%
5.1 | Module delivery - Batch 1 | 2023-08-29 | 1 | 2023-08-30 | 2023-09-01 | 1 | 2023-09-04 | 100% | RT: we need to start mounting in phases before all MS is complete | 3. Construction | 1. Financial Close
5.2 | Module delivery - Batch 2 | 2023-09-06 | 1 | 2023-09-07 | 2023-09-11 | 1 | 2023-09-12 | 100%
5.3 | Module delivery - Batch 3 | 2023-09-14 | 1 | 2023-09-15 | 2023-09-19 | 1 | 2023-09-20 | 100%
5.4 | Module mounting | 2023-08-31 | 70 | 2023-12-07 | 2023-09-05 | 48 | 2023-11-10 | 100% | RT: too long need to push
6 | Commissioning | 0 | 13 | 2023-12-21 | 2024-01-26 | 6 | 2024-02-08 | 100%
6.1 | Cold commissioning | 2023-12-07 | 3 | 2023-12-12 | 2024-01-26 | 1 | 2024-01-29 | 100% | 6x inverters are switched on, not all of them have strings plugged in.
6.2 | Cold commissioning - Phased | 0 | 3 | 1900-01-03 | 2024-01-30 | 1 | 2024-01-31 | 100%
6.3 | Practical Completion | 2023-12-12 | 7 | 2023-12-21 | 2024-02-02 | 4 | 2024-02-08 | 100% | Next 6x inverters to be switched.
7 | Project Closure | 2024-01-11 | 12 | 2024-01-31 | 2024-02-08 | 58 | 2024-05-13 | 100%
7.1 | Equipment serial numbers | 2024-01-11 | 0 | 2024-01-11 | 2024-02-08 | 1 | 2024-02-09 | 100%
7.2 | Fiber Installation |  |  |  | 2024-03-05 | 15 | 2024-03-26 | 100%
7.4 | Snags completion - 1 | 2024-01-11 | 3 | 2024-01-16 | 2024-03-01 | 20 | 2024-03-29 | 100%
7.4 | Snags completion - 2 |  |  |  | 2024-04-15 | 20 | 2024-05-13 | 100%
7.5 | System Performance Monitoring | 2024-01-16 | 7 | 2024-01-25 | 2024-03-29 | 1 | 2024-04-01 | 100%
7.6 | Handover documentation | 2024-01-25 | 2 | 2024-01-29 | 2024-04-09 | 1 | 2024-04-10 | 100%
7.7 | Handover to Client | 2024-01-29 | 1 | 2024-01-30 | 2024-04-10 | 1 | 2024-04-11 | 100%
7.8 | Handover to O&M | 2024-01-30 | 1 | 2024-01-31 | 2024-04-11 | 1 | 2024-04-12 | 100%
8 | QA Inspections | 2024-01-11 | 1 | 2024-01-11 | 2024-02-11 | 15 | 2024-03-01 | 100%
8.1 | Inspection | 2024-01-11 | 1 | 2024-01-11 | 2024-02-11 | 15 | 2024-03-01 | 100%
9 | SSEG |  |  |  | 2026-02-11 | 41 | 2026-04-09 | 100%
9.1 | Control Phil Submission |  |  |  | 2026-02-11 | 2 | 2026-02-13 | 0%
9.2 | Control Phil Pre-Approval |  |  |  | 2026-02-13 | 15 | 2026-03-06 | 0%
9.3 | Onsite Meeting - SCADA & Control Stakeholders |  |  |  | 2026-03-06 | 2 | 2026-03-10 | 0%
9.4 | Control Phil Approval |  |  |  | 2026-03-10 | 10 | 2026-03-24 | 0%
9.5 | Implementation |  |  |  | 2026-03-24 | 5 | 2026-03-31 | 0%
9.6 | Testing & Monitoring |  |  |  | 2026-03-31 | 5 | 2026-04-07 | 0%
9.7 | Close Out |  |  |  | 2026-04-07 | 2 | 2026-04-09 | 0%
9.8
9.9
Formulas:
Planned Start = MIN([Planned Start, row below]:E17)
Planned Start = WORKDAY.INTL([Planned End, row above],0,1,Data!$C3:C14)
Planned End = MAX([Planned End, row below]:G17)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I17)
Actual Start = [Actual End, row above]
Actual End = MAX([Actual End, row below]:K17)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C14)

## Data (hidden)
Public holidays | Drop down list
2021-01-01 | Approved
2021-03-22 | Pending
2021-04-02 | Declined
2021-04-05 | Abanded
2021-04-27
2021-05-01
2021-06-16
2021-08-09
2021-09-24
2021-12-16
2021-12-25 |  | Manual dates
2021-12-26

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | PLANNED |  | ACTUAL | Difference
EXPENDITURE |  | 18682949.9513 |  | 19234297.2704 | -551347.3191
No. | Item | Planned Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | Panels | 8604405.81 |  | 7861415.2827 | 742990.5273
2 | Inverters | 1020000 |  | 1056455 | -36455
3 | Mounting Structures | 524979 |  | 351446.8 | 173532.2
4 | DC Equipment | 637505.76 |  | 1160597.76 | -523092
5 | Monitoring | 24567 |  | 102506.6 | -77939.6
6 | AC Equipment | 637698.258 |  | 954731.35 | -317033.092
7 | Product Add On | 4530000 |  | 625278.5239 | 3904721.4761
8 | AC & DC installation | 1661472 |  | 1378000 | 283472
9 | Site Logistics | 289840.0333 |  | 143094.86 | 146745.1733
10 | Due Dilligence | 78746.85 |  | 54897.75 | 23849.1
11 | BDP Commission | 0 |  | 0 | 0
12 | Engineering | 661555.24 |  | 133516.3238 | 528038.9162
13 | General Expenses | 12180 |  | 5372.6 | 6807.4
14 | Service Add On | 0 |  | 5406984.42 | -5406984.42
| check: | 0 | #REF! | 0

## Expenditure Breakdown
PLANNED EXPENDITURE BREAKDOWN | [6 empty] | 18682949.9513 | ACTUAL EXPENDITURE BREAKDOWN | [8 empty] | 19234297.2704 | Comment
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | Payment date | Total | No. | Prodcut / Service | Description of Work | QTY | Rate / Unit | Actual Total | Payment date | PO NUMBER | [Finance Only] INVOICE RECEIPT DATE | Total
1 | Panels | Longi 455 | 3846 | 10% | 860440.581 | 2023-06-21 | 8604405.81 | 1 | Panels | Jinko 550Wp | 3182 | 10% | 799123.4463 | 2023-06-13 | 2093284.6164 | 2023-06-30 | 7861415.2827 |  | RT: this is from the PO Dayne signed: | Jinko ORDER 22 May
[8 empty] | 1 | Panels |  |  |  | 379626.8243 | 2024-02-22 |  | 2023-06-30
[8 empty] | 1 | Panels |  |  |  | 881171.972 | 2024-03-22 |  | 2023-06-30
[8 empty] | 1 | Panels |  |  |  | 1554041.55 | 2024-03-25 |  | 2023-06-30
[8 empty] | 1 | Panels |  |  |  | 3083109.5 | 2024-04-02 |  | 2023-06-30
1 | 8604405.81 | 7265214 |  | 90% | 7743965.229 | 2023-07-21 |  | 1 | Panels | 7991234.4627 |  | 90% | 1294161.1702 | 2024-04-02 |  | 2023-06-30 |  |  |  | 0.2304 | USD/Wp FCA Walvis Bay
[8 empty] | 1 | Panels | Allocated to 26 Marine Drive | -75 | 2511.39 | -188354.25 | 2024-05-31 |  | 2024-05-31
1 |  | Module delivery to site |  |  | 0 | 2023-07-21 |  | 1 | Panels | Shipping and Clearing |  |  | 39939.25 | 2023-09-30 |  | 2023-08-31 |  |  | USD RoE: | 19.5 | as of 22 May
[8 empty] | 1 | Panels |  |  |  | 3997.43 | 2023-08-01 |  | 2023-08-31
1 | [7 empty] | 1 | Panels | Shipping and Clearing | [9 empty] | 4.4928 | per Wp
|  | Cash handling / Admin fees on | [5 empty] | 1 | Panels
[8 empty] | 1 | Panels | Balance of order that went to Sable Square (6 Pallets)
[8 empty] | 1 | Panels | Jinko 550W | 186
[8 empty] | 1 | Panels
[8 empty] | 1 | Panels | Cash handling / Admin fees on |  |  | 5328.39 | 2023-06-28 |  | 2023-06-30
[8 empty] | 1 | Panels
[8 empty] | 1 | Panels | Silver solutions - Forklift hire |  |  | 4300 | 2023-10-26 |  | 2023-10-31
[8 empty] | 1 | Panels
[8 empty] | 1 | Panels | Delivery to storage |  |  | 4550 | 2023-11-16 |  | 2023-10-31
1 | [7 empty] | 1 | Panels | Handling in/Handling out |  |  | 420 | 2023-11-16 |  | 2023-10-31
1 | [7 empty] | 1 | Panels | [10 empty] | 7862045.4763 | final price tbc once FEC booked
2 | Inverters | SMA 110 | 12 | 85000 | 1020000 | 2023-08-03 | 1020000 | 2 | Inverters | Huawei 100ktl - Deposit | 12 | 89060 | 106872 | 2023-08-17 |  | 2023-08-31 | 1056455 | changed from 89000
2 | [5 empty] | 2023-08-03 |  | 2 | Inverters | Huawei 100KTl - Balance |  |  | 961848 | 2023-10-03 |  | 2023-08-31
[8 empty] | 2 | Inverters | Huawei 100KTl - Replace faulty Inverter |  |  | 76795 | 2024-07-01 |  | 2024-05-31
2 | [7 empty] | 2 | Inverters | Huawei 100KTl - RMA from Supplaier allocated to Stock |  |  | -89060 | 2024-08-31 |  | 2024-08-31
2 | [7 empty] | 2 | Inverters
3 | Mounting Structures | Lumax |  |  | 524979 | 2023-07-20 | 524979 | 3 | Mounting Structures | Schletter |  | 0.18316 | 320522 | 2023-08-10 |  | 2023-06-30 | 351446.8
3 | [7 empty] | 3 | Mounting Structures |  |  |  | 24371 | 2023-08-10 |  | 2023-06-30
[9 empty] | Mounting Structures | Schletter - Additional Clamps |  |  | 6553.8 | 2024-02-29 |  | 2024-02-29
3 | [7 empty] | 3 | Mounting Structures | Stock allocated to Dekro Paint |  |  | -18280.34 | 2023-07-31 |  | 2023-06-30
3 | [7 empty] | 3 | Mounting Structures | Received the stock back from Dekro Paint |  |  | 18280.34 | 2023-07-31 |  | 2023-06-30
4 | DC Equipment | DC Cable | 29292 | 11.28 | 330413.76 | 2023-10-04 | 637505.76 | 4 | DC Equipment | DC Cable - Red - Delivered | 20000 | 13.92 | 278400 | 2023-08-31 | Rubicon Bulk Order | 2023-08-31 | 1160597.76
4 |  | Earth Cable | 29292 | 10.3 | 301707.6 | 2023-10-04 |  | 4 | DC Equipment | DC Cable - Black - Delivered | 20000 | 13.92 | 278400 | 2023-08-31 | Rubicon Bulk Order | 2023-08-31
[9 empty] | DC Equipment | DC Cable - Zonn - Red | 3500 | 15.47 | 54145 | 2023-10-06 |  | 2023-08-31
[9 empty] | DC Equipment | DC Cable - Zonn - Black | 3500 | 14.6 | 51100 | 2023-10-06 |  | 2023-08-31
[9 empty] | DC Equipment | DC Cable - KBE - Red - Krannich | 3000 | 14.28 | 42841.93 | 2023-11-13 | 85683.86 | 2023-10-31
[9 empty] | DC Equipment | DC Cable - KBE - Black - Krannich | 3000 | 14.28 | 42841.93 | 2023-11-13 |  | 2023-10-31
[13 empty] | 725 | 2023-11-13 |  | 2023-10-31
4 |  | Earth clamp | 384.6 | 14 | 5384.4 | 2023-10-04 |  | 4 | DC Equipment | DC Equipment - Deposit | 50% | 420555 | 210277.5 | 2023-06-15 |  | 2023-06-30
[8 empty] | 4 | DC Equipment | DC Equipment - Onsite | 40% |  | 168222 | 2023-08-31 |  | 2023-08-31
4 | [7 empty] | 4 | DC Equipment | DC Equipment - Retention | 10% | 42055.5 | 33644.4 | 2024-07-11 |  | 2024-06-30
[8 empty] | 0 | DC Equipment | DC Equipment - Retention |  |  | 8411.1 | 2024-08-15 |  | 2024-06-30
5 | Monitoring | Solarlog |  |  | 21000 | 2023-08-03 | 24567 | 5 | Monitoring | Smartlogger - Deposit |  |  | 749.9 | 2023-08-17 |  | 2023-08-31 | 102506.6
5 |  | Revenue Grade Meter |  |  | 3567 | 2023-03-29 |  | 5 | Monitoring | Smartlogger - Balance |  |  | 6749.1 | 2023-10-03 |  | 2023-08-31
[8 empty] | 5 | Monitoring | Smartlogger Replacement |  |  | 9011 | 2024-02-29 |  | 2024-01-31
5 | [7 empty] | 5 | Monitoring | Techsitter X2 |  |  | 26788 | 2024-02-28 | Techsitter Inv: MN8940233 | 2024-01-31
[8 empty] | 5 | Monitoring | Shipping of Techsitters |  |  | 242.39 | 2024-02-29 | DSV Inv: 180047661 | 2024-01-31
[8 empty] | 5 | Monitoring | SPD |  |  | 1655 | 2023-09-07 | Plustead electrical Inv: 1001/97633203 | 2023-09-07
[8 empty] | 5 | Monitoring | Techsitter | 0 | 15000 | 0
[8 empty] | 5 | Monitoring | Techsitter CTs |  |  | 9006.66 | 2024-02-29 |  | 2024-01-31
[8 empty] | 5 | Monitoring | CT's |  |  | 4910 | 2024-02-16 | Accuenergy Inv: ASAI-002363 | 2024-01-31
[8 empty] | 5 | Monitoring | UPS |  |  | 2082.61 | 2023-06-19 |  | 2023-06-30
[8 empty] | 5 | Monitoring |  |  |  | 1999.13 | 2024-02-08 | Roedolph Exp Claim | 2024-01-31
[8 empty] | 5 | Monitoring | Switch |  |  | 239.13 | 2023-04-15 |  | 2023-05-31
[8 empty] | 5 | Monitoring |  |  |  | 6225 | 2024-02-16 | Accuenergy Inv: ASAI-002350 | 2024-01-31
[8 empty] | 5 | Monitoring | Router | 1 | 2694 | 2969.31 | 2023-07-20 |  | 2023-07-31
[8 empty] | 5 | Monitoring | Lithium Batteries |  |  | 2606.09 | 2024-01-22 | Takelot - Order 145230153 | 2024-01-31
[8 empty] | 5 | Monitoring | Battery Charger UPS |  |  | 1039 | 2023-08-10 |  | 2023-08-31
[8 empty] | 5 | Monitoring |  |  |  | 2463 | 2024-01-25 | Current Automation Inv: SOQ294289 | 2024-01-31
5 | [7 empty] | 5 | Monitoring | Pyronometer |  |  | 11667.2 | 2024-05-16 | Geosun Inv: 2366 | 2024-04-30
5 | [7 empty] | 5 | Monitoring | Delivery |  |  | 433.29 | 2024-05-31 |  | 2024-04-30
5 | [7 empty] | 5 | Monitoring | Power Supply |  |  | 1201.79 | 2024-02-08 | Roedolph Exp Claim | 2024-01-31
5 | [7 empty] | 5 | Monitoring | Rogowski Coil Kit + Delivery |  |  | 10469 | 2024-02-29 | Accuenergy Inv: 002453 | 2024-01-31
[20 empty] | BUDGET | Installer Allocation
6 | AC Equipment | 50% Deposit |  | 50% | 318849.129 | 2023-06-16 | 637698.258 | 6 | AC Equipment | AC Equipment - Deposit | 388553.54 | 50% | 194276.77 | 2023-06-15 |  | 2023-06-30 | 954731.35 |  |  | AC Equipment | 637698.258
6 | [7 empty] | 6 | AC Equipment | AC Equipment - Onsite |  | 40% | 86956.5217 | 2024-01-26 |  | 2023-12-31 |  |  |  | DC Equipment | 307092
[8 empty] | 0 | AC Equipment | AC Equipment - Onsite |  |  | 68464.8943 | 2024-02-01 |  | 2023-12-31
6 | [7 empty] | 6 | AC Equipment | AC Equipment - Retention | 38855.354 | 10% | 31084.2832 | 2024-07-11 |  | 2024-06-30 |  |  |  | AC Labour | 437482.5
[13 empty] | 7771.0708 | 2024-08-15 |  | 2024-06-30
[10 empty] | Switch Board - PV DB |  |  | 434902.77 | 2023-09-29 |  | 2023-07-31
[10 empty] | Switch Board - Comms DB |  |  | 6757.02 | 2023-09-29 |  | 2023-07-31
[10 empty] | Switch Board - Site Work |  |  | 87414.48 | 2023-09-29 |  | 2023-07-31
[10 empty] | Switch Board - Cubicle |  |  | 37103.54 | 2023-11-01 |  | 2023-10-31 |  | TC: Added cost 24/10/2023
RV: Switchboard absorbed the cost
6 | 637698.258 | 50% on site |  | 50% | 318849.129 | 2023-10-04 |  | 6 | AC Equipment | [10 empty] | DC Labour | 1223989.5
[20 empty] | Offloading | 8500
7 | Product Add On | SCADA & SSEG extras |  |  | 280000 | 2023-05-08 | 4530000 | 7 | Product Add On | Metering & SCADA & SSEG extras | 281640.5739 |  | 281640.5739 | 2024-05-23 | PO3053-MGP-20240412 | 2024-05-31 | 625278.5239 |  |  | Roof Access | 92066.7
[10 empty] | Fibre Installation 40% Deposit |  |  | 41579.5826 | 2024-02-29 | Comtel Inv: CEIN023698 | 2024-02-29
[10 empty] | Fibre Installation 60% Balance |  |  | 62369.3674 | 2024-04-12 |  | 2024-02-29
7 |  | CAPEX Expenditure |  |  | 4000000 | 2023-05-08 |  | 7 | Product Add On | Waterpoints |  |  | 21664 | 2024-07-11 | PO3204-MGP-20240627 | 2024-06-30 |  |  |  | Other | 0
7 |  | Walkways, Inverter Cages, Warranty Extensions |  |  | 250000 | 2023-05-08 |  | 7 | Product Add On | Cat Ladder, Inverter Cages | [9 empty] | Other | 0
Site Demob
[10 empty] | FDT Electric Aircon Installation 50% Deposit |  |  | 28620 | 2024-01-29 |  | 2024-01-31
[10 empty] | FDT Electric Aircon Installation 2nd Unit 50% Deposit |  |  | 14675 | 2024-03-25 | PO3008-MGP-20240319 | 2024-03-31
[13 empty] | 14675 | 2024-04-12 |  | 2024-03-31
[10 empty] | Lester & Co |  |  | 2850 | 2024-05-16 |  | 2024-05-31 |  | PO3092-MGP-20240507
[10 empty] | Brice & Co. Inverter room modification & Roof Gate |  |  | 29745 | 2023-06-22 |  | 2023-06-30
[10 empty] | Brice & Co Inverter Steel Structure - Deposit |  |  | 19942.5 | 2024-01-25 | Brice & Co Inv: BC/0154 | 2023-11-30
[10 empty] | Brice & Co Inverter Steel Structure - Balance |  |  | 19942.5 | 2024-01-25 | Brice & Co Inv: BC/0154 | 2023-11-30
[10 empty] | All in Glass Aluminium - Single Y Louvred door |  |  | 10780 | 2023-12-22 |  | 2023-11-30
[10 empty] | 100KTL inverter to be replaced by RMA |  |  | 76795 | 2024-07-01 |  | 2024-05-31
[10 empty] | All in Glass Aluminium - Healt & Safety File |  |  | 0
7 | [7 empty] | 7 | Product Add On | Lifelines, Temporary Walkboards |  |  | 0 |  |  |  |  | RV: 75k removed |  | Other | 0
Only services to be capture below, products above | [19 empty] | Total | 2706828.958
8 | AC & DC installation | Upfront |  | 30% | 498441.6 | 2023-06-16 | 1661472 | 8 | AC & DC installation | Upfront | 360000 | 20% | 275600 | 2023-06-15 |  | 2023-06-30 | 1378000 |  |  | Less 15% | 2300804.6143
8 | 437482.5 | AC Complete |  | 15% | 249220.8 | 2023-10-04 |  | 8 | AC & DC installation | MS Complete - Partial | 1018000 | 15% | 168222 | 2023-08-31 |  | 2023-08-31 |  |  |  | R/Wp | 1.3148
[8 empty] | 0 | AC & DC installation | MS Complete - Partial |  | 15% | 38478 | 2023-08-10 |  | 2023-08-31
8 | 1223989.5 | DC Complete |  | 15% | 249220.8 | 2023-12-07 |  | 8 | AC & DC installation | Panels Complete |  | 15% | 206700 | 2023-11-17 |  | 2023-11-30
8 | 0 | Practical Completion |  | 30% | 498441.6 | 2024-01-16 |  | 8 | AC & DC installation | AC Tie-In complete |  | 15% | 195861.42 | 2023-12-07 |  | 2023-12-31 |  |  |  | ACTUAL | Installer Price
[13 empty] | 10838.58 | 2024-02-16 |  | 2023-12-31
8 | [7 empty] | 8 | AC & DC installation | Practical Completion |  | 20% | 275600 | 2024-04-18 |  | 2024-03-31 |  |  |  | AC Equipment | 388553.54
8 | [7 empty] | 8 | AC & DC installation | Retention | 206700 | 15% | 165360 | 2024-07-11 |  | 2024-06-30 |  |  |  | DC Equipment | 420555
8 |  | Retention |  | 10% | 166147.2 | 2024-02-15 |  | 8 | AC & DC installation |  |  |  | 41340 | 2024-08-16 |  | 2024-06-30 |  |  |  | AC Labour | 360000
[20 empty] | DC Labour | 1018000
9 | Site Logistics | Scaffolding |  |  | 46033.35 | 2023-06-16 | 289840.0333 | 9 | Site logistics - Smart Solar | Site logistics - Deposit | 50% |  | 50550 | 2023-06-15 |  | 2023-06-30 | 143094.86 |  |  | Offloading | 0
[8 empty] | 9 | 101100 | Site Logistics - Onsite | 40% |  | 40440 | 2023-12-21 |  | 2023-12-31
9 |  |  |  |  | 46033.35 | 2023-06-16 |  | 9 |  | Site logistics - Retention | 10% | 10110 | 8088 | 2024-08-15 |  | 2024-06-30 |  |  |  | Site logistics | 101100
9 |  | Telehandler |  |  | 0 | 2023-02-22 |  | 9 |  |  |  |  | 2022 | 2024-08-15 |  | 2024-06-30 |  |  |  | Other | 0
[8 empty] | 9 |  | Forklift |  |  | 4300 | 2023-10-26 |  | 2023-10-31 |  | TC - 2023/10/26
[8 empty] | 9 |  | Telehandler Extra - VO Smart Solar |  |  | 33700 | 2024-04-04 |  | 2024-03-31
9 |  | Offloading |  |  | 8500 | 2023-03-09 |  | 9 | [11 empty] | Other | 0
9 |  | Security |  |  | 139200 | 2023-03-09 |  | 9 | Site logistics - EE | Security |  |  | 0 | [6 empty] | Other | 0
9 | [7 empty] | 9 |  | Site Office |  |  | 739.83 | 2023-12-01 |  | 2023-12-31 |  |  |  | Other | 0
[13 empty] | 573.91 | 2023-12-01 |  | 2023-11-30
[13 empty] | 584.11 | 2023-12-01 |  | 2023-11-30
[13 empty] | 585.3 | 2023-12-01 |  | 2023-11-30
[13 empty] | 470.22 | 2024-02-12 |  | 2024-01-31
[13 empty] | 972.84 | 2024-03-28 | Spear Inv:4794/202402/1 | 2024-03-31
9 |  | Storage |  |  | 50073.3333 | 2023-03-09 |  | 9 |  |  |  |  | 68.65 | 2024-04-25 |  | 2024-04-30 |  |  |  | Other | 0
9 | [7 empty] | 9 | [9 empty] | RV: Double check figures |  | Other | 0
[20 empty] | Total | 2288208.54
10 | Due Dilligence | Structural sign off |  |  | 52497.9 | 2023-06-14 | 78746.85 | 10 | Due Dilligence | Structural sign off |  |  | 11750 | 2023-03-09 |  | 2023-05-31 | 54897.75 |  |  | R/Wp | 1.3076
10 |  | Electrical Sign off |  |  | 26248.95 | 2023-03-09 |  | 10 | Due Dilligence | Electrical Sign off |  |  | 16250 | 2024-04-04 |  | 2024-04-30 |  | TC: OG amount 26248,95
10 | [5 empty] | 2024-01-20 |  | 10 |  | SSEg Costs |  |  | 16276 | 2023-10-30 |  | 2023-05-31
10 | [7 empty] | 10 |  | Red Team |  |  | 621.75 | 2023-11-30 |  | 2023-11-30
[13 empty] | 10000 | 2024-04-30 |  | 2024-04-30
10 | [7 empty] | 10 |  | APEX Site software Upgrade | [7 empty] | PO3297-MGP-20240815 - RV Approved
11 | BDP Commission |  |  |  | 0 | 2024-01-20 | 0 | 11 | BDP Commission | [7 empty] | 0 |  |  | Dayne | R1,10p/w - All In (DB Excl)
12 | Engineering | EE Project Management |  |  | 661555.24 | 2023-03-09 | 661555.24 | 12 | Engineering | EE Project Management |  |  | 3786.92 | 2023-05-25 |  | 2023-05-31 | 133516.3238 |  |  | Alex | R1.20p/w - All in (DB Excl)
[13 empty] | 3769.9 | 2023-06-25 |  | 2023-06-30
[13 empty] | 5504.78 | 2023-07-25 |  | 2023-07-31
[13 empty] | 5016.82 | 2023-08-25 |  | 2023-08-31
[13 empty] | 0 | 2023-09-25 |  | 2023-09-30
[13 empty] | 3515.63 | 2023-10-25 |  | 2023-10-31
[13 empty] | 5859.38 | 2023-11-25 |  | 2023-11-30
[13 empty] | 0 | 2023-12-25 |  | 2023-12-31
[13 empty] | 1367.85 | 2024-01-25 |  | 2024-01-31
[8 empty] | 0 | Engineering | Matriarch Defects Period |  |  | 104695.0438 | 2024-04-30 |  | 2024-04-30
13 | General Expenses | Car travel to site |  |  | 12180 | 2023-03-09 | 12180 | 13 | General Expenses | Car travel to site |  |  | 715.28 | 2023-06-08 |  | 2023-05-31 | 5372.6
13 | [7 empty] | 13 | General Expenses |  |  |  | 106.72 | 2023-07-06 |  | 2023-06-30
[8 empty] | 13 |  |  |  |  | 69.6 | 2023-08-04 |  | 2023-07-31
[8 empty] | 13 |  |  |  |  | 69.6 | 2023-09-07 |  | 2023-08-31
[8 empty] | 13 |  |  |  |  | 1005.16 | 2023-11-05 |  | 2023-09-30
[8 empty] | 13 |  |  |  |  | 139.2 | 2023-11-07 |  | 2023-10-31
[8 empty] | 13 |  |  |  |  | 533.6 | 2023-12-07 |  | 2023-11-30
13 | [7 empty] | 13 | General Expenses |  | 1 |  | 0 | 2023-12-31 | PO3042-MGP-20240408 |  |  | This is for R&D and not an expense for the project. Captured under monitoring
13 | [7 empty] | 13 |  |  |  |  | 607.84 | 2024-02-08 |  | 2024-01-31
[8 empty] | 13 |  |  |  |  | 948.8 | 2024-03-07 |  | 2024-02-29
[8 empty] | 13 |  |  |  |  | 909.92 | 2024-04-05 |  | 2024-03-31
[8 empty] | 13 |  |  |  |  | 208.8 | 2024-05-09 |  | 2024-04-30
[8 empty] | 13 |  |  |  |  | 58.08 | 2024-07-05 |  | 2024-06-30
13 | [7 empty] | 13
14 | Service Add On | [5 empty] | 0 | 14 | Service Add On | Welcome Bonus |  |  | 2000000 | 2024-05-09 | Spear Holdco Inv: 4794/202405/52190/I | 2024-05-31 | 5406984.42
14 | [7 empty] | 14 | Service Add On |  |  |  | 1000000 | 2024-05-23 | Spear Holdco Inv: 4794/202405/52190/I | 2024-05-31
[8 empty] | 0 | Service Add On |  |  |  | 1000000 | 2024-05-24 | Spear Holdco Inv: 4794/202405/52190/I | 2024-05-31
14 | [7 empty] | 14 | Service Add On | Penalties - December 2023 |  |  | 75000 | 2024-02-12 | Spear Inv: M00002/2024/03 | 2024-01-31
[8 empty] | 14 | Service Add On | Penalties - January 2024 |  |  | 75000 | 2024-02-12 | Spear Inv:4794/202401/50984/I | 2024-01-31
[8 empty] | 14 | Service Add On |  |  |  | 75000 | 2024-03-28 | Spear Inv:4794/202402/1 | 2024-03-31
[8 empty] | 14 | Service Add On | Provision for Construction Penalty
[8 empty] | 14 | Service Add On | Site Visits |  |  | 626.88 | 2024-10-31 |  | 2024-10-31
[8 empty] | 14 | Service Add On | Site Visits |  |  | 358.16 | 2024-12-06 |  | 2024-11-30
[8 empty] | 14 | Service Add On | Site Visits |  |  | 164.54 | 2025-02-07 |  | 2025-01-31
[8 empty] | 14 | Service Add On | Site Visits |  |  | 280.72 | 2025-03-06 |  | 2025-02-28
[8 empty] | 14 | Service Add On | Site Visits |  |  | 582.54 | 2025-04-04 |  | 2025-03-31
[8 empty] | 14 | Service Add On | Site Visits |  |  | 499.32 | 2025-05-08 |  | 2025-04-30
[8 empty] | 14 | Service Add On | Penalty |  |  | 543170.74 | 2024-12-13 |  | 2024-11-30
[8 empty] | 14 | Service Add On | Smartlogger |  |  | 7639.55 | 2025-02-28 |  | 2025-01-31
[8 empty] | 14 | Service Add On | Kathea Support |  |  | 18000 | 2025-04-30 |  | 2025-03-31 |  | PO3759-MGP-20250321 - RV Approved
[8 empty] | 14 | Service Add On | De Kock & Cronje - additional Labour |  |  | 24772 | 2025-04-30 |  | 2025-03-31 |  | PO3760-MGP-20250324 - RV Approved
[8 empty] | 14 | Service Add On | Supply, Install and Commission between Plant, PPC, RTU and Control Centre - Deposit | 283043.05 | 10% | 28304.305 | 2025-11-13 |  | 2025-11-30 |  | PO4372-MGP-20251015 - RV Approved
[8 empty] | 14 | Service Add On | Supply, Install and Commission between Plant, PPC, RTU and Control Centre - Balance |  | 90% | 254738.745 | 2025-11-30 |  | 2025-11-30
[8 empty] | 14 | Service Add On
[8 empty] | 14 | Service Add On
[8 empty] | 14 | Service Add On
[8 empty] | 14 | Service Add On
[8 empty] | 14 | Service Add On
[8 empty] | 14 | Service Add On
[8 empty] | 14 | Service Add On
[8 empty] | 14 | Service Add On
[8 empty] | 14 | Service Add On
[8 empty] | 14 | Service Add On
[8 empty] | 14 | Service Add On
[8 empty] | 14 | Service Add On
[8 empty] | 14 | Service Add On
[8 empty] | 14 | Service Add On
[8 empty] | 14 | Service Add On
[8 empty] | 14 | Service Add On | Encombi (2nd meter) |  |  | 32128.96 | 2025-05-31 |  | 2025-04-30 |  | PO3783-MGP-20250402 - MI Approved
[8 empty] | 14 | Service Add On | SN Electrcal - Installation of Encombi |  |  | 21322.79 | 2025-04-03 |  | 2025-03-31 |  | PO3781-MGP-20250328 - RV Approved
[8 empty] | 14 | Service Add On | Teltonika Port Switch |  |  | 3905 | 2025-01-09 |  | 2024-12-31
[8 empty] | 14 | Service Add On | Fiber Connections |  | 30099.98 | 30839.11 | 2025-02-20 |  | 2025-01-31 |  | PO3554-MGP-20250122 - RV Approved
[8 empty] | 14 | Service Add On | Encombi |  |  | 80752.14 | 2025-01-30 |  | 2024-12-31 |  | PO3487-MGP-20241125 - RV Approved
[8 empty] | 14 | Service Add On | Jantiza - Kathea |  |  | 32566 | 2025-02-28 |  | 2025-06-30 |  | PO3483-MGP-20241125 - RV Approved
[8 empty] | 14 | Service Add On | MV CTs - De Kock & Cronje |  |  | 93894 | 2025-04-30 |  | 2025-03-31 |  | PO3468-MEG-20241121 - RV Approved
[8 empty] | 14 | Service Add On | Switches - Fiber Compatible |  |  | 3705 | 2025-02-28 | Comtel | 2025-06-30 |  | PO3484-MGP-20241125 - RV Approved
14 | [7 empty] | 14 | Service Add On | Enclosure |  |  | 3733.92 | 2024-12-12 | Frontline PI QTE99478 | 2024-11-30 |  | PO3481-MGP-20241122 - RV Approved
Formulas:
Payment date = [Payment date, row above]
Payment date = +[Payment date, row above]
Note on Q6: Tasneema Van Harte: Jinko: MCSSLB23Q2125
Note on Q7: Tasneema Van Harte: Tasneema Van Harte: Jinko: MCSSLB23Q2125
Note on Q8: Tasneema Van Harte: Tasneema Van Harte: Jinko: MCSSLB23Q2125
Note on Q9: Tasneema Van Harte: Tasneema Van Harte: Jinko: MCSSLB23Q2125
Note on Q11: Tasneema Van Harte: Jinko: MCSSLB23Q2125
Note on Q20: Thami Cambalele: NETTY CUSTOMS INV IS00014013
Note on Q22: Thami Cambalele: SILVER SOLUTIONS INV06105539
Note on Q24: Thami Cambalele: SUPPLY CHAIN INV SCO03718
Note on Q25: Thami Cambalele: SUPPLY CHAIN INV SCO03718
Note on Q28: Thami Cambalele: ISELI INV: CINV008542
Note on Q29: Thami Cambalele: ISELI INV: CINV008542
Note on Q34: Thami Cambalele: SCHLETTER INV IN109961
Note on Q35: Tasneema Van Harte: Schletter Inv: IN109974
Note on Q36: Thami Cambalele: SCHLETTER INV IN110826
Note on Q43: Thami Cambalele: Rubicon INVWCRE-0046245
Note on Q44: Thami Cambalele: Rubicon INVWCRE-0046245
Note on Q46: Thami Cambalele: KRANNICH INV 15-10007341
Note on Q47: Thami Cambalele: KRANNICH INV 15-10007341
Note on Q48: Thami Cambalele: KRANNICH INV 15-10007341
Note on Q49: Tasneema Van Harte: Smart Solar Inv: SUB041P1
Note on Q50: Thami Cambalele: SMART SOLAR INV SUB041P2.1
Note on Q51: Mizelda Isaacs: Smart Solar: SUB041P7
Note on T51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Mizelda Isaacs please capture this invoice here
Note on Q52: Tasneema Van Harte: Smart Solar: SUB041P7
Note on Q54: Thami Cambalele: ISELI INV: QEQT01000C
Note on Q55: Thami Cambalele: ISELI INV: QEQT01000C
Note on Q56: Thami Cambalele: KATHEA INV 517145
Note on Q61: Thami Cambalele: ACCUENERGY INV: ASAI-002453
Note on Q65: Tasneema Van Harte: Takealot - Ord 126946613
Note on Q67: Tasneema Van Harte: Otto Inv: IO123446
Note on Q69: Tasneema Van Harte: Netty Customs Inv: SOQ284932
Note on Q72: Tasneema Van Harte: DSV Inv: 180066791
Note on Q76: Tasneema Van Harte: Smart Solar Inv: SUB041P1
Note on Q77: Thami Cambalele: SMART SOLAR INV SUB041P2.2
Note on Q78: Tasneema Van Harte: SMART SOLAR INV SUB041P2.2
Note on Q79: Mizelda Isaacs: Smart Solar: SUB041P7
Note on Q80: Tasneema Van Harte: Smart Solar: SUB041P7
Note on Q81: Tasneema Van Harte: Switchboard Inv: SQ-9190
Note on Q82: Tasneema Van Harte: Switchboard Inv: SQ-9190
Note on Q83: Tasneema Van Harte: Switchboard Inv: SQ-9190
Note on Q84: Thami Cambalele: SWITCHBOARD - INV 2-SOI000216
Note on Q88: Thami Cambalele: Spear Holdco INV 4794/202405/52343/I
Note on Q91: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inv QU503456
Note on Q94: Tasneema Van Harte: FDT Electrical Inv: 1555
Note on Q95: Mizelda Isaacs: INV1618 - Only pay 50% of invoice
Note on Q97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Invoice
Note on Q98: Thami Cambalele: BRICE & CO INV BC/0061
Note on Q101: Thami Cambalele: ALL IN GLASS INV0000700
Note on Q102: Thami Cambalele: Kathea INV 51763
Note on Q106: Tasneema Van Harte: Smart Solar Inv: SUB041P1
Note on Q107: Thami Cambalele: SMART SOLAR INV SUB041P2.1
Note on Q108: Tasneema Van Harte: SMART SOLAR INV SUB041P2.1
Note on Q109: Thami Cambalele: SMART SOLAR INV SUB041P5
Note on Q110: Thami Cambalele: SMART SOLAR INV SUB041P4
Note on Q111: Tasneema Van Harte: SUB041P4
Note on Q112: Mizelda Isaacs: SUB040P6
Note on Q113: Mizelda Isaacs: Smart Solar Inv: SUB041PS7
Note on Q114: Tasneema Van Harte: Smart Solar Inv: SUB041PS7
Note on Q116: Tasneema Van Harte: Smart Solar Inv: SUB041P1
Note on Q117: Thami Cambalele: SMART SOLAR INV SUB041P2.2
Note on Q118: Mizelda Isaacs: Smart Solar: SUB041P7
Note on Q119: Tasneema Van Harte: Smart Solar: SUB041P7
Note on Q120: Thami Cambalele: SILVER SOLUTIONS INV06105539
Note on Q121: Mizelda Isaacs: SmartSolar: Inv SUB041P8
Note on Q125: Tasneema Van Harte: Spear Inv:4794/202312/1
Note on Q126: Tasneema Van Harte: Spear Inv:4794/202311/1
Note on Q127: Tasneema Van Harte: Spear Inv: 4794/202310/1
Note on Q128: Tasneema Van Harte: Spear Inv: 4794/202308/49750/I
Note on Q129: Thami Cambalele: SPEAR REIT INV 4794/202401/1
Note on Q131: Tasneema Van Harte: Spear Inv:4794/202405/1
Note on Q134: Tasneema Van Harte: L & B Consulting Inv: 1237
Note on Q135: Thami Cambalele: MJ BLELOCH INV 1207
Note on Q136: Tasneema Van Harte: Spear Reit Limited - Inv 3553/20110/42517
Note on Q138: Tasneema Van Harte: Matriarch Inv: 1828
Note on Q153: Thami Cambalele: MATRIARCH INV-2439
Note on Q183: Tasneema van Harte: Spear Reit inv: M00001/2024/11
Note on Q184: Tasneema van Harte: Menlo Inv: INV0002431
Note on Q185: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kathea Inv 519355
Note on Q186: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: De Kock & Cronje DCI105610
Note on Q205: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SN Electrical - In EMG001
Note on Q206: Tasneema van Harte: Accuenergy Inv: # ASAI-004314
Note on Q207: Tasneema van Harte: Cometel Inv: CEIN036764 + CEIN036802
Note on Q208: Tasneema van Harte: Kathea Energy Inv: 518991 + 518973
Note on Q210: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: De Kock & Cronje Inv DCI105609
Note on Q212: Tasneema van Harte: Front Line Electrical Inv: QTE99478

## Expenditure Breakdown-IDC (hidden)
ACTUAL EXPENDITURE BREAKDOWN | [6 empty] | 18009413.9527
No. | Prodcut / Service | Description of Work | QTY | Rate / Unit | Actual Total | Payment date | Total | DIRECTORY & COMMENTS (The below indicates the directory of the invoices for the associated material/service that incurred an expense during the project)
1 | Panels | Jinko 550W Solar Panel - Deposit | 3182 | 10% | 799123.4463 | 2023-06-13 | 8049769.5327 | IDC Funding\Busamed+Spear Round2\Busamed+Spear Shared Folder\7. Drawdown Requests\Mega Park Phase 2\Invoices\1. Panels
1 | Panels | Jinko 550W Solar Panel - Balance |  | 90% | 7192111.0164 | 2024-02-05
1 | Panels | Shipping and Clearing |  |  | 39939.25 | 2023-09-30
1 | Panels | Shipping and Clearing |  |  | 3997.43 | 2023-08-01
1 | Panels | Cash handling / Admin fees on |  |  | 5328.39 | 2023-06-28
1 | Panels | Silver solutions - Forklift hire |  |  | 4300 | 2023-10-26
1 | Panels | Delivery to storage |  |  | 4550 | 2023-11-16
1 | Panels | Handling in/Handling out |  |  | 420 | 2023-11-16
2 | Inverters | Huawei 100ktl - Deposit | 12 | 89060 | 106872 | 2023-08-17 | 1068720 | IDC Funding\Busamed+Spear Round2\Busamed+Spear Shared Folder\7. Drawdown Requests\Mega Park Phase 2\Invoices\2. Inverters
2 | Inverters | Huawei 100KTl - Balance |  |  | 961848 | 2023-10-03
3 | Mounting Structures | Schletter |  |  | 320522 | 2023-08-10 | 351446.8 | IDC Funding\Busamed+Spear Round2\Busamed+Spear Shared Folder\7. Drawdown Requests\Mega Park Phase 2\Invoices\3. Balance of System
3 | Mounting Structures | Schletter - Additional Clamps |  |  | 24371 | 2023-08-10
3 | Mounting Structures | Schletter - Additional Clamps |  |  | 6553.8 | 2024-02-28
3 | Mounting Structures | Stock allocated to Dekro Paint |  |  | -18280.34 | 2023-07-31
3 | Mounting Structures | Received the stock back from Dekro Paint |  |  | 18280.34 | 2023-07-31
4 | DC Equipment | DC Cable - Red - Delivered | 20000 | 13.92 | 278400 | 2023-08-31 | 1169008.86 | IDC Funding\Busamed+Spear Round2\Busamed+Spear Shared Folder\7. Drawdown Requests\Mega Park Phase 2\Invoices\3. Balance of System
4 | DC Equipment | DC Cable - Black - Delivered | 20000 | 13.92 | 278400 | 2023-08-31
4 | DC Equipment | DC Cable - Zonn - Red | 3500 | 15.47 | 54145 | 2023-10-06
4 | DC Equipment | DC Cable - Zonn - Black | 3500 | 14.6 | 51100 | 2023-10-06
4 | DC Equipment | DC Cable - KBE - Red - Krannich | 3000 | 14.28 | 42841.93 | 2023-11-13
4 | DC Equipment | DC Cable - KBE - Black - Krannich | 3000 | 14.28 | 42841.93 | 2023-11-13
4 | DC Equipment - Subcontractor | DC Equipment - Deposit | 50% | 420555 | 210277.5 | 2023-06-15 |  | IDC Funding\Busamed+Spear Round2\Busamed+Spear Shared Folder\7. Drawdown Requests\Mega Park Phase 2\Invoices\4. Subcontractors
4 | DC Equipment - Subcontractor | DC Equipment - Onsite | 40% |  | 168222 | 2023-08-31
4 | DC Equipment - Subcontractor | DC Equipment - Retention | 10% |  | 42055.5 | 2024-02-26
5 | Monitoring | Smartlogger - Deposit |  |  | 749.9 | 2023-08-17 | 142410.71 | IDC Funding\Busamed+Spear Round2\Busamed+Spear Shared Folder\7. Drawdown Requests\Mega Park Phase 2\Invoices\3. Balance of System
5 | Monitoring | Smartlogger - Balance |  |  | 6749.1 | 2023-10-03
5 | Monitoring | Smartlogger Replacement |  |  | 9011 | 2024-02-29
5 | Monitoring | Techsitter X2 |  |  | 26788 | 2024-01-31
5 | Monitoring | SPD |  |  | 1655 | 2023-09-07
5 | Monitoring | Techsitter | 4 | 15000 | 60000 | 2024-02-28
5 | Monitoring | Techsitter CTs |  |  | 9006.66 | 2024-02-28
5 | Monitoring | UPS |  |  | 2082.61 | 2023-06-19
5 | Monitoring | Switch |  |  | 239.13 | 2023-04-15
5 | Monitoring | Router | 1 | 2694 | 2969.31 | 2023-07-20
5 | Monitoring | Battery Charger UPS |  |  | 1039 | 2023-08-10
5 | Monitoring | Comms |  |  | 15000 | 2024-02-28
5 | Monitoring | Ethernet Switches |  |  | 6300 | 2024-01-31
5 | Monitoring | Power Supply |  |  | 821 | 2024-01-31
6 | AC Equipment-Subcontractor | AC Equipment - Deposit | 388553.54 | 50% | 194276.77 | 2023-06-15 | 954731.35 | IDC Funding\Busamed+Spear Round2\Busamed+Spear Shared Folder\7. Drawdown Requests\Mega Park Phase 2\Invoices\4. Subcontractors
6 | AC Equipment-Subcontractor | AC Equipment - Onsite |  | 40% | 86956.5217 | 2024-01-26
6 | AC Equipment-Subcontractor | AC Equipment - Onsite |  |  | 68464.8943 | 2024-01-31
6 | AC Equipment-Subcontractor | AC Equipment - Retention |  | 10% | 38855.354 | 2024-02-26
6 | AC Equipment | Switch Board - PV DB |  |  | 434902.77 | 2023-09-29 |  | IDC Funding\Busamed+Spear Round2\Busamed+Spear Shared Folder\7. Drawdown Requests\Mega Park Phase 2\Invoices\3. Balance of System
6 | AC Equipment | Switch Board - Comms DB |  |  | 6757.02 | 2023-09-29
6 | AC Equipment | Switch Board - Site Work |  |  | 87414.48 | 2023-09-29
6 | AC Equipment | Switch Board - Cubicle |  |  | 37103.54 | 2023-11-01
7 | Product Add On | Metering & SCADA & SSEG extras |  |  | 400000 | 2024-02-26 | 534030 | IDC Funding\Busamed+Spear Round2\Busamed+Spear Shared Folder\7. Drawdown Requests\Mega Park Phase 2\Invoices\3. Balance of System
7 | Product Add On | Waterpoints |  |  | 25000 | 2024-02-26
7 | Product Add On | FDT Electric Aircon Installation 50% Deposit |  |  | 28620 | 2024-01-29
7 | Product Add On | Brice & Co. Inverter room modification & Roof Gate |  |  | 29745 | 2023-06-22
7 | Product Add On | Brice & Co Inverter Steel Structure - Deposit |  |  | 19942.5 | 2024-01-25
7 | Product Add On | Brice & Co Inverter Steel Structure - Balance |  |  | 19942.5 | 2024-01-25
7 | Product Add On | All in Glass Aluminium - Single Y Louvred door |  |  | 10780 | 2023-12-22
8 | AC & DC installation | Upfront | 360000 | 20% | 275600 | 2023-06-15 | 1378000 | IDC Funding\Busamed+Spear Round2\Busamed+Spear Shared Folder\7. Drawdown Requests\Mega Park Phase 2\Invoices\4. Subcontractors
8 | AC & DC installation | MS Complete - Partial | 1018000 | 15% | 175695 | 2023-08-03
0 | AC & DC installation | MS Complete - Partial |  | 15% | 31005 | 2023-08-10
8 | AC & DC installation | Panels Complete |  | 15% | 206700 | 2023-11-17
8 | AC & DC installation | AC Tie-In complete |  | 15% | 206700 | 2024-02-13
8 | AC & DC installation | Practical Completion |  | 20% | 275600 | 2024-02-13
8 | AC & DC installation | Retention |  | 15% | 206700 | 2024-02-26
9 | Site logistics - Subcontractor | Site logistics - Deposit | 50% |  | 50550 | 2023-06-15 | 156400 | IDC Funding\Busamed+Spear Round2\Busamed+Spear Shared Folder\7. Drawdown Requests\Mega Park Phase 2\Invoices\4. Subcontractors
9 | Site logistics - Subcontractor | Site Logistics - Onsite | 40% |  | 40440 | 2023-12-21
9 | Site logistics - Subcontractor | Site logistics - Retention | 10% |  | 10110 | 2024-02-26
9 | Site logistics - Subcontractor | Forklift |  |  | 4300 | 2023-10-26
9 | Site logistics - Subcontractor | Telehandler Extra - VO Smart Solar |  |  | 36000 | 2024-02-13
9 | Site logistics - Emergent | Site Office - August |  |  | 739.83 | 2023-12-01 |  | IDC Funding\Busamed+Spear Round2\Busamed+Spear Shared Folder\7. Drawdown Requests\Mega Park Phase 2\Invoices\4. Subcontractors
9 | Site logistics - Emergent | Site Office - September |  |  | 573.91 | 2023-12-01
9 | Site logistics - Emergent | Site Office - October |  |  | 584.11 | 2023-12-01
9 | Site logistics - Emergent | Site Office - November |  |  | 585.3 | 2023-12-01
9 | Site logistics - Emergent | Site Office - December |  |  | 470.12 | 2024-01-25
10 | Due Dilligence | Structural sign off |  |  | 11750 | 2023-03-09 | 54896.7 | IDC Funding\Busamed+Spear Round2\Busamed+Spear Shared Folder\7. Drawdown Requests\Mega Park Phase 2\Invoices\4. Subcontractors
10 | Due Dilligence | Electrical Sign off |  |  | 26248.95 | 2024-02-26
10 | Due Dilligence | SSEg Costs |  |  | 16276 | 2023-10-30
10 | Due Dilligence | Red Team |  |  | 621.75 | 2023-11-30
14 | Service Add On | Welcome Bonus - 1 |  |  | 2000000 | 2024-02-28 | 4150000 | IDC Funding\Busamed+Spear Round2\Busamed+Spear Shared Folder\7. Drawdown Requests\Mega Park Phase 2\Invoices\4. Subcontractors
14 | Service Add On | Welcome Bonus - 2 |  |  | 2000000 | 2024-02-28
14 | Service Add On | Penalties - December 2023 |  |  | 75000 | 2024-01-31
14 | Service Add On | Penalties - January 2024 |  |  | 75000 | 2024-01-31
Note on F6: Tasneema Van Harte: Jinko: MCSSLB23Q2125
Note on F7: Tasneema Van Harte: Jinko: MCSSLB23Q2125
Note on F10: Thami Cambalele: NETTY CUSTOMS INV IS00014013
Note on F11: Thami Cambalele: SILVER SOLUTIONS INV06105539
Note on F12: Thami Cambalele: SUPPLY CHAIN INV SCO03718
Note on F13: Thami Cambalele: SUPPLY CHAIN INV SCO03718
Note on F15: Thami Cambalele: ISELI INV: CINV008542
Note on F16: Thami Cambalele: ISELI INV: CINV008542
Note on F18: Thami Cambalele: SCHLETTER INV IN109961
Note on F19: Tasneema Van Harte: Schletter Inv: IN109974
Note on F26: Thami Cambalele: Rubicon INVWCRE-0046245
Note on F27: Thami Cambalele: Rubicon INVWCRE-0046245
Note on F28: Thami Cambalele: KRANNICH INV 15-10007341
Note on F29: Thami Cambalele: KRANNICH INV 15-10007341
Note on F30: Tasneema Van Harte: Smart Solar Inv: SUB041P1
Note on F31: Thami Cambalele: SMART SOLAR INV SUB041P2.1
Note on F34: Thami Cambalele: ISELI INV: QEQT01000C
Note on F35: Thami Cambalele: ISELI INV: QEQT01000C
Note on F36: Thami Cambalele: KATHEA INV 517145
Note on F42: Tasneema Van Harte: Takealot - Ord 126946613
Note on F43: Tasneema Van Harte: Otto Inv: IO123446
Note on F44: Tasneema Van Harte: Netty Customs Inv: SOQ284932
Note on F49: Tasneema Van Harte: Smart Solar Inv: SUB041P1
Note on F50: Thami Cambalele: SMART SOLAR INV SUB041P2.2
Note on F51: Tasneema Van Harte: SMART SOLAR INV SUB041P2.2
Note on F53: Tasneema Van Harte: Switchboard Inv: SQ-9190
Note on F54: Tasneema Van Harte: Switchboard Inv: SQ-9190
Note on F55: Tasneema Van Harte: Switchboard Inv: SQ-9190
Note on F56: Thami Cambalele: SWITCHBOARD - INV 2-SOI000216
Note on F60: Tasneema Van Harte: FDT Electrical Inv: 1555
Note on F61: Thami Cambalele: BRICE & CO INV BC/0061
Note on F64: Thami Cambalele: ALL IN GLASS INV0000700
Note on F66: Tasneema Van Harte: Smart Solar Inv: SUB041P1
Note on F67: Thami Cambalele: SMART SOLAR INV SUB040P3
Note on F68: Thami Cambalele: SMART SOLAR INV SUB040P3
Note on F69: Thami Cambalele: SMART SOLAR INV SUB041P5
Note on F70: Thami Cambalele: SMART SOLAR INV SUB041P4
Note on F74: Tasneema Van Harte: Smart Solar Inv: SUB041P1
Note on F75: Thami Cambalele: SMART SOLAR INV SUB041P2.2
Note on F77: Thami Cambalele: SILVER SOLUTIONS INV06105539
Note on F80: Tasneema Van Harte: Spear Inv:4794/202312/1
Note on F81: Tasneema Van Harte: Spear Inv:4794/202311/1
Note on F82: Tasneema Van Harte: Spear Inv: 4794/202310/1
Note on F83: Tasneema Van Harte: Spear Inv: 4794/202308/49750/I
Note on F85: Tasneema Van Harte: L & B Consulting Inv: 1237
Note on F87: Tasneema Van Harte: Spear Reit Limited - Inv 3553/20110/42517
Note on F88: Tasneema Van Harte: Matriarch Inv: 1828

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2023-02-06 to 2025-08-25
PLANNED |  | CHECK | CHECK
| Planned Revenue | 20939008.7697 | 20939008.7697 | 0 | 10469504.3849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5234752.1924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2093900.877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2093900.877 | 0 | 0 | 0 | 0 | 0 | 1046950.4385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 10469504.3849 | 10469504.3849 | 10469504.3849 | 10469504.3849 | 10469504.3849 | 10469504.3849 | 10469504.3849 | 10469504.3849 | 10469504.3849 | 10469504.3849 | 10469504.3849 | 10469504.3849 | 10469504.3849 | 10469504.3849 | 10469504.3849 | 10469504.3849 | 10469504.3849 | 10469504.3849 | 10469504.3849 | 10469504.3849 | 10469504.3849 | 10469504.3849 | 10469504.3849 | 10469504.3849 | 10469504.3849 | 15704256.5773 | 15704256.5773 | 15704256.5773 | 15704256.5773 | 15704256.5773 | 15704256.5773 | 15704256.5773 | 15704256.5773 | 17798157.4543 | 17798157.4543 | 17798157.4543 | 17798157.4543 | 17798157.4543 | 17798157.4543 | 17798157.4543 | 17798157.4543 | 17798157.4543 | 17798157.4543 | 17798157.4543 | 17798157.4543 | 17798157.4543 | 17798157.4543 | 17798157.4543 | 17798157.4543 | 19892058.3312 | 19892058.3312 | 19892058.3312 | 19892058.3312 | 19892058.3312 | 19892058.3312 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697
| Planned Expenditure | 18682949.9513 | 18682949.9513 |  | 0 | 0 | 0 | 897757.5233 | 0 | 0 | 3567 | 0 | 0 | 0 | 0 | 0 | 4530000 | 0 | 0 | 0 | 0 | 961855.329 | 860440.581 | 0 | 0 | 0 | 8268944.229 | 0 | 1041000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1205575.689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249220.8 | 0 | 0 | 0 | 0 | 0 | 498441.6 | 0 | 0 | 0 | 166147.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 897757.5233 | 897757.5233 | 897757.5233 | 901324.5233 | 901324.5233 | 901324.5233 | 901324.5233 | 901324.5233 | 901324.5233 | 5431324.5233 | 5431324.5233 | 5431324.5233 | 5431324.5233 | 5431324.5233 | 6393179.8523 | 7253620.4333 | 7253620.4333 | 7253620.4333 | 7253620.4333 | 15522564.6623 | 15522564.6623 | 16563564.6623 | 16563564.6623 | 16563564.6623 | 16563564.6623 | 16563564.6623 | 16563564.6623 | 16563564.6623 | 16563564.6623 | 16563564.6623 | 17769140.3513 | 17769140.3513 | 17769140.3513 | 17769140.3513 | 17769140.3513 | 17769140.3513 | 17769140.3513 | 17769140.3513 | 17769140.3513 | 18018361.1513 | 18018361.1513 | 18018361.1513 | 18018361.1513 | 18018361.1513 | 18018361.1513 | 18516802.7513 | 18516802.7513 | 18516802.7513 | 18516802.7513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513 | 18682949.9513
| PLANNED CashFlow |  |  | 0 | 10469504.3849 | 10469504.3849 | 10469504.3849 | 9571746.8615 | 9571746.8615 | 9571746.8615 | 9568179.8615 | 9568179.8615 | 9568179.8615 | 9568179.8615 | 9568179.8615 | 9568179.8615 | 5038179.8615 | 5038179.8615 | 5038179.8615 | 5038179.8615 | 5038179.8615 | 4076324.5325 | 3215883.9515 | 3215883.9515 | 3215883.9515 | 3215883.9515 | -5053060.2775 | -5053060.2775 | -6094060.2775 | -859308.085 | -859308.085 | -859308.085 | -859308.085 | -859308.085 | -859308.085 | -859308.085 | -859308.085 | 29017.1029 | 29017.1029 | 29017.1029 | 29017.1029 | 29017.1029 | 29017.1029 | 29017.1029 | 29017.1029 | 29017.1029 | -220203.6971 | -220203.6971 | -220203.6971 | -220203.6971 | -220203.6971 | -220203.6971 | -718645.2971 | 1375255.5799 | 1375255.5799 | 1375255.5799 | 1209108.3799 | 1209108.3799 | 1209108.3799 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184 | 2256058.8184
ACTUAL |  | CHECK | CHECK
| Actual + Forecast Revenue | 20939008.7697 | 20939008.7697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2204986.237 | 1739130.4348 | 6956521.7391 | 3478260.8696 | 1325357.2969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5234752.1924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Forecast Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2204986.237 | 3944116.6717 | 10900638.4109 | 14378899.2804 | 15704256.5773 | 15704256.5773 | 15704256.5773 | 15704256.5773 | 15704256.5773 | 15704256.5773 | 15704256.5773 | 15704256.5773 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697 | 20939008.7697
| Actual + Forecast Expenditure | 19234297.2704 | 18959665.3204 | 0 | 0 | 0 | 0 | 11750 | 0 | 0 | 0 | 0 | 239.13 | 0 | 0 | 0 | 0 | 0 | 3786.92 | 0 | 715.28 | 1529827.7163 | 35597.51 | 5328.39 | 106.72 | 0 | 2969.31 | 5504.78 | 4067.03 | 384410 | 107621.9 | 5016.82 | 893244 | 1724.6 | 0 | 0 | 569013.52 | 1073842.1 | 0 | 0 | 12115.63 | 54384.7 | 139.2 | 298078.86 | 5859.38 | 3104.9 | 196395.02 | 0 | 51220 | 0 | 0 | 0 | 0 | 133278.4617 | 97084.8943 | 3808.76 | 172443.8 | 379626.8243 | 103650.4326 | 948.8 | 0 | 881171.972 | 1644689.39 | 4428130.5902 | 77044.3674 | 275600 | 68.65 | 114695.0438 | 2000208.8 | 14517.2 | 2281640.5739 | -187920.96 | 0 | 0 | 0 | 0 | 153648.08 | 251752.6832 | 0 | 0 | 0 | 0 | 67632.1708 | 0 | -89060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626.88 | 0 | 0 | 0 | 0 | 358.16 | 546904.66 | 0 | 0 | 0 | 3905 | 0 | 0 | 80752.14 | 164.54 | 0 | 30839.11 | 43910.55 | 280.72 | 0 | 0 | 0 | 21905.33 | 0 | 0 | 0 | 136666 | 499.32 | 0 | 0 | 32128.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Forecast Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 11750 | 11750 | 11750 | 11750 | 11750 | 11989.13 | 11989.13 | 11989.13 | 11989.13 | 11989.13 | 11989.13 | 15776.05 | 15776.05 | 16491.33 | 1546319.0463 | 1581916.5563 | 1587244.9463 | 1587351.6663 | 1587351.6663 | 1590320.9763 | 1595825.7563 | 1599892.7863 | 1984302.7863 | 2091924.6863 | 2096941.5063 | 2990185.5063 | 2991910.1063 | 2991910.1063 | 2991910.1063 | 3560923.6263 | 4634765.7263 | 4634765.7263 | 4634765.7263 | 4646881.3563 | 4701266.0563 | 4701405.2563 | 4999484.1163 | 5005343.4963 | 5008448.3963 | 5204843.4163 | 5204843.4163 | 5256063.4163 | 5256063.4163 | 5256063.4163 | 5256063.4163 | 5256063.4163 | 5389341.878 | 5486426.7723 | 5490235.5323 | 5662679.3323 | 6042306.1565 | 6145956.5891 | 6146905.3891 | 6146905.3891 | 7028077.3611 | 8672766.7511 | 13100897.3413 | 13177941.7087 | 13453541.7087 | 13453610.3587 | 13568305.4025 | 15568514.2025 | 15583031.4025 | 17864671.9764 | 17676751.0164 | 17676751.0164 | 17676751.0164 | 17676751.0164 | 17676751.0164 | 17830399.0964 | 18082151.7796 | 18082151.7796 | 18082151.7796 | 18082151.7796 | 18082151.7796 | 18149783.9504 | 18149783.9504 | 18060723.9504 | 18060723.9504 | 18060723.9504 | 18060723.9504 | 18060723.9504 | 18060723.9504 | 18060723.9504 | 18060723.9504 | 18060723.9504 | 18061350.8304 | 18061350.8304 | 18061350.8304 | 18061350.8304 | 18061350.8304 | 18061708.9904 | 18608613.6504 | 18608613.6504 | 18608613.6504 | 18608613.6504 | 18612518.6504 | 18612518.6504 | 18612518.6504 | 18693270.7904 | 18693435.3304 | 18693435.3304 | 18724274.4404 | 18768184.9904 | 18768465.7104 | 18768465.7104 | 18768465.7104 | 18768465.7104 | 18790371.0404 | 18790371.0404 | 18790371.0404 | 18790371.0404 | 18927037.0404 | 18927536.3604 | 18927536.3604 | 18927536.3604 | 18959665.3204 | 18959665.3204 | 18959665.3204 | 18959665.3204 | 18959665.3204 | 18959665.3204 | 18959665.3204 | 18959665.3204 | 18959665.3204 | 18959665.3204 | 18959665.3204 | 18959665.3204 | 18959665.3204 | 18959665.3204
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | -11750 | -11750 | -11750 | -11750 | -11750 | -11989.13 | -11989.13 | -11989.13 | -11989.13 | -11989.13 | -11989.13 | -15776.05 | -15776.05 | -16491.33 | -1546319.0463 | -1581916.5563 | -1587244.9463 | -1587351.6663 | -1587351.6663 | -1590320.9763 | -1595825.7563 | -1599892.7863 | -1984302.7863 | -2091924.6863 | -2096941.5063 | -2990185.5063 | -2991910.1063 | -2991910.1063 | -2991910.1063 | -3560923.6263 | -4634765.7263 | -4634765.7263 | -4634765.7263 | -4646881.3563 | -4701266.0563 | -4701405.2563 | -4999484.1163 | -5005343.4963 | -5008448.3963 | -5204843.4163 | -5204843.4163 | -5256063.4163 | -5256063.4163 | -5256063.4163 | -5256063.4163 | -5256063.4163 | -5389341.878 | -5486426.7723 | -5490235.5323 | -5662679.3323 | -6042306.1565 | -6145956.5891 | -6146905.3891 | -6146905.3891 | -7028077.3611 | -8672766.7511 | -10895911.1043 | -9233825.0369 | -2552903.2978 | 925288.9218 | 2135951.1748 | 135742.3748 | 121225.1748 | -2160415.3991 | -1972494.4391 | -1972494.4391 | -1972494.4391 | -1972494.4391 | 3262257.7533 | 3108609.6733 | 2856856.9901 | 2856856.9901 | 2856856.9901 | 2856856.9901 | 2856856.9901 | 2789224.8193 | 2789224.8193 | 2878284.8193 | 2878284.8193 | 2878284.8193 | 2878284.8193 | 2878284.8193 | 2878284.8193 | 2878284.8193 | 2878284.8193 | 2878284.8193 | 2877657.9393 | 2877657.9393 | 2877657.9393 | 2877657.9393 | 2877657.9393 | 2877299.7793 | 2330395.1193 | 2330395.1193 | 2330395.1193 | 2330395.1193 | 2326490.1193 | 2326490.1193 | 2326490.1193 | 2245737.9793 | 2245573.4393 | 2245573.4393 | 2214734.3293 | 2170823.7793 | 2170543.0593 | 2170543.0593 | 2170543.0593 | 2170543.0593 | 2148637.7293 | 2148637.7293 | 2148637.7293 | 2148637.7293 | 2011971.7293 | 2011472.4093 | 2011472.4093 | 2011472.4093 | 1979343.4493 | 1979343.4493 | 1979343.4493 | 1979343.4493 | 1979343.4493 | 1979343.4493 | 1979343.4493 | 1979343.4493 | 1979343.4493 | 1979343.4493 | 1979343.4493 | 1979343.4493 | 1979343.4493 | 1979343.4493
| Installer Expenditure |  | 2028487.686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730704.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38478 | 0 | 0 | 336444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4300 | 0 | 0 | 206700 | 0 | 0 | 195861.42 | 0 | 40440 | 0 | 0 | 0 | 0 | 86956.5217 | 68464.8943 | 0 | 10838.58 | 0 | 0 | 0 | 0 | 0 | 0 | 33700 | 0 | 275600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Installer Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730704.27 | 730704.27 | 730704.27 | 730704.27 | 730704.27 | 730704.27 | 730704.27 | 730704.27 | 769182.27 | 769182.27 | 769182.27 | 1105626.27 | 1105626.27 | 1105626.27 | 1105626.27 | 1105626.27 | 1105626.27 | 1105626.27 | 1105626.27 | 1109926.27 | 1109926.27 | 1109926.27 | 1316626.27 | 1316626.27 | 1316626.27 | 1512487.69 | 1512487.69 | 1552927.69 | 1552927.69 | 1552927.69 | 1552927.69 | 1552927.69 | 1639884.2117 | 1708349.106 | 1708349.106 | 1719187.686 | 1719187.686 | 1719187.686 | 1719187.686 | 1719187.686 | 1719187.686 | 1719187.686 | 1752887.686 | 1752887.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686 | 2028487.686

## Finance (2)
|  |  | 2023-05-31 | 2023-06-30 | 2023-07-31 | 2023-08-31 | 2023-09-30 | 2023-10-31 | 2023-11-30 | 2023-12-31 | 2024-01-31 | 2024-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-31 | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-03-05
Equipment | 12120842.4166 |  | 239.13 | 8777837.7327 | 532043.58 | 1953116.68 | 0 | 132782.4 | 50665 | 155421.416 | 103542.06 | 110502.75 | 29350 | 12100.49 | 249726.3239 | 102574.854 | 0 | -89060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Installation | 1517100 |  | 0 | 326150 | 0 | 206700 | 0 | 4300 | 206700 | 247140 | 0 | 0 | 309300 | 0 | 0 | 216810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Other Expenses | 5604765.9538 |  | 32528.2 | 3876.62 | 5574.38 | 5086.42 | 1005.16 | 3654.83 | 8758.05 | 739.83 | 152445.91 | 948.8 | 76882.76 | 131222.4938 | 4000000 | 58.08 | 0 | 0 | 0 | 626.88 | 547262.82 | 84657.14 | 38643.2 | 280.72 | 158571.33 | 32628.28 | 0 | 0 |  | 319314.05
| 7121865.9538 |  | 32767.33 | 9107864.3527 | 537617.96 | 2164903.1 | 1005.16 | 140737.23 | 266123.05 | 403301.246 | 255987.97 | 111451.55 | 415532.76 | 143322.9838 | 4249726.3239 | 319442.934 | 0 | -89060 | 0 | 626.88 | 547262.82 | 84657.14 | 38643.2 | 280.72 | 158571.33 | 32628.28 | 0 | 0
Forecasted Expenses |  |  | 6251445.38 | 6251445.38 | 6251445.38 | 6251445.38 | 6251445.38 | 6251445.38 | 6251445.38 | 6251445.38 | 6251445.38 | 6251445.38 | 6251446.38 | 6251447.38 | 6251448.38 | 6251449.38 | 6251450.38 | 6251451.38 | 6251452.38 | 6251453.38 | 6251454.38 | 6251455.38 | 6251456.38 | 6251457.38 | 6251458.38 | 6251459.38 | 6251460.38 | 6251461.38
Proportion of Exp recognised compared to forecasted expense |  |  | 0.5203% | 5.279% | 0.08917% | 3.388% | 0.01608% | 0.1272% | 3.447% | 3.965% | 2.439% | 0.01518% | 6.177% | 2.099% | 63.99% | 3.469% | 0% | 0% | 0% | 0.01003% | 8.754% | 1.354% | 0.6181% | 0.00449% | 2.537% | 0.5219% | 0% | 0%
Forecasted Revenue for Services |  |  | 7849455.8006 | 7849455.8006 | 7849455.8006 | 7849455.8006 | 7849455.8006 | 7849455.8006 | 7849455.8006 | 7849455.8006 | 7849455.8006 | 7849455.8006 | 7849456.8006 | 7849457.8006 | 7849458.8006 | 7849459.8006 | 7849460.8006 | 7849461.8006 | 7849462.8006 | 7849463.8006 | 7849464.8006 | 7849465.8006 | 7849466.8006 | 7849467.8006 | 7849468.8006 | 7849469.8006 | 7849470.8006 | 7849471.8006
Revenue to be recognised | 7849455.8006 |  | 40843.1415 | 414388.8668 | 6999.3172 | 265923.8051 | 1262.1016 | 9988.2639 | 270533.9866 | 311243.5047 | 191414.5225 | 1191.3347 | 484899.7668 | 164765.9119 | 5022489.7166 | 272304.4165 | 0 | 0 | 0 | 787.1245 | 687155.3372 | 106297.3795 | 48521.256 | 352.4782 | 199105.6537 | 40968.7855 | 0 | 0 |  | 6335666.956
Rev Recognised for Panels | 9426585.7561 |  |  | 8880628.2474 |  | 238533.6253 |  |  |  | 307423.8833 | [19 empty] | 0
Rev Recognised for Inverters | 1117464.4343 |  |  |  |  | 1117464.4343 | [23 empty] | 0
Rev Recognised for AC Equipment | 575142.511 |  |  | 215863.0778 | 359279.4333 | [24 empty] | 0
Rev Recognised for DC Equipment | 698421.5818 |  |  | 233641.6667 |  | 301112.693 |  | 116938.8889 | [7 empty] | 46728.3333 | [13 empty] | 0
Rev Recognised for Mounting Structure | 698632.4737 |  |  |  | 698632.4737 | [24 empty] | 0
Rev Recognised for Monitoring | 26914.4596 |  | 265.7 |  | 3299.2333 | [5 empty] | 23349.5262 | [18 empty] | 0
Rev Recognised for Other Equipment (Inverter Cage + Walkways + Warranty Extension) | 546391.7526 |  |  |  | 33050 |  |  |  | 56294.4444 |  |  | 115498.8333 | 32611.1111 |  | 176942.92 | 131994.4444 | [13 empty] | -0.00075601
|  |  | 265.7 | 9330132.9919 | 1094261.1403 | 1657110.7526 | 0 | 116938.8889 | 56294.4444 | 307423.8833 | 23349.5262 | 115498.8333 | 32611.1111 | 0 | 176942.92 | 178722.7778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Allocated to I/S |  |  | 41108.8415 | 9744521.8586 | 1101260.4575 | 1923034.5577 | 1262.1016 | 126927.1528 | 326828.431 | 618667.388 | 214764.0488 | 116690.168 | 517510.8779 | 164765.9119 | 5199432.6366 | 842234.3343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8129083.0509
1007782.3851
Total Revenue |  |  | 20939008.7697
Recognised |  |  | 20939008.7662
0.0034785
SP |  | 100 | 109398.8889
P |  | 10
CP |  | 90 | 98459

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate |  |  |  | FINANCIAL CLOSE CERTIFICATE
Project Name: | Mega Park Extension
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | 1020000 | 0 | 1020000 | 0 | 1020000
Inverters | 1020000
Optimizers | 0
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | 524979 | 0 | 524979 | 0 | 524979
Mounting Structure | 524979
Delivery fee
|  | >Name< |  | >Name<
DC Cable | 330413.76 | 0 | 330413.76 | 0 | 330413.76
DC Cable | 330413.76
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
Solarlog | 21000
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | 280000 | 0 | #REF! | 0 | #REF!
SCADA | 280000
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | >Installer Name 1< |  | Variance | >Installer Name 2< |  | Variance
AC installation | 437482.5 | 0.25 |  | 0 | 437482.5 |  | 0 | 437482.5
AC equipment | 1223989.5 | 0.69945 |  | 0 | 1223989.5 |  | 0 | 1223989.5
DC installation | 637698.258 | 0.36441 |  | 0 | 637698.258 |  | 0 | 637698.258
DC equipment | 307092 | 0.17549 |  | 0 | 307092 |  | 0 | 307092
Storage | 0 |  |  |  | 0 |  |  | 0
Panel lifting equipment | 239766.7 |  |  |  | 239766.7 |  |  | 239766.7
Offloading | 0 |  |  |  | 0 |  |  | 0
Totals | 2846028.958 |  | 0 |  | 2846028.958 | 0 |  | 2846028.958
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | 437482.5 | 0.25 |  | 0 | 437482.5 |  | 0 | 437482.5
AC equipment | 637698.258 | 0.36441 |  |  | 637698.258 |  | 0 | 1223989.5
DC installation | 1223989.5 | 0.69945 |  | 0 | 1223989.5 |  | 0 | 637698.258
DC equipment | 307092 | 0.17549 |  |  | 307092 |  |  | 307092
Storage | 0 |  |  |  | 0 |  |  | 0
Panel lifting equipment | 239766.7 |  |  |  | 239766.7 |  |  | 239766.7
Offloading | 0 |  |  |  | 0 |  |  | 0
Totals | 2846028.958 |  | 0 |  | 2846028.958 | 0 |  | 2846028.958
Budget Summary
Budget | 2846028.958
>Installer Name 1< | 0
>Installer Name 2< | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
Loss | 2846028.958
All amounts are exc VAT

## Decision Register (hidden)
Mega Park Extension |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Mega Park Extension | 0 | 0 | 0