## Tasks
Engineering
OPERATIONAL SITES
Task Type | Task ID | Task Name | Parent ID | Parent Name | Parent URL | Status | Task Content | Assignee | Priority | Latest Comment | Comment Count | Assigned Comment Count | Due Date | Start Date | Date Created | Date Updated | Date Closed | Date Done | Created By | Space | Folder | List | Subtask ID's | Subtask URL's | tags | Lists | Sprints | Linked Tasks | Linked Docs | Time Logged | Time Logged Rolled Up | Time Estimate | Time Estimate Rolled Up | Time In Status | Points Estimate | Points Estimate Rolled Up | Approval Signature (signature) | Completion % (automatic progress) | STAGE (drop down) | Site (labels) | Site (short text) | Summary (text) | TRACKING (drop down) | Task Name (text)
Task | 86c4cq20w | Gezina Galleries |  |  |  | OPERATIONAL SITES |  | johan snyman |  | Please remove the circuit breaker here as it is only a signal, and show a relay N/O at the generator switching said signal | 2 | 0 | 2026-02-25 |  | 2025-07-08 19:44 | 2026-02-06 10:06 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 506 hours |  | 0 |  | 100% |  | Gezina Galleries |  |  | Green
Task | 86c6ywwve | Riverside Mall - Project Engineering |  |  |  | OPERATIONAL SITES |  | Gerhard |  | Hi @Paul Dreyer @Gerhard @Mary Boakye , when can we have the updated/latest Techsitter Target File for * Riverside Mall * as this is needed when ordering the meters? | 8 | 0 | 2026-02-26 |  | 2025-12-08 09:42 | 2026-02-20 10:50 |  |  | Gerhard | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 816 hours |  | 0 |  | 100% |  | Riverside Mall |  | - Project for Riverside Mall assigned to [@Gerhard](#88690613). - Status is 'to do' and progress is at 0%. - Due by 12/12/2025 02:00 AM (UTC). | Green
Task | 86c82g6pe | Meraki PH3 |  |  |  | OPERATIONAL SITES |  | johan snyman, Dean Cornelius |  | @johan snyman you can send the EP to LLoyd | 2 | 0 | 2026-02-27 |  | 2026-02-06 08:44 | 2026-02-16 10:05 |  |  | johan snyman | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 195 hours |  | 0 |  | 0% |  | Meraki Ph3 |  | - [@johan snyman](#100552512) is working on this project. - Status is in progress, but 0% is done so far. - Due date was 02/06/2026 at 02:00 AM UTC. | Green
Task | 86c6yvmzu | 7th Avenue - Project Engineering |  |  |  | OPERATIONAL SITES |  | Gerhard |  | Hi @Paul Dreyer @Gerhard @Mary Boakye , when can we have the updated/latest Techsitter Target File for 7th Avenue Park as this is needed when ordering the meters? | 13 | 0 | 2026-03-03 |  | 2025-12-08 07:11 | 2026-02-20 11:15 |  |  | Gerhard | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 664 hours |  | 0 |  | 100% |  | 7th Avenue |  | - Project for 7th Avenue assigned to [@Brandon Watts](#88690611) and [@Gerhard](#88690613). - Due by 12/12/2025 02:00 AM (UTC). - Current progress is 0%. - No comments or updates yet. | Green
Task | 86c7gq4gp | TopSteel - Project Engineering |  |  |  | OPERATIONAL SITES |  | Gerhard |  | @Gerhard when can we have the updated/latest Techsitter Targets File as this is needed when ordering the meters? | 3 | 0 | 2026-03-03 |  | 2026-01-12 09:51 | 2026-02-11 21:20 |  |  | Gerhard | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 534 hours |  | 0 |  | 100% |  | Top Steel |  | - Project for Top Steel is in progress. - Assigned to [@Gerhard](#88690613). - Due by 01/16/2026 02:00 AM (UTC). - Progress is at 0%. | Green
Task | 86c425wba | Steelpark |  |  |  | OPERATIONAL SITES |  | Gerhard |  | @Gerhard when can we have the updated/latest Techsitter Targets File as this is needed when ordering the meters? | 21 | 0 | 2026-03-13 |  | 2025-06-18 07:42 | 2026-02-11 21:18 |  |  | Gerhard | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 334 hours |  | 0 |  | 100% |  | Steelpark |  |  | Green
Task | 86c4a4x3g | Marikana Shoprite |  |  |  | OPERATIONAL SITES |  | johan snyman |  | @johan snyman do is this still in progress? Do you require support? | 4 | 0 |  |  | 2025-07-03 12:40 | 2026-01-14 09:50 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 1133 hours |  | 0 |  | 100% |  | Marikana Shoprite |  |  | Green
Task | 86c59z4z0 | BMG Fluid Tech |  |  |  | OPERATIONAL SITES |  | johan snyman |  | ╕±╖ⁿ╢≈-GIV0250-NRS Report.pdf NRS-2017_150T_250T.pdf @Keith Abdulla please see attached the NRS documents as sent on Whatsapp. Let me know if you need anything else | 9 | 0 |  |  | 2025-09-03 08:50 | 2026-02-13 10:06 |  |  | Keith Abdulla | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 2547 hours |  | 0 |  | 100% |  | BMG Fluid Tech |  |  | Green
Task | 86c59awuz | Coega Steel Phase 2 |  |  |  | OPERATIONAL SITES |  | Dean Cornelius |  | DSP-HWE-PVA-EP-MST-003-0A_Rev02.pdf JUPITER-(3000K, 6000K, 9000K)-H1 Smart Transformer Station Installation Guide (with Built-In SACU).pdf FusionSolar8.0 Solution Overview v1.0-202308.pdf | 4 | 0 |  |  | 2025-09-02 08:49 | 2025-12-10 10:01 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 2547 hours |  | 0 |  | 100% |  | Coega Steel |  |  | Green
Task | 86c4cq240 | Pretoria North |  |  |  | OPERATIONAL SITES |  | johan snyman |  |  | 0 | 0 |  |  | 2025-07-08 19:45 | 2026-02-13 10:06 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 2547 hours |  | 0 |  | 0% |  | Shoprite Pretoria North |  |  | Green
Task | 86c4mwwpx | Malvern Engineering |  |  |  | OPERATIONAL SITES |  | johan snyman |  | @Dean Cornelius Hi Dean, updated the EP to show the new inverter location and TIE-IN point. Will share the document. Had to update the DC cable trays and earthing. | 14 | 0 |  |  | 2025-07-22 10:30 | 2025-12-10 10:01 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 2547 hours |  | 0 |  | 100% |  | Malvern Engineering |  |  | Green
Task | 86c5hqzbj | Dipula - Seshego Circle |  |  |  | OPERATIONAL SITES |  | johan snyman |  | @johan snyman , can you please upload the latest EP and PVSOL and remove the old versions | 17 | 0 |  |  | 2025-09-17 14:44 | 2025-12-15 10:12 |  |  | Gerhard | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 1998 hours |  | 0 |  | 100% |  | seshego cicle |  |  | Green
Task | 86c1kz25n | Superspar Despatch |  |  |  | OPERATIONAL SITES |  | johan snyman |  | @johan snyman @Dean Cornelius please confirm when the As-built EP will be available | 24 | 0 |  |  | 2025-01-13 13:06 | 2026-02-23 09:33 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering | 86c8dzwjc | https://app.clickup.com/t/86c8dzwjc |  | Engineering | [7 empty] | 1875 hours |  | 0 |  | 66.67% |  | Superspar Despatch PH 2 |  |  | Green
Task | 86c5dq063 | BMG Fluid Tech |  |  |  | OPERATIONAL SITES |  | johan snyman |  | @Dean Cornelius updated it now and attached the image | 8 | 0 |  |  | 2025-09-10 07:12 | 2026-02-13 08:16 |  |  | johan snyman | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 269 hours |  | 0 |  | 0% |  | BMG Fluid Tech |  | - [@johan snyman](#100552512) shared the SLD file and asked [@Dean Cornelius](#88707129) for feedback. - [@Dean Cornelius](#88707129) confirmed the design is good and asked about site constraints. - [@johan snyman](#100552512) confirmed constraints were considered and explained the tie breaker placement. - Task marked 100% complete and status is 'complete' as of 09/15/2025. | Green
Task | 86c4cq2bf | Tsakane Corner |  |  |  | OPERATIONAL SITES |  | johan snyman |  | Hi @Dean Cornelius uploaded the as build. I will load everything into the handover folders once completed. Let me know if I need to change anything. | 1 | 0 |  |  | 2025-07-08 19:45 | 2026-02-13 11:16 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 266 hours |  | 0 |  | 100% |  | Tsakane Corner |  |  | Green
PROVIDE FEEDBACK
Task Type | Task ID | Task Name | Parent ID | Parent Name | Parent URL | Status | Task Content | Assignee | Priority | Latest Comment | Comment Count | Assigned Comment Count | Due Date | Start Date | Date Created | Date Updated | Date Closed | Date Done | Created By | Space | Folder | List | Subtask ID's | Subtask URL's | tags | Lists | Sprints | Linked Tasks | Linked Docs | Time Logged | Time Logged Rolled Up | Time Estimate | Time Estimate Rolled Up | Time In Status | Points Estimate | Points Estimate Rolled Up | Approval Signature (signature) | Completion % (automatic progress) | STAGE (drop down) | Site (labels) | Site (short text) | Summary (text) | TRACKING (drop down) | Task Name (text)
Task | 86c5z0m0m | Mahikeng - Builders Express |  |  |  | PROVIDE FEEDBACK |  | johan snyman, Dean Cornelius |  | @Dean Cornelius Uploaded the as build with change as received from site. | 7 | 0 | 2026-02-25 |  | 2025-10-13 14:34 | 2026-02-24 12:26 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering | 86c8d3bbd | https://app.clickup.com/t/86c8d3bbd |  | Engineering | [7 empty] | 1 hours |  | 0 | Dean Cornelius | 90% |  | Mahikeng |  |  | Green
Task | 86c8dz47d | Stringing updates on EP | 86c6h1pvp | Randfontein Commissioning checks | https://app.clickup.com/t/86c6h1pvp | PROVIDE FEEDBACK |  | johan snyman |  | @johan snyman please note this ticket | 1 | 0 | 2026-02-25 |  | 2026-02-24 08:49 | 2026-02-24 12:43 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 1 hours |  | 0 |  | 0% |  | Randfontein Station |  | - [@johan snyman](#100552512) assigned. - Progress is 0%. - Due by 02/25/2026 02:00 AM UTC. - Site: Randfontein Station. - Status: to do.
Task | 86c7jq33x | Review PV Reports from Matriarch |  |  |  | PROVIDE FEEDBACK |  | Paul Dreyer |  |  | 0 | 0 | 2026-03-31 |  | 2026-01-14 12:05 | 2026-02-20 10:01 |  |  | Paul Dreyer | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 771 hours |  | 0 |  | 0% |  | Engineering Internal |  | - Review PV reports from Matriarch for Engineering Internal. - Due by 01/16/2026 02:00 AM (UTC). - Status is to do, 0% complete. - No users assigned yet. | Green
Task | 86c8auz9j | Swellengrebel | 86c6h1p1a | Commissioning QC | https://app.clickup.com/t/86c6h1p1a | PROVIDE FEEDBACK |  | Kashmil Samuel, Dean Cornelius | LOW |  | 0 | 0 | 2026-04-03 |  | 2026-02-19 08:53 | 2026-02-23 07:29 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 30 hours |  | 0 |  | 0% |  | Swellengrebel |  | - Part of 'Commissioning QC' for Swellengrebel site. - Progress is at 0%. - Due by 04/03/2026 02:00 AM UTC. - No assignees or comments yet.
QC APPROVED
Task Type | Task ID | Task Name | Parent ID | Parent Name | Parent URL | Status | Task Content | Assignee | Priority | Latest Comment | Comment Count | Assigned Comment Count | Due Date | Start Date | Date Created | Date Updated | Date Closed | Date Done | Created By | Space | Folder | List | Subtask ID's | Subtask URL's | tags | Lists | Sprints | Linked Tasks | Linked Docs | Time Logged | Time Logged Rolled Up | Time Estimate | Time Estimate Rolled Up | Time In Status | Points Estimate | Points Estimate Rolled Up | Approval Signature (signature) | Completion % (automatic progress) | STAGE (drop down) | Site (labels) | Site (short text) | Summary (text) | TRACKING (drop down) | Task Name (text)
Task | 86c6ccnc9 | Inverter room requires cooling/ventilation |  |  |  | QC APPROVED | Portfolio: Dipula PV Phase 1 Site: Black Heath Range Road Category: Critical Discipline: Inverter room environment Snag/Issue: Inverter room requires cooling/ventilation Next Step: Room ventilation cooling assessment Date raised: 2025-10-29 Verified by: V3 Source ID: BLA-013 | Peet Verreynnne | URGENT | Black Heath Range Road_Heatload_calculations_APPROVED.pdf @Dean Cornelius please review and forward to Justin, I opted for the ventilation route. Note these calculations assume we remove 1 of the inverters from the room as per my previous comments on the changes required to match OEM specs | 5 | 0 | 2025-12-04 |  | 2025-10-29 | 2026-01-26 15:25 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 1946 hours |  | 0 |  | 0% | QA | BlackHeath | Black Heath Range Road |  | Green | BLA-013 – Black Heath Range Road – Inverter room environment – Inverter room requires cooling/ventilation
Task | 86c86hf87 | GQ Fresh Produce + Cost Proposal - Word Template |  |  |  | QC APPROVED |  | Mary Boakye, Tanaka Zimuto |  |  | 0 | 0 | 2026-02-23 |  | 2026-02-12 10:42 | 2026-02-24 07:49 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 6 hours |  | 0 |  | 0% |  |  |  | - Project is in 'to do' status, not started yet. - Progress is at 0%. - No comments or subtasks added so far.
NEEDS APROVAL
Task Type | Task ID | Task Name | Parent ID | Parent Name | Parent URL | Status | Task Content | Assignee | Priority | Latest Comment | Comment Count | Assigned Comment Count | Due Date | Start Date | Date Created | Date Updated | Date Closed | Date Done | Created By | Space | Folder | List | Subtask ID's | Subtask URL's | tags | Lists | Sprints | Linked Tasks | Linked Docs | Time Logged | Time Logged Rolled Up | Time Estimate | Time Estimate Rolled Up | Time In Status | Points Estimate | Points Estimate Rolled Up | Approval Signature (signature) | Completion % (automatic progress) | STAGE (drop down) | Site (labels) | Site (short text) | Summary (text) | TRACKING (drop down) | Task Name (text)
Task | 86c6xxubf | 6th Avenue Shopping Centre + Cost Proposal - Word Template |  |  |  | NEEDS APROVAL |  | Brandon Watts, Tanaka Zimuto |  | Waiting on client to confirm system size. | 1 | 0 | 2026-02-19 |  | 2025-12-05 12:36 | 2026-02-20 10:06 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 99 hours |  | 0 |  | 0% |  | 6th Avenue |  | - Project is at 0% progress and has not started yet. - Status is 'to do'. - No updates, comments, or subtasks added. - No users assigned. | Green
Task | 86c877mg6 | PnP Bethal - GA |  |  |  | NEEDS APROVAL |  | Brandon Watts |  |  | 0 | 0 | 2026-02-25 |  | 2026-02-13 10:10 | 2026-02-24 10:25 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 3 hours |  | 0 |  | 0% |  | PnP Bethal |  | - [@Brandon Watts](#88690611) is assigned. - Site: PnP Bethal. - Progress is at 0%. - Status is to do. | Green
HOLD
Task Type | Task ID | Task Name | Parent ID | Parent Name | Parent URL | Status | Task Content | Assignee | Priority | Latest Comment | Comment Count | Assigned Comment Count | Due Date | Start Date | Date Created | Date Updated | Date Closed | Date Done | Created By | Space | Folder | List | Subtask ID's | Subtask URL's | tags | Lists | Sprints | Linked Tasks | Linked Docs | Time Logged | Time Logged Rolled Up | Time Estimate | Time Estimate Rolled Up | Time In Status | Points Estimate | Points Estimate Rolled Up | Approval Signature (signature) | Completion % (automatic progress) | STAGE (drop down) | Site (labels) | Site (short text) | Summary (text) | TRACKING (drop down) | Task Name (text)
Task | 86c7kd6yx | Superspar Despatch Ph2 | 86c6h1p1a | Commissioning QC | https://app.clickup.com/t/86c6h1p1a | HOLD |  | Dean Cornelius, Peet Verreynnne | URGENT | @Peet Verreynnne all form of checks and results outstanding. This site has been done for 2 weeks, please put some pressure on like you do best. | 2 | 0 | 2026-02-25 |  | 2026-01-15 09:27 | 2026-02-23 10:25 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 150 hours |  | 0 |  | 0% |  | Superspar Despatch PH 2 |  | - [@Kashmil Samuel](#88702296) and [@Dean Cornelius](#88707129) are assigned. - Status is to do, progress is 0%. - Due by 01/30/2026 02:00 AM UTC. - Priority is Normal. | Green
Task | 86c0p6bwe | Mega Park SCADA |  |  |  | HOLD |  | Dean Cornelius, Keith Abdulla, Roedolph |  | RTU installed. Awaiting De Cock & Cronje + Spear to install new relays. They are holding op the SSEG progress now. | 43 | 0 | 2026-02-27 | 2025-08-04 | 2024-10-16 08:03 | 2026-02-02 07:58 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering | 86c14rfxn | https://app.clickup.com/t/86c14rfxn |  | Engineering | [7 empty] | 3124 hours |  | 0 |  | 90% |  | Mega Park |  |  | Green
Task | 86c6j4j3a | BMG Fluid tech | 86c6h1p1a | Commissioning QC | https://app.clickup.com/t/86c6h1p1a | HOLD |  | Dean Cornelius, Peet Verreynnne | URGENT | Still 2 snags outstanding | 6 | 0 | 2026-02-27 |  | 2025-11-17 09:29 | 2026-02-23 08:44 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 1517 hours |  | 0 |  | 0% |  | BMG Fluid Tech |  | - [@Kashmil Samuel](#88702296) and [@Dean Cornelius](#88707129) are assigned. - Due by 11/21/2025 02:00 AM UTC. - Progress is at 0%. - Status is to do. | Green
Task | 86c14rfxn | Activate SCADA with COCT | 86c0p6bwe | Mega Park SCADA | https://app.clickup.com/t/86c0p6bwe | HOLD |  | Dean Cornelius, Keith Abdulla | URGENT |  | 0 | 0 | 2026-02-27 | 2025-03-27 | 2024-11-25 18:32 | 2026-02-02 07:58 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 987 hours |  | 0 |  | 0% |  | Mega Park |  |  | Green
Task | 86c5kyx4z | Mondi Water flow and pressure calcs |  |  |  | HOLD | Use the site development plan to calculate where the best water flow points need to be to ensure that effective cleaning is happening. (show where we tie - in the layout of how water will flow with pressure, for each of the equipment that is going to be used) | Gerhard |  | @Johannes Potgieter please setup session to unblock | 5 | 0 | 2026-02-27 |  | 2025-09-22 14:36 | 2026-02-02 10:08 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 868 hours |  | 0 |  | 100% |  | Mondi |  |  | Green
Task | 86c6h1prd | Pimville Commissioning checks | 86c6h1p1a | Commissioning QC | https://app.clickup.com/t/86c6h1p1a | HOLD |  | Dean Cornelius, Peet Verreynnne | URGENT | Snag report not done correctly - marked in yellow where intervention is needed. | 4 | 0 | 2026-02-27 |  | 2025-11-14 07:04 | 2026-02-24 09:18 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 272 hours |  | 0 |  | 0% |  | Pimville |  | - Location: Pimville. - Assigned to [@Kashmil Samuel](#88702296) and [@Dean Cornelius](#88707129). - Due by 11/28/2025. Progress is 0%. - Status: to do. Priority: normal. | Green
Task | 86c7ngbzb | Case study to determine accurate irradiance model |  |  |  | HOLD | Request by Dayne: Evaluation of nearby sites currently operating to be compared to PVSol models on various weather models to determine most accurate model. We will start with Cape Town sites. | Paul Dreyer | LOW |  | 0 | 0 | 2026-02-27 |  | 2026-01-19 09:54 | 2026-02-18 10:03 |  |  | Paul Dreyer | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 196 hours |  | 0 |  | 0% |  | Engineering Internal |  | - [@Paul Dreyer](#106514301) will compare data from Cape Town sites to PVSol models using different weather models. - Goal is to find the most accurate irradiance model. - Work has not started yet (0% complete). - Status is 'to do'. | Green
Task | 86c6h1pay | Dobson Point Commissioning checks | 86c6h1p1a | Commissioning QC | https://app.clickup.com/t/86c6h1p1a | HOLD |  | Dean Cornelius, Peet Verreynnne | URGENT | As-built engineering pack stringing to be rectified Snags to be completed | 6 | 0 | 2026-02-27 |  | 2025-11-14 07:00 | 2026-02-23 07:37 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 171 hours |  | 0 |  | 0% |  | Dobson Point |  | - Assigned to [@Kashmil Samuel](#88702296) and [@Dean Cornelius](#88707129). - Site: Dobson Point. Progress: 0%. - Due by 11/27/2025 02:00 AM UTC. Status: to do. - Priority: Normal. No comments or subtasks yet. | Green
Task | 86c6h1q40 | Tsakane Corner Commissioning checks | 86c6h1p1a | Commissioning QC | https://app.clickup.com/t/86c6h1p1a | HOLD |  | Dean Cornelius, Peet Verreynnne | URGENT | No snags published | 3 | 0 | 2026-02-27 |  | 2025-11-14 07:10 | 2026-02-23 08:42 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 125 hours |  | 0 |  | 0% |  | Tsakane Corner |  | - Assigned to [@Kashmil Samuel](#88702296) and [@Dean Cornelius](#88707129). - Due by 12/18/2025. Status is to do. Priority is normal. - Progress is at 0%. - Site: Tsakane Corner. | Green
Task | 86c7jkj33 | DC SLD | 86c7gptuv | Swellengrebel - Project Engineering | https://app.clickup.com/t/86c7gptuv | HOLD |  | Brandon Watts |  |  | 0 | 0 | 2026-02-27 |  | 2026-01-14 10:52 | 2026-02-20 10:06 |  |  | Gerhard | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 99 hours |  | 0 |  | 0% |  | Swellengrebel |  | - Assigned to [@Brandon Watts](#88690611). - Due by 01/21/2026 02:00 AM UTC. - Location: Swellengrebel. - Progress is at 0%. - Status is to do. | Green
Task | 86c7jknqv | EP Layouts | 86c7gptuv | Swellengrebel - Project Engineering | https://app.clickup.com/t/86c7gptuv | HOLD |  | Brandon Watts |  |  | 0 | 0 | 2026-02-27 |  | 2026-01-14 10:55 | 2026-02-20 10:07 |  |  | Gerhard | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 99 hours |  | 0 |  | 0% |  | Swellengrebel |  | - [@Brandon Watts](#88690611) is assigned. - Site: Swellengrebel. - Progress is at 0%. - Due date is 01/21/2026. - Status is to do. | Green
Task | 86c7jkpnc | PVSol updates | 86c7gptuv | Swellengrebel - Project Engineering | https://app.clickup.com/t/86c7gptuv | HOLD |  | Brandon Watts |  | Please confirm if the PVSol Matches the assigned panel on the tracker. | 1 | 0 | 2026-02-27 |  | 2026-01-14 10:56 | 2026-02-20 10:07 |  |  | Gerhard | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 99 hours |  | 0 |  | 0% |  | Swellengrebel |  | - Assigned to [@Brandon Watts](#88690611). - Due by Jan 21, 2026. - Site: Swellengrebel. - Progress is 0%. Status: to do. | Green
Task | 86c6p8pdg | SLD updates | 86c3c9ua1 | Upper East Side Hotel | https://app.clickup.com/t/86c3c9ua1 | HOLD |  | Gerhard |  | more info required ( site visit) | 5 | 0 | 2026-02-27 |  | 2025-11-24 11:17 | 2026-02-22 18:32 |  |  | Gerhard | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 95 hours |  | 0 |  | 0% |  | Upper East Side Hotel |  | - Site: Upper East Side Hotel - Progress: 0% - Status: to do - No updates or comments yet | Green
Task | 86c3c9ua1 | Upper East Side Hotel |  |  |  | HOLD |  | Gerhard |  | @Gerhard , as per Sandile from CoCT, we need to specify the cable length, type from TX1, TX2 going into our MDB’s. Including all cable lengths that needs to be confirmed in our internal reticulation on SLD. | 16 | 0 | 2026-02-27 |  | 2025-05-05 11:17 | 2026-02-23 08:40 |  |  | Gerhard | Emergent Energy | Engineering | Engineering | 86c6p8pdg | https://app.clickup.com/t/86c6p8pdg |  | Engineering | [7 empty] | 29 hours |  | 0 |  | 85.71% |  | Upper East Side Hotel |  |  | Green
Task | 86c6h1q1u | Sibassa Commissioning checks | 86c6h1p1a | Commissioning QC | https://app.clickup.com/t/86c6h1p1a | HOLD |  | Dean Cornelius, Peet Verreynnne | URGENT | Snags outstanding - tbc | 4 | 0 | 2026-02-27 |  | 2025-11-14 07:09 | 2026-02-23 08:42 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 29 hours |  | 0 |  | 0% |  | Shoprite Sibasa |  | - [@Kashmil Samuel](#88702296) and [@Dean Cornelius](#88707129) are assigned. - Site: Shoprite Sibasa. - Progress is 0%. - Due by 12/18/2025. Status: to do. | Green
Task | 86c6h1pvp | Randfontein Commissioning checks | 86c6h1p1a | Commissioning QC | https://app.clickup.com/t/86c6h1p1a | HOLD |  | Dean Cornelius, Peet Verreynnne | URGENT | I'll upload everything to the handover folder | 4 | 0 | 2026-02-27 |  | 2025-11-14 07:05 | 2026-02-24 11:06 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 5 hours |  | 0 |  | 0% |  | Randfontein Station |  | - [@Kashmil Samuel](#88702296) and [@Dean Cornelius](#88707129) are assigned. - Location: Randfontein Station. - Progress is at 0%. - Due by 12/15/2025 02:00 AM UTC. - Status: to do. | Green
Task | 86c83qhky | Mayo Macs | 86c6h1p1a | Commissioning QC | https://app.clickup.com/t/86c6h1p1a | HOLD |  | Dean Cornelius, Peet Verreynnne | URGENT | Full retest to be done before we can sign off. | 6 | 0 | 2026-03-04 |  | 2026-02-09 07:44 | 2026-02-24 09:23 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 335 hours |  | 0 |  | 0% |  | Mayo Macs |  | - High priority, due by 02/13/2026 02:00 AM UTC. - Assigned to [@Kashmil Samuel](#88702296) and [@Dean Cornelius](#88707129). - Progress is at 0%. Status: to do. - No comments or subtasks. | Green
Task | 86c6xvnmb | Check via site visit if EP for review will work, or make notes accordingly | 86c6e8hk0 | De Drift | https://app.clickup.com/t/86c6e8hk0 | HOLD |  | Gerhard |  |  | 0 | 0 | 2026-03-23 |  | 2025-12-05 11:32 | 2026-02-06 10:15 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 627 hours |  | 0 |  | 0% |  | De Drift |  | - [@Gerhard](#88690613) needs to visit De Drift site to check if EP for review will work or make notes. - Status is to do, 0% complete, due by 12/12/2025. - No comments or updates yet. | Green
Task | 86c7fjp9k | AC DB GA QC | 86c6f8yy1 | M5 Freeway Park | https://app.clickup.com/t/86c6f8yy1 | HOLD |  | Gerhard |  |  | 0 | 0 | 2026-03-26 |  | 2026-01-09 13:47 | 2026-01-23 10:07 |  |  | Gerhard | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 867 hours |  | 0 |  | 0% |  | M5 Freeway Park |  | - Assigned to [@Gerhard](#88690613). - Location: M5 Freeway Park. - Progress: 0%. - Due by 01/09/2026 02:00 AM UTC. - Status: to do. | Green
Task | 86c7gptuv | Swellengrebel - Project Engineering |  |  |  | HOLD |  | Brandon Watts, johan snyman |  | @Roedolph do we have modules for this site yet? | 2 | 0 | 2026-03-30 |  | 2026-01-12 09:39 | 2026-02-19 14:48 |  |  | Gerhard | Emergent Energy | Engineering | Engineering | 86c7jkj33 86c7jknqv 86c7jkpnc | https://app.clickup.com/t/86c7jkj33 https://app.clickup.com/t/86c7jknqv https://app.clickup.com/t/86c7jkpnc |  | Engineering | [7 empty] | 123 hours |  | 0 |  | 50% |  | Swellengrebel |  | - [@Brandon Watts](#88690611) and [@johan snyman](#100552512) are assigned. Status is on hold, 50% complete, and Priority is Green. - Recent comments from [@Dean Cornelius](#88707129) and [@Brandon Watts](#88690611) ask about module confirmation; waiting for update from [@Roedolph](#82664963). - Closed subtasks: AC DB GA QC, COMMS DB GA QC, and AC COMMS SLD. Open subtasks: DC SLD, EP Layouts, and PVSol updates, all assigned to [@Brandon Watts](#88690611) and due soon. | Green
Task | 86c6f924g | Create EP | 86c6f8yy1 | M5 Freeway Park | https://app.clickup.com/t/86c6f8yy1 | HOLD |  | Brandon Watts |  |  | 0 | 0 | 2026-03-31 |  | 2025-11-11 13:48 | 2026-01-08 08:27 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 1876 hours |  | 0 |  | 0% |  | M5 Freeway Park |  | - Assigned to [@Gerhard](#88690613). - Due by 11/18/2025 at 2:00 AM (UTC). - Site: M5 Freeway Park. Status: to do, 0% complete. - No comments or updates yet. | Green
Task | 86c6f8yy1 | M5 Freeway Park |  |  |  | HOLD |  | Brandon Watts |  | PVSol completed | 3 | 0 | 2026-03-31 |  | 2025-11-11 13:44 | 2026-01-19 10:15 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering | 86c6f924g 86c7fjp9k | https://app.clickup.com/t/86c6f924g https://app.clickup.com/t/86c7fjp9k |  | Engineering | [7 empty] | 867 hours |  | 0 |  | 60% |  | M5 Freeway Park |  | - Project is called M5 Freeway Park. - Status is to do, with 0% completed. - Due date is 11/21/2025 at 2:00 AM (UTC). - No updates or comments from users like [@Dean Cornelius](#88707129). | Green
Task | 86c82g6w0 | 25 Superior Road |  |  |  | HOLD |  | johan snyman |  |  | 0 | 0 |  |  | 2026-02-06 08:45 | 2026-02-12 15:17 |  |  | johan snyman | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 286 hours |  | 0 |  | 0% |  | 25 Superior |  | - Project for 25 Superior Road is in progress. - Assigned to [@johan snyman](#100552512). - Due by 02/10/2026 02:00 AM (UTC). - Progress is at 0%.
IN PROGRESS
Task Type | Task ID | Task Name | Parent ID | Parent Name | Parent URL | Status | Task Content | Assignee | Priority | Latest Comment | Comment Count | Assigned Comment Count | Due Date | Start Date | Date Created | Date Updated | Date Closed | Date Done | Created By | Space | Folder | List | Subtask ID's | Subtask URL's | tags | Lists | Sprints | Linked Tasks | Linked Docs | Time Logged | Time Logged Rolled Up | Time Estimate | Time Estimate Rolled Up | Time In Status | Points Estimate | Points Estimate Rolled Up | Approval Signature (signature) | Completion % (automatic progress) | STAGE (drop down) | Site (labels) | Site (short text) | Summary (text) | TRACKING (drop down) | Task Name (text)
Task | 86c6j5vtp | PNP Bethal - Project Engineering |  |  |  | IN PROGRESS |  | johan snyman |  | image.png @johan snyman please see my notes here. Please inquire about the 2 inverters and if they will be in one location or 2 (combined back-up or seperate) Also see that both inverters will need their own battery set with a combiner box. There will be a comms wire from each battery set to the inverter. | 4 | 0 | 2026-02-24 |  | 2025-11-17 10:34 | 2026-02-24 12:47 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering | 86c8e37zm 86c8e38cx | https://app.clickup.com/t/86c8e37zm https://app.clickup.com/t/86c8e38cx |  | Engineering | [7 empty] | 531 hours |  | 0 |  | 33.33% |  | PnP Bethal |  | - Site visit and report for PNP Bethal planned. - Progress is at 0%. - Status is 'to do'. - No updates or comments yet. | Green
Task | 86c8d2zy5 | Update EP to as-built | 86c6h1q1u | Sibassa Commissioning checks | https://app.clickup.com/t/86c6h1q1u | IN PROGRESS |  | johan snyman |  |  | 0 | 0 | 2026-02-24 |  | 2026-02-23 08:23 | 2026-02-23 10:09 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 28 hours |  | 0 |  | 0% |  | Shoprite Sibasa |  | - Assigned to [@johan snyman](#100552512). - Due by 02/24/2026 02:00 AM UTC. - Progress is at 0%. - Site: Shoprite Sibasa. | Green
Task | 86c8d32mf | Inspect EP according to notes | 86c6h1q40 | Tsakane Corner Commissioning checks | https://app.clickup.com/t/86c6h1q40 | IN PROGRESS |  | johan snyman |  | image.png @johan snyman I see these notes are made in Tsakane's inspection form, please investigate and let me know if it is correct or if we have to make ammendments. | 1 | 0 | 2026-02-24 |  | 2026-02-23 08:38 | 2026-02-23 10:09 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 28 hours |  | 0 |  | 0% |  | Tsakane Corner |  | - [@johan snyman](#100552512) needs to inspect EP at Tsakane Corner. - Due by 02/24/2026 02:00 AM UTC. - Progress is at 0%. - Status is to do. | Green
Task | 86c8dyyj8 | Provide updated IP configuration and full network diagram | 86c8dyycz | Red Rocket final closeout | https://app.clickup.com/t/86c8dyycz | IN PROGRESS |  | Paul Dreyer |  |  | 0 | 0 | 2026-02-24 |  | 2026-02-24 08:22 | 2026-02-24 08:22 |  |  | Paul Dreyer | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 5 hours |  | 0 |  | 0% |  | Red Rocket |  | - [@Paul Dreyer](#106514301) assigned to update IP configuration and network diagram for Red Rocket. - No progress made yet (0% complete). - Status is to do, no comments or subtasks.
Task | 86c7nf5vb | Fairlands Spar Expansion + First Assessment - PowerPoint Template |  |  |  | IN PROGRESS |  | Mary Boakye |  |  | 0 | 0 | 2026-02-25 |  | 2026-01-19 08:39 | 2026-02-20 10:14 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 627 hours |  | 0 |  | 0% |  | Fairlands |  | - Project is at 0% progress and not started yet. - Status is 'to do'. - No updates, comments, or assigned users as of now. | Green
Task | 86c84nbp5 | Maynard Mall - Expansion + Sizing Rational Request |  |  |  | IN PROGRESS |  | Paul Dreyer |  |  | 0 | 0 | 2026-02-25 |  | 2026-02-10 09:41 | 2026-02-24 08:07 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 316 hours |  | 0 |  | 0% |  | Maynard Mall |  | - Project for Maynard Mall expansion and sizing rationale created. - No progress yet (0% complete). - No comments or updates from [@Johannes Potgieter](#62645671). - Status is to do. | Green
Task | 86c7jja4x | EP updates | 86c52cck1 | Mondi Engineering tracker | https://app.clickup.com/t/86c52cck1 | IN PROGRESS |  | Gerhard | URGENT |  | 0 | 0 | 2026-02-25 |  | 2026-01-14 10:18 | 2026-02-20 10:11 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 99 hours |  | 0 |  | 0% |  | Mondi |  | - Urgent priority, 0% progress, assigned to [@Brandon Watts](#88690611). - Related to Mondi site, status is to do. - No comments or updates yet. | Green
Task | 86c8d3bbd | Update As Build | 86c5z0m0m | Mahikeng - Builders Express | https://app.clickup.com/t/86c5z0m0m | IN PROGRESS |  | johan snyman |  |  | 0 | 0 | 2026-02-25 |  | 2026-02-23 09:04 | 2026-02-23 09:04 |  |  | johan snyman | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 29 hours |  | 0 |  | 0% |  | Mahikeng |  | - Assigned to [@johan snyman](#100552512). - Site: Mahikeng. - Progress: 0%. - Status: in progress. | Green
Task | 86c889d8x | Lulamanzi Berries + Cost Proposal - Word Template |  |  |  | IN PROGRESS |  | Tanaka Zimuto |  |  | 0 | 0 | 2026-02-26 |  | 2026-02-16 08:42 | 2026-02-23 10:16 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 28 hours |  | 0 |  | 0% |  |  |  | - Project for Lulamanzi Berries Word template and cost proposal. - Progress is at 0%. - Status is to do. - No users assigned or updates from [@Johannes Potgieter](#62645671). | Green
Task | 86c8c59g4 | Kansai Plascon - Tender Clarification & Pricing Schedule + Cost Proposal - Word Template |  |  |  | IN PROGRESS |  | Tanaka Zimuto |  |  | 0 | 0 | 2026-02-26 |  | 2026-02-20 15:42 | 2026-02-23 10:15 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 27 hours |  | 0 |  | 0% |  |  |  | - Project is at 0% completion and in 'to do' status. - No updates, comments, or subtasks yet. - No user assigned. | Green
Task | 86c8c10j4 | Lonsa Group + First Assessment - PowerPoint Template |  |  |  | IN PROGRESS |  | Brandon Watts |  |  | 0 | 0 | 2026-02-26 |  | 2026-02-20 13:42 | 2026-02-23 11:15 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 26 hours |  | 0 |  | 0%
Task | 86c6j4r00 | Upper East side | 86c6h1p1a | Commissioning QC | https://app.clickup.com/t/86c6h1p1a | IN PROGRESS |  | Dean Cornelius, Kashmil Samuel, Peet Verreynnne | URGENT | No Snags recorded yet Techsitter not filled in IV curve tests outstanding | 1 | 0 | 2026-02-27 |  | 2025-11-17 09:41 | 2026-02-23 09:09 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 964 hours |  | 0 |  | 0% |  | Upper East Side Hotel |  | - [@Kashmil Samuel](#88702296) and [@Dean Cornelius](#88707129) are assigned. - Due by 12/05/2025 02:00 AM UTC. - Progress is at 0%. - Site: Upper East Side Hotel. - Status: to do. | Green
Task | 86c73fn2w | Fedgroup Site Design Reviews |  |  |  | IN PROGRESS |  | Brandon Watts |  |  | 0 | 0 | 2026-02-27 |  | 2025-12-15 13:05 | 2026-02-23 10:10 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering | 86c73fr88 86c73ft9j 86c73ftp0 | https://app.clickup.com/t/86c73fr88 https://app.clickup.com/t/86c73ft9j https://app.clickup.com/t/86c73ftp0 |  | Engineering | [7 empty] | 820 hours |  | 0 |  | 0% |  | Fedgroup |  | - Fedgroup site design reviews planned, not started yet. - Progress is at 0%. - No comments or updates from [@Johannes Potgieter](#62645671). - Status is 'to do'. | Green
Task | 86c73fr88 | Yield vs Actuals vs As-Build vs Contractual values | 86c73fn2w | Fedgroup Site Design Reviews | https://app.clickup.com/t/86c73fn2w | IN PROGRESS |  | Brandon Watts, Tanaka Zimuto |  | @Johannes Potgieter May you please assist with the PM files for Olivedale. The folder in the server are empty. | 1 | 1 | 2026-02-27 |  | 2025-12-15 13:08 | 2026-02-23 10:10 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 771 hours |  | 0 |  | 0% |  | Olivedale |  | - Site: Olivedale - Progress: 0% - Status: to do - No updates or comments yet | Green
Task | 86c73ft9j | Yield vs Actuals vs As-Build vs Contractual values | 86c73fn2w | Fedgroup Site Design Reviews | https://app.clickup.com/t/86c73fn2w | IN PROGRESS |  | Brandon Watts, Tanaka Zimuto |  | Hi @Johannes Potgieter The signed yield has been overstated not realistic and chances are very low that it will be achieved. Next step is for us to re-do the PVSol with the correct parameters and then adjust the targets. However, we cant just go ahead due to the contractual obligations. Who can assist with comunicating this to the client and Matriarch? Can we engage Karl | 3 | 1 | 2026-02-27 |  | 2025-12-15 13:10 | 2026-02-23 10:10 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 771 hours |  | 0 |  | 0% |  | Mossop |  | - Assigned to [@Brandon Watts](#88690611). - Site: Olivedale. - Progress is 0%. - Status is to do. | Green
Task | 86c73ftp0 | Yield vs Actuals vs As-Build vs Contractual values | 86c73fn2w | Fedgroup Site Design Reviews | https://app.clickup.com/t/86c73fn2w | IN PROGRESS |  | Tanaka Zimuto, Brandon Watts |  | @Johannes Potgieter I have observed that the system was production-limited for an extended period until 23 October 2025, after which production ramped up significantly. Based on the platform data, the system was set to “No Limit Control,” which resulted in the increase in production. There appears to be an issue with the grid meter, which is likely the reason the control system was previously limiting production. The grid meter profile is closely following the PV production curve, indicating that the meter may be installed in the incorrect location. Matriarch needs to confirm why the system was configured to No Limit Control despite the apparent grid metering issue. | 1 | 0 | 2026-02-27 |  | 2025-12-15 13:10 | 2026-02-23 10:10 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 771 hours |  | 0 |  | 0% |  | Madelief |  | - Assigned to [@Brandon Watts](#88690611). - Site: Olivedale. - Progress: 0%. - Status: to do. | Green
Task | 86c7vxrca | BMG Engineering - Phase 3 + Cost Proposal - Word Template |  |  |  | IN PROGRESS |  | Tanaka Zimuto |  |  | 0 | 0 | 2026-02-27 |  | 2026-01-28 07:40 | 2026-02-23 10:16 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 363 hours |  | 0 |  | 0% |  | BMG Phase 3 |  | - Project is at 0% completion and has not started yet. - No comments or updates from [@Johannes Potgieter](#62645671). - Status is 'to do'. - No subtasks or parent tasks. | Green
Task | 86c6ag7pb | Coega Steels 50 MW BESS + Data Analysis + CP |  |  |  | IN PROGRESS |  | Mary Boakye, Tanaka Zimuto, Paul Dreyer | URGENT | We will need 2 runs per side of 3x 630 1core MV 22kV XLPE Cu cable which will come to 3600 meters | 2 | 0 | 2026-02-27 |  | 2025-11-03 12:32 | 2026-02-23 11:41 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 170 hours |  | 0 |  | 0% |  | Coega Steel |  |  | Green
Task | 86c8d42n7 | Aria Property Group - 12 Nourse Avenue + Site visit Report |  |  |  | IN PROGRESS |  | Paul Dreyer |  |  | 0 | 0 | 2026-02-27 |  | 2026-02-23 09:43 | 2026-02-23 11:42 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 28 hours |  | 0 |  | 0% |  | 12 Nourse Avenue |  | - Project is at 0% progress and has not started yet. - No updates or comments from [@Johannes Potgieter](#62645671). - Status is 'to do'. | Green
Task | 86c6j4nbk | Coega Steel | 86c6h1p1a | Commissioning QC | https://app.clickup.com/t/86c6h1p1a | IN PROGRESS |  | Dean Cornelius, Kashmil Samuel | HIGH |  | 0 | 0 | 2026-03-04 |  | 2025-11-17 09:36 | 2026-02-24 09:19 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 1108 hours |  | 0 |  | 0% |  | Coega Steel |  | - [@Kashmil Samuel](#88702296) and [@Dean Cornelius](#88707129) are assigned. - Due by 12/10/2025 02:00 AM UTC. - Progress is at 0%. - Status is to do. | Green
Task | 86c6h1pye | Seshego Circle Commissioning checks | 86c6h1p1a | Commissioning QC | https://app.clickup.com/t/86c6h1p1a | IN PROGRESS |  | Dean Cornelius, Kashmil Samuel | HIGH |  | 0 | 0 | 2026-03-06 |  | 2025-11-14 07:07 | 2026-02-23 07:56 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 964 hours |  | 0 |  | 0% |  | seshego cicle |  | - [@Kashmil Samuel](#88702296) and [@Dean Cornelius](#88707129) are assigned. - Site: seshego cicle. - Progress is at 0%. - Due by 12/09/2025 02:00 AM UTC. - Status: to do. | Green
Task | 86c8dyycz | Red Rocket final closeout |  |  |  | IN PROGRESS |  | Paul Dreyer | HIGH |  | 0 | 0 | 2026-03-06 | 2026-02-24 | 2026-02-24 08:20 | 2026-02-24 08:24 |  |  | Paul Dreyer | Emergent Energy | Engineering | Engineering | 86c8dyyj8 86c8dyyx6 86c8dyzfn 86c8dz3f2 86c8dz6pu 86c8dyz9a 86c8dzezv | https://app.clickup.com/t/86c8dyyj8 https://app.clickup.com/t/86c8dyyx6 https://app.clickup.com/t/86c8dyzfn https://app.clickup.com/t/86c8dz3f2 https://app.clickup.com/t/86c8dz6pu https://app.clickup.com/t/86c8dyz9a https://app.clickup.com/t/86c8dzezv |  | Engineering | [7 empty] | 5 hours |  | 0 |  | 0% |  | Red Rocket |  | - [@Paul Dreyer](#106514301) is working on Red Rocket network re-integration. - Status is in progress, but 0% is complete so far. - No comments or subtasks yet.
Task | 86c8auz0f | 7th Avenue | 86c6h1p1a | Commissioning QC | https://app.clickup.com/t/86c6h1p1a | IN PROGRESS |  | Dean Cornelius, Kashmil Samuel | LOW |  | 0 | 0 | 2026-03-11 |  | 2026-02-19 08:52 | 2026-02-24 09:57 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 4 hours |  | 0 |  | 0% |  | 7th Avenue |  | - [@Kashmil Samuel](#88702296) and [@Dean Cornelius](#88707129) are assigned. - Due by 03/06/2026 02:00 AM UTC. - Progress is at 0%. - Status is to do.
Task | 86c8dyc3h | Top Steel | 86c6h1p1a | Commissioning QC | https://app.clickup.com/t/86c6h1p1a | IN PROGRESS |  | Kashmil Samuel, Dean Cornelius | LOW |  | 0 | 0 | 2026-03-11 |  | 2026-02-24 07:17 | 2026-02-24 09:57 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 4 hours |  | 0 |  | 0% |  | Top Steel |  | - Assigned to [@Kashmil Samuel](#88702296) and [@Dean Cornelius](#88707129). - Progress is 0%. - Status is to do.
Task | 86c52cck1 | Mondi Engineering tracker |  |  |  | IN PROGRESS |  | Johannes Potgieter |  | Updates as per discussion will be ready for internal review by Thursday and printed for the Friday workshop with JA electrical | 5 | 0 | 2026-03-13 |  | 2025-08-19 10:36 | 2026-02-24 11:56 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering | 86c7jja4x 86c8e3h3r | https://app.clickup.com/t/86c7jja4x https://app.clickup.com/t/86c8e3h3r |  | Engineering | [7 empty] | 2 hours |  | 0 |  | 71.43% |  | Mondi |  |  | Green
Task | 86c8dyc4d | Riverside Mall | 86c6h1p1a | Commissioning QC | https://app.clickup.com/t/86c6h1p1a | IN PROGRESS |  | Kashmil Samuel, Dean Cornelius | LOW |  | 0 | 0 | 2026-03-20 |  | 2026-02-24 07:17 | 2026-02-24 09:57 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 4 hours |  | 0 |  | 0% |  | Riverside Mall |  | - Assigned to [@Kashmil Samuel](#88702296) and [@Dean Cornelius](#88707129). - Progress is at 0%. - Status is to do. - No comments or subtasks yet.
Task | 86c6e8hk0 | De Drift |  |  |  | IN PROGRESS |  | Gerhard |  | image.png @Gerhard please add the generator as per the SLD given into our SLD with the relevant meter for gen-integration | 11 | 0 | 2026-06-09 |  | 2025-11-10 09:07 | 2026-02-19 09:16 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering | 86c6xvnmb | https://app.clickup.com/t/86c6xvnmb |  | Engineering | [7 empty] | 1035 hours |  | 0 |  | 88.89% |  | De Drift |  |  | Green
Task | 86c6h1p1a | Commissioning QC |  |  |  | IN PROGRESS |  | Dean Cornelius, Peet Verreynnne, Kashmil Samuel |  | Waterside place needs everything | 1 | 0 |  |  | 2025-11-14 06:53 | 2026-02-24 07:16 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering | 86c6h1pay 86c6h1prd 86c6h1pvp 86c6h1pye 86c6h1q1u 86c6h1q40 86c6j4j3a 86c6j4nbk 86c6j4r00 86c7kd6yx 86c83qhky 86c8auz0f 86c8auz9j 86c8auzgn 86c8dyc3h 86c8dyc4d 86c8dyc5e | https://app.clickup.com/t/86c6h1pay https://app.clickup.com/t/86c6h1prd https://app.clickup.com/t/86c6h1pvp https://app.clickup.com/t/86c6h1pye https://app.clickup.com/t/86c6h1q1u https://app.clickup.com/t/86c6h1q40 https://app.clickup.com/t/86c6j4j3a https://app.clickup.com/t/86c6j4nbk https://app.clickup.com/t/86c6j4r00 https://app.clickup.com/t/86c7kd6yx https://app.clickup.com/t/86c83qhky https://app.clickup.com/t/86c8auz0f https://app.clickup.com/t/86c8auz9j https://app.clickup.com/t/86c8auzgn https://app.clickup.com/t/86c8dyc3h https://app.clickup.com/t/86c8dyc4d https://app.clickup.com/t/86c8dyc5e |  | Engineering | [7 empty] | 2455 hours |  | 0 |  | 57.5% |  | Dipula and Red Rocket |  | - [@Kashmil Samuel](#88702296) and [@Dean Cornelius](#88707129) are working on this. - Status is in progress, due by 11/18/2025 02:00 AM UTC. - Progress is at 0%. - Related parties: Dipula and Red Rocket. | Green
Task | 86c7ww90v | Busamed Harrismith |  |  |  | IN PROGRESS |  | johan snyman | HIGH |  | 0 | 0 |  |  | 2026-01-29 08:39 | 2026-02-23 10:09 |  |  | johan snyman | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 629 hours |  | 0 |  | 0% |  | Busamed - Harrismith |  | - Project for Busamed - Harrismith is in progress. - Assigned to [@johan snyman](#100552512). - Due by 02/06/2026 02:00 AM UTC. - Progress is at 0%. | Green
Task | 86c10n9p6 | Trident Steel PE |  |  |  | IN PROGRESS |  | Gerhard, Roedolph | URGENT | Hi Dean, please QC, i only had to change the fault rates | 20 | 0 |  |  | 2024-11-14 08:35 | 2026-02-23 08:56 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering |  | Engineering Sign Off: https://app.clickup.com/t/86c22jqc9) | [5 empty] | 149 hours |  | 0 |  | 100% |  | Trident Steel PE |  |  | Green
Task | 86c875qcb | Altix Medical Centre + First Assessment - PowerPoint Template |  |  |  | IN PROGRESS |  | Mary Boakye |  |  | 0 | 0 |  |  | 2026-02-13 06:42 | 2026-02-23 10:13 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 27 hours |  | 0 |  | 0% |  |  |  | - Project for PowerPoint template for Altix Medical Centre and First Assessment. - No work started yet, progress is at 0%. - No comments or updates from [@Johannes Potgieter](#62645671). - Status is 'to do'.
TO DO
Task Type | Task ID | Task Name | Parent ID | Parent Name | Parent URL | Status | Task Content | Assignee | Priority | Latest Comment | Comment Count | Assigned Comment Count | Due Date | Start Date | Date Created | Date Updated | Date Closed | Date Done | Created By | Space | Folder | List | Subtask ID's | Subtask URL's | tags | Lists | Sprints | Linked Tasks | Linked Docs | Time Logged | Time Logged Rolled Up | Time Estimate | Time Estimate Rolled Up | Time In Status | Points Estimate | Points Estimate Rolled Up | Approval Signature (signature) | Completion % (automatic progress) | STAGE (drop down) | Site (labels) | Site (short text) | Summary (text) | TRACKING (drop down) | Task Name (text)
Task | 86c7xpvxt | Steelcorp - 54 Moore Street + Meter installation |  |  |  | TO DO |  | Kashmil Samuel |  | I have done both site visits as well will upload report later today | 3 | 0 | 2026-02-06 |  | 2026-01-30 08:40 | 2026-02-09 10:58 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 605 hours |  | 0 |  | 0% |  |  |  | - Project is at 0% progress. - Status is 'to do', no work started yet. - No comments or updates from [@Johannes Potgieter](#62645671).
Project | 86c86mvwt | Corporate Park Metering Clarification |  |  |  | TO DO |  | Johannes Potgieter |  |  | 0 | 0 | 2026-02-20 |  | 2026-02-12 12:24 | 2026-02-12 12:24 |  |  | Roedolph | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 289 hours |  | 0 |  | 0% |  | Corporate Park |  | - Assigned to [@Johannes Potgieter](#62645671). - Location: Corporate Park. - Status: to do. Progress: 0%. - Priority: Green. Due by 02/20/2026 02:00 AM (UTC). | Green
Task | 86c8e3h3r | CIVIL GA reviews | 86c52cck1 | Mondi Engineering tracker | https://app.clickup.com/t/86c52cck1 | TO DO |  | Gerhard |  |  | 0 | 0 | 2026-02-24 |  | 2026-02-24 11:50 | 2026-02-24 11:50 |  |  | Gerhard | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 2 hours |  | 0 |  | 0% |  | Mondi |  | - Assigned to [@Gerhard](#88690613). - Status: to do, 0% complete. - Due by 02/24/2026 02:00 AM (UTC). - Site: Mondi.
Task | 86c8d3fvp | As-built EP to be done | 86c7kd6yx | Superspar Despatch Ph2 | https://app.clickup.com/t/86c7kd6yx | TO DO |  | Brandon Watts |  | @Brandon Watts please update the EP to as-built for us. I do not think this site had a project engineer unfortunately. | 1 | 0 | 2026-02-25 |  | 2026-02-23 09:14 | 2026-02-23 09:15 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 28 hours |  | 0 |  | 0% |  | Superspar Despatch PH 2 |  | - Assigned to [@Brandon Watts](#88690611). - Due by 02/25/2026, progress is 0%. - Site: Superspar Despatch PH 2. - Status: to do.
Task | 86c8dyyx6 | Re-configure devices on site based on new configuration | 86c8dyycz | Red Rocket final closeout | https://app.clickup.com/t/86c8dyycz | TO DO |  | Paul Dreyer |  |  | 0 | 0 | 2026-02-25 |  | 2026-02-24 08:23 | 2026-02-24 08:32 |  |  | Paul Dreyer | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 5 hours |  | 0 |  | 0% |  | Red Rocket |  | - [@Paul Dreyer](#106514301) is assigned to re-configure devices for Red Rocket site. - Progress is at 0%. - Status is to do.
Task | 86c8dz3yu | Update as-built EP to be correct | 86c6h1pay | Dobson Point Commissioning checks | https://app.clickup.com/t/86c6h1pay | TO DO |  | johan snyman |  | @johan snyman please not this ticket | 1 | 0 | 2026-02-25 |  | 2026-02-24 08:47 | 2026-02-24 08:48 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 5 hours |  | 0 |  | 0% |  | Dobson Point |  | - [@johan snyman](#100552512) needs to update the as-built engineering pack for Dobson Point. - Progress is at 0%. - Due by 02/25/2026 02:00 AM UTC. - Status is to do.
Task | 86c8dzwjc | As-built EP update | 86c1kz25n | Superspar Despatch | https://app.clickup.com/t/86c1kz25n | TO DO |  | Brandon Watts | HIGH | @Brandon Watts image.png I see the modules changed as well | 2 | 0 | 2026-02-26 |  | 2026-02-24 09:43 | 2026-02-24 10:21 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 4 hours |  | 0 |  | 0% |  | Superspar Despatch PH 2 |  | - High priority update for Superspar Despatch PH 2 as-built EP. - Assigned to [@Brandon Watts](#88690611), 0% complete. - Due by 02/26/2026. - No progress or comments yet.
Task | 86c8e37zm | PV DB GA | 86c6j5vtp | PNP Bethal - Project Engineering | https://app.clickup.com/t/86c6j5vtp | TO DO |  | Gerhard |  |  | 0 | 0 | 2026-02-27 |  | 2026-02-24 11:41 | 2026-02-24 12:48 |  |  | Gerhard | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 2 hours |  | 0 |  | 0% |  | PnP Bethal |  | - Assigned to [@Gerhard](#88690613). - Site: PnP Bethal. - Progress: 0%. - Due by 02/27/2026. Status: to do.
Task | 86c8e38cx | COMS DB GA | 86c6j5vtp | PNP Bethal - Project Engineering | https://app.clickup.com/t/86c6j5vtp | TO DO |  | Gerhard |  |  | 0 | 0 | 2026-02-27 |  | 2026-02-24 11:42 | 2026-02-24 11:42 |  |  | Gerhard | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 2 hours |  | 0 |  | 0% |  | PnP Bethal |  | - Assigned to [@Gerhard](#88690613). - Site: PnP Bethal. Status: to do. Progress: 0%. - Due by 02/27/2026 02:00 AM UTC. - No comments or updates yet.
Task | 86c88akh0 | WERDA Products Cost Proposal |  |  |  | TO DO |  | Paul Dreyer | NORMAL |  | 0 | 0 | 2026-03-02 |  | 2026-02-16 09:54 | 2026-02-24 08:20 |  |  | Paul Dreyer | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 5 hours |  | 0 |  | 0% |  | WERDA |  | - [@Paul Dreyer](#106514301) is working on a cost proposal for WERDA products. - Due date is 02/25/2026 at 02:00 AM UTC. - Status is in progress and completion is at 0%. - No comments or subtasks have been added yet. | Green
Task | 86c8dz3f2 | Provide SOP for RR mains breaker operation | 86c8dyycz | Red Rocket final closeout | https://app.clickup.com/t/86c8dyycz | TO DO |  | Paul Dreyer |  |  | 0 | 0 | 2026-03-02 |  | 2026-02-24 08:45 | 2026-02-24 09:14 |  |  | Paul Dreyer | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 5 hours |  | 0 |  | 0% |  | Red Rocket |  | - [@Paul Dreyer](#106514301) is assigned to create SOP for RR mains breaker operation. - Site is Red Rocket. Status is to do and 0% complete. - No comments or subtasks yet.
Task | 86c8dyz9a | Provide RCA for Tie-in 2 main DB breaker trips | 86c8dyycz | Red Rocket final closeout | https://app.clickup.com/t/86c8dyycz | TO DO |  | Paul Dreyer |  |  | 0 | 0 | 2026-03-05 |  | 2026-02-24 08:25 | 2026-02-24 09:17 |  |  | Paul Dreyer | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 5 hours |  | 0 |  | 0% |  | Red Rocket |  | - [@Paul Dreyer](#106514301) is assigned. - Status: to do. Progress: 0%. - Site: Red Rocket. - No comments or updates yet. Parent project: Red Rocket final closeout.
Task | 86c8dyzfn | Provide updated HO documents | 86c8dyycz | Red Rocket final closeout | https://app.clickup.com/t/86c8dyycz | TO DO |  | Paul Dreyer |  |  | 0 | 0 | 2026-03-05 |  | 2026-02-24 08:25 | 2026-02-24 09:17 |  |  | Paul Dreyer | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 5 hours |  | 0 |  | 0% |  | Red Rocket |  | - [@Paul Dreyer](#106514301) needs to provide updated HO documents for Red Rocket. - Progress is at 0%. - Status is to do.
Task | 86c8dz6pu | Provide RCA for network issues | 86c8dyycz | Red Rocket final closeout | https://app.clickup.com/t/86c8dyycz | TO DO |  | Paul Dreyer |  |  | 0 | 0 | 2026-03-05 |  | 2026-02-24 08:57 | 2026-02-24 09:17 |  |  | Paul Dreyer | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 5 hours |  | 0 |  | 0% |  | Red Rocket |  | - Assigned to [@Paul Dreyer](#106514301). - Site: Red Rocket. - Progress: 0% complete, status is to do. - No comments or subtasks yet.
Task | 86c8dzezv | Training Session with RR | 86c8dyycz | Red Rocket final closeout | https://app.clickup.com/t/86c8dyycz | TO DO |  | Paul Dreyer |  |  | 0 | 0 | 2026-03-06 |  | 2026-02-24 09:16 | 2026-02-24 09:16 |  |  | Paul Dreyer | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 4 hours |  | 0 |  | 0% |  | Red Rocket |  | - Assigned to [@Paul Dreyer](#106514301). - Site: Red Rocket. - Progress: 0% complete, status is to do. - No comments or subtasks yet.
Task | 86c8dyc5e | Steel Park | 86c6h1p1a | Commissioning QC | https://app.clickup.com/t/86c6h1p1a | TO DO |  | Kashmil Samuel, Dean Cornelius | LOW |  | 0 | 0 | 2026-03-27 |  | 2026-02-24 07:18 | 2026-02-24 07:21 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 6 hours |  | 0 |  | 0% |  | Steelpark |  | - Assigned to [@Kashmil Samuel](#88702296) and [@Dean Cornelius](#88707129). - Status: to do. Progress: 0%. - Linked to Steelpark.
Task | 86c8auzgn | De Drift Mall | 86c6h1p1a | Commissioning QC | https://app.clickup.com/t/86c6h1p1a | TO DO |  | Dean Cornelius, Kashmil Samuel | LOW |  | 0 | 0 | 2026-05-29 |  | 2026-02-19 08:54 | 2026-02-19 08:54 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 125 hours |  | 0 |  | 0% |  | De Drift |  | - Assigned to [@Kashmil Samuel](#88702296) and [@Dean Cornelius](#88707129). - Due by 05/29/2026 02:00 AM UTC. - Progress is at 0%. - Location: De Drift. - Status: to do.
Task | 86c6597pp | Universal cooling requirement calculator |  |  |  | TO DO |  | Gerhard |  | Create a multi level cooling calc that can be used by business devs, PMs and Engineers which will all yield a reliable outcome. Rely on libraries and dropdowns for easy selection. Include diagrams to assist people to solve the problem. | 1 | 0 |  |  | 2025-10-24 11:12 | 2026-01-19 10:08 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 2954 hours |  | 0 |  | 0% |  | Emergent |  |  | Green
Task | 86c889d8c | Mayo Macs Paddock Site Visit + Site visit Report |  |  |  | TO DO |  | Roedolph |  |  | 0 | 0 |  |  | 2026-02-16 08:42 | 2026-02-20 10:17 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 197 hours |  | 0 |  | 0% |  |  |  | - Site visit and report for Mayo Macs Paddock not started yet (0% complete). - No updates or comments from [@Johannes Potgieter](#62645671). - Status is 'to do'.
Task | 86c8ab7t4 | National Ships Chandler + Meter installation |  |  |  | TO DO |  | Lloyd Brown |  |  | 0 | 0 |  |  | 2026-02-18 14:42 | 2026-02-20 10:02 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 143 hours |  | 0 |  | 0% |  |  |  | - Project is at 0% progress and has not started yet. - No updates or comments from [@Johannes Potgieter](#62645671). - Status is set to 'to do'.
Project | 86c8dfb92 | Landrover Waterford + First Assessment - PowerPoint Template |  |  |  | TO DO |  |  |  |  | 0 | 0 |  |  | 2026-02-23 14:43 | 2026-02-23 14:43 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 23 hours |  | 0 |  | 0% |  |  |  | - Project is at 0% progress and has not been started yet. - Status is 'to do'. - No comments or updates from users so far.
Project | 86c8dh4pa | Eris Property Group - Tender Site Meeting + Site visit Report |  |  |  | TO DO |  |  |  |  | 0 | 0 |  |  | 2026-02-23 15:43 | 2026-02-23 15:43 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 22 hours |  | 0 |  | 0% |  |  |  | - Project is at 0% completion, not started yet. - No updates or comments from [@Johannes Potgieter](#62645671). - No subtasks or parent tasks linked. - Status is 'to do'.