SOP — Project Development → Project Management Handover (PD → PM)

Ownership: Project Management (outside Engineering).
Engineering role: Consulted in the meeting; QM starts EP planning after the handover.
System of record for this step: Outlook (invite + follow-up) and SharePoint. No ClickUp before the meeting.

1) Purpose

- Transfer a contracted, buildable scope from PD to PM with as close to zero ambiguity.

  - Client expectation of system functionality and or material functionality.

  - Budget – Funding type

  - Time expectancies

- Share Compliance & HSE procedures

2) Scope & Trigger

In scope

- Commercial basis and approvals (PO/LOA/Contract/NTP; funding model).

- Approved scope and exclusions (as per CP).

- Site constraints and client rules (access, inductions, permits, shutdown windows). – Move to PM

- Procurement early planning (market availability, LLIs, vendor engagement plan).

- Comms & document control setup (where files live; team channels).

  - Stakeholder

  - Folder setup

- Handover Charter finalisation (decisions captured live—no separate action register here).

- Notify Engineering to start EP planning inputs.

Trigger

- PD sends an Outlook invite for the PD→PM Handover and attaches:

  - Handover Charter (draft) – Operational owned

  - Roof Quality Report (RQR)

  - Structural Assessment (SA)

  - Site Inspection Report (SIR)

- Include SharePoint link to the folder containing these documents.

3) Roles & Accountability (RACI)

| Function | Role in this SOP |
| --- | --- |
| PM | Responsible & Accountable. Runs the meeting. Finalises the Charter. Sends follow-up. Sets up ClickUp project. Books Baseline Program workshop. Notifies HoPE. |
| PD | Consulted. Provides complete commercial & scope pack. Owns accuracy of CP/contract basis and client commitments. Co-edits Charter with PM during meeting. |
| Program Manager (PmP) | Consulted. Validates scheduling intent, identifies program risks, agrees Baseline Program workshop timing. |
| Project Finance | Consulted. Confirms payment terms/milestones; aligns COS cadence and inputs. (COS planned/executed jointly by PmP + Project Finance; Finance Manager has final approval to pull COS forward.) |
| Procurement Lead | Consulted. States market availability, LLIs, vendor plan. Issues short market note after meeting. |
| Compliance/HSE | Consulted. Starts Safety File build; lists client HSE submissions, inductions, permits. |
| Construction Manager (CM) | Consulted. Flags site readiness constraints (access, laydown, cranage, powerdowns). |
| Engineering (HoPE / OE) | Consulted. In-meeting: call out constructability assumptions and EP prerequisites. Post-meeting: start EP planning (no EP deliverables due). |
| COO | Informed. Receives follow-up and Charter link as required. |
| Client | Informed via PM per comms plan. |

Escalation path: PM → PmP / Project Finance → COO.

4) Definition of Ready (DoR) — to run the handover

Outlook invite must include:

- Attachments: Handover Charter (draft), RQR, SIR, SA.

- Attendees : PD, PM, PmP, Project Finance, Procurement Lead, Compliance/HSE, CM, Design Engineer, Project Engineer.

- Body content: Objectives + Agenda (see templates), SharePoint link [TBC path], meeting duration, conferencing link.

- Calendar slot with minimum 3 days lead time: 60–90 minutes.
If any DoR item missing: reply-all “DoR-Fail” to the invite; list missing items; request updated invite.

5) Definition of Done (DoD) — handover complete

- Meeting held. Handover Charter updated live with decisions and clarifications. (No separate action register in this SOP.)

- Procurement posts Market Availability Note (LLIs, indicative lead times, stock status, supplier notes, risks).

- Compliance/HSE starts Safety File build; publishes initial requirements list (client HSE submissions, inductions, permits).

- Baseline Program workshop is booked (date/time confirmed in follow-up).

- Team setup (post-meeting):

  - ClickUp project created (structure below).

  - Excel project plan created (columns below).

  - Both added to Project Dashboard.

- Engineering outcome: HoPE starts EP planning (outline deliverables, dependencies, QA gates internally).

- PM sends follow-up email unless not accepted with reason why not accepted.

6) Meeting Agenda (run by PM) — step-by-step

- Open & objectives (2–3 min) — purpose, outcomes, timebox, document of record (Charter).

- Commercial basis (5–10 min) — PO/LOA/Contract/NTP; funding model; payment terms; special conditions; confirm Pipedrive deal → “Won” [if used].

- Scope & exclusions (10 min) — accepted CP option; inclusions/exclusions; conditions precedent; confirm no pending client deviations.

- Site rules & constraints (10–15 min) — access windows; working hours; inductions; hot-work/permits; shutdown windows; security; storage; laydown; cranage; roof access & fall arrest; utilities isolation protocols.

- Compliance & HSE update (10 min) — Safety File build start; client HSE submissions; induction and permit register creation; first target dates.

- Procurement early planning (10–15 min) — items to plan now; market availability & LLIs; vendor onboarding; confirm who sends Market Availability Note and by when.

- Scheduling intent & Baseline Program (10 min) — key proposed dates, dependencies; critical path items; book Baseline Program workshop (owner, date, attendees).

- Engineering inputs (5–10 min) — HoPE/OE confirms EP prerequisites and missing inputs to unblock EP planning.

- Comms & document control (5 min) — confirm channels (client + internal), SharePoint path, naming/version rules.

- Close (3–5 min) — recap decisions captured in Charter; confirm post-meeting outputs and timelines.

7) Post-Meeting Outputs & Owners

| Output | Owner | Due |
| --- | --- | --- |
| Updated Handover Charter saved to SP; link shared | PM | ≤ [3 Days] |
| Market Availability Note (bullets) – BOQ in tracker | Procurement | ≤ [7 Days] |
| Safety File build started; initial client HSE list posted | Compliance/HSE | ≤ [7 Days] |
| Baseline Program workshop invite sent | PM / PmP | ≤ [7 Days] |
| ClickUp project created (structure below) | PM / PmP / Project Finance | ≤ [7 Days] |
| Excel project plan created (columns below) | PM | ≤ [7 Days] |
| Project added to Dashboard (status visible) | PM / Ops Admin [TBC] | ≤ [7 Days] |
| ------------------------------Pause here |  |  |

8) SharePoint — structure & naming

- Path: [TBC Root]/Projects/Client_Site/YYYY-MM-DD

  - 01_Commercial

  - 02_Handover_Charter

  - 03_HSE_Compliance

  - 04_Procurement

  - 05_Scheduling

  - 06_ClickUp_Project

  - 07_Excel_Plan

  - _Archive

- Naming: Client_Site_DocType_v{major.minor}_YYYYMMDD.ext

- Versioning: keep all versions; mark latest CURRENT.

11) ClickUp — project structure (created after handover)

- Space/List: Projects » Client_Site

- Suggested Folders & Lists:

  - Program & Reporting

    - Statuses: New → In-Progress → For Review → Done

    - Recurring: Weekly lookahead; Daily site update; Internal weekly ops review

  - Compliance & HSE

    - Statuses: New → Submitted → Approved → Done

    - Templates: Safety File index; Inductions; Permit tracker

  - Procurement

    - Statuses: RFQ → PO → In Transit → On Site → Closed

    - Fields: LLI (Y/N); Vendor; Lead time (days); Delivery window

  - Site Readiness

    - Statuses: Planning → Scheduled → Complete

    - Items: Access & inductions; Laydown & storage; Cranage; Powerdowns; Client constraints

  - Engineering (Info only)

    - Task: “EP planning started” (EP production lives in Engineering; this is a dependency/flag only)

- Project fields (examples): Phase; Health (R/A/G); LLI exposure (Y/N); Compliance status; Baseline Program booked (Y/N/date); COS cadence.

12) Excel project plan — minimum columns

- WBS; Task; Owner; Start; Finish; Duration (days); Predecessors; Status; Notes; Milestone (Y/N); SLA (days).

- Flags: HSE-critical (Y/N); LLI-dependent (Y/N); Client-dependent (Y/N).

- Views: next-14-day milestones; LLI-dependent tasks; HSE-critical tasks.

13) Dashboard — minimum tiles

- Project Health (R/A/G with reason).

- Baseline Program booked (Yes/No + date).

- LLI exposure (count and list).

- Compliance status (Safety File started? submissions due in 7 days?).

- Next 7-day milestones (count + list).

- COS cadence set? (Yes/No + next date).

14) Compliance & HSE — starter pack (after handover)

- Safety File index (legal appointments, RAMS, inductions, permits, inspections, audits, incident plan).

- Client HSE submissions list with due dates.

- Induction & Permit tracker setup.

- First-week targets: submit induction requests; draft first RAMS per site rules; schedule site HSE briefing with client [TBC].

15) Procurement — Market Availability Note (template)

Subject: Market Availability — Client/Site
Items:

- Inverters — lead time; stock status; approved vendors; risks

- Switchgear/protection — lead time; stock status; spec dependencies

- Cable trays/steel — lead time; local availability; alternates

- DC/AC cable — lead time; length estimates; alternates

- Cranage/special services — booking windows; constraints
LLIs summary: …
Risks & mitigations: …
Next update: …

16) Program — Baseline Workshop (outline)

- Confirm WBS and phase gates.

- Drop in LLIs and HSE gates.

- Fix critical path and float.

- Agree reporting rhythm (weekly lookahead, daily site update).

- Align outages/shutdown windows with client.

- Target deliverable: Baseline Program v1 with owners and dates.

17) Finance — COS alignment (rules embedded)

- Ownership: COS planned/executed jointly by PmP + Project Finance.

- Governance: Finance Manager holds final approval to pull COS forward.

- After handover: set COS cadence, data sources (ClickUp + Excel + QBO [TBC]), first submission date.

18) Engineering — participation & handoff

In the meeting

- Call out constructability assumptions to freeze (access, penetrations, trays/walkways, fall-risk).

- Confirm EP prerequisites: surveys, logging, as-builts, client data, metering/export positions.

After the meeting

- HoPE starts EP planning (internal pre-plan; deliverables list; QA gates; dependencies).

- No EP production deliverables due at this stage.

19) SLAs (slot house numbers)

- Invite → Meeting held: ≤ [TBC days].

- PM follow-up (Charter link + outputs): ≤ [TBC h].

- Procurement Market Note: ≤ [TBC h].

- Safety File start confirmation: ≤ [TBC h].

- Baseline Program workshop invite: ≤ [TBC h].

- ClickUp project + Excel plan + Dashboard live: ≤ [TBC h].

20) KPIs

- Invite readiness: % invites meeting DoR first time.

- Trigger → Meeting: days.

- Meeting → Setup complete: hours to ClickUp + Excel + Dashboard.

- Procurement responsiveness: hours to Market Note.

- Baseline Program booked: days from meeting.

- Engineering start: hours to HoPE confirmation.

- Rework due to handover gaps: # scope/term changes within 5 working days.

21) Quality Gates

- DoR met (attachments, attendees, agenda, SP link).

- Charter updated and stored (versioned; CURRENT tagged).

- Procurement Market Note posted.

- Safety File build confirmed started.

- Baseline Program workshop booked.

- ClickUp project + Excel plan + Dashboard live.

- HoPE confirmed EP planning started.

22) Change Control

- Any post-handover change (scope/terms/rules) → update Charter v{n+1} with reason; email group; adjust ClickUp/Excel plan/Dashboard once live.

23) Common Failure Modes & Controls

- Missing attachments → DoR-Fail reply; block meeting until complete.

- Unclear scope vs CP → read CP acceptance/exclusions in meeting; edit Charter live.

- LLIs underestimated → Procurement market check + alternates documented.

- Compliance late start → HSE publishes Safety File index + first due dates in follow-up.

- No single source of truth → confirm SP path + naming/version; link in follow-up.

- Premature ClickUp tasks → enforce “no ClickUp before meeting”; create after.

24) Templates (ready to use)

24.1 Outlook Invite — PD→PM Handover

Subject: PD→PM Handover — Client/Site — YYYY-MM-DD
Attachments: Handover Charter (draft), RQR, SIR
Body:

- Objectives: confirm commercial basis; approved scope/exclusions; site rules; HSE kickoff; procurement market status & LLIs; scheduling intent + book Baseline Program workshop; comms setup; Engineering inputs to start EP planning.

- Agenda: as per SOP §7.

- Attendees: PD, PM, PmP, Project Finance, Procurement, Compliance/HSE, CM, HoPE (Engineering – consulted)

- SharePoint link: …

- Duration: 60–90 min

- Meeting link: …

24.2 DoR-Fail reply (if needed)

Handover paused — missing {item(s)} (Charter/RQR/SIR/attendees/agenda/SP link). Please re-issue the invite with the required items. We will proceed once complete.

24.3 PM Follow-Up Email (post-meeting)

- Decisions locked: (5–10 bullets)

- Updated Charter: link

- Baseline Program workshop: date/time (invite sent)

- Procurement: Market Availability Note by Name due {TBC h}

- Compliance: Safety File build started; first submissions due {date}

- Setup: ClickUp project link; Excel plan link; Dashboard tile link

- Engineering: HoPE to start EP planning (Charter/RQR/SIR linked)