# SOP — First Assessment (FA)

# Purpose

Rapid desktop assessment to decide Go / Rework / No-Go.

Produce an FA Pack to unlock Cost Proposal.

# Scope & Triggers

In scope:

PV desktop layout & yield

Integration constraints

High-level BoM & cost

Risks & assumptions

Out of scope:

Detailed EP/SLD

Structural sign-off

Final pricing

Procurement

Trigger:

PD posts FA request in MS Teams (Engineering intake channel [TBC]).

Automation creates ClickUp FA task for Engineering.

PM not informed at FA stage.

# Definitions & DoR/DoD

DoR (Definition of Ready) to start FA:

Teams post includes: Client & Site; address or GPS pin.

Load profile (Datatool) or stated operating hours.

Roof plan/photos or Google Maps/Earth link.

Notes: export allowed? gens on site? roof/ground type? obvious constraints.

System intent: ☐ PV  ☐ PV+Gen  ☐ PV+BESS.

Requested due date.

ClickUp task auto-created with link back to the Teams thread.

If any item missing → DoR-Fail (pause SLA; request items in thread).

DoD (Definition of Done) for FA:

FA Pack stored (SharePoint [TBC path] or attached to the Teams thread):

Helioscope layout PDF + inputs summary.

Load summary (Datatool) incl. peak/base, weekday/weekend shape.

High-level BoM & Costing sheet (± range) with top cost drivers.

Constraints & Risk/Assumption log with owners.

FA Summary (1-pager) with recommendation.

HoD review done; Decision captured in ClickUp: Go / Rework / No-Go.

Assumptions & gaps listed; actions assigned.

# Roles (RACI)

R — OE (assigned engineer)

A — HoD

C — PD, PoD, HoPD

I — (PM not informed at FA stage)

Prioritisation: PoD & PD | Workload assigning: PoD | Triage: HoD

Escalation: OE → PD → PoHD → HoD

# Steps (Who / What / Tool / SLA)

| Step | Who | What | Tool | SLA |
| --- | --- | --- | --- | --- |
| 0 | PD | Post FA request with required inputs (use intake template) | MS Teams | Start |
| 1 | Automation | Create ClickUp FA task; include Teams thread link | ClickUp | Instant |
| 2 | HoD | Triage; set priority & complexity (Std/Complex/BESS); assign OE | ClickUp | ≤ [TBC] h |
| 3 | OE | Verify DoR from Teams thread; if gaps, reply and pause SLA (DoR-Fail) | Teams | ≤ [TBC] h |
| 4 | OE | Desktop layout & yield (module/inverter family, tilt, azimuth, DC/AC) | Helioscope | ≤ [TBC] |
| 5 | OE | Load summary (peak/base; weekday/weekend shape; seasonality) | Datatool | — |
| 6 | OE | Constraint check (usable roof, shading, access/walkways, roof types, export rule—basic, gens presence) | Helioscope/Maps | — |
| 7 | OE | High-level BoM & Costing sheet with ± range & top 3 cost drivers | EE Costing sheet | — |
| 8 | OE | Risk & Assumption log with owners & due dates | Template | — |
| 9 | OE | Compile FA Summary (1-pager); self-check against Quality Gate | Template | — |
| 10 | OE | Store files (SP [TBC] or attach in Teams); post “For-Review” note | Teams/SharePoint | — |
| 11 | HoD | QA review; record Decision and comments | ClickUp | ≤ [TBC] |
| 12 | OE | Assigns back to PD and closes SharePoint ticket | ClickUp/Teams | Immediate |

# Quality gates (control points)

Intake complete (DoR met) in Teams thread.

Helioscope layout shows: keep-outs & walkways; shading run; tilt/azimuth; DC/AC; EE default libraries [TBC].

Yield table includes PR & specific yield.

Load summary states peak kW, base kW, weekday vs weekend profile.

Costing sheet attached with range and drivers.

Constraints & Risks logged with RAG + owners.

Assumptions explicit (export, structural, access, network/protection TBC in EP).

HoD decision captured in ClickUp.

# Artefacts (forms, logs, file paths)

FA Summary (1-pager) — headings:

Client & Site | Date | OE | Version

Proposed System (kWp DC / kVA AC), DC/AC; Est. Yield (kWh/yr; PR; specific yield)

Load overview (peak/base, daytime match %)

Layout notes (areas used, tilt/azimuth, shading notes)

Integration context (export policy, gens present, BESS intent)

Capex range (R x–y); top 3 cost drivers

Constraints & Risks (RAG + owner)

Assumptions

Recommendation: Go / Rework / No-Go

Risk & Assumption Log — columns: Item | Type | Description | RAG | Owner | Due/Review | Status/Notes

Storage path: SharePoint [TBC root]/Engineering/01_FA/Client_Site/YYYY-MM-DD

Folders: 01_Inputs / 02_Design / 03_Costing / 04_Output / _Archive (no SP link in ClickUp; Teams is comms anchor).

# KPIs & reporting

Lead Time: Teams post → HoD decision.

On-time Delivery: % FAs within SLA.

First-Pass Yield: % Go without rework.

Rework Rate: % needing rework; top 3 causes.

DoR-Fail Count: per week by cause (missing load/photos/map/etc.).

# Change control

Any scope/intent change (e.g., add BESS, ground-mount) → set ClickUp Scope Change = Yes, post reason in Teams, version bump (FA_v{n+1}); reset SLA if material [rule TBC].

Keep prior versions in _Archive; mark latest CURRENT.

# Teams Intake — PD post template

Title: FA Request — Client/Site — Due: YYYY-MM-DD

Body:

• Address / GPS

• Intent: ☐ PV  ☐ PV+Gen  ☐ PV+BESS

• Export: ☐ Allowed  ☐ Not allowed  ☐ Unknown

• Gens on site: ☐ Yes  ☐ No  ☐ Unknown

• Constraints/notes

• Requested due date

Attachments: Datatool (or ops hours); Roof plan/photos or Maps/Earth link