## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 8692848.61 |  | 8692848.61 |  |  |  | Start Date | 7660876.7788 | 5862298.65 | 968085.2901 | 1227752.7776 | 642119.2497 | 1187462.17
2 | Planned Expenditure | 8166239.0135 |  | 7090051.4276 | VO PM Limit | Current VO Total
3 | Planned Profit | 526609.5965 |  | 1602797.1824 | 26330.4798 | 19400 |  | End Date - PC
4 | Planned Margin | 6.058% |  | 18.44%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE |  | MILESTONE NOTES & COMMENTS
1 | Deposit |  | 20% | 1738569.722 |  | 2025-04-30 | 004730 | 2025-05-01 | 2025-04-30
2 | Delivery of Panels |  | 20% | 1738569.722 |  | 2025-08-15 | 004730 | 2025-05-01 | 2025-07-04
3 | Delivery of Inverters |  | 15% | 1303927.2915 |  | 2025-07-25 | 004730 | 2025-05-01 | 2025-07-04
4 | Commissioning Complete |  | 15% | 1303927.2915 |  | 2025-11-03 | 004730 | 2025-05-01 | 2026-01-02
5 | Final Completion Issued |  | 25% | 2173212.1525 |  | 2025-11-04 | 004730 | 2025-05-01 | 2026-01-02
6 | Handover |  | 5% | 434642.4305 |  | 2026-03-13 | 004730 | 2025-05-01 | 2026-01-16
7 | - |  | 0% | 0
|  |  | 100% | 8692848.61
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 3042497.0135
2 | Delivery of Panels |  | 30% | 2607854.583
3 | Delivery of Inverters |  | 20% | 1738569.722
4 | Practical Completion |  | 10% | 869284.861
5 | Handover |  | 5% | 434642.4305
| Total |  | 100% | 8692848.61
|  |  | 100% | 8692848.61

## Project Plan
[9 empty] | 2026-03-05 | 2026-03-05
| PROJECT PLAN | Gezina Galleries | [5 empty] | Still have a inverter down (possible RMA)
| PROJECT SIZE (kWp) | 954
| PROJECT DEVELOPER | Natasha Watkins Baker
| PROJECT MANAGERS | Eon Van Rensburg
| CONTRACT VALUE | 8692848.61
| Phase: | Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Excpeted Status | Comment
|  |  | 102 |  |  | 74 |  | 98.85% | 96.97%
1 | Project Initiation | 2025-04-22 | 80 | 2025-07-11 | 2025-04-29 | 17 | 2025-05-16 | 100% | 100%
1.1 | BD Handover | 2025-04-22 | 1 | 2025-04-23 | 2025-05-13 | 1 | 2025-05-14 | 100% | 100%
1.2 | Project Introduction | 2025-07-10 | 1 | 2025-07-11 | 2025-05-15 | 1 | 2025-05-16 | 100% | 100%
1.3 | HSE | 2025-04-22 | 10 | 2025-05-07 | 2025-04-29 | 10 | 2025-05-14 | 100% | 100%
1.4 | Installer Kick Off | 2025-07-03 | 1 | 2025-07-04 | 2025-05-14 | 1 | 2025-05-15 | 100% | 100%
1.5 | Project Review | 2025-07-03 | 1 | 2025-07-04 | 2025-05-08 | 1 | 2025-05-09 | 100% | 100%
2 | Site Establishment | 2025-07-17 | 1 | 2025-07-18 | 2025-09-29 | 1 | 2025-09-30 | 100% | 100%
2.1 | Solar Contractor Establishment | 2025-07-17 | 1 | 2025-07-18 | 2025-09-29 | 1 | 2025-09-30 | 100% | 100% |  | 55 | Net Work Days
3 | AC Installation | 2025-06-26 | 70 | 2025-09-04 | 2025-06-27 | 115 | 2025-10-20 | 100% | 100% |  | 11 | Total Weeks
3.1 | Inverters delivered | 2025-07-18 | 1 | 2025-07-21 | 2025-06-27 | 1 | 2025-06-30 | 100% | 100% |  | 86.7273 | kW/Week Installation Rate
3.2 | Inverters Mounted | 2025-07-21 | 5 | 2025-07-28 | 2025-10-02 | 5 | 2025-10-09 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-06-26 | 25 | 2025-07-31 | 2025-09-01 | 29 | 2025-10-13 | 100% | 100%
3.4 | AC Works | 2025-07-31 | 25 | 2025-09-04 | 2025-10-02 | 12 | 2025-10-20 | 100% | 100%
3.5 | AC Tie-In | 2025-07-31 | 3 | 2025-08-05 | 2025-10-17 | 1 | 2025-10-20 | 100% | 100%
4 | DC Works | 2025-07-17 | 88 | 2025-10-13 | 2025-06-27 | 166 | 2025-12-10 | 100% | 100%
4.1 | Lifeline Installation (If Applicable) | [6 empty] | 0% | 0%
4.1 | Mounting Structure delivered | 2025-07-17 | 1 | 2025-07-18 | 2025-06-27 | 1 | 2025-06-30 | 100% | 100%
4.2 | Mounting Structure installation | 2025-07-18 | 20 | 2025-08-15 | 2025-10-02 | 25 | 2025-11-06 | 100% | 100%
4.3 | DC Cable delivered | 2025-07-17 | 1 | 2025-07-18 | 2025-06-27 | 1 | 2025-06-30 | 100% | 100%
4.4 | DC Stringing | 2025-09-12 | 20 | 2025-10-13 | 2025-11-21 | 13 | 2025-12-10 | 100% | 100%
5 | Module installation | 2025-08-08 | 38 | 2025-09-15 | 2025-06-27 | 157 | 2025-12-01 | 100% | 100%
5.1 | Module delivery | 2025-08-08 | 1 | 2025-08-11 | 2025-06-27 | 1 | 2025-06-30 | 100% | 100%
5.2 | Module mounting | 2025-08-11 | 25 | 2025-09-15 | 2025-10-27 | 25 | 2025-12-01 | 100% | 100%
6 | Commissioning | 2025-10-13 | 14 | 2025-10-27 | 2025-12-10 | 2 | 2025-12-12 | 100% | 100%
6.1 | Commissioning | 2025-10-13 | 5 | 2025-10-20 | 2025-12-10 | 1 | 2025-12-11 | 100% | 100%
6.2 | Practical Completion | 2025-10-20 | 5 | 2025-10-27 | 2025-12-11 | 1 | 2025-12-12 | 100% | 100%
7 | QA Inspections | 2025-10-27 | 1 | 2025-10-28 | 2025-12-12 | 32 | 2026-01-13 | 100% | 100%
7.1 | Red-Team Inspection | 2025-10-27 | 1 | 2025-10-28 | 2025-12-12 | 20 | 2026-01-13 | 100% | 100%
7.2 | Anderson Consulting Inspection |  |  |  | 2026-01-23 | 1 | 2026-01-26 | 100% | 100%
8 | Project Closure | 2025-10-28 | 14 | 2025-11-11 | 2026-01-12 | 57 | 2026-03-10 | 90.82% | 75.75%
8.1 | Equipment serial numbers | 2025-10-28 | 2 | 2025-10-30 | 2026-01-13 | 2 | 2026-01-15 | 100% | 100%
8.2 | Snags completion | 2025-10-28 | 5 | 2025-11-04 | 2026-01-30 | 12 | 2026-02-17 | 100% | 100%
8.3 | System Performance Monitoring | 2025-11-04 | 5 | 2025-11-11 | 2026-01-12 | 5 | 2026-01-19 | 100% | 100%
8.4 | Handover documentation | 2025-10-28 | 5 | 2025-11-04 | 2026-01-12 | 22 | 2026-02-11 | 100% | 100%
8.5 | Handover to Client | 2025-11-04 | 1 | 2025-11-05 | 2026-03-05 | 1 | 2026-03-06 | 0% | 0%
8.6 | Handover to Matriarch | 2025-10-30 | 5 | 2025-11-06 | 2026-02-27 | 7 | 2026-03-10 | 50% | 54.55% | request sent
Formulas:
Planned Start = MIN([Planned Start, row below]:E16)
Planned Start = WORKDAY.INTL([Planned End, row above],0,1,Data!$C3:C14)
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = WORKDAY.INTL([Actual End, row above],0,1,Data!$C3:C14)
Actual End = MAX([Actual End, row below]:K16)
Actual End = MAX([Actual End, row below])
Excpeted Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 8166239.0135 |  | 7090051.4276 | 1076187.5859
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 2005152.38 |  | 1905787.2 | 99365.18
2 | 2. Inverters | 560000 |  | 332186.77 | 227813.23
3 | 3. Mounting Structures | 429471 |  | 252145.2 | 177325.8
4 | 4. DC Equipment | 748943.9 |  | 788073.5 | -39129.6
5 | 5. Monitoring | 49000 |  | 40802.14 | 8197.86
6 | 6. AC Equipment | 1016362.1 |  | 449654.02 | 566708.08
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 0 |  | 219758 | -219758
9 | 9. AC & DC installation | 771925 |  | 954000 | -182075
10 | 10. Site Logistics | 191986 |  | 364435 | -172449
11 | 11. Due Dilligence | 158578.5 |  | 126810.13 | 31768.37
12 | 12. BDP Commission | 131652.3975 |  | 0 | 131652.3975
13 | 13. Engineering | 286542.736 |  | 108660.6076 | 177882.1284
14 | 14. General Expenses | 16625 |  | 14988.86 | 1636.14
15 | 15. Service Add On | 1800000 |  | 1532750 | 267250
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 8166239.0135 | 8692848.6035 | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 7090051.4276
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | ERROR on REV | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 2005152.38 | 2025-07-29 | 2005152.38 | 2179513.4565 | 1 | 1. Panels | Jinko 620W - Menlo | 1539 | 1233.8 | 491874.5391 | PO3894-DIP-PH2=20250514 | Menlo Inv INV0003032 | 2025-06-30 | 2179513.4565 | 0 | 2025-07-29 | 1905787.2
1 |  | Delivery Budget |  |  |  | 2025-08-21 |  |  | 1 | 1. Panels |  |  |  | 1406943.6609 |  | Menlo Inv INV0003032 | 2025-06-30 | 0 |  | 2025-08-21
1 | [8 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [8 empty] | 1 | 1. Panels | Jinko 620W - Menlo |  |  | 6169 |  | MSA Energy Solutions INV0003443 | 2025-11-30 | 0 |  | 2026-01-23
1 | [8 empty] | 1 | 1. Panels | Transport |  |  | 800 |  | MSA Energy Solutions INV0003443 | 2025-11-30 | 0 |  | 2026-01-23
1 | [8 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[22 empty] | AC Equipment | 1016362.1
2 | Inverters | Inverter Budget |  |  | 560000 | 2025-08-21 | 560000 | 608695.6522 | 2 | 2. Inverters | Huawei 100KTL - Menlo | 8 | 68870 | 332186.77 | PO3894-DIP-PH2=20250514 | Menlo Inv INV0003032 | 2025-06-30 | 608695.6522 | 0 | 2025-08-21 | 332186.77 | DC Equipment | 438633.9
2 | [5 empty] | 2025-08-22 |  |  | 2 | 2. Inverters | Huawei 100KTL |  |  | 68870 |  | Allocated from Joburg Storeroom | 2026-02-28 | 0 |  | 2026-02-28 |  | AC Labour | 238595
2 | [8 empty] | 2 | 2. Inverters | Huawei 100KTL - RMA |  |  | -68870 |  |  | 2026-04-30 | 0 |  | 2026-04-30 |  | DC Labour | 533330
2 | [8 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [8 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 51911
2 | [8 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 17575
2 | [8 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 429471 | 2025-07-29 | 429471 | 466816.3043 | 3 | 3. Mounting Structures | Schletter Structure |  |  | 245639.2 | PO3917-DIP-Ph2-Gezi-20250515 - RVApproved | Schletter - INV1902 | 2025-06-30 | 466816.3043 | 0 | 2025-07-29 | 252145.2 | Other | 0
3 | [8 empty] | 3 | 3. Mounting Structures | Additional Clamps |  |  | 6506 | PO4484-DIP-Ph2-Gezi-20251124 - RV Approved | Schletter - INV2459 | 2025-11-30 | 0 |  | 2025-12-30 |  | Total | 2304907
3 | [8 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Less 15% | 1959170.95
3 | [8 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | R/Wp | 2.0536
3 | [8 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [8 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL - Cosmic Sun | Installer Price
[22 empty] | AC Equipment | 202590
4 | DC Equipment | DC Cable Budget | 25489.75 |  | 310310 | 2025-08-22 | 748943.9 | 814069.4565 | 4 | 4. DC Equipment | DC Cable - Menlo | 25000 | 13.4 | 335000 | PO3894-DIP-PH2-20250514 | Menlo Inv INV0003032 | 2025-06-30 | 425683.8041 | 0.003016 | 2025-08-22 | 788073.5 | DC Equipment | 292473.5
4 |  | DC Equipment Budget |  |  | 438633.9 | 2025-08-22 |  |  | 4 | 4. DC Equipment | DC Cable - Menlo | 1000 | 13.4 | 13400 |  | Menlo Inv INV0003032 | 2025-06-30 | 17021.3478 |  | 2025-08-22 |  | AC Labour | 286200
4 | [8 empty] | 4 | 4. DC Equipment | DC Cable - Helukabel | 6000 |  | 89700 | PO4495-GEZ-20251126 - RV Approved | Helukabel - PSI0047534 | 2025-12-31 | 0 |  | 2026-01-30 |  | DC Labour | 667800
4 | [8 empty] | 4 | 4. DC Equipment | DC Cable - Rubicon | 4000 |  | 57500 |  | Rubicon Inv: INVWCRE-0072974 | 2025-12-31 | 0 |  | 2026-01-30 |  | Offloading | 13200
4 | [8 empty] | 4 | 4. DC Equipment | Project Kick Off | 292473.5 | 10% | 29247.35 | PO3868-DIP-Ph2-Gezi-20250512 - RV Approved | Cosmic Sun: CS_GZG_001 | 2025-05-31 | 37001.3284 |  | 2025-05-15 |  | Scaffolding | 42405
4 | [8 empty] | 4 | 4. DC Equipment | Site Establishment |  | 15% | 43871.025 |  | Cosmic Sun: CS_GZG_002 | 2025-06-30 | 55727.1622 |  | 2025-06-26 |  | Storage | 9350
4 | [8 empty] | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 58494.7 |  | Cosmic Sun - CS_GZG_004 | 2025-08-31 | 74302.8829 |  | 2025-10-24 |  | Telehandler | 0
4 | [8 empty] | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 73118.375 |  | Cosmic Sun - CS_GZG_003 A | 2025-08-31 | 92878.6037 |  | 2025-12-18 |  | HSE | 4500
4 | [8 empty] | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 29247.35 |  | Cosmic Sun - CS_GZG_005 A | 2025-08-31 | 37151.4415 |  | 2025-12-18 |  | Other | 0
4 | [8 empty] | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 29247.35 |  | Cosmic Sun - CS_GZG_006 A | 2025-08-31 | 37151.4415 |  | 2026-02-05 |  | Other | 0
4 | [8 empty] | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 14623.675 |  | Cosmic Sun - CS_GZG_007 A | 2025-08-31 | 18575.7207 |  | 2026-02-13 |  | Total | 1518518.5
4 | [8 empty] | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 14623.675 |  | Cosmic Sun - CS_GZG_008 A | 2025-08-31 | 18575.7207 |  | 2026-03-15 |  | R/Wp | 1.5917
4 | [8 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [8 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [8 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 34000 | 2025-07-17 | 49000 | 53260.8696 | 5 | 5. Monitoring | Smartlogger - Menlo |  |  | 8598.35 | PO3894-DIP-PH2=20250514 | Menlo Inv: INV0002928 | 2025-05-31 | 11430.8535 | 0.0019877 | 2025-07-17 | 40802.14
5 |  | Revenue Metering |  |  | 15000 | 2025-05-29 |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 14805 | PO3828-DIP-Ph2-Gezi-20250429 - RV Approved | Accuenergy - Inv ASAI-005354 | 2025-04-30 | 19230.025 |  | 2025-05-29
[6 empty] | 2025-07-29 |  |  | 5 | 5. Monitoring |  |  |  | 214.29 |  | Accenergy - INV ASAI-005800 | 2025-06-30 | 437.2924 |  | 2025-07-29
5 | [5 empty] | 2025-06-30 |  |  | 5 | 5. Monitoring | Techsitter |  |  | 14934 |  | Matriarch Inv: 4451 | 2025-06-30 | 19214.3023 |  | 2025-06-30
5 | [5 empty] | 2025-05-22 |  |  | 5 | 5. Monitoring | UPS |  |  | 2250.5 | PO3863-DIP Ph2-20250509 - RV Approved | Frontline Electrical - INV725690 | 2025-05-31 | 2948.3945 |  | 2025-05-22
5 | [8 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [8 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [8 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 1016362.1 | 2025-07-29 | 1016362.1 | 1104741.413 | 6 | 6. AC Equipment | [7 empty] | 0 | -0.0012363 |  | 449654.02
6 | [5 empty] | 2025-07-29 |  |  | 6 | 6. AC Equipment | PVDB |  |  | 247064.02 | PO3892-DIP-Ph2-Gezina-20250513 - RV Approved | Switchboard Inv: 2-SOI002101 | 2025-06-30 | 606310.9164 |  | 2025-07-29
[9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
[9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
[9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
[9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [8 empty] | 6 | 6. AC Equipment | Project Kick Off | 202590 | 10% | 20259 | PO3868-DIP-Ph2-Gezi-20250512 - RV Approved | Cosmic Sun: CS_GZG_001 | 2025-05-31 | 50466.9579 |  | 2025-05-15
6 | [8 empty] | 6 | 6. AC Equipment | Site Establishment |  | 15% | 30388.5 |  | Cosmic Sun: CS_GZG_002 | 2025-06-30 | 74660.59 |  | 2025-06-26
6 | [8 empty] | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 40518 |  | Cosmic Sun - CS_GZG_004 | 2025-08-31 | 99547.4533 |  | 2025-10-24
6 | [8 empty] | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 50647.5 |  | Cosmic Sun - CS_GZG_003 A | 2025-08-31 | 124434.3167 |  | 2025-12-18
6 | [8 empty] | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 20259 |  | Cosmic Sun - CS_GZG_005 A | 2025-08-31 | 49773.7267 |  | 2025-12-18
6 | [8 empty] | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 20259 |  | Cosmic Sun - CS_GZG_006 A | 2025-08-31 | 49773.7267 |  | 2026-02-05
6 | [8 empty] | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 10129.5 |  | Cosmic Sun - CS_GZG_007 A | 2025-08-31 | 24886.8633 |  | 2026-02-13
6 | [8 empty] | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 10129.5 |  | Cosmic Sun - CS_GZG_008 A | 2025-08-31 | 24886.8633 |  | 2026-03-15
6 | [8 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [8 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [8 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [8 empty] | 7 | 7.BESS
7 | [8 empty] | 7 | 7.BESS
7 | [8 empty] | 7 | 7.BESS
7 | [8 empty] | 7 | 7.BESS
7 | [8 empty] | 7 | 7.BESS
7 | [8 empty] | 7 | 7.BESS
7 | [8 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 0 | 0 | 8 | 8. Product Add On | Estop |  |  | 6000 | PO4393-DIP-Ph2-Gezi-20251023 - RV Approved | Cosmic Sun - CS_GZG_011_VO | 2025-11-30 |  | 0 | 2025-11-19 | 219758
8 | [8 empty] | 8 | 8. Product Add On | Installation of SPD - Recover Cost from SWB |  |  | 1728.1 | PO4562-DIP-Ph2-Gezi-20260121 - RV Approved | Cosmic Sun - CS_GZG_012 | 2026-01-31 |  |  | 2026-01-29
[9 empty] | 8 | 8. Product Add On | Installation of SPD - Recover Cost from SWB |  |  | -1728.1 |  | Switchboard - 2-ARI001536 | 2026-02-28 |  |  | 2026-02-28
8 | [5 empty] | 2025-07-31 |  |  | 8 | 8. Product Add On | Inverter Cage with Roof |  |  | 95783 | PO4019-DIP-Ph2-Gezi-20250623 - RV Approved | The Engineering Hub INV/2025/06/05765 | 2025-06-30 |  |  | 2025-07-31
8 | [8 empty] | 8 | 8. Product Add On
8 | [8 empty] | 8 | 8. Product Add On
8 | [8 empty] | 8 | 8. Product Add On | Waterpoints |  |  | 16488 | PO4339-DIP-Ph2-Gezi-20250929 - RV Approved | NDAWONGA TRADING - 1485 | 2025-11-30 |  |  | 2025-12-12
8 | [8 empty] | 8 | 8. Product Add On
8 | [8 empty] | 8 | 8. Product Add On | CS - Tie In Kiosk |  |  | 15620 | PO4351-DIP-Ph2-Gezi-20251006 - RV Approved | Cosmic Sun - CS_GZG_010 | 2025-10-31 |  |  | 2025-10-24
8 | [8 empty] | 8 | 8. Product Add On | Modification on inverter cage |  |  | 85867 | PO4579-DIP-Ph2-Gezi-20260127 - RV Approved | The Engineering Hub INV/2026/01/0248 | 2026-01-31 |  |  | 2026-02-26
9 | AC & DC Installation | AC Installation Budget |  |  | 238595 | 2025-05-15 | 771925 | 908147.0588 | 9 | 9. AC & DC installation | [7 empty] | 0 | 0 |  | 954000
9 |  | DC Installation Budget |  |  | 533330 | 2025-05-15 |  |  | 9 | 9. AC & DC installation | Project Kick Off | 954000 | 10% | 95400 | PO3868-DIP-Ph2-Gezi-20250512 - RV Approved | Cosmic Sun: CS_GZG_001 | 2025-05-31 | 90814.7059 |  | 2025-05-15
9 | [8 empty] | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 143100 |  | Cosmic Sun: CS_GZG_002 | 2025-06-30 | 136222.0588 |  | 2025-06-26
9 | [8 empty] | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 190800 |  | Cosmic Sun - CS_GZG_004 | 2025-08-31 | 181629.4118 |  | 2025-10-24
9 | [8 empty] | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 238500 |  | Cosmic Sun - CS_GZG_003_B | 2025-11-30 | 227036.7647 |  | 2025-12-18
9 | [8 empty] | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 95400 |  | Cosmic Sun - CS_GZG_005_B | 2025-11-30 | 90814.7059 |  | 2026-01-29
9 | [8 empty] | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 95400 |  | Cosmic Sun - CS_GZG_006_B | 2025-11-30 | 90814.7059 |  | 2026-02-05
9 | [8 empty] | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 47700 |  | Cosmic Sun - CS_GZG_007_B | 2025-12-31 | 45407.3529 |  | 2026-02-13
9 | [8 empty] | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 47700 |  | Cosmic Sun - CS_GZG_008_B | 2025-12-31 | 45407.3529 |  | 2026-03-15
9 | [8 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [8 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [8 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-09-01 | 191986 | 225865.8824 | 10 | 10. Site Logistics | [7 empty] | 0 | 0.0043192 |  | 364435
[9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
[6 empty] | 2025-09-01 |  |  | 10 | 10. Site Logistics | Security - July |  |  | 68600 | PO4055-DIP-Ph2-Gezi-20250627 - RV Approved | Bidvest Protea Coin: 749745 | 2025-07-31 | 72467.8632 |  | 2025-09-01
[9 empty] | 10 | 10. Site Logistics | Security - August |  |  | 59780 |  | Bidvest Protea Coin: 760988 | 2025-09-30 | 41618.0831 |  | 2025-10-31
[6 empty] | 2025-09-30 |  |  | 10 | 10. Site Logistics | Security - September |  |  | 59780 |  | Bidvest Protea Coin: 760989 | 2025-09-30 | 42250.3031 |  | 2025-10-09
[9 empty] | 10 | 10. Site Logistics | Security - October |  |  | 60760 |  | Bidvest Protea Coin: 763696 | 2025-10-31 | 4428.63 |  | 2025-11-13
10 |  | Scaffolding |  |  | 51911 | 2025-09-30 |  |  | 10 | 10. Site Logistics | Security - November |  |  | 10780 |  | Bidvest Protea Coin: 773193 | 2025-12-31 | 4323.91 |  | 2026-01-15
10 |  | Security |  |  | 114000 | 2025-09-30 |  |  | 10 | 10. Site Logistics | Security - December |  |  | 35280 |  | Bidvest Protea Coin: 768743 | 2026-01-31 | 0 |  | 2026-02-05
10 |  | Storage |  |  | 17575 | 2025-09-30 |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [8 empty] | 10 | 10. Site Logistics | Project Kick Off | 69455 | 10% | 6945.5 | PO3868-DIP-Ph2-Gezi-20250512 - RV Approved | Cosmic Sun: CS_GZG_001 | 2025-05-31 | 8551.1514 |  | 2025-05-15
10 | [8 empty] | 10 | 10. Site Logistics | Site Establishment |  | 15% | 10418.25 |  | Cosmic Sun: CS_GZG_002 | 2025-06-30 | 12303.8035 |  | 2025-06-26
10 | [8 empty] | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 13891 |  | Cosmic Sun - CS_GZG_004 | 2025-08-31 | 15182.3231 |  | 2025-10-24
10 | [8 empty] | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 17363.75 |  | Cosmic Sun - CS_GZG_003_B | 2025-11-30 | 11245.3691 |  | 2025-12-18
10 | [8 empty] | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 6945.5 |  | Cosmic Sun - CS_GZG_005_B | 2025-11-30 | 4498.1477 |  | 2026-01-29
10 | [8 empty] | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 6945.5 |  | Cosmic Sun - CS_GZG_006_B | 2025-11-30 | 4498.1477 |  | 2026-02-05
10 | [8 empty] | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 3472.75 |  | Cosmic Sun - CS_GZG_007_B | 2025-12-31 | 2249.0681 |  | 2026-02-13
10 | [8 empty] | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 3472.75 |  | Cosmic Sun - CS_GZG_008_B | 2025-12-31 | 2249.0781 |  | 2026-03-15
10 | [8 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [8 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [8 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 23859.5 | 2025-09-30 | 158578.5 | 186562.9412 | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 26198.38 |  | Sunspot Investments E027 | 2025-07-31 | 38186.0914 | 0.0024512 | 2026-01-29 | 126810.13
11 |  | Structural Sign Off |  |  | 47719 | 2025-09-30 |  |  | 11 | 11. Due Dilligence | Structural Sign Off (Includes Seshego Circle) |  |  | 7811.75 | PO3745-DIP-Ph2-20250313 - RV Approved | L&B Consulting - Invoice 1934 | 2025-04-30 | 32551.7616 |  | 2025-04-10
11 |  | Grid Study |  |  | 80000 | 2025-09-30 |  |  | 11 | 11. Due Dilligence | Grid Study |  |  | 79700 | PO4079-DIP-Ph2-Gezi-20250701 - RV Approved | Okusha EE19 | 2025-07-31 | 82803.6633 |  | 2026-03-31
11 |  | Lightning Risk Assessment |  |  | 7000 | 2025-09-30 |  |  | 11 | 11. Due Dilligence | Lightning Risk Assessment |  |  | 5100 | PO3844-Dipula Ph2-20250430 - RV Approved | LPS Inv: IN306837 | 2025-04-30 | 21251.8301 |  | 2025-06-26
11 | [5 empty] | 2025-09-30 |  |  | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 8000 |  | Matriarch - INV-6571 | 2026-02-28 | 11769.5923 |  | 2026-03-31
2025-09-30
12 | BDP Commission | Referral Fee |  |  | 98739.2981 | 2025-09-30 | 131652.3975 | 0 | 12 | 12. BDP Commission | Referral Fee | [9 empty] | 0
12 | BDP Commission | PD Fee |  |  | 32913.0994 | 2025-09-30 |  |  | 12 | 12. BDP Commission | PD Fee
13 | Engineering | Matriarch Defects Period |  |  | 74142.736 | 2025-12-31 | 286542.736 | 325616.7455 | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 108660.6076 |  |  | 2026-03-31 | 325616.7455 | 0 | 2026-04-30 | 108660.6076
13 |  | Management |  |  | 48000 | 2025-12-31 |  |  | 13 | 13. Engineering | Management |  |  | 0 |  |  |  | 0
13 |  | Project manager |  |  | 68000 | 2025-12-31 |  |  | 13 | 13. Engineering | Project manager |  |  | 0 |  |  |  | 0
13 |  | Planner time |  |  | 62400 | 2025-12-31 |  |  | 13 | 13. Engineering | Planner time |  |  | 0 |  |  |  | 0
13 |  | De Snagging |  |  | 34000 | 2025-12-31 |  |  | 13 | 13. Engineering | De Snagging |  |  | 0 |  |  |  | 0
13 | [8 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 16625 | 2025-05-08 | 16625 | 19558.8235 | 14 | 14. General Expenses | Travel |  |  | 2022.74 |  | Site Visit | 2025-04-30 | 2581.9413 | -0.0012047 | 2025-05-08 | 14988.86
14 | [5 empty] | 2025-04-30 |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-04-30 | 0 |  | 2025-04-30
14 | [5 empty] | 2025-06-09 |  |  | 14 | 14. General Expenses | Travel |  |  | 1399.46 |  | Expense Claim | 2025-05-31 | 3254.7881 |  | 2025-06-09
14 | [5 empty] | 2025-07-04 |  |  | 14 | 14. General Expenses | Travel |  |  | 3154.74 |  | Expense Claim | 2025-06-30 | 5031.9455 |  | 2025-07-04
14 | [5 empty] | 2025-07-31 |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-07-31 | 0 |  | 2025-07-31
14 | [5 empty] | 2025-08-31 |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-08-31 | 0 |  | 2025-08-31
14 | [5 empty] | 2025-09-30 |  |  | 14 | 14. General Expenses | Travel |  |  | 980.56 |  | Expense Claim | 2025-09-30 | 2071.1254 |  | 2025-10-10
14 | [5 empty] | 2025-10-31 |  |  | 14 | 14. General Expenses | Travel |  |  | 3618.49 |  | Expense Claim | 2025-10-31 | 3650.162 |  | 2025-11-06
14 | [5 empty] | 2025-11-30 |  |  | 14 | 14. General Expenses | Travel |  |  | 1827.75 |  | Expense Claim | 2025-11-30 | 1572.1723 |  | 2025-12-05
14 | [5 empty] | 2025-12-31 |  |  | 14 | 14. General Expenses | Travel |  |  | 495.04 |  | Expense Claim | 2025-12-31 | 698.1003 |  | 2026-01-08
14 | [8 empty] | 14 | 14. General Expenses | Travel |  |  | 990.08 |  | Expense Claim | 2026-01-31 | 349.295 |  | 2026-02-05
[9 empty] | 14 | 14. General Expenses | Travel |  |  | 500 |  |  | 2026-02-28 | 349.295 |  | 2026-03-05
14 | [8 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | Welcome Bonus |  |  | 1800000 | 2025-07-11 | 1800000 | 1800000 | 15 | 15. Service Add On | Welcome Bonus- Site Establishment |  |  | 752000 |  | Luxanio Trading - 23400/202506/274897/I | 2025-06-30 | 865473.1458 | -5167.1847 | 2025-07-11 | 1532750
15 | [8 empty] | 15 | 15. Service Add On | Welcome Bonus- Commissioning |  |  | 752000 |  | Luxanio Trading - 23400/202506/274897/I | 2025-06-30 | 865473.1458 |  | 2026-01-15
15 | [8 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [5 empty] | 2025-08-31 |  |  | 15 | 15. Service Add On | Community Engagement |  |  | 0 |  |  | 2025-08-31 | 69053.71 |  | 2025-08-31
15 | [8 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [8 empty] | 15 | 15. Service Add On | CS - Standing Time - VO |  |  | 19400 |  | Cosmic Sun - CS_GZG_009 | 2025-09-30 | 0 |  | 2025-10-24
15 | [8 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [8 empty] | 15 | 15. Service Add On | Client Electrician Labour |  |  | 4950 | PO4500-DIP-Ph2-Gezi-20251127 - RV Approved | Ecom Electrical | 2025-11-30 | 0 |  | 2025-11-28
15 | [8 empty] | 15 | 15. Service Add On | Metering Data - Powertech |  |  | 4400 | PO4652-DIP-Ph2-Gezi-20260303 - RV Approved | PowerTech - INV0001463 | 2026-02-28 | 5167.1832 |  | 2026-02-28
15 | [8 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [8 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [8 empty] | 15 | 15. Service Add On | [7 empty] | 0
| Panel Procurement Budget | 2005152.38 |  | 2179513.4565
| Inverter Procurement Budget | 560000 |  | 608695.6522
| Mounting Structure Budget | 429471 |  | 466816.3043
| DC Equipment Budget | 748943.9 |  | 814069.4565
| AC Equipment Budget | 1016362.1 |  | 1104741.413
| Monitoring Budget | 49000 |  | 53260.8696
| Optional Extras Budget | 0 |  | 0
| MV Metering Budget | 0 |  | 0
| ADD ON | 0 |  | 0
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 238595 |  | 280700
| DC Installer Budget | 533330 |  | 627447.0588
| In-House Expense Budget | 286542.736 |  | 325616.7455
| Compliance Budget | 158578.5 |  | 186562.9412
| Offloading Budget | 8500 |  | 10000
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 17575 |  | 20676.4706
| On Site Security | 114000 |  | 134117.6471
| Roof Access Budget for Installers | 51911 |  | 61071.7647
| EPC Management Fee | 0 |  | 0
| ADD ON | 1800000 |  | 1800000
Expenses
| Total EE Expense Budget | 16625 |  | 19558.8235
Note on H45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Roedolph Venter have we arranged for 60 days payment terms with AccuEnergy? Our terms is 30 days from statement making it payable 31 May and not 30 June.
Note on W127: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 8692848.61 | 8692848.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1738569.722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1303927.2915 | 0 | 0 | 1738569.722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3477139.444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 434642.4305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1738569.722 | 1738569.722 | 1738569.722 | 1738569.722 | 1738569.722 | 1738569.722 | 1738569.722 | 1738569.722 | 1738569.722 | 1738569.722 | 1738569.722 | 1738569.722 | 3042497.0135 | 3042497.0135 | 3042497.0135 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 8258206.1795 | 8258206.1795 | 8258206.1795 | 8258206.1795 | 8258206.1795 | 8258206.1795 | 8258206.1795 | 8258206.1795 | 8258206.1795 | 8258206.1795 | 8258206.1795 | 8258206.1795 | 8258206.1795 | 8258206.1795 | 8258206.1795 | 8258206.1795 | 8258206.1795 | 8258206.1795 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61
| Planned Expenditure | 8166239.0135 | 8166239.0135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16625 | 771925 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 1800000 | 34000 | 0 | 3450985.48 | 0 | 0 | 1308943.9 | 0 | 8500 | 0 | 0 | 0 | 473716.8975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286542.736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16625 | 788550 | 788550 | 803550 | 803550 | 803550 | 803550 | 803550 | 803550 | 2603550 | 2637550 | 2637550 | 6088535.48 | 6088535.48 | 6088535.48 | 7397479.38 | 7397479.38 | 7405979.38 | 7405979.38 | 7405979.38 | 7405979.38 | 7879696.2775 | 7879696.2775 | 7879696.2775 | 7879696.2775 | 7879696.2775 | 7879696.2775 | 7879696.2775 | 7879696.2775 | 7879696.2775 | 7879696.2775 | 7879696.2775 | 7879696.2775 | 7879696.2775 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135 | 8166239.0135
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1738569.722 | 1721944.722 | 950019.722 | 950019.722 | 935019.722 | 935019.722 | 935019.722 | 935019.722 | 935019.722 | 935019.722 | -864980.278 | -898980.278 | 404947.0135 | -3046038.4665 | -3046038.4665 | -1307468.7445 | -2616412.6445 | -2616412.6445 | -2624912.6445 | -2624912.6445 | -2624912.6445 | -2624912.6445 | -3098629.542 | -3098629.542 | -3098629.542 | -3098629.542 | -3098629.542 | 378509.902 | 378509.902 | 378509.902 | 378509.902 | 378509.902 | 378509.902 | 378509.902 | 378509.902 | 91967.166 | 91967.166 | 91967.166 | 91967.166 | 91967.166 | 91967.166 | 91967.166 | 91967.166 | 91967.166 | 91967.166 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965 | 526609.5965
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 8692848.61 | 8692848.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1738569.722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3042497.0135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3477139.444 | 0 | 434642.4305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1738569.722 | 1738569.722 | 1738569.722 | 1738569.722 | 1738569.722 | 1738569.722 | 1738569.722 | 1738569.722 | 1738569.722 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 4781066.7355 | 8258206.1795 | 8258206.1795 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61 | 8692848.61
| Actual + Planned Expenditure | 7090051.4276 | 7090051.4276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7811.75 | 0 | 0 | 0 | 2022.74 | 151851.85 | 2250.5 | 14805 | 0 | 1399.46 | 0 | 232877.775 | 18088.74 | 752000 | 8598.35 | 0 | 1080575.0491 | 0 | 0 | 2087530.4309 | 0 | 68600 | 0 | 0 | 0 | 0 | 60760.56 | 0 | 338723.7 | 59780 | 3618.49 | 60760 | 6000 | 4950 | 1827.75 | 16488 | 429135.975 | 0 | 6506 | 495.04 | 762780 | 6969 | 277471.98 | 188121.93 | 75925.925 | 0 | 157408.9 | 500 | 75925.925 | 0 | 0 | 87700 | 0 | 0 | 0 | 39790.6076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7811.75 | 7811.75 | 7811.75 | 7811.75 | 9834.49 | 161686.34 | 163936.84 | 178741.84 | 178741.84 | 180141.3 | 180141.3 | 413019.075 | 431107.815 | 1183107.815 | 1191706.165 | 1191706.165 | 2272281.2141 | 2272281.2141 | 2272281.2141 | 4359811.645 | 4359811.645 | 4428411.645 | 4428411.645 | 4428411.645 | 4428411.645 | 4428411.645 | 4489172.205 | 4489172.205 | 4827895.905 | 4887675.905 | 4891294.395 | 4952054.395 | 4958054.395 | 4963004.395 | 4964832.145 | 4981320.145 | 5410456.12 | 5410456.12 | 5416962.12 | 5417457.16 | 6180237.16 | 6187206.16 | 6464678.14 | 6652800.07 | 6728725.995 | 6728725.995 | 6886134.895 | 6886634.895 | 6962560.82 | 6962560.82 | 6962560.82 | 7050260.82 | 7050260.82 | 7050260.82 | 7050260.82 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276 | 7090051.4276
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7811.75 | -7811.75 | -7811.75 | 1730757.972 | 1728735.232 | 1576883.382 | 1574632.882 | 1559827.882 | 1559827.882 | 1558428.422 | 1558428.422 | 1325550.647 | 4349958.9205 | 3597958.9205 | 3589360.5705 | 3589360.5705 | 2508785.5214 | 2508785.5214 | 2508785.5214 | 421255.0905 | 421255.0905 | 352655.0905 | 352655.0905 | 352655.0905 | 352655.0905 | 352655.0905 | 291894.5305 | 291894.5305 | -46829.1695 | -106609.1695 | -110227.6595 | -170987.6595 | -176987.6595 | -181937.6595 | -183765.4095 | -200253.4095 | -629389.3845 | -629389.3845 | 2841244.0595 | 2840749.0195 | 2512611.45 | 2505642.45 | 2228170.47 | 2040048.54 | 1964122.615 | 1964122.615 | 1806713.715 | 1806213.715 | 1730287.79 | 1730287.79 | 1730287.79 | 1642587.79 | 1642587.79 | 1642587.79 | 1642587.79 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824 | 1602797.1824
|  | CHECK | CHECK
| Revenue Recognition | -5167.1689 | 8698015.7789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75615.558 | 0 | 0 | 0 | 204468.1797 | 0 | 0 | 0 | 0 | 6338584.9275 | 0 | 0 | 0 | 193457.6179 | 0 | 0 | 0 | 917804.2058 | 0 | 0 | 0 | 0 | 85939.5116 | 0 | 0 | 0 | 8078.792 | 0 | 0 | 0 | 430480.0132 | 0 | 0 | 0 | 0 | 100334.8624 | 0 | 0 | 0 | 349.295 | 0 | 0 | 0 | 17286.0705 | 0 | 0 | 0 | 0 | 325616.7455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 8698015.7789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75615.558 | 75615.558 | 75615.558 | 75615.558 | 280083.7376 | 280083.7376 | 280083.7376 | 280083.7376 | 280083.7376 | 6618668.6651 | 6618668.6651 | 6618668.6651 | 6618668.6651 | 6812126.283 | 6812126.283 | 6812126.283 | 6812126.283 | 7729930.4888 | 7729930.4888 | 7729930.4888 | 7729930.4888 | 7729930.4888 | 7815870.0004 | 7815870.0004 | 7815870.0004 | 7815870.0004 | 7823948.7924 | 7823948.7924 | 7823948.7924 | 7823948.7924 | 8254428.8056 | 8254428.8056 | 8254428.8056 | 8254428.8056 | 8254428.8056 | 8354763.668 | 8354763.668 | 8354763.668 | 8354763.668 | 8355112.963 | 8355112.963 | 8355112.963 | 8355112.963 | 8372399.0335 | 8372399.0335 | 8372399.0335 | 8372399.0335 | 8372399.0335 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789 | 8698015.7789

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | Grand Total
(blank)
1. Panels |  |  |  | 2179513.4565 |  |  |  |  | 0 |  | 0 |  |  | 2179513.4565
2. Inverters | 0 |  |  | 608695.6522 | [6 empty] | 0 |  |  | 608695.6522
3. Mounting Structures |  |  |  | 466816.3043 |  |  |  |  | 0 |  | 0 |  |  | 466816.3043
4. DC Equipment |  |  | 37001.3284 | 498432.3141 |  | 278635.811 |  |  |  | 0 | 0 |  |  | 814069.4535
5. Monitoring |  | 19230.025 | 14379.2479 | 19651.5947 | [6 empty] | 0 |  |  | 53260.8676
6. AC Equipment |  |  | 50466.9579 | 680971.5064 |  | 373302.95 |  |  |  |  | 0 |  |  | 1104741.4143
8. Product Add On
9. AC & DC installation |  |  | 90814.7059 | 136222.0588 |  | 181629.4118 |  |  | 408666.1765 | 90814.7059 | 0 |  |  | 908147.0588
10. Site Logistics | 0 |  | 8551.1514 | 12303.8035 | 72467.8632 | 15182.3231 | 83868.3862 | 4428.63 | 20241.6645 | 8822.0562 | 0 | 0 |  | 225865.878
11. Due Dilligence |  | 53803.5917 |  |  | 120989.7547 | [7 empty] | 11769.5923 | 186562.9387
13. Engineering | 0 | [9 empty] | 0 |  | 325616.7455 | 325616.7455
14. General Expenses |  | 2581.9413 | 3254.7881 | 5031.9455 | 0 | 0 | 2071.1254 | 3650.162 | 1572.1723 | 698.1003 | 0 | 349.295 | 349.295 | 19558.8247
15. Service Add On | 0 |  |  | 1730946.2916 |  | 69053.71 | 0 |  | 0 |  | 0 |  |  | 1800000.0016
12. BDP Commission
7.BESS
Grand Total | 0 | 75615.558 | 204468.1797 | 6338584.9275 | 193457.6179 | 917804.2058 | 85939.5116 | 8078.792 | 430480.0132 | 100334.8624 | 0 | 349.295 | 337735.6328 | 8692848.5957

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | Grand Total
(blank)
1. Panels |  |  |  | 1898818.2 |  |  |  |  | 6969 |  |  |  | 1905787.2
2. Inverters |  |  |  | 332186.77 | [8 empty] | 332186.77
3. Mounting Structures |  |  |  | 245639.2 |  |  |  |  | 6506 |  |  |  | 252145.2
4. DC Equipment |  |  | 29247.35 | 392271.025 |  | 219355.125 |  |  |  | 147200 |  |  | 788073.5
5. Monitoring |  | 14805 | 10848.85 | 15148.29 | [8 empty] | 40802.14
6. AC Equipment |  |  | 20259 | 277452.52 |  | 151942.5 | [6 empty] | 449654.02
8. Product Add On |  |  |  | 95783 |  |  |  | 15620 | 22488 |  | 87595.1 | -1728.1 | 219758
9. AC & DC installation |  |  | 95400 | 143100 |  | 190800 |  |  | 429300 | 95400 |  |  | 954000
10. Site Logistics |  |  | 6945.5 | 10418.25 | 68600 | 13891 | 119560 | 60760 | 31254.75 | 17725.5 | 35280 |  | 364435
11. Due Dilligence |  | 12911.75 |  |  | 105898.38 | [6 empty] | 8000 | 126810.13
13. Engineering | 0 | [10 empty] | 108660.6076 | 108660.6076
14. General Expenses |  | 2022.74 | 1399.46 | 3154.74 | 0 | 0 | 980.56 | 3618.49 | 1827.75 | 495.04 | 990.08 | 500 | 14988.86
15. Service Add On |  |  |  | 1504000 |  | 0 | 19400 |  | 4950 |  |  |  | 1528350
12. BDP Commission
7.BESS
Grand Total | 0 | 29739.49 | 164100.16 | 4917971.995 | 174498.38 | 575988.625 | 139940.56 | 79998.49 | 503295.5 | 260820.54 | 123865.18 | 115432.5076 | 7085651.4276

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate | [5 empty] | FINANCIAL CLOSE CERTIFICATE
Project Name: | Gezina Galleries
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion: |  |  |  | 1. Financial Close | 1. Financial Close
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 0.29129 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.14901 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.10081 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 0.24126 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
Gezina Galleries |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Gezina Galleries | 0 | 0 | 0