## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | PLANNED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW
1 | Planned Revenue | 11535559.451 |  | 11729547.531 |  |  | 11729547.531 | Start Date
2 | Planned Expenditure | 10556110.2244 |  | 11767622.9706 | VO PM Limit | Current VO Total | 10805125.0743 | 2025-02-03
3 | Planned Profit | 979449.2266 |  | -38075.4396 | 48972.4613 | 1033460.29 | 924422.4567 | End Date - PC
4 | Planned Margin | 8.491% |  | -0.3246% |  |  | 7.881% | 2025-04-25
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Deposit |  | 35% | 4037445.8079 |  | 2024-12-09 | 004646 | 2025-01-16 | 2025-01-22
2 | Delivery of Main Equipment (Solar Panels Inverters and Balance of System) |  | 30% | 3460667.8353 |  | 2025-02-24 | 004646 | 2025-01-16 | 2025-02-07
3 | Delivery of Main Equipment (Inverters, Batteries and Balance of System) |  | 20% | 2307111.8902 |  | 2025-03-17 | 004646 | 2025-01-16 | 2025-01-22
4 | Installation Completion Date (Physical Completion) |  | 10% | 1153555.9451 |  | 2025-05-16 | 004646 | 2025-01-16 | 2025-05-12
5 | Handover |  | 5% | 576777.9726 |  | 2025-06-02 | 004646 | 2025-01-16 | 2025-06-27
6 | VO - Roof Repairs |  | 70% | 73118.58 |  | 2025-05-16 | 004636 | 2024-12-13 | 2024-12-13
6 | VO - Roof Repairs |  |  | 76103.02 |  | 2025-06-02 | 004636 | 2024-12-13 | 2025-02-13
6 | VO - Roof Repairs |  | 30% | 44766.48 |  | 2025-05-16 | 004654 | 2025-01-27 | 2025-02-13
|  |  | 200% | 11729547.531
KEY: | contains an error (in result or a check has failed)
| Red Font - IF TEXT : content not yet confirmed |  |  |  |  | 663294.6684
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
[7 empty] | 5517006.9565 | 1479561.1487
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 4105341.6359
2 | Delivery of Panels |  | 30% | 3518864.2593
3 | Delivery of Inverters |  | 20% | 2345909.5062
4 | Practical Completion |  | 10% | 1172954.7531
5 | Handover |  | 5% | 586477.3766
| Total |  | 100% | 11729547.531
|  |  | 100% | 11729547.531

## Project Plan
[9 empty] | 2026-02-12 | 2026-02-12
| PROJECT PLAN | Mayo Macs | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 400
SITE ADDRESS
| BUSINESS DEVELOPER | Megan
| PROJECT MANAGERS | JT
| INSTALLER | TBC
| CONTRACT VALUE | 11535559.451
| Phase: | DLP
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status |  | Comment
|  |  | 81 |  |  | 93 |  | 100% | 100%
1 | Project Initiation | 2024-10-29 | 25 | 2024-11-23 | 2024-11-15 | 25 | 2025-01-28 | 100% | 100%
1.1 | BD Handover | 2024-11-15 | 1 | 2024-11-18 | 2024-11-15 | 1 | 2024-11-18 | 100% | 100%
1.2 | Project Introduction | 2025-01-16 | 1 | 2025-01-17 | 2025-01-16 | 1 | 2025-01-17 | 100% | 100%
1.3 | HSE | 2025-01-10 | 10 | 2025-01-24 | 2025-01-10 | 10 | 2025-01-24 | 100% | 100%
1.4 | Installer Kick Off | 2025-01-27 | 1 | 2025-01-28 | 2025-01-27 | 1 | 2025-01-28 | 100% | 100%
1.5 | Project Review | 2025-01-22 | 1 | 2025-01-23 | 2025-01-22 | 1 | 2025-01-23 | 100% | 100%
2 | Site Establishment | 2025-01-27 | 8 | 2025-02-04 | 2025-01-27 | 9 | 2025-02-05 | 100% | 100%
2.1 | Installer on site & Roof Assessment | 2025-02-03 | 1 | 2025-02-04 | 2025-02-03 | 2 | 2025-02-05 | 100% | 100% |  | 155
2.2 | Battery/Inverter Room Construction | 2025-01-27 | 30 | 2025-03-10 | 2025-01-27 | 40 | 2025-03-25 | 100% | 100% |  | 160
3 | AC Installation | 2025-01-15 | 84 | 2025-04-09 | 2025-01-15 | 90 | 2025-04-15 | 100% | 100% |  | 31
3.1.1 | Inverters delivered | 2025-02-24 | 1 | 2025-02-25 | 2025-02-20 | 1 | 2025-02-21 | 100% | 100%
3.1.2 | Hybrid Inverters Delivered | 2025-02-24 | 1 | 2025-02-25 | 2025-03-13 | 1 | 2025-03-14 | 100% | 100%
3.1.3 | Batteries Delivered | 2025-01-15 | 30 | 2025-02-26 | 2025-01-15 | 41 | 2025-03-13 | 100% | 100%
3.2 | Inverters Mounted | 2025-02-25 | 10 | 2025-03-11 | 2025-03-14 | 1 | 2025-03-17 | 100% | 100% |  | 12.9032
3.3 | Solar DB Lead Time | 2025-01-27 | 30 | 2025-03-10 | 2025-01-27 | 40 | 2025-03-25 | 100% | 100%
3.4 | AC Works | 2025-03-11 | 20 | 2025-04-09 | 2025-03-17 | 20 | 2025-04-15 | 100% | 100%
3.5 | AC Tie-In | 2025-04-02 | 3 | 2025-04-07 | 2025-04-08 | 1 | 2025-04-09 | 100% | 100%
4 | DC Works | 2025-02-03 | 28 | 2025-03-03 | 2025-02-12 | 64 | 2025-04-17 | 100% | 100%
4.1 | Mounting Structure delivered | 2025-02-03 | 1 | 2025-02-04 | 2025-02-12 | 1 | 2025-02-13 | 100% | 100%
4.2 | Mounting Structure installation | 2025-02-04 | 12 | 2025-02-20 | 2025-02-13 | 12 | 2025-03-03 | 100% | 100%
4.3 | DC Cable delivered | 2025-02-03 | 1 | 2025-02-04 | 2025-02-20 | 1 | 2025-02-21 | 100% | 100%
4.4 | DC Stringing | 2025-02-04 | 19 | 2025-03-03 | 2025-03-22 | 19 | 2025-04-17 | 100% | 100%
5 | Module installation | 2025-02-03 | 53 | 2025-03-28 | 2025-02-20 | 40 | 2025-04-01 | 100% | 100%
5.1 | Module delivery | 2025-02-03 | 1 | 2025-02-04 | 2025-02-20 | 1 | 2025-02-21 | 100% | 100%
5.2 | Module mounting | 2025-02-13 | 30 | 2025-03-28 | 2025-02-24 | 25 | 2025-04-01 | 100% | 100%
6 | Commissioning | 2025-04-09 | 16 | 2025-04-25 | 2025-04-17 | 20 | 2025-05-07 | 100% | 100%
6.1 | Commissioning | 2025-04-09 | 5 | 2025-04-16 | 2025-04-17 | 5 | 2025-04-29 | 100% | 100%
6.2 | Practical Completion | 2025-04-16 | 5 | 2025-04-25 | 2025-04-29 | 5 | 2025-05-07 | 100% | 100%
6.3 | Post-Installation Commissioning | 2025-04-25 | 10 | 2025-05-13 | 2025-05-07 | 15 | 2025-05-28 | 100% | 100%
7 | QA Inspections | 2025-04-09 | 14 | 2025-04-23 | 2025-05-07 | 19 | 2025-05-26 | 100% | 100%
7.1 | Red-Team Inspection | 2025-04-09 | 8 | 2025-04-23 | 2025-05-07 | 13 | 2025-05-26 | 100% | 100%
8 | Project Closure | 2025-04-05 | 37 | 2025-05-12 | 2025-05-03 | 131 | 2025-09-11 | 100% | 100%
8.1 | Equipment serial numbers | 2025-04-05 | 2 | 2025-04-08 | 2025-05-03 | 2 | 2025-05-06 | 100% | 100%
8.2 | Snags completion | 2025-04-09 | 2 | 2025-04-11 | 2025-05-26 | 73 | 2025-09-05 | 100% | 100%
8.3 | System Performance Monitoring | 2025-04-25 | 2 | 2025-04-30 | 2025-08-22 | 10 | 2025-09-05 | 100% | 100%
8.4 | Handover documentation | 2025-04-23 | 10 | 2025-05-09 | 2025-05-03 | 5 | 2025-05-09 | 100% | 100%
8.5 | Handover to Client | 2025-05-09 | 1 | 2025-05-12 | 2025-09-10 | 1 | 2025-09-11 | 100% | 100%
8.6 | Handover to Matriarch | 2025-04-16 | 5 | 2025-04-25 | 2025-07-17 | 25 | 2025-08-21 | 100% | 100%
Formulas:
Actual Start = MIN([Actual Start, row below]:I18)
Actual Start = WORKDAY.INTL([Actual End, row above],0,1,Data!$C3:C26)-7
Actual End = MAX([Actual End, row below]:K18)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C26)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C26)
Planned End = MAX([Planned End, row below])
Planned Start = MIN([Planned Start, row below]:E23)
Planned Start = [Planned Start, row above]

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  |  | COSTED |  | PLANNED |  | ACTUAL | Difference from costed | Difference from planned
| EXPENDITURE |  | 10556110.2244 |  | 10804925.0743 |  | 11767622.9706 | -1211512.7462 | -962697.8963
| No. | Item | Costed Expenditure |  | Planned Expenditure |  | Actual Expenditure | Saving / Overrun | Saving / Overrun | Comments on variations from planned expenditure
| 1 | Panels | 1077596.56 |  | 948317.8 |  | 908317.8 | 169278.76 | 40000
| 2 | Inverters | 210000 |  | 252941.6025 |  | 180931.83 | 29068.17 | 72009.7725
| 3 | Mounting Structures | 180180 |  | 86297.652 |  | 86550.7 | 93629.3 | -253.048
| 4 | DC Equipment | 344364.8 |  | 313434 |  | 362150 | -17785.2 | -48716
| 5 | Monitoring | 174000 |  | 50640.35 |  | 68208.04 | 105791.96 | -17567.69
| 6 | AC Equipment | 381282.7261 |  | 1167527.65 |  | 1167527.6575 | -786244.9314 | -0.0075
| 7 | Battery Systems | 7393826.9565 |  | 6474594 |  | 6386529 | 1007297.9565 | 88065
| 8 | Product Add On | 0 |  | 135656 |  | 418886.97 | -418886.97 | -283230.97
| 9 | AC & DC Installation | 342160 |  | 676952 |  | 676952 | -334792 | 0
| 10 | Site Logistics | 54108.8333 |  | 314687 |  | 114637 | -60528.1667 | 200050
| 11 | Due Dilligence | 111020 |  | 82026.4 |  | 38759.07 | 72260.93 | 43267.33
| 12 | BDP Commission | 0 |  | 0 |  | 0 | 0 | 0
| 13 | Engineering | 239970.3484 |  | 255808.0931 |  | 144194.4931 | 95775.8553 | 111613.6 | RV: Matriarch defects percentage 1.25%
| 14 | General Expenses | 47600 |  | 46042.5267 |  | 67232.7 | -19632.7 | -21190.1733
| 15 | Service Add On | 0 |  | 0 |  | 1146745.71 | -1146745.71 | -1146745.71
|  | check: | 0 | #REF! | 0 | #REF! | 0
Copy amounts in column H and paste as values at Project review.

## Data (hidden)
Public holidays |  | Drop down list
2024-01-01 | New Years Day | Approved
2024-03-21 | Human Rights day | Pending
2024-03-29 | Good Friday | Declined
2024-04-01 | Family Day | Abanded
2024-05-01 | Workers day
2024-06-17 | Youth Day Holiday
2024-08-09 | Womens Day
2024-09-24 | Heritage Day
2024-12-16 | Day of Reconciliation
2024-12-25 | Christmas Day
2024-12-26 | Day of Goodwill |  | Manual dates
2025-01-01 | New Years Day
2025-03-21 | Human Rights day
2025-04-18 | Good Friday
2025-04-21 | Family Day
2025-04-27 | Freedom Day
2025-04-28 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 10556110.2244 | 11729547.531 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY |  |  |  |  | 11767622.9706
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | Project Related date | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS | PO NUMBER | COMMENTS
1 | Panels | Jinko 580W | 728 | 1425.27 | 1037596.56 | 2025-04-21 | 1077596.56 | 1171300.6087 |  | 1 | 1. Panels | Jinko 585W | 683.7607 | 1327.95 | 908317.8 | Menlo Inv0002362 | 2024-12-31 | 1146065.703 | -0.0042663 | 2025-02-20 | 908317.8 |  |  | 19
1 | [9 empty] | 1 | 1. Panels | [5 empty] | 2025-01-31 | 25234.91 | [5 empty] | BUDGET - Solar | Installer Allocation
1 |  | Module delivery to site |  |  | 40000 | 2025-04-21 |  |  |  | 1 | 1. Panels | Module delivery to site | [5 empty] | 0 | [5 empty] | AC Equipment | 1142809.6826
1 | [9 empty] | 1 | 1. Panels | [6 empty] | 0 | [5 empty] | DC Equipment | 202684.8
1 | [9 empty] | 1 | 1. Panels | [6 empty] | 0 | [5 empty] | AC Labour | 446100 | 3.1864
1 | [9 empty] | 1 | 1. Panels | [6 empty] | 0 | [5 empty] | DC Labour | 242060 | 1.729
[24 empty] | Offloading | 8500
2 | Inverters | Huawei 100KTL | 3 | 70000 | 210000 | 2025-03-26 | 210000 | 228260.8696 |  | 2 | 2. Inverters | Huawei 100KTL | 3 | 68870 | 206611.05 | Menlo Inv0002362 | 2024-12-31 | 179134.8498 | -0.0043874 | 2025-02-20 | 180931.83 |  |  | Roof Access/Scaffolding | 40675.5
2 | [9 empty] | 2 | 2. Inverters | Huawei 50KTL | 1 | 43190.78 | 43190.78 | Menlo INV0002702 | 2025-03-31 | 49126.0242 |  | 2025-05-08 |  | PO3735-MMS-20250311 - RV Approved |  | Storage | 4933.3333
2 | [9 empty] | 2 | 2. Inverters | Huawei 100KTL - Moved to stock (JHB) | 1 | -68870 | -68870 | Allocated to Joburg Storeroom | 2026-01-31 | 0 |  | 2026-01-31 |  |  |  | Telehandler | 0
2 | [9 empty] | 2 | 2. Inverters | [6 empty] | 0 | [5 empty] | Other | 0
[24 empty] | Total | 2087763.3159
3 | Mounting Structures | IBR Roof |  |  | 180180 | 2025-03-05 | 180180 | 195847.8261 |  | 3 | 3. Mounting Structures | IBR Roof - Schletter |  |  | 80274.7 | Schletter - INV1406 | 2025-02-28 | 186596.4211 | 0 | 2025-03-28 | 86550.7 | PO3638-MMS-20250211 - RV Approved |  | Less 15% | 1774598.8186 | [SM: Target Installation Price]
3 | [9 empty] | 3 | 3. Mounting Structures | Delivery |  |  | 3980 | Schletter - INV1406 | 2025-02-28 | 9251.4049 |  | 2025-03-28 |  | PO3638-MMS-20250211 - RV Approved |  | R/Wp | 4.4365
3 | [9 empty] | 3 | 3. Mounting Structures | End Clamps Top Up - JHB Warehouse | 100 | 11.48 | 1148 | Allocated from Stock | 2025-03-31 | 0 |  | 2025-03-31
3 | [9 empty] | 3 | 3. Mounting Structures | End Clamps Top Up - Scheltter | 100 | 11.48 | 1148 | Schletter - INV1611 | 2025-03-31 |  |  | 2025-04-30 |  | PO3756-MMS-20250319 - RV Approved |  | ACTUAL | Installer Price
[24 empty] | AC Equipment | 1142809.6826
4 | DC Equipment | DC Cable | 10120 | 14 | 141680 | 2025-03-05 | 344364.8 | 374309.5652 |  | 4 | 4. DC Equipment | DC Cable | 12000 | 13.3 | 159600 | Menlo Inv0002362 | 2024-12-31 | 187862.4449 | -0.0019967 | 2025-02-20 | 362150 |  |  | DC Equipment | 202684.8
4 |  | Project Kick Off |  | 10% | 20268.48 | 2025-01-27 |  |  |  | 4 | 4. DC Equipment | DC Cable |  |  | 55100 | Menlo INV0002767 | 2025-03-31 | 13110.7502 |  | 2025-05-22 |  | PO3765-MMS-20250325 - RV Approved |  | AC Labour | 100100 | 0.715
[10 empty] | 4 | 4. DC Equipment | DC Cable - Additional order due to inverter room placement - VO | 4000 | 13.3 | 53200 | MENLO - INV0002594 | 2025-02-28 | 72136.6255 |  | 2025-04-24 |  |  |  | DC Labour | 242060
4 | 202684.8 | Site Establishment |  | 15% | 30402.72 | 2025-02-03 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 94250 | 10% | 9425 | Matthews Group INV 1423 | 2025-01-31 | 11255.5359 |  | 2025-02-07 |  | PO3567-MMS-20250127 - RV Approved |  | Offloading | 8500 | 1.729
4 |  | AC Installation Complete |  | 20% | 40536.96 | 2025-04-09 |  |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 14137.5 | Matthews Group INV-1424 | 2025-01-31 | 16883.3039 |  | 2025-02-13 |  |  |  | Roof Access/Scaffolding | 40675.5
4 |  | DC Installation Complete |  | 25% | 50671.2 | 2025-03-03 |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 18850 | Matthews Group INV-1451 | 2025-04-30 | 19482.9085 |  | 2025-04-24 |  |  |  | Storage | 4933.3333
4 |  | Commissioning Complete |  | 10% | 20268.48 | 2025-04-25 |  |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 23562.5 | Matthews Group INV 1445 | 2025-04-30 | 24353.6356 |  | 2025-04-24 |  |  |  | Telehandler | 0
4 |  | Site De-establisment |  | 10% | 20268.48 | 2025-04-11 |  |  |  | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 9425 | Matthews Group INV 1452 | 2025-04-30 | 9741.4542 |  | 2025-05-08 |  |  |  | Other | 0
4 |  | Handover Document Complete |  | 5% | 10134.24 | 2025-05-09 |  |  |  | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 9425 | Matthews Group INV-1461 | 2025-05-31 | 9741.4542 |  | 2025-06-12 |  |  |  | Other | 0
4 |  | End of Defects Period |  | 5% | 10134.24 | 2025-08-07 |  |  |  | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 4712.5 | Matthews Group INV-1462 | 2025-06-30 | 4870.7271 |  | 2025-05-16 |  |  |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 4712.5 | Matthews Group INV-1463 | 2025-06-30 | 4870.7271 |  | 2025-07-31 |  |  |  | Total | 1741763.3159
[24 empty] | R/Wp | 4.3544
5 | Monitoring | Smartlogger 3000 |  |  | 26000 | 2025-03-26 | 174000 | 189130.4348 |  | 5 | 5. Monitoring | Smartlogger 3000 |  |  | 7639.54 | MENLO - INV0002488 | 2025-01-31 | 31106.6534 | -0.0048587 | 2025-02-20 | 68208.04
5 |  | Comms DB |  |  | 8000 | 2025-03-26 |  |  |  | 5 | 5. Monitoring | CTs, Router - AccuEnergy |  |  | 6486.5 | Accuenergy - INV ASAI-004649 | 2025-01-31 | 26411.709 |  | 2025-02-27 |  | PO3566-MMS-20250127 - RV Approved
[10 empty] | 5 | 5. Monitoring
5 | [9 empty] | 5 | 5. Monitoring | Data Guru - Herholdts |  |  | 27100 | Herholdts' - INV1005888 | 2025-02-28 | 86134.1805 |  | 2025-03-28 |  | PO3663-MMS-20250217 - RV Approved |  | ACTUAL - GreenWay Solar | Installer Price |  | ACTUAL - Matthews Group | Installer Price
5 |  | Apex Controller |  |  | 125000 | 2025-04-25 |  |  |  | 5 | 5. Monitoring | Revenue Grade Meter |  |  | 11169 | Matriach INV-3710 | 2025-01-31 | 45477.8968 |  | 2025-01-31 |  |  |  | AC Equipment | 2107709.65 |  | AC Equipment | 1167527.65 |  | 940182
5 |  | Revenue Grade Meter |  |  | 15000 | 2025-03-26 |  |  |  | 5 | 5. Monitoring | Meter + Fibre Optic Port + rogowski Coil |  |  | 15813 | Accuenergy Inv: ASAI-007060 | 2025-12-31 | 0 |  | 2026-01-07 |  |  |  | DC Equipment | 90086.98 |  | DC Equipment | 94250 |  | -4163.02
5 | [9 empty] | 5 | 5. Monitoring | [6 empty] | 0 | [5 empty] | AC Labour | 707500 | 1.7688 | AC Labour | 328952 | 0.82238 | 378548
[24 empty] | DC Labour | 487883 | 1.2197 | DC Labour | 348000 | 0.87 | 139883
6 | AC Equipment | Project Kick Off |  | 10% | 38128.2726 | 2025-01-27 | 381282.7261 | 414437.7457 |  | 6 | 6. AC Equipment | [6 empty] | 0 | 0 |  | 1167527.6575 |  |  | Roof Access | 45135.2 |  | Equipment Hire - Offloading & Rigging | 76862 |  | -31726.8
6 | [9 empty] | 6 | 6. AC Equipment | Project Kick Off | 1167527.65 | 10% | 116752.77 | Matthews Group INV 1423 | 2025-01-31 | 41443.7761 |  | 2025-02-07 |  | PO3567-MMS-20250127 - RV Approved |  | Offloading & Rigging | 46000 |  | Accommodation 6 Weeks |  |  | 46000
6 | 381282.7261 | Site Establishment |  | 15% | 57192.4089 | 2025-02-03 |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 175129.15 | Matthews Group INV-1424 | 2025-01-31 | 62165.6624 |  | 2025-02-13 |  |  |  | Site Costs and General | 45630 |  | HSE | 14375 |  | 31255
6 |  | AC Installation Complete |  | 20% | 76256.5452 | 2025-04-09 |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 233505.53 | Matthews Group INV-1451 | 2025-04-30 | 82887.5486 |  | 2025-04-24 |  |  |  | HSE | 15525 |  | Other | 0 |  | 15525
6 |  | DC Installation Complete |  | 25% | 95320.6815 | 2025-03-03 |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 291881.9125 | Matthews Group INV 1445 | 2025-04-30 | 103609.4358 |  | 2025-04-24 |  |  |  | Other | 0 |  | Other | 0 |  | 0
6 |  | Commissioning Complete |  | 10% | 38128.2726 | 2025-04-25 |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 116752.765 | Matthews Group INV 1452 | 2025-04-30 | 41443.7743 |  | 2025-05-08 |  |  |  | Other | 0 |  | VO | 190762.14 |  | -190762.14
6 |  | Site De-establisment |  | 10% | 38128.2726 | 2025-04-11 |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 116752.765 | Matthews Group INV-1461 | 2025-05-31 | 41443.7743 |  | 2025-06-12 |  |  |  | Other | 0 |  | Other | 0 |  | 0
6 |  | Handover Document Complete |  | 5% | 19064.1363 | 2025-05-09 |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 58376.3825 | Matthews Group INV-1462 | 2025-06-30 | 20721.8872 |  | 2025-05-16 |  |  |  | Total | 3545469.83 |  | Total | 2220728.79 |  | 1324741.04
6 |  | End of Defects Period |  | 5% | 19064.1363 | 2025-08-07 |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 58376.3825 | Matthews Group INV-1463 | 2025-06-30 | 20721.8872 |  | 2025-07-31 |  |  |  | R/Wp | 8.8637 |  | R/Wp | 5.5518
[27 empty] | R/kWh | 1.5862 | r
7 | Battery Systems | Battery Inverter + Battery Bank |  |  | 6161300 | 2025-03-05 | 7393826.9565 | 8036768.431 |  | 7 | 7. Battery Systems | Battery Inverter + Battery Bank | [5 empty] | 0 | -0.001275 |  | 6386529
7 | [9 empty] | 7 | 7. Battery Systems | ATESS -PCS630 |  |  | 521100 | Herholdts INV994108 | 2025-01-31 | 650850.7032 |  | 2025-02-13 |  | PO3539-MMS-20250114 - RV Approved
[10 empty] | 7 | 7. Battery Systems | ATESS -RTF600 |  |  | 584600 | Herholdts INV994108 | 2025-01-31 | 730161.8136 |  | 2025-02-13
[10 empty] | 7 | 7. Battery Systems | ATESS -TRF630 |  |  | 296000 | Herholdts INV994108 | 2025-01-31 | 369702.1841 |  | 2025-02-13
[10 empty] | 7 | 7. Battery Systems | FW-800/560-HV+ | 2 | 2461447 | 4922894 | Herholdts INV994324 | 2025-01-31 | 6148664.405 |  | 2025-02-13
[10 empty] | 7 | 7. Battery Systems | Storage/Delivery |  |  | 0 |  |  | 0
7 |  | Installation |  |  | 346000 | 2025-01-27 |  |  |  | 7 | 7. Battery Systems | [6 empty] | 0
7 |  | AC+DC Equipment |  |  | 498000 | 2025-01-27 |  |  |  | 7 | 7. Battery Systems | 3rd Aircon/Additional - RCF Tech - VO |  |  | 20645 | RCF Tech INV002 | 2025-07-31 | 0 |  | 2025-07-04 |  | PO4087-MMS-20250702 - RV Approved
7 |  | AC Cable |  |  | 263526.9565 | 2025-02-26 |  |  |  | 7 | 7. Battery Systems | [6 empty] | 0
7 |  | Airconditioned Container - 1 per 1000kWh |  |  | 125000 | 2025-02-26 |  |  |  | 7 | 7. Battery Systems | Airconditioned Container - 1 per 1000kWh (Provision for Commissioning Assistance) | [5 empty] | 0
7 | [9 empty] | 7 | 7. Battery Systems | Aircons - RCF Tech - Deposit |  |  | 33032 | RCF Tech QU001 | 2025-04-30 | 126963.8092 |  | 2025-04-10 |  | PO3789-MMS-20250404 - MI Approved
7 | [9 empty] | 7 | 7. Battery Systems | Aircons - RCF Tech - last 20% |  |  | 8258 | RCF Tech QU001 | 2025-04-30 | 10425.5173 |  | 2025-05-08
8 | Product Add On | [5 empty] | 0 | 193988.08 |  | 8 | 8. Product Add On | Roof Remedial - Oryx Revamp | 70% | 135656 | 94959.2 | Oryx Revamp: Inv 1892 | 2024-12-31 | 43975.951 | -0.00023404 | 2024-12-12 | 418886.97 | PO3519-MMS-20241209
8 | [9 empty] | 8 | 8. Product Add On | Roof Remedial - Oryx Revamp | 30% |  | 40696.8 | Oryx Revamp: Inv 1892 | 2024-12-31 | 18846.8362 |  | 2025-01-23
[10 empty] | 8 | 8. Product Add On | Additional Aircons 2x 60000BTU - RCF Tech - VO | 80% | 103835 | 83068 | RCF Tech Inv004 | 2025-08-31 | 61634.14 |  | 2025-08-14 |  | PO4215-MMS-20250812
8 | [9 empty] | 8 | 8. Product Add On |  | 20% |  | 20767 | RCF Tech Inv004 | 2025-08-31 | 13633.19 |  | 2025-09-01
8 | [9 empty] | 8 | 8. Product Add On | Trunking Clamp and Screws - Lumax |  |  | 6715 | Lumax Inv 1001/70000751 | 2025-03-31 | 9149.55 |  | 2025-04-30 |  | PO3726-MMS-20250306
8 | [9 empty] | 8 | 8. Product Add On | Lithium Extinguishers - Firebreak SA |  |  | 22794.36 | Firebreak PFI_10024 | 2025-06-30 | 25509.433 |  | 2025-06-26 |  | PO4014-MMS-20250619 - RV Approved
[10 empty] | 8 | 8. Product Add On | Modifications . DC SCOPE - VO |  |  | 17157.5 | Matthews Group - INV-1590 | 2026-01-31 |  |  | 2026-01-23
[10 empty] | 8 | 8. Product Add On | Modifications . DC SCOPE - VO |  |  | 88678.15 | Matthews Group - INV-1589 | 2026-01-31 |  |  | 2026-01-23
8 | [9 empty] | 8 | 8. Product Add On | Energitrack controller & Commission Support - Herholdts |  |  | 7200 |  | 2025-08-31 |  |  | 2025-09-30 |  | PO4262-MMS-20250821 - RV Approved
8 | [9 empty] | 8 | 8. Product Add On | Motorized Breaker Upgrade and Grid Relay - All Electrical - VO |  |  | 36485.85 | All Electrical - IN144166 | 2025-08-31 | 21238.98 |  | 2025-08-19 |  | PO4263-MMS-20250821 - RV Approved
8 | [9 empty] | 8 | 8. Product Add On | Delivery of Fire Extinguishers |  |  | 365.11 | DSV Inv: 180138260 | 2025-07-31 |  |  | 2025-08-31 |  | PO4014-MMS-20250619 - RV Approved
Only services to be capture below, products above
9 | AC & DC Installation | Project Kick Off |  | 10% | 34216 | 2025-01-27 | 342160 | 402541.1765 |  | 9 | 9. AC & DC installation | Project Kick Off | 676952 | 10% | 67695.2 | Matthews Group INV 1423 | 2025-01-31 | 40254.1176 | 0 | 2025-02-07 | 676952 | PO3567-MMS-20250127 - RV Approved
9 | 100100 | Site Establishment |  | 15% | 51324 | 2025-02-03 |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 101542.8 | Matthews Group INV-1424 | 2025-01-31 | 60381.1765 |  | 2025-02-13
9 | 242060 | AC Installation Complete |  | 20% | 68432 | 2025-04-09 |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 135390.4 | Matthews Group INV-1451 | 2025-04-30 | 80508.2353 |  | 2025-04-24
9 |  | DC Installation Complete |  | 25% | 85540 | 2025-03-03 |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 169238 | Matthews Group INV 1445 | 2025-04-30 | 100635.2941 |  | 2025-04-24
9 |  | Commissioning Complete |  | 10% | 34216 | 2025-04-25 |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 67695.2 | Matthews Group INV 1452 | 2025-04-30 | 40254.1176 |  | 2025-05-08
9 |  | Site De-establisment |  | 10% | 34216 | 2025-04-11 |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 67695.2 | Matthews Group INV-1461 | 2025-05-31 | 40254.1176 |  | 2025-06-12
9 |  | Handover Document Complete |  | 5% | 17108 | 2025-05-09 |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 33847.6 | Matthews Group INV-1462 | 2025-06-30 | 20127.0588 |  | 2025-05-16
9 |  | End of Defects Period |  | 5% | 17108 | 2025-08-07 |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 33847.6 | Matthews Group INV-1463 | 2025-06-30 | 20127.0588 |  | 2025-07-31
10 | Site Logistics | [5 empty] | 54108.8333 | 63657.451 |  | 10 | 10. Site Logistics | Additional Security - VO |  |  | 16380 | DIVERGENT - Inv 1117175 | 2025-03-31 | 3052.5431 | -0.0003558 | 2025-03-20 | 114637 | PO3734-MMS-20250311 - RV Approved
10 |  | Offloading |  |  | 8500 | 2025-04-25 |  |  |  | 10 | 10. Site Logistics | Night Guard |  |  | 7020 | Divergent - Inv 1117291 | 2025-03-31 | 109.27 |  | 2025-04-03 |  | PO3766-MMS-20250325 - RV Approved
10 |  | Storage |  |  | 4933.3333 | 2025-04-25 |  |  |  | 10 | 10. Site Logistics | Project Kick Off | 91237 | 10% | 9123.7 | Matthews Group INV 1423 | 2025-01-31 | 6079.1608 |  | 2025-02-07 |  | PO3567-MMS-20250127 - RV Approved
10 |  | Scaffolding |  |  | 40675.5 | 2025-04-25 |  |  |  | 10 | 10. Site Logistics | Site Establishment |  | 15% | 13685.55 | Matthews Group INV-1424 | 2025-01-31 | 9118.7411 |  | 2025-02-13
10 | [9 empty] | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 18247.4 | Matthews Group INV-1451 | 2025-04-30 | 12684.565 |  | 2025-04-24
10 | [9 empty] | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 22809.25 | Matthews Group INV 1445 | 2025-04-30 | 14824.1688 |  | 2025-04-24
10 | [9 empty] | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 9123.7 | Matthews Group INV 1452 | 2025-04-30 | 5929.6675 |  | 2025-05-08
10 | [9 empty] | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 9123.7 | Matthews Group INV-1461 | 2025-05-31 | 5929.6675 |  | 2025-06-12
10 | [9 empty] | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 4561.85 | Matthews Group INV-1462 | 2025-06-30 | 2964.8338 |  | 2025-05-16
10 | [9 empty] | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 4561.85 | Matthews Group INV-1463 | 2025-06-30 | 2964.8338 |  | 2025-07-31
10 | [9 empty] | 10 | 10. Site Logistics | [6 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [6 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2025-04-16 | 111020 | 130611.7647 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 15750 | Sunspot: E024 | 2025-05-31 | 76116.3795 | 0.0010186 | 2025-07-24 | 38759.07
[10 empty] | 11 | 11. Due Dilligence | Travel |  |  | 3982.67 | Sunspot: E024 | 2025-05-31 | 13420.9504 |  | 2025-07-24
11 |  | Structural sign off |  |  | 20020 | 2025-02-03 |  |  |  | 11 | 11. Due Dilligence | Structural sign off |  |  | 11026.4 | LB Consulting Inv-1838 | 2024-11-30 | 14115.7344 |  | 2024-11-28 |  | PO3471-MMS-20241121 - RV Approved
11 | [9 empty] | 11 | 11. Due Dilligence | Red Team |  |  | 8000 | Matriarch - INV-4423 | 2025-05-31 | 26958.6994 |  | 2025-05-31
11 |  | Grid Study - Outside of CoCT |  |  | 80000 | 2025-04-16 |  |  |  | 11 | 11. Due Dilligence | Grid Study - Outside of CoCT | [5 empty] | 0 |  |  |  |  | No Grid study required
11 | [9 empty] | 11 | 11. Due Dilligence | [6 empty] | 0
12 | BDP Commission | [5 empty] | 0 | 0 |  | 12 | BDP Commission | [9 empty] | 0
12 | BDP Commission | [8 empty] | 12 | BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 128356.7484 | 2025-05-26 | 239970.3484 | 272693.5778 |  | 13 | 13. Engineering | Matriarch Defects Period |  |  | 144194.4931 | Matriarch - INV-4422 | 2025-05-31 | 272693.5778 | 0 | 2025-05-31 | 144194.4931
13 |  | Management |  |  | 16000 | 2025-05-26 |  |  |  | 13 | 13. Engineering | Management |  |  | 0 |  | 2025-05-31 | 0 |  | 2025-05-31
13 |  | Project manager |  |  | 54400 | 2025-05-26 |  |  |  | 13 | 13. Engineering | Project manager |  |  | 0 |  | 2025-05-31 | 0 |  | 2025-05-31
13 |  | Planner time |  |  | 20800 | 2025-05-26 |  |  |  | 13 | 13. Engineering | Planner time |  |  | 0 |  | 2025-05-31 | 0 |  | 2025-05-31
13 |  | De Snagging |  |  | 20413.6 | 2025-05-26 |  |  |  | 13 | 13. Engineering | De Snagging |  |  | 0 |  | 2025-05-31 | 0 |  | 2025-05-31
13 | [9 empty] | 13 | 13. Engineering
13 | [9 empty] | 13 | 13. Engineering
14 | General Expenses | Car travel to site |  |  | 47600 | 2025-05-26 | 47600 | 56000 |  | 14 | 14. General Expenses | Travel to site |  |  | 6375.86 | Expense Claim | 2024-12-31 | 7754.7473 | -0.0040461 | 2025-01-09 | 67232.7
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 5594.87 | Expense Claim | 2025-01-31 | 7583.8909 |  | 2025-02-07
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 725.13 | Expense Claim | 2025-02-28 | 4142.1544 |  | 2025-03-07
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 4534.32 | Expense Claim | 2025-03-31 | 8392.208 |  | 2025-04-04
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 4040.3 | Expense Claim | 2025-04-30 | 7747.5088 |  | 2025-05-08
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 10015.22 | Expense Claim | 2025-05-31 | 20379.4947 |  | 2025-06-09
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 5888.69 | Expense Claim | 2025-06-30 | 0 |  | 2025-07-04
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 6060.22 | Expense Claim | 2025-07-31 | 0 |  | 2025-08-07
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 20384.45 | Expense Claim | 2025-08-31 | 0 |  | 2025-09-05
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 3613.64 | Expense Claim | 2026-01-31 | 0 |  | 2026-02-05
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | Delivery of Fluke Meter |  |  | 267.01 | DSV Inv: 180137116 | 2025-06-30 |  | 0 | 2025-07-29 | 1146745.71
[10 empty] | 15 | 15. Service Add On | Borrower Interest |  |  | 140381.96 | Fedgroup Ventures - LT000578_250630 | 2025-07-31 |  |  | 2025-07-18
[10 empty] | 15 | 15. Service Add On | Borrower Interest - July |  |  | 145862.3 | Fedgroup Ventures - LT000578_250631 | 2025-07-31 |  |  | 2025-08-07
[10 empty] | 15 | 15. Service Add On | Borrower Interest - August |  |  | 142388.65 | Fedgroup Ventures - LT000578_250831 | 2025-08-31 |  |  | 2025-09-11
15 | [9 empty] | 15 | 15. Service Add On | RTF Turn Around - Matthews Group - VO |  |  | 26436 | Matthews Group MG INV1514 | 2025-08-31 |  |  | 2025-08-29 |  | PO4201-MMS-20250805 - RV Approved
15 | [9 empty] | 15 | 15. Service Add On | Panels & BESS Room Cleaning - Sunray - VO |  |  | 14110 | Sunray Energy Solutions #89 | 2025-09-30 |  |  | 2025-09-11 |  | PO4312-MMS-20250916 - RV Approved
15 | [9 empty] | 15 | 15. Service Add On | Fire Extinguishers Mount and Service Aircons - RCT Tech - VO |  |  | 1650 | RCF Tech INV003 | 2025-08-31 |  |  | 2025-09-18 |  | PO4315-MMS-20250916 - RV Approved
15 | [9 empty] | 15 | 15. Service Add On | AC Cable & DC Trunking VO - VO |  | 50% | 95381.07 | Matthews Group INV 1456 | 2025-04-30 |  |  | 2025-04-24 |  | PO3814-MMS-20250417 - RV Approved
[10 empty] | 15 | 15. Service Add On | DB upgrade - VO |  |  | 99508 | Matthews Group INV 1525 | 2025-08-31 |  |  | 2025-10-07
[10 empty] | 15 | 15. Service Add On | Atess 250kw 450-900V 5x100A MPPT - VO |  |  | 161300 | Herholdts - INV1208290 | 2026-01-31 |  |  | 2026-02-28
[10 empty] | 15 | 15. Service Add On | Grid Relay - VO |  |  | 12408.35 | All Electrical - SO140653 | 2025-08-31 |  |  | 2025-08-27
15 | [9 empty] | 15 | 15. Service Add On | AC Cable & DC Trunking VO |  | 50% | 95381.07 | Matthews Group INV 1456 | 2025-04-30 |  |  | 2025-07-17
15 | [9 empty] | 15 | 15. Service Add On | MPPT Installation Labour and Sundries - Matthews Group - VO |  | 50% | 105835.65 | [6 empty] | PO4555-MMS-20260116
15 | [9 empty] | 15 | 15. Service Add On | MPPT Installation Labour and Sundries - Matthews Group - VO |  | 50% | 105835.65
11729547.5514
Note on R14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please confirm if this is coming from Stock and update the amount as per stock sheet Reply: No we purchased the inverter
Note on W82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @thami, please mark these dates is black
Note on W134: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date
Note on W135: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2024-11-04 to 2026-07-13
PLANNED |  | CHECK | CHECK
| Planned Revenue | 11535559.451 | 11729547.531 | 0 | 0 | 0 | 0 | 0 | 4037445.8079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3460667.8353 | 0 | 0 | 2307111.8902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1271441.0051 | 0 | 0 | 652880.9926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 4037445.8079 | 4037445.8079 | 4037445.8079 | 4037445.8079 | 4037445.8079 | 4037445.8079 | 4037445.8079 | 4037445.8079 | 4037445.8079 | 4037445.8079 | 4037445.8079 | 7498113.6432 | 7498113.6432 | 7498113.6432 | 9805225.5334 | 9805225.5334 | 9805225.5334 | 9805225.5334 | 9805225.5334 | 9805225.5334 | 9805225.5334 | 9805225.5334 | 11076666.5385 | 11076666.5385 | 11076666.5385 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531
| Planned Expenditure | 10556110.2244 | 10556110.2244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 936612.7526 | 158939.1289 | 0 | 0 | 388526.9565 | 6714691.8815 | 0 | 0 | 259000 | 0 | 277838.2578 | 91000 | 1349318.1459 | 0 | 46306.3763 | 0 | 0 | 287570.3484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46306.3763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 936612.7526 | 1095551.8815 | 1095551.8815 | 1095551.8815 | 1484078.838 | 8198770.7196 | 8198770.7196 | 8198770.7196 | 8457770.7196 | 8457770.7196 | 8735608.9774 | 8826608.9774 | 10175927.1233 | 10175927.1233 | 10222233.4996 | 10222233.4996 | 10222233.4996 | 10509803.8481 | 10509803.8481 | 10509803.8481 | 10509803.8481 | 10509803.8481 | 10509803.8481 | 10509803.8481 | 10509803.8481 | 10509803.8481 | 10509803.8481 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244 | 10556110.2244
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 4037445.8079 | 4037445.8079 | 4037445.8079 | 4037445.8079 | 4037445.8079 | 4037445.8079 | 4037445.8079 | 3100833.0553 | 2941893.9263 | 2941893.9263 | 2941893.9263 | 6014034.8051 | -700657.0764 | -700657.0764 | 1606454.8138 | 1347454.8138 | 1347454.8138 | 1069616.556 | 978616.556 | -370701.59 | -370701.59 | -417007.9663 | 854433.0388 | 854433.0388 | 566862.6904 | 1219743.6829 | 1219743.6829 | 1219743.6829 | 1219743.6829 | 1219743.6829 | 1219743.6829 | 1219743.6829 | 1219743.6829 | 1219743.6829 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066 | 1173437.3066
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 11729547.531 | 11729547.531 | 0 | 0 | 0 | 0 | 0 | 73118.58 | 0 | 0 | 0 | 0 | 0 | 6344557.6981 | 0 | 3460667.8353 | 120869.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1153555.9451 | 0 | 0 | 0 | 0 | 0 | 576777.9726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 73118.58 | 73118.58 | 73118.58 | 73118.58 | 73118.58 | 73118.58 | 6417676.2781 | 6417676.2781 | 9878344.1134 | 9999213.6134 | 9999213.6134 | 9999213.6134 | 9999213.6134 | 9999213.6134 | 9999213.6134 | 9999213.6134 | 9999213.6134 | 9999213.6134 | 9999213.6134 | 9999213.6134 | 9999213.6134 | 9999213.6134 | 11152769.5585 | 11152769.5585 | 11152769.5585 | 11152769.5585 | 11152769.5585 | 11152769.5585 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531 | 11729547.531
| Actual + Planned Expenditure | 11767622.9706 | 11555951.6706 | 0 | 0 | 0 | 11026.4 | 0 | 94959.2 | 0 | 0 | 0 | 6375.86 | 0 | 40696.8 | 11169 | 208591.54 | 6629089 | 1282168.39 | 6486.5 | 725.13 | 0 | 16380 | 111354.7 | 12702.32 | 33032 | 0 | 1062066.0625 | 7863 | 258485.745 | 101498.3325 | 55100 | 152194.4931 | 0 | 213011.885 | 0 | 22794.36 | 26533.69 | 0 | 235763.03 | 19732.67 | 101765.3425 | 151922.52 | 83068 | 36485.85 | 39209.46 | 41151.45 | 156498.65 | 1650 | 0 | 7200 | 99508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15813 | 0 | 105835.65 | -68870 | 3613.64 | 0 | 0 | 161300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 11026.4 | 11026.4 | 105985.6 | 105985.6 | 105985.6 | 105985.6 | 112361.46 | 112361.46 | 153058.26 | 164227.26 | 372818.8 | 7001907.8 | 8284076.19 | 8290562.69 | 8291287.82 | 8291287.82 | 8307667.82 | 8419022.52 | 8431724.84 | 8464756.84 | 8464756.84 | 9526822.9025 | 9534685.9025 | 9793171.6475 | 9894669.98 | 9949769.98 | 10101964.4731 | 10101964.4731 | 10314976.3581 | 10314976.3581 | 10337770.7181 | 10364304.4081 | 10364304.4081 | 10600067.4381 | 10619800.1081 | 10721565.4506 | 10873487.9706 | 10956555.9706 | 10993041.8206 | 11032251.2806 | 11073402.7306 | 11229901.3806 | 11231551.3806 | 11231551.3806 | 11238751.3806 | 11338259.3806 | 11338259.3806 | 11338259.3806 | 11338259.3806 | 11338259.3806 | 11338259.3806 | 11338259.3806 | 11338259.3806 | 11338259.3806 | 11338259.3806 | 11338259.3806 | 11338259.3806 | 11338259.3806 | 11354072.3806 | 11354072.3806 | 11459908.0306 | 11391038.0306 | 11394651.6706 | 11394651.6706 | 11394651.6706 | 11555951.6706 | 11555951.6706 | 11555951.6706 | 11555951.6706 | 11555951.6706 | 11555951.6706 | 11555951.6706 | 11555951.6706 | 11555951.6706 | 11555951.6706 | 11555951.6706 | 11555951.6706 | 11555951.6706 | 11555951.6706 | 11555951.6706 | 11555951.6706 | 11555951.6706 | 11555951.6706 | 11555951.6706 | 11555951.6706 | 11555951.6706
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | -11026.4 | -11026.4 | -32867.02 | -32867.02 | -32867.02 | -32867.02 | -39242.88 | -39242.88 | 6264618.0181 | 6253449.0181 | 9505525.3134 | 2997305.8134 | 1715137.4234 | 1708650.9234 | 1707925.7934 | 1707925.7934 | 1691545.7934 | 1580191.0934 | 1567488.7734 | 1534456.7734 | 1534456.7734 | 472390.7109 | 464527.7109 | 206041.9659 | 1258099.5785 | 1202999.5785 | 1050805.0853 | 1050805.0853 | 837793.2003 | 837793.2003 | 1391776.8129 | 1365243.1229 | 1365243.1229 | 1129480.0929 | 1109747.4229 | 1007982.0804 | 856059.5604 | 772991.5604 | 736505.7104 | 697296.2504 | 656144.8004 | 499646.1504 | 497996.1504 | 497996.1504 | 490796.1504 | 391288.1504 | 391288.1504 | 391288.1504 | 391288.1504 | 391288.1504 | 391288.1504 | 391288.1504 | 391288.1504 | 391288.1504 | 391288.1504 | 391288.1504 | 391288.1504 | 391288.1504 | 375475.1504 | 375475.1504 | 269639.5004 | 338509.5004 | 334895.8604 | 334895.8604 | 334895.8604 | 173595.8604 | 173595.8604 | 173595.8604 | 173595.8604 | 173595.8604 | 173595.8604 | 173595.8604 | 173595.8604 | 173595.8604 | 173595.8604 | 173595.8604 | 173595.8604 | 173595.8604 | 173595.8604 | 173595.8604 | 173595.8604 | 173595.8604 | 173595.8604 | 173595.8604 | 173595.8604 | 173595.8604
|  | CHECK | CHECK
| Revenue Recognition | -193988.1004 | 11729547.5514 | 0 | 0 | 0 | 14115.7344 | 0 | 0 | 0 | 0 | 1583640.5322 | 0 | 0 | 0 | 8282775.6402 | 0 | 0 | 0 | 358260.7865 | 0 | 0 | 0 | 0 | 82940.3455 | 0 | 0 | 0 | 681491.6406 | 0 | 0 | 0 | 506938.1155 | 0 | 0 | 0 | 0 | 122878.4467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96506.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 11729547.5514 | 0 | 0 | 0 | 14115.7344 | 14115.7344 | 14115.7344 | 14115.7344 | 14115.7344 | 1597756.2665 | 1597756.2665 | 1597756.2665 | 1597756.2665 | 9880531.9067 | 9880531.9067 | 9880531.9067 | 9880531.9067 | 10238792.6932 | 10238792.6932 | 10238792.6932 | 10238792.6932 | 10238792.6932 | 10321733.0387 | 10321733.0387 | 10321733.0387 | 10321733.0387 | 11003224.6792 | 11003224.6792 | 11003224.6792 | 11003224.6792 | 11510162.7947 | 11510162.7947 | 11510162.7947 | 11510162.7947 | 11510162.7947 | 11633041.2414 | 11633041.2414 | 11633041.2414 | 11633041.2414 | 11633041.2414 | 11633041.2414 | 11633041.2414 | 11633041.2414 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514 | 11729547.5514
| Installer Expenditure |  | 1938729.6575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193872.97 | 290809.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 872428.3425 | 0 | 193872.965 | 96936.4825 | 0 | 0 | 0 | 193872.965 | 0 | 0 | 0 | 0 | 0 | 0 | 96936.4825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Installer Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193872.97 | 484682.42 | 484682.42 | 484682.42 | 484682.42 | 484682.42 | 484682.42 | 484682.42 | 484682.42 | 484682.42 | 484682.42 | 1357110.7625 | 1357110.7625 | 1550983.7275 | 1647920.21 | 1647920.21 | 1647920.21 | 1647920.21 | 1841793.175 | 1841793.175 | 1841793.175 | 1841793.175 | 1841793.175 | 1841793.175 | 1841793.175 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575 | 1938729.6575

## Finance - Revenue
REVENUE RECOGNITION AMOUNT | (All)
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels |  | (blank) | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-12-31 | 2025-08-31 | 2025-09-30 | 2026-01-31 | Grand Total
(blank)
BDP Commission
1. Panels | 0 | 0 |  | 1146065.703 | 25234.91 | [10 empty] | 1171300.613
2. Inverters |  | 0 |  | 179134.8498 |  |  | 49126.0242 | [7 empty] | 0 | 228260.874
3. Mounting Structures | [5 empty] | 195847.8261 | 0 | [8 empty] | 195847.8261
4. DC Equipment |  |  |  | 187862.4449 | 28138.8399 | 72136.6255 | 13110.7502 | 53577.9983 | 9741.4542 | 9741.4542 | [5 empty] | 374309.5672
5. Monitoring | 0 |  |  |  | 102996.2592 | 86134.1805 | [5 empty] | 0 |  |  |  | 189130.4396
6. AC Equipment | 0 |  |  |  | 103609.4384 |  |  | 227940.7587 | 41443.7743 | 41443.7743 | [5 empty] | 414437.7457
8. Product Add On |  |  |  | 62822.7872 |  |  | 9149.55 |  |  | 25509.433 |  |  | 96506.31 |  |  | 193988.0802
9. AC & DC installation |  |  |  |  | 100635.2941 |  |  | 221397.6471 | 40254.1176 | 40254.1176 | [5 empty] | 402541.1765
10. Site Logistics | 0 |  |  |  | 15197.9019 |  | 3161.8131 | 33438.4013 | 5929.6675 | 5929.6675 | [5 empty] | 63657.4513
11. Due Dilligence | 0 | 0 | 14115.7344 | [5 empty] | 116496.0293 | [6 empty] | 130611.7637
13. Engineering | [8 empty] | 272693.5778 | [6 empty] | 272693.5778
14. General Expenses |  |  |  | 7754.7473 | 7583.8909 | 4142.1544 | 8392.208 | 7747.5088 | 20379.4947 | 0 | 0 |  | 0 |  | 0 | 56000.004
15. Service Add On
7. Battery Systems |  | 0 |  |  | 7899379.1058 |  |  | 137389.3264 |  |  | 0 |  |  |  |  | 8036768.4323
Grand Total | 0 | 0 | 14115.7344 | 1583640.5322 | 8282775.6402 | 358260.7865 | 82940.3455 | 681491.6406 | 506938.1155 | 122878.4467 | 0 | 0 | 96506.31 |  | 0 | 11729547.5514
|  |  | 14115.73 | 1520817.74 | 8282775.64 | 358260.79 | 82940.35 | 681491.64 | 506938.12 | 122878.45 |  | 11570218.46 |  | 159329.0914
|  |  | 0.004382 | 62822.7922 | 0.00018182 | -0.0035108 | -0.0045431 | 0.00058274 | -0.0045391 | -0.0032714

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-12-31 | 2026-01-31 | Grand Total
BDP Commission
(blank)
1. Panels |  | 2024-12-31: 908317.8 | 908317.8
2. Inverters |  | 2024-12-31: 206611.05; 2025-03-31: 43190.78; 2026-01-31: -68870 | 180931.83
3. Mounting Structures |  | 2025-02-28: 84254.7; 2025-03-31: 2296 | 86550.7
4. DC Equipment |  | 2024-12-31: 159600; 2025-01-31: 23562.5; 2025-02-28: 53200; 2025-03-31: 55100; 2025-04-30: 51837.5; 2025-05-31: 9425; 2025-06-30: 9425 | 362150
5. Monitoring |  | 2025-01-31: 25295.04; 2025-02-28: 27100; 2025-12-31: 15813 | 68208.04
6. AC Equipment |  | 2025-01-31: 291881.92; 2025-04-30: 642140.2075; 2025-05-31: 116752.765; 2025-06-30: 116752.765 | 1167527.6575
8. Product Add On |  | 2024-12-31: 135656; 2025-03-31: 6715; 2025-06-30: 22794.36; 2025-07-31: 365.11; 2025-08-31: 147520.85; 2026-01-31: 105835.65 | 418886.97
9. AC & DC installation |  | 2025-01-31: 169238; 2025-04-30: 372323.6; 2025-05-31: 67695.2; 2025-06-30: 67695.2 | 676952
10. Site Logistics |  | 2025-01-31: 22809.25; 2025-03-31: 23400; 2025-04-30: 50180.35; 2025-05-31: 9123.7; 2025-06-30: 9123.7 | 114637
11. Due Dilligence |  | 2024-11-30: 11026.4; 2025-05-31: 27732.67 | 38759.07
13. Engineering |  | 2025-05-31: 144194.4931 | 144194.4931
14. General Expenses |  |  | 6375.86 | 5594.87 | 725.13 | 4534.32 | 4040.3 | 10015.22 | 5888.69 | 6060.22 | 20384.45 |  |  | 3613.64 | 67232.7
15. Service Add On | 211671.3 | 2025-04-30: 190762.14; 2025-06-30: 267.01; 2025-07-31: 286244.26; 2025-08-31: 282391; 2025-09-30: 14110; 2026-01-31: 161300 | 1146745.71
7. Battery Systems | 0 | 2025-01-31: 6324594; 2025-04-30: 41290; 2025-07-31: 20645 | 6386529
Grand Total | 211671.3 | 11026.4 | 1416560.71 | 6862975.58 | 165279.83 | 135236.1 | 1352574.0975 | 384939.0481 | 231946.725 | 313314.59 | 450296.3 | 14110 | 15813 | 201879.29 | 11767622.9706

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | 210000 | 0 | 210000 | 0 | 210000
Inverters | 210000
Optimizers | 0
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | 180180 | 0 | 180180 | 0 | 180180
Mounting Structure | 180180
Delivery fee
|  | >Name< |  | >Name<
DC Cable | 141680 | 0 | 141680 | 0 | 141680
DC Cable | 141680
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
Smartlogger 3000 | 26000
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | 0 | 0 | #REF! | 0 | #REF!
SCADA | 0
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | 1142809.6826 | 2.857 | 277892.91 | 0.69473 | 864916.7726 |  | 0 | 1142809.6826
DC Equipment | 202684.8 | 0.50671 | 142158.25 | 0.3554 | 60526.55 |  | 0 | 202684.8
AC Labour | 446100 | 1.1153 | 96174 | 0.24044 | 349926 |  | 0 | 446100
DC Labour | 242060 | 0.60515 | 230160 | 0.5754 | 11900 |  | 0 | 242060
Offloading | 8500 |  | 0 |  | 8500 |  |  | 8500
Roof Access/Scaffolding | 40675.5 |  | 29257.61 |  | 11417.89 |  |  | 40675.5
Storage | 4933.3333 |  |  |  | 4933.3333 |  |  | 4933.3333
Telehandler | 0
HSE | 0
Totals | 2087763.3159 |  | 775642.77 |  | 1312120.5459 | 0 |  | 2087763.3159
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | 1142809.6826
AC equipment | 0 | 0 |  |  | 0 |  | 0 | 202684.8
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | 446100
DC equipment | 20268.48 | 0.050671 |  |  | 20268.48 |  |  | 242060
Storage | 0 |  |  |  | 0 |  |  | 8500
Panel lifting equipment | 13433.3333 |  |  |  | 13433.3333 |  |  | 40675.5
Offloading | 0 |  |  |  | 0 |  |  | 4933.3333
Totals | #REF! |  | 0 |  | #REF! | 0 |  | 2087763.3159
Budget Summary
Budget | 2087763.3159
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
Loss | 2087763.3159
All amounts are exc VAT

## Decision Register (hidden)
Mayo Macs |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Mayo Macs | 0 | 0 | 0