## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate |  |  |  | FINANCIAL CLOSE CERTIFICATE
Project Name: | BMG Fluid Tech
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Change Register
Change Register
ID | Description | Folder URL | Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001 | Carport Single Row redesign from south face to North. | https://emergy.sharepoint.com/:f:/s/Emergent_Energy/IgAEhud4kKKoSbGrY_3Epw1qAUy8KJZITDPiWcKbL-Mlzgc?e=mtZGfR | 4 week delay/extension to PC due for new strut manufacturing lead times. | 2025-10-16 | JT and Schletter | Approved | Client Signed off | 2025-11-06 | Multiple reitarations occurred from intial V1 to V4 being the final one.
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010

## BOQ
Item | Supplier | Description | Quantity | Comments
PV Module
Mounting Structure
DC Cable Red & Black
Inverters
Current Transformers (Production)
Current Transformers (Consumption)
Solar Production Meter
Solar Consumption Meter
Wi-Fi Router & Sim
Switch
Back Up Battery
PVDB
Supplier List
Accuenergy
Krannich
Menlo
Red Pole
Schletter
Switchboard
Techsitter

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 3984069.2478 |  | 3984069.2478 |  |  | 3984069.2478 | Start Date | 2930458.9461 | 2867100.36 | 265580.7587 | 409781.6656 | 186463.7645 | 348464.8
2 | Planned Expenditure | 3079187.045 |  | 3276882.0256 | VO PM Limit | Current VO Total | 3164175.1756 | 2025-07-30
3 | Planned Profit | 904882.2028 |  | 707187.2222 | 45244.1101 | 66149.26 | 819894.0722 | End Date - PC
4 | Planned Margin | 22.71% |  | 17.75% |  |  | 20.58% | 2025-10-20
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE |  | MILESTONE NOTES & COMMENTS
1 | Acceptance and Initial Deposit |  | 50% | 1992034.6239 |  | 2025-05-31 | 004769 | 2025-06-18 | 2025-06-25
2 | Delivery of Panels |  | 25% | 996017.312 |  | 2025-09-03 | 004827 | 2025-08-31 | 2025-09-08
3 | Delivery of Inverters |  | 10% | 398406.9248 |  | 2025-09-07 | 004804 | 2025-07-31 | 2025-08-19
4 | Practical Completion |  | 10% | 398406.9248 |  | 2025-11-20 | 004928 | 2026-01-22 | 2026-02-11 |  | Site achieved PC today - 22 Jan - Invoice Sent
5 | Handover |  | 5% | 199203.4624 |  | 2025-12-05 |  |  | 2026-03-02
6 | - |  | 0% | 0
7 | - |  | 0% | 0
|  |  | 100% | 3984069.2478
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 1394424.2367
2 | Delivery of Panels |  | 30% | 1195220.7744
3 | Delivery of Inverters |  | 20% | 796813.8496
4 | Practical Completion |  | 10% | 398406.9248
5 | Handover |  | 5% | 199203.4624
| Total |  | 100% | 3984069.2478
|  |  | 100% | 3984069.2478

## Project Plan
[9 empty] | 2026-02-12 | 2026-02-12
| PROJECT PLAN | BMG Fluid Tech |  |  | Net Work Days |  | 100 |  | 0 | QC snags shared with installer
| PROJECT SIZE (kWp) | 144 |  |  | Total Weeks |  | 20
| PROJECT DEVELOPER | Cole Bisset |  |  | kW/Week Installation Rate |  | 7.2
| PROJECT MANAGERS | JT Moorosi
| CONTRACT VALUE | 3984069.2478
| Phase: | QA
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Expected Status | Comment
|  |  | 75 |  |  | 145 |  | 88.55% | 90.42%
1 | Project Initiation | 2025-05-08 | 113 | 2025-08-29 | 2025-05-08 | 113 | 2025-08-29 | 100% | 100%
1.1 | BD Handover | 2025-05-08 | 1 | 2025-05-09 | 2025-05-08 | 1 | 2025-05-09 | 100% | 100%
1.2 | Project Introduction | 2025-08-16 | 1 | 2025-08-18 | 2025-08-16 | 1 | 2025-08-18 | 100% | 100%
1.3 | HSE | 2025-08-16 | 10 | 2025-08-29 | 2025-08-16 | 10 | 2025-08-29 | 100% | 100%
1.4 | Installer Kick Off | 2025-08-16 | 1 | 2025-08-18 | 2025-08-16 | 1 | 2025-08-18 | 100% | 100%
1.5 | Project Review | 2025-07-17 | 1 | 2025-07-18 | 2025-07-17 | 1 | 2025-07-18 | 100% | 100%
2 | Site Establishment | 2025-08-30 | 1 | 2025-08-31 | 2025-08-30 | 1 | 2025-08-31 | 100% | 100%
2.1 | Solar Contractor Establishment | 2025-08-30 | 1 | 2025-08-31 | 2025-08-30 | 1 | 2025-08-31 | 100% | 100%
3 | AC Installation | 2025-08-11 | 79 | 2025-10-29 | 2025-08-11 | 102 | 2025-11-21 | 64.13% | 64.13%
3.1 | Inverters delivered | 2025-08-31 | 1 | 2025-09-01 | 2025-08-31 | 1 | 2025-09-01 | 100% | 100%
3.2 | Inverters Mounted | 2025-10-13 | 5 | 2025-10-20 | 2025-10-13 | 5 | 2025-10-20 | 100% | 100%
3.3 | Container Assembly and Delivery - Solar DB | 2025-08-11 | 40 | 2025-10-07 | 2025-08-11 | 40 | 2025-10-07 | 100% | 100% | AC Junction Box to be delivered at the container manufacturer to pre-fit/install on week ending 19th Sep and the rest of the boards Week of the 25th Sep.
3.4 | Trench to BESS | 2025-10-08 | 4 | 2025-10-12 | 2025-10-08 | 4 | 2025-10-12 | 100% | 100%
3.5 | AC Cabling | 2025-10-14 | 12 | 2025-10-26 | 2025-10-20 | 29 | 2025-11-18 | 100% | 100%
3.6 | Container Plinths | 2025-09-11 | 10 | 2025-09-26 | 2025-09-11 | 10 | 2025-09-26 | 100% | 100% | Curing will take up to 10 days
3.7 | AC Tie-In | 2025-10-26 | 3 | 2025-10-29 | 2025-11-18 | 3 | 2025-11-21 | 100% | 100%
4 | DC Works | 2025-07-31 | 103 | 2025-11-11 | 2025-07-31 | 133 | 2025-12-11 | 100% | 100%
4.1 | Base Prep | 2025-09-08 | 4 | 2025-09-12 | 2025-09-08 | 4 | 2025-09-12 | 100% | 100%
4.2 | Rebar and Concrete | 2025-09-18 | 4 | 2025-09-25 | 2025-09-18 | 4 | 2025-09-25 | 100% | 100% | Only started pouring concrete 18 september
4.3 | Trenches and re-instatement | 2025-09-26 | 4 | 2025-10-02 | 2025-09-26 | 4 | 2025-10-02 | 100% | 100%
4.4 | Structures | 2025-10-03 | 10 | 2025-10-17 | 2025-10-03 | 17 | 2025-10-28 | 100% | 100%
4.5 | New Structure lead time |  |  |  | 2025-10-27 | 30 | 2025-12-08 | 100% | 100%
4.6 | New Strucutre Installation |  |  |  | 2025-12-08 | 3 | 2025-12-11 | 100% | 100%
4.7 | DC Cable delivered | 2025-07-31 | 1 | 2025-08-01 | 2025-07-31 | 1 | 2025-08-01 | 100% | 100%
4.8 | DC Stringing | 2025-10-28 | 10 | 2025-11-11 | 2025-11-10 | 10 | 2025-11-24 | 100% | 100%
5 | Module installation | 2025-08-27 | 65 | 2025-10-31 | 2025-08-27 | 78 | 2025-11-13 | 100% | 100%
5.1 | Module delivery | 2025-08-27 | 1 | 2025-08-28 | 2025-08-27 | 1 | 2025-08-28 | 100% | 100%
5.2 | Module mounting | 2025-10-20 | 9 | 2025-10-31 | 2025-10-31 | 9 | 2025-11-13 | 100% | 100%
6 | Commissioning | 2025-11-11 | 2 | 2025-11-13 | 2025-12-11 | 42 | 2026-01-22 | 100% | 100%
6.1 | Commissioning - Partial | 2025-11-11 | 1 | 2025-11-12 | 2025-12-11 | 1 | 2025-12-12 | 100% | 100%
6.2 | Commissioning - Full | 2025-11-12 | 1 | 2025-11-13 | 2026-01-21 | 1 | 2026-01-22 | 100% | 100%
7 | QA Inspections | 2025-11-13 | 1 | 2025-11-14 | 2025-12-12 | 3 | 2025-12-15 | 100% | 100%
7.1 | Red-Team Inspection | 2025-11-13 | 1 | 2025-11-14 | 2025-12-12 | 1 | 2025-12-15 | 100% | 100%
8 | Project Closure | 2025-11-14 | 14 | 2025-11-28 | 2026-01-20 | 34 | 2026-02-23 | 44.25% | 59.25%
8.1 | Equipment serial numbers | 2025-11-14 | 2 | 2025-11-18 | 2026-01-22 | 18 | 2026-02-17 | 40% | 80.77%
8.2 | Snags completion | 2025-11-14 | 5 | 2025-11-21 | 2026-01-20 | 18 | 2026-02-13 | 50% | 95.83% | qc snags shared 4 feb
8.3 | System Performance Monitoring | 2025-11-21 | 5 | 2025-11-28 | 2026-01-21 | 5 | 2026-01-28 | 90% | 100%
8.4 | Handover documentation | 2025-11-14 | 5 | 2025-11-21 | 2026-01-28 | 13 | 2026-02-16 | 45% | 78.95%
8.5 | Handover to Client | 2025-11-21 | 1 | 2025-11-24 | 2026-02-16 | 1 | 2026-02-17 | 0% | 0%
8.6 | Handover to Matriarch | 2025-11-16 | 5 | 2025-11-21 | 2026-02-16 | 5 | 2026-02-23 | 0% | 0%
Formulas:
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = [Actual Start, row above]
Actual End = MAX([Actual End, row below]:K16)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C14)
Expected Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )
Note on O54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Peet Verreynne check here Reply: @Roedolph Venter noted and on it

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 3079187.045 |  | 3276882.0256 | -197694.9806
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 370402.239 |  | 280023.2 | 90379.039
2 | 2. Inverters | 140000 |  | 137740.7 | 2259.3
3 | 3. Mounting Structures | 518256 |  | 1247029.42 | -728773.42 | Look at costing for carport
4 | 4. DC Equipment | 140380.1 |  | 259295 | -118914.9 | DC run spec is inaccurate, DC run much longer then expected
5 | 5. Monitoring | 174000 |  | 41389.35 | 132610.65
6 | 6. AC Equipment | 236614.8174 |  | 416739.86 | -180125.0426
7 | 7.BESS | 710967.8261 |  | 0 | 710967.8261
8 | 8. Product Add On | 536231.13 |  | 516856.72 | 19374.41
9 | 9. AC & DC installation | 141305 |  | 220320 | -79015
10 | 10. Site Logistics | 25300 |  | 80250 | -54950
11 | 11. Due Dilligence | 29000 |  | 19950 | 9050
12 | 12. BDP Commission | 23202.1078 |  | 0 | 23202.1078
13 | 13. Engineering | 31077.8248 |  | 49800.8656 | -18723.0408
14 | 14. General Expenses | 2450 |  | 7486.91 | -5036.91
15 | 15. Service Add On | 0 |  | 0 | 0
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 3079187.045 | 3984069.2478 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 3276882.0256
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FORECASTED PAYMENT DATE | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 370402.239 | 2025-10-27 | 370402.239 | 514447.5542 |  | 1 | 1. Panels | JA Solar 615 | 235 | 1156.4 | 271754 |  | Menlo INV0003177 | 2025-08-31 | 507353.1164 | 0 | 2025-10-24 | 280023.2
1 |  | Delivery Budget | [7 empty] | 1 | 1. Panels | Transport - Futile trip |  |  | 3800 |  | Menlo INV0003177 | 2025-08-31 | 7094.4378 |  | 2025-10-24
1 | [9 empty] | 1 | 1. Panels | JA Solar 615 |  |  | 3469.2 |  | Menlo INV0003504 | 2025-12-31 | - |  | 2026-02-05
1 | [9 empty] | 1 | 1. Panels | Transport |  |  | 1000 |  | Menlo INV0003504 | 2025-12-31 | - |  | 2026-02-05
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 236614.8174
2 | Inverters | Inverter Budget |  |  | 140000 | 2025-09-30 | 140000 | 194444.4444 |  | 2 | 2. Inverters | Huawei 100KTL | 2 | 68870 | 137740.7 |  | Menlo - INV0003112 | 2025-07-31 | 194444.4444 | 0 | 2025-08-07 | 137740.7 | DC Equipment | 93410.1
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | AC Labour | 50386
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 90919
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 0
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 0
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
[23 empty] | HSE | 0
3 | Mounting Structures | Structure Budget |  |  | 518256 | 2025-09-30 | 518256 | 719800 |  | 3 | 3. Mounting Structures | Schletter Structure - Deposit |  | 689400 | 344700 | PO4094-BMGFT-20250707 | Schletter - INV1971 | 2025-07-31 | 192541.2316 | 0.0042398 | 2025-07-17 | 1247029.42 | BESS Installation & Equipment | 707431.438
3 | [9 empty] | 3 | 3. Mounting Structures | Schletter - Balance |  |  | 344700 |  | Schletter - INVQ0135 | 2025-08-31 | 192541.2316 |  | 2025-09-30 |  | Total | 1187261.3554
[10 empty] | 3 | 3. Mounting Structures |  |  |  | -344700 |  | Schletter - INVQ0135 | 2025-09-30 | 0 |  | 2025-09-30
[10 empty] | 3 | 3. Mounting Structures |  |  |  | -344700 |  | Schletter - CRN0273 | 2025-09-30 | 0 |  | 2025-09-30
[10 empty] | 3 | 3. Mounting Structures |  |  |  | 694199.98 |  | Schletter - INV2238 | 2025-09-30 |  |  | 2025-09-30
3 | [9 empty] | 3 | 3. Mounting Structures | Delivery Charge |  |  | 4800 |  | Schletter - INV2416 | 2025-11-30 | 0 |  | 2025-12-30 |  | Less 15% | 1009172.1521
[10 empty] | 3 | 3. Mounting Structures | CT Struts |  |  | 12832.45 |  | Schletter - INV2528 | 2025-12-31 | 0 |  | 2026-01-29
[10 empty] | 3 | 3. Mounting Structures
3 | [9 empty] | 3 | 3. Mounting Structures | Civil Engineering Services - Schletter |  |  | 25790.99 | PO4139-BMGFT-20250721 | Schletter INVQ0136 | 2025-08-31 | 14406.2343 |  | 2025-09-30 |  | R/Wp | 7.0081
[10 empty] | 3 | 3. Mounting Structures |  |  |  | -25790.99 |  | Schletter INVQ0136 | 2025-09-30 | 0 |  | 2025-10-30
[10 empty] | 3 | 3. Mounting Structures |  |  |  | 25790.99 |  | Schletter - INV2518 | 2025-12-31 | 0 |  | 2026-01-29
[10 empty] | 3 | 3. Mounting Structures
[10 empty] | 3 | 3. Mounting Structures | Carport Installation - iEco Solar | 509406 | 60% | 305643.6 | PO4207-BMGFT-20250807 - RV Approved | Ieco Solar InvEME01 | 2025-08-31 | 170725.2544 |  | 2025-08-14
[10 empty] | 3 | 3. Mounting Structures |  |  | 20% | 101881.2 |  | Ieco Solar InvEME02 | 2025-08-31 | 56908.4181 |  | 2025-10-31
[10 empty] | 3 | 3. Mounting Structures |  |  | 15% | 76410.9 |  | Ieco Solar InvEME02 | 2025-08-31 | 42681.3136 |  | 2025-11-13
[10 empty] | 3 | 3. Mounting Structures |  |  | 5% | 25470.3 |  | Ieco Solar InvEME02 | 2025-08-31 | 14227.1045 |  | 2026-02-19
[10 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
[10 empty] | 3 | 3. Mounting Structures | Re-establishment Cost - Carport Variation - Cost TBC (RV Approved) - VO |  |  | 0 |  |  |  | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [9 empty] | 3 | 3. Mounting Structures | Carport Contigency | [5 empty] | 2025-10-31 | 35769.2076 |  |  |  | ACTUAL - MG | Installer Price | ACTUAL - MG | Installer Price | ACTUAL - CS AC/DC Only | Installer Price |  | ACTUAL - CS Carport | Installer Price | ACTUAL - IECO | Installer Price
[23 empty] | AC Equipment | 651077.5 | Carport Install | 0 | AC Equipment | 350590.6 |  | Carport Assembly | 110400 | Carport Scope | 372600 | 447120
4 | DC Equipment | DC Cable Budget |  |  | 46970 | 2025-09-30 | 140380.1 | 194972.3611 |  | 4 | 4. DC Equipment | DC Cable | 12000 | 13.5 | 134446.46 | PO4182-BMGFT-2025073 - RV Approved | Rubicon INVWCRE-0069699 | 2025-07-31 | 121813.0797 | 0 | 2025-08-31 | 259295 | DC Equipment | 86573.26 | DC Equipment | 0 | DC Equipment | 97295 |  | Civils Works (Provisional) | 639500 | Spoil Removal | 7700 | 9240
4 |  | DC Equipment Budget |  |  | 93410.1 | 2025-09-30 |  |  |  | 4 | 4. DC Equipment |  |  |  | 27553.54 | PO4182-BMGFT-2025073 - RV Approved | Rubicon INVWCRE-0069699 | 2025-07-31 | 0 |  | 2025-09-01 |  | AC Labour | 67387 | AC Labour | 0 | AC Labour | 112320 | 0.1872 | Trenching | 0 | Reinstate Bases | 13000
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | DC Labour | 93600 | DC Labour | 0 | DC Labour | 108000 | 0.18 | Scanning | 14950 | Site Establish - PGs | 77706
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Offloading | 7290 | Offloading | 0 | Offloading | 16900 |  | Offloading | 0 | Sleeves | 1575
4 | [9 empty] | 4 | 4. DC Equipment | Project Kick Off | 97295 | 10% | 9729.5 | PO4166-BMGFT-20250728 - RV Approved | Cosmic Sun: CS_BMG_001_AC DC | 2025-07-31 | 7315.9281 |  | 2025-07-31 |  | Scaffolding | 0 | Scaffolding | 0 | Scaffolding | 0 |  | Scaffolding | 0 | Trenching | 16975
4 | [9 empty] | 4 | 4. DC Equipment | Site Establishment |  | 15% | 14594.25 |  | Cosmic Sun - CS_BMG_002_AC DC | 2025-07-31 | 10973.8922 |  | 2025-10-02 |  | Storage | 0 | Storage | 0 | Storage | 6600 |  | Storage | 0 | Scanning | 19850
4 | [9 empty] | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 19459 |  | Cosmic Sun - CS_BMG_002_AC DC | 2025-07-31 | 14631.8563 |  | 2025-12-12 |  | Telehandler | 0 | Telehandler | 0 | Telehandler | 0 |  | Telehandler | 0 | Telehandler | 0
4 | [9 empty] | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 24323.75 |  | Cosmic Sun - CS_BMG_002_AC DC | 2025-07-31 | 18289.8204 |  | 2025-12-18 |  | HSE | 5720 | HSE | 0 | HSE | 1500 |  | HSE | 4500 | HSE | 0
4 | [9 empty] | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 9729.5 |  | Cosmic Sun - CS_BMG_002_AC DC | 2025-07-31 | 7315.9281 |  | 2026-01-29 |  | Trench | 28795 | Other | 0 | Trenching | 55250 |  | Other | 0 | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 9729.5 |  | Cosmic Sun - CS_BMG_002_AC DC | 2025-07-31 | 7315.9281 |  | 2026-01-29 |  | PnGs | 40161 | PnGs | 0 | Other | 0 |  | Other | 0 | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 4864.75 |  | Cosmic Sun - CS_BMG_002_AC DC | 2025-07-31 | 3657.9641 |  | 2026-01-29 |  | Total | 980603.76 | Total | 0 | Total | 748455.6 |  | Total | 769350 | Total | 509406 | 369680
4 | [9 empty] | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 4864.75 |  | Cosmic Sun - CS_BMG_002_AC DC | 2025-07-31 | 3657.9641 |  | 2026-02-28 |  | R/Wp | 6.8097 | R/Wp | 0 | R/Wp | 5.1976 |  | R/Wp | 5.3427 | R/Wp | 3.5375
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | R/kWh | 1.6343 | R/kWh | 0 | R/kWh | 1.2474 |  | R/kWh | 1.2822 | R/kWh | 0.84901
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
[27 empty] | CS Total | 1517805.6
5 | Monitoring | Monitoring Budget |  |  | 159000 | 2025-09-30 | 174000 | 241666.6667 |  | 5 | 5. Monitoring | [7 empty] | 0 | 0 |  | 41389.35 |  |  |  |  | R/Wp | 10.5403
5 |  | Revenue Metering |  |  | 15000 | 2025-05-31 |  |  |  | 5 | 5. Monitoring | CTs Techsitter, Router and Switch |  |  | 7642 | PO4080-BMG-20250701 - RV Approved | Accuenergy - ASAI-006262 | 2025-08-31 | 98177.4848 |  | 2025-09-30 | [5 empty] | R/kWh | 2.5297
5 | [9 empty] | 5 | 5. Monitoring | Techsitter |  |  | 11169 |  | Matriarch - INV-4999 | 2025-08-31 | 143489.1819 |  | 2025-08-31
5 | [9 empty] | 5 | 5. Monitoring | Smartlogger- RMA from Kroonstad |  |  | 8598.35 |  | Allocated from Kroonstad | 2025-11-30 | 0 |  | 2025-11-30
5 | [9 empty] | 5 | 5. Monitoring | Grid meter and CTs |  |  | 6900 | PO4525-BMGFT-20251208 - RV Approved | Accuenergy - ASAI-007074 | 2025-12-31 | 0 |  | 2026-01-07
5 | [9 empty] | 5 | 5. Monitoring | Rogowski Coils |  |  | 4110 |  | Accuenergy - ASAI-006969 | 2025-11-30 | 0 |  | 2026-01-07
[10 empty] | 5 | 5. Monitoring | Energy Meter |  |  | 2970 |  | Accuenergy - ASAI-006969 | 2025-11-30 | 0 |  | 2026-01-07
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 236614.8174 | 2025-09-30 | 236614.8174 | 328631.6908 |  | 6 | 6. AC Equipment | [7 empty] | 0 | 0 |  | 416739.86
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | Project Kick Off | 350590.6 | 10% | 35059.06 | PO4166-BMGFT-20250728 - RV Approved | Cosmic Sun: CS_BMG_001_AC DC | 2025-07-31 | 32863.1691 |  | 2025-07-31
6 | [9 empty] | 6 | 6. AC Equipment | Site Establishment |  | 15% | 52588.59 |  | Cosmic Sun - CS_BMG_002_AC DC | 2025-07-31 | 49294.7536 |  | 2025-10-02
6 | [9 empty] | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 70118.12 |  | Cosmic Sun - CS_BMG_002_AC DC | 2025-07-31 | 65726.3382 |  | 2025-12-12
6 | [9 empty] | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 87647.65 |  | Cosmic Sun - CS_BMG_002_AC DC | 2025-07-31 | 82157.9227 |  | 2025-12-18
6 | [9 empty] | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 35059.06 |  | Cosmic Sun - CS_BMG_002_AC DC | 2025-07-31 | 32863.1691 |  | 2026-01-29
6 | [9 empty] | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 35059.06 |  | Cosmic Sun - CS_BMG_002_AC DC | 2025-07-31 | 32863.1691 |  | 2026-01-29
6 | [9 empty] | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 17529.53 |  | Cosmic Sun - CS_BMG_002_AC DC | 2025-07-31 | 16431.5845 |  | 2026-01-29
6 | [9 empty] | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 17529.53 |  | Cosmic Sun - CS_BMG_002_AC DC | 2025-07-31 | 16431.5845 |  | 2026-02-28
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | Variation Breaker and Delivery - Cosmic Sun - VO |  |  | 17891.32 | PO4313-BMGFT-20250916 - RV Approved | CS_BMG_005_VO | 2025-10-31 | 0 |  | 2025-11-06
[10 empty] | 6 | 6. AC Equipment | Variation Additional AC cable excluding 95mm - Cosmic Sun - VO |  |  | 32171.96 |  | CS_BMG_005_VO | 2025-10-31 |  |  | 2025-11-06
6 | [9 empty] | 6 | 6. AC Equipment | Variation Additional AC cable 95mm - Cosmic Sun - VO |  |  | 16085.98 |  | CS_BMG_006_VO | 2025-11-30 | 0 |  | 2025-12-04
7 | BESS | Battery Inverter + Battery Bank |  |  | 0 |  | 710967.8261 | 789964.2512 |  | 7 | 7.BESS | [7 empty] | 0 | 0 |  | 0
7 |  | Ps and Gs |  |  | 67400 | 2025-11-30 |  |  |  | 7 | 7.BESS | BESS Supply & Install | [5 empty] | 2025-08-31 | 789964.2512
7 |  | Installation |  |  | 197200 | 2025-11-30 |  |  |  | 7 | 7.BESS | Installation |  | 197200 |  |  |  |  | 0
7 |  | AC+DC Equipment |  |  | 112400 | 2025-11-30 |  |  |  | 7 | 7.BESS | AC+DC Equipment |  | 112400 |  |  |  |  | 0
7 |  | Inverter Cables |  |  | 37500 | 2025-11-30 |  |  |  | 7 | 7.BESS | Inverter Cables |  | 37500 |  |  |  |  | 0
7 |  | Main Gateway Cable (Tie-In) |  |  | 296467.8261 | 2025-11-30 |  |  |  | 7 | 7.BESS | Main Gateway Cable (Tie-In) |  | 296467.8261 |  |  |  |  | 0
7 | [9 empty] | 7 | 7.BESS | [7 empty] | 0
7 | [9 empty] | 7 | 7.BESS | [7 empty] | 0
8 | Product Add On | DC Combiner Cabinet |  |  | 121304.45 | 2025-11-30 | 536231.13 | 744765.4583 |  | 8 | 8. Product Add On | DC Combiner Cabinet |  | 121304.45 |  |  |  |  | 0 | 0.0040847 |  | 516856.72
8 |  | Trenching cost |  |  | 18000 | 2025-11-30 |  |  |  | 8 | 8. Product Add On | Trenching cost |  | 18000 |  |  |  |  | 0
8 |  | Battery Storage Container with HVAC systems |  |  | 348926.68 | 2025-07-31 |  |  |  | 8 | 8. Product Add On | [7 empty] | 0
8 |  | Delivery of BESS Storage |  |  | 48000 | 2025-06-30 |  |  |  | 8 | 8. Product Add On | Delivery of BESS Storage | [6 empty] | 0
[10 empty] | 8 | 8. Product Add On | [7 empty] | 0
[10 empty] | 8 | 8. Product Add On | Battery Storage Container with HVAC systems | 400000 | 50% | 200000 |  | GivEnergy INV-0012 | 2025-07-31 | 332484.5796 |  | 2025-07-24
[10 empty] | 8 | 8. Product Add On |  |  | 50% | 200000 |  | GivEnergy INV-0012 | 2025-07-31 | 332484.5796 |  | 2025-07-29
[10 empty] | 8 | 8. Product Add On | [7 empty] | 0
[10 empty] | 8 | 8. Product Add On | Changeover DB & Boards Customization - Cosmic Sun |  |  | 63955.72 | PO4247-BMGFT-20250820 - RV Approved | Cosmic Sun - CS_BMG_004_VO | 2025-08-31 | 38322.3871 |  | 2025-08-21
[10 empty] | 8 | 8. Product Add On | [7 empty] | 0
[10 empty] | 8 | 8. Product Add On | [7 empty] | 0
[10 empty] | 8 | 8. Product Add On | BESS Container Concrete Plinths - Fidelis |  |  | 27360 | PO4316-BMGFT-20250916 - RV approved | Fidelis Solar - INV0000186 | 2025-09-30 | 41473.9079 |  | 2025-09-18
[10 empty] | 8 | 8. Product Add On | [7 empty] | 0
[10 empty] | 8 | 8. Product Add On | Fiber |  |  | 18931 | PO4479-BMGFT-20251119 - RV Approved | Volkirk Properties - INV0001309 | 2025-11-30 | 0 |  | 2025-11-28
[10 empty] | 8 | 8. Product Add On | Fibre |  |  | 6610 |  | Volkirk Properties - INV0001336 | 2025-12-31 |  |  | 2025-12-18
[10 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 50386 | 2025-08-30 | 141305 | 157005.5556 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0 |  | 220320
9 |  | DC Installation Budget |  |  | 90919 | 2025-08-30 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 220320 | 10% | 22032 | PO4166-BMGFT-20250728 - RV Approved | Cosmic Sun: CS_BMG_001_AC DC | 2025-07-31 | 15700.5556 |  | 2025-07-31
9 | [9 empty] | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 33048 |  | Cosmic Sun - CS_BMG_002_AC DC | 2025-07-31 | 23550.8333 |  | 2025-10-02
9 | [9 empty] | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 44064 |  | Cosmic Sun - CS_BMG_003F | 2025-11-30 | 31401.1111 |  | 2025-12-12
9 | [9 empty] | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 55080 |  | Cosmic Sun: CS_BMG_007F | 2025-12-31 | 39251.3889 |  | 2025-12-18
9 | [9 empty] | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 22032 |  | Cosmic Sun: CS_BMG_008 | 2025-12-31 | 15700.5556 |  | 2026-01-15
9 | [9 empty] | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 22032 |  | Cosmic Sun - CS_BMG_009 | 2026-01-31 | 15700.5556 |  | 2026-01-29
9 | [9 empty] | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 11016 |  | Cosmic Sun - CS_BMG_010 | 2026-01-31 | 7850.2778 |  | 2026-01-29
9 | [9 empty] | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 11016 |  |  | 2026-02-28 | 7850.2778 |  | 2026-02-28
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-08-30 | 25300 | 28111.1111 |  | 10 | 10. Site Logistics | [7 empty] | 0 | 0 |  | 80250
10 |  | Scaffolding |  |  | 0 |  |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Security |  |  | 16800 | 2025-08-30 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 0 |  |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | Project Kick Off | 80250 | 10% | 8025 | PO4166-BMGFT-20250728 - RV Approved | Cosmic Sun: CS_BMG_001_AC DC | 2025-07-31 | 2811.1111 |  | 2025-07-31
10 | [9 empty] | 10 | 10. Site Logistics | Site Establishment |  | 15% | 12037.5 |  | Cosmic Sun - CS_BMG_002_AC DC | 2025-07-31 | 4216.6667 |  | 2025-10-02
10 | [9 empty] | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 16050 |  | Cosmic Sun - CS_BMG_002_AC DC | 2025-07-31 | 5622.2222 |  | 2025-12-12
10 | [9 empty] | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 20062.5 |  | Cosmic Sun - CS_BMG_002_AC DC | 2025-07-31 | 7027.7778 |  | 2025-12-18
10 | [9 empty] | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 8025 |  | Cosmic Sun - CS_BMG_002_AC DC | 2025-07-31 | 2811.1111 |  | 2026-01-29
10 | [9 empty] | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 8025 |  | Cosmic Sun - CS_BMG_002_AC DC | 2025-07-31 | 2811.1111 |  | 2026-01-29
10 | [9 empty] | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 4012.5 |  | Cosmic Sun - CS_BMG_002_AC DC | 2025-07-31 | 1405.5556 |  | 2026-01-29
10 | [9 empty] | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 4012.5 |  | Cosmic Sun - CS_BMG_002_AC DC | 2025-07-31 | 1405.5556 |  | 2026-02-28
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2025-11-27 | 29000 | 32222.2222 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 13950 |  | SunSpot - E033 | 2025-12-31 | 22531.3283 | 0 | 2026-01-23 | 19950
11 |  | Structural Sign Off |  |  | 18000 | 2025-11-27 |  |  |  | 11 | 11. Due Dilligence | [7 empty] | 0
11 | [9 empty] | 11 | 11. Due Dilligence | [7 empty] | 0
11 | [9 empty] | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 |  | Matriarch - INV-6235 | 2026-01-31 | 9690.8939 |  | 2026-02-26
11 | [9 empty] | 11 | 11. Due Dilligence | [7 empty] | 0
12 | BDP Commission | Referral Fee |  |  | 0 | 2025-11-28 | 23202.1078 | 0 |  | 12 | 12. BDP Commission | Referral Fee |  |  | 0 | [6 empty] | 0
12 | BDP Commission | PD Fee |  |  | 23202.1078 | 2025-11-28 |  |  |  | 12 | 12. BDP Commission | PD Fee |  |  | 0
13 | Engineering | Matriarch Defects Period |  |  | 31077.8248 | 2025-11-30 | 31077.8248 | 35315.71 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 49800.8656 |  |  | 2026-02-28 | 35315.71 | 0 | 2026-02-26 | 49800.8656
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 2450 | 2025-11-30 | 2450 | 2722.2222 |  | 14 | 14. General Expenses | [7 empty] | 0 | 0 |  | 7486.91
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 0 |  |  | 2025-04-30 | 0 |  | 2025-04-30
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-05-31 | 0 |  | 2025-05-31
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 458.39 |  | Expense Claim | 2025-06-30 | 647.0887 |  | 2025-07-04
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 459.51 |  | Expense Claim | 2025-07-31 | 583.7362 |  | 2025-08-07
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 308.45 |  | Expense Claim | 2025-08-31 | 380.5695 |  | 2025-09-05
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 845.78 |  | Expense Claim | 2025-09-30 | 820.1975 |  | 2025-10-10
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 3844.23 |  | Expense Claim | 2025-10-31 | 1633.5093 |  | 2025-11-06
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 410.79 |  | Expense Claim | 2025-11-30 | 170.1516 |  | 2025-12-05
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-12-31 | 0 |  | 2025-12-31
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 659.76 |  | Expense Claim | 2026-01-31 | 239.8871 |  | 2026-02-05
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 500 |  |  | 2026-02-28 | 181.7988 |  | 2026-03-07
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | [7 empty] | 0 | 0 |  | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
| Panel Procurement Budget | 370402.239 |  | 514447.5542
| Inverter Procurement Budget | 140000 |  | 194444.4444
| Mounting Structure Budget | 518256 |  | 719800
| DC Equipment Budget | 140380.1 |  | 194972.3611
| AC Equipment Budget | 236614.8174 |  | 328631.6908
| Monitoring Budget | 174000 |  | 241666.6667
| Optional Extras Budget | 0 |  | 0
| MV Metering Budget | 0 |  | 0
| ADD ON | 536231.13 |  | 744765.4583
| Battery System | 710967.8261 |  | 789964.2512
| Generator | 0 |  | 0
Services
| AC Installer Budget | 50386 |  | 55984.4444
| DC Installer Budget | 90919 |  | 101021.1111
| In-House Expense Budget | 31077.8248 |  | 35315.71
| Compliance Budget | 29000 |  | 32222.2222
| Offloading Budget | 8500 |  | 9444.4444
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 0 |  | 0
| On Site Security | 16800 |  | 18666.6667
| Roof Access Budget for Installers | 0 |  | 0
| EPC Management Fee | 0 |  | 0
| ADD ON | 0 |  | 0
Expenses
| Total EE Expense Budget | 2450 |  | 2722.2222
Note on W36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @JT Moorosi when is the 5% due?
Note on Q38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Roedolph Venter @JT Moorosi who is the supplier and can we request the back dated invoice - January. Reply: Hi @Mizelda Isaacs if I recall correctly, this was contingency for iEco. And I did follow up with Neil last week and he advised finance lady will touch base with you to sort. If not, please advise and will give him a ring in a few and revert. Reply: @JT Moorosi, please reach out to Neil and request the invoice to be dated January. I have not had any feedback from their accounts department

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-04-07 to 2051-03-13
PLANNED |  | CHECK | CHECK
| Planned Revenue | 3984069.2478 | 3984069.2478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1992034.6239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1394424.2367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 398406.9248 | 0 | 199203.4624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1992034.6239 | 1992034.6239 | 1992034.6239 | 1992034.6239 | 1992034.6239 | 1992034.6239 | 1992034.6239 | 1992034.6239 | 1992034.6239 | 1992034.6239 | 1992034.6239 | 1992034.6239 | 1992034.6239 | 1992034.6239 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3784865.7854 | 3784865.7854 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478
| Planned Expenditure | 3079187.045 | 3079187.045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 348926.68 | 0 | 0 | 0 | 166605 | 0 | 0 | 0 | 0 | 1194250.9174 | 0 | 0 | 0 | 370402.239 | 0 | 0 | 0 | 936002.2086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 15000 | 15000 | 63000 | 63000 | 63000 | 63000 | 411926.68 | 411926.68 | 411926.68 | 411926.68 | 578531.68 | 578531.68 | 578531.68 | 578531.68 | 578531.68 | 1772782.5974 | 1772782.5974 | 1772782.5974 | 1772782.5974 | 2143184.8364 | 2143184.8364 | 2143184.8364 | 2143184.8364 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045 | 3079187.045
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1977034.6239 | 1977034.6239 | 1977034.6239 | 1977034.6239 | 1977034.6239 | 1929034.6239 | 1929034.6239 | 1929034.6239 | 1929034.6239 | 1580107.9439 | 1580107.9439 | 1580107.9439 | 1580107.9439 | 1413502.9439 | 2807927.1807 | 2807927.1807 | 2807927.1807 | 2807927.1807 | 1613676.2633 | 1613676.2633 | 1613676.2633 | 1613676.2633 | 1243274.0243 | 1243274.0243 | 1243274.0243 | 1641680.9491 | 705678.7404 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028 | 904882.2028
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 3984069.2478 | 3984069.2478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1992034.6239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 398406.9248 | 0 | 0 | 996017.312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 398406.9248 | 0 | 0 | 199203.4624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1992034.6239 | 1992034.6239 | 1992034.6239 | 1992034.6239 | 1992034.6239 | 1992034.6239 | 1992034.6239 | 1992034.6239 | 2390441.5487 | 2390441.5487 | 2390441.5487 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3386458.8607 | 3784865.7854 | 3784865.7854 | 3784865.7854 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478 | 3984069.2478
| Actual + Planned Expenditure | 3276882.0256 | 3276882.0256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 458.39 | 0 | 344700 | 200000 | 274845.56 | 138200.21 | 305643.6 | 63955.72 | 145615.46 | 27861.99 | 0 | 27360 | 0 | 495201.31 | 845.78 | 0 | 275554 | 76090.21 | 53907.51 | 76410.9 | 0 | 27529.35 | 16496.77 | 149691.12 | 193723.9 | 0 | 4800 | 13980 | 22032 | 13950 | 203705.34 | 5128.96 | 0 | 25470.3 | 93223.6456 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 458.39 | 458.39 | 345158.39 | 545158.39 | 820003.95 | 958204.16 | 1263847.76 | 1327803.48 | 1473418.94 | 1501280.93 | 1501280.93 | 1528640.93 | 1528640.93 | 2023842.24 | 2024688.02 | 2024688.02 | 2300242.02 | 2376332.23 | 2430239.74 | 2506650.64 | 2506650.64 | 2534179.99 | 2550676.76 | 2700367.88 | 2894091.78 | 2894091.78 | 2898891.78 | 2912871.78 | 2934903.78 | 2948853.78 | 3152559.12 | 3157688.08 | 3157688.08 | 3183158.38 | 3276382.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256 | 3276882.0256
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1992034.6239 | 1991576.2339 | 1991576.2339 | 1646876.2339 | 1446876.2339 | 1172030.6739 | 1033830.4639 | 728186.8639 | 1062638.0687 | 917022.6087 | 889160.6187 | 1885177.9307 | 1857817.9307 | 1857817.9307 | 1362616.6207 | 1361770.8407 | 1361770.8407 | 1086216.8407 | 1010126.6307 | 956219.1207 | 879808.2207 | 879808.2207 | 852278.8707 | 835782.1007 | 686090.9807 | 492367.0807 | 492367.0807 | 487567.0807 | 473587.0807 | 451555.0807 | 437605.0807 | 233899.7407 | 228770.7807 | 627177.7054 | 601707.4054 | 508483.7599 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222 | 707187.2222
|  | CHECK | CHECK
| Revenue Recognition | -1934.7081 | 3986003.956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 647.0887 | 0 | 0 | 0 | 1643505.1234 | 0 | 0 | 0 | 2076270.9851 | 0 | 0 | 0 | 0 | 42294.1055 | 0 | 0 | 0 | 37402.7169 | 0 | 0 | 0 | 31571.2627 | 0 | 0 | 0 | 0 | 77483.2728 | 0 | 0 | 0 | 33481.6144 | 0 | 0 | 0 | 43347.7865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 3986003.956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 647.0887 | 647.0887 | 647.0887 | 647.0887 | 1644152.2122 | 1644152.2122 | 1644152.2122 | 1644152.2122 | 3720423.1973 | 3720423.1973 | 3720423.1973 | 3720423.1973 | 3720423.1973 | 3762717.3028 | 3762717.3028 | 3762717.3028 | 3762717.3028 | 3800120.0196 | 3800120.0196 | 3800120.0196 | 3800120.0196 | 3831691.2823 | 3831691.2823 | 3831691.2823 | 3831691.2823 | 3831691.2823 | 3909174.5551 | 3909174.5551 | 3909174.5551 | 3909174.5551 | 3942656.1694 | 3942656.1694 | 3942656.1694 | 3942656.1694 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956 | 3986003.956

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | Grand Total
(blank)
1. Panels | 0 |  |  |  |  | 514447.5542 |  |  |  | 0 | 0 |  |  | 514447.5542
2. Inverters |  |  |  |  | 194444.4444 | [5 empty] | 0 |  |  | 194444.4444
3. Mounting Structures | 0 |  |  |  | 192541.2316 | 491489.5565 | 0 | 35769.2076 | 0 | 0 | 0 |  |  | 719799.9958
4. DC Equipment |  |  |  |  | 194972.3611 | [5 empty] | 0 |  |  | 194972.3611
5. Monitoring | 0 |  |  |  |  | 241666.6667 |  |  | 0 | 0 | 0 |  |  | 241666.6667
6. AC Equipment | 0 |  |  |  | 328631.6908 |  |  | 0 | 0 |  | 0 |  |  | 328631.6908
8. Product Add On | 0 |  |  |  | 664969.1592 | 38322.3871 | 41473.9079 |  | 0 |  | 0 |  |  | 744765.4542
9. AC & DC installation |  |  |  |  | 39251.3889 |  |  |  | 31401.1111 | 54951.9444 | 0 | 23550.8333 | 7850.2778 | 157005.5556
10. Site Logistics |  |  |  |  | 28111.1111 | [5 empty] | 0 |  |  | 28111.1111
11. Due Dilligence | 0 | [8 empty] | 22531.3283 | 0 | 9690.8939 |  | 32222.2222
13. Engineering | [10 empty] | 0 |  | 35315.71 | 35315.71
14. General Expenses | 0 | 0 | 0 | 647.0887 | 583.7362 | 380.5695 | 820.1975 | 1633.5093 | 170.1516 | 0 |  | 239.8871 | 181.7988 | 4656.9387
15. Service Add On | [10 empty] | 0 |  |  | 0
12. BDP Commission
7.BESS | 0 |  |  |  |  | 789964.2512 |  |  |  |  | 0 |  |  | 789964.2512
Grand Total | 0 | 0 | 0 | 647.0887 | 1643505.1234 | 2076270.9851 | 42294.1055 | 37402.7169 | 31571.2627 | 77483.2728 | 0 | 33481.6144 | 43347.7865 | 3986003.956
|  |  |  | 647.09 | 1643505.12 | 2076270.99
|  |  |  | -0.0012656 | 0.0034238 | -0.0048611

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | Grand Total
(blank)
1. Panels | [5 empty] | 275554 |  |  |  | 4469.2 |  |  |  | 280023.2
2. Inverters |  |  |  |  | 137740.7 | [8 empty] | 137740.7
3. Mounting Structures | 0 |  |  |  | 344700 | 879896.99 | -20991.01 |  | 4800 | 38623.44 |  |  |  | 1247029.42
4. DC Equipment |  |  |  |  | 259295 | [8 empty] | 259295
5. Monitoring | [5 empty] | 18811 |  |  | 15678.35 | 6900 |  |  |  | 41389.35
6. AC Equipment |  |  |  |  | 350590.6 |  |  | 50063.28 | 16085.98 |  |  |  |  | 416739.86
8. Product Add On |  |  |  |  | 400000 | 63955.72 | 27360 |  | 18931 | 6610 |  |  |  | 516856.72
9. AC & DC installation |  |  |  |  | 55080 |  |  |  | 44064 | 77112 |  | 33048 | 11016 | 220320
10. Site Logistics |  |  |  |  | 80250 | [8 empty] | 80250
11. Due Dilligence | [9 empty] | 13950 |  | 6000 |  | 19950
13. Engineering | [12 empty] | 49800.8656 | 49800.8656
14. General Expenses |  | 0 | 0 | 458.39 | 459.51 | 308.45 | 845.78 | 3844.23 | 410.79 | 0 |  | 659.76 | 500 | 7486.91
15. Service Add On
12. BDP Commission | [10 empty] | 0 |  |  | 0
7.BESS
Grand Total | 0 | 0 | 0 | 458.39 | 1628115.81 | 1238526.16 | 7214.77 | 53907.51 | 99970.12 | 147664.64 | 0 | 39707.76 | 61316.8656 | 3276882.0256

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 1.9298 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.98721 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.66787 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 1.5983 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
BMG Fluid Tech |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | BMG Fluid Tech | 0 | 0 | 0