## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | PLANNED |  | ACTUAL |  | FINANCIAL REVIEW | TIMELINE REVIEW |  | Allocated in 2024 | Budgeted | Acutal
1 | Planned Revenue | 1735813.3393 |  | 1776820.4493 |  | 1735813.3393 | Start Date | Sales | 576833.4438 | 1158979.8955 | 1199987.0055
2 | Planned Expenditure | 1461076.77 |  | 1332390.74 |  | 1396689.3867 | 2024-10-12 | COS | 462261.2 | 926219.1567 | 870129.54
3 | Planned Profit | 274736.5693 |  | 444429.7093 |  | 339123.9525 | End Date - PC | GP | 114572.2438 | 232760.7388 | 329857.4655
4 | Planned Margin | 15.83% |  | 25.01% |  | 19.54% | 2024-12-06
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Acceptance and Initial Deposit |  | 35% | 607534.6687 | 2024-07-18 | 004471 | 2024-07-15 | 2024-07-17
2 | Delivery of Inverters |  | 25% | 433953.3348 | 2024-10-02 | 004554 | 2024-10-02 | 2024-10-08
3 | Delivery of Panels |  | 25% | 433953.3348 | 2024-10-30 | 004583 | 2024-11-01 | 2024-11-08
4 | Practical Completion |  | 10% | 173581.3339 | 2024-11-29 | 004619 | 2024-11-28 | 2025-01-27
5 | Handover |  | 5% | 86790.667 | 2024-12-26 | 004692 | 2025-02-26 | 2025-10-16
6 | VO - Walkways |  | 0% | 49914.42 |  | 004619 | 2024-11-28 | 2025-01-27
7 | Credit Note - Walk ways |  | 0% | -8907.31 |  | 004931 | 2026-01-23 | 2026-03-31
|  |  | 100% | 1776820.4493
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 621887.1572
2 | Delivery of Panels |  | 30% | 533046.1348
3 | Delivery of Inverters |  | 20% | 355364.0899
4 | Practical Completion |  | 10% | 177682.0449
5 | Handover |  | 5% | 88841.0225
| Total |  | 100% | 1776820.4493
|  |  | 100% | 1776820.4493
Formulas:
PAYMENT RECEIVED DATE = [TIMELINE REVIEW]+7

## Project Plan
[9 empty] | 2025-10-13 | 2025-10-13
| PROJECT PLAN | SA Metal - 20 Christiaan | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 148
| BUSINESS DEVELOPER | Peet
| PROJECT MANAGER | Lloyd
| CONTRACT VALUE | 1735813.3393
| Phase: | Compliance Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status |  | Comment
|  |  | 64 |  |  | 65 |  | 100% | 100%
1 | Project Initiation | 2024-08-14 | 37 | 2024-09-20 | 2024-08-14 | 37 | 2024-09-20 | 100% | 100%
1.1 | BD Handover | 2024-08-14 | 1 | 2024-08-15 | 2024-08-14 | 1 | 2024-08-15 | 100% | 100%
1.2 | Project Introduction | 2024-09-05 | 1 | 2024-09-06 | 2024-09-05 | 1 | 2024-09-06 | 100% | 100%
1.3 | HSE | 2024-09-05 | 15 | 2024-09-20 | 2024-09-05 | 15 | 2024-09-20 | 100% | 100%
1.4 | Installer Kick Off | 2024-09-13 | 1 | 2024-09-16 | 2024-09-13 | 1 | 2024-09-16 | 100% | 100%
1.5 | Project Review | 2024-09-12 | 1 | 2024-09-13 | 2024-09-12 | 1 | 2024-09-13 | 100% | 100%
2 | Site Establishment | 2024-09-25 | 1 | 2024-09-26 | 2024-09-25 | 1 | 2024-09-26 | 100% | 100%
2.1 | Installer on site & Roof Assessment | 2024-09-25 | 1 | 2024-09-26 | 2024-09-25 | 1 | 2024-09-26 | 100% | 100%
3 | AC Installation | 2024-10-21 | 32 | 2024-11-22 | 2024-10-21 | 32 | 2024-11-22 | 100% | 100%
3.1 | Inverters delivered | 2024-09-25 | 1 | 2024-09-26 | 2024-09-30 | 1 | 2024-10-01 | 100% | 100%
3.2 | Inverters Mounted | 2024-09-26 | 1 | 2024-09-27 | 2024-10-01 | 1 | 2024-10-02 | 100% | 100%
3.3 | Solar DB lead time | 2024-09-25 | 30 | 2024-11-06 | 2024-09-25 | 30 | 2024-11-06 | 100% | 100%
3.4 | AC Works | 2024-09-26 | 10 | 2024-10-10 | 2024-10-01 | 10 | 2024-10-15 | 100% | 100%
3.5 | AC Tie - in | 2024-10-04 | 1 | 2024-10-07 | 2024-10-09 | 1 | 2024-10-10 | 100% | 100%
4 | DC Works | 2024-10-10 | 42 | 2024-11-21 | 2024-10-10 | 42 | 2024-11-21 | 100% | 100%
4.1 | Mounting Structure delivered | 2024-10-10 | 1 | 2024-10-11 | 2024-10-10 | 1 | 2024-10-11 | 100% | 100%
4.2 | Mounting Structure installation | 2024-10-10 | 8 | 2024-10-22 | 2024-10-10 | 8 | 2024-10-22 | 100% | 100%
4.3 | DC Cable delivered | 2024-10-10 | 1 | 2024-10-11 | 2024-10-10 | 1 | 2024-10-11 | 100% | 100%
4.3 | DC Stringing | 2024-11-12 | 5 | 2024-11-19 | 2024-11-12 | 5 | 2024-11-19 | 100% | 100%
5 | Module installation | 2024-10-23 | 29 | 2024-11-21 | 2024-10-23 | 29 | 2024-11-21 | 100% | 100%
5.1 | Module delivery | 2024-10-23 | 1 | 2024-10-24 | 2024-10-23 | 1 | 2024-10-24 | 100% | 100%
5.2 | Module mounting | 2024-10-22 | 15 | 2024-11-12 | 2024-10-22 | 15 | 2024-11-12 | 100% | 100%
6 | Commissioning | 2024-11-22 | 7 | 2024-11-29 | 2024-11-26 | 3 | 2024-11-29 | 100% | 100%
6.1 | Commissioning | 2024-11-22 | 1 | 2024-11-25 | 2024-11-25 | 1 | 2024-11-26 | 100% | 100%
6.2 | Practical Completion | 2024-11-22 | 4 | 2024-11-28 | 2024-11-25 | 4 | 2024-11-29 | 100% | 100%
7 | QA Inspections | 2024-11-29 | 11 | 2024-12-10 | 2024-11-29 | 11 | 2024-12-10 | 100% | 100%
7.1 | Red-Team Inspection | 2024-11-28 | 3 | 2024-12-03 | 2024-11-29 | 3 | 2024-12-04 | 100% | 100%
8 | Project Closure | 2024-12-07 | 53 | 2025-01-29 | 2024-12-07 | 53 | 2025-01-29 | 100% | 100%
8.1 | Equipment serial numbers | 2024-12-03 | 1 | 2024-12-04 | 2024-12-04 | 1 | 2024-12-05 | 100% | 100%
8.2 | Snags completion | 2024-12-04 | 5 | 2024-12-11 | 2024-12-05 | 33 | 2025-01-24 | 100% | 100%
8.3 | System Performance Monitoring | 2024-12-11 | 5 | 2024-12-19 | 2024-12-12 | 5 | 2024-12-20 | 100% | 100%
8.4 | Handover documentation | 2024-12-11 | 5 | 2024-12-19 | 2024-12-12 | 5 | 2024-12-20 | 100% | 100%
8.5 | Handover to Client | 2024-12-19 | 1 | 2024-12-20 | 2025-02-20 | 1 | 2025-08-29 | 100% | 100%
8.6 | Handover to Matriarch | 2024-11-30 | 1 | 2024-12-02 | 2025-04-29 | 1 | 2025-04-30 | 100% | 100%

## Data (hidden)
Public holidays |  | Drop down list
2024-01-01 | New Years Day | Approved
2024-03-21 | Human Rights day | Pending
2024-03-29 | Good Friday | Declined
2024-04-01 | Family Day | Abanded
2024-05-01 | Workers day
2024-06-17 | Youth Day Holiday
2024-08-09 | Womens Day
2024-09-24 | Heritage Day
2024-12-16 | Day of Reconciliation
2024-12-25 | Christmas Day
2024-12-26 | Day of Goodwill |  | Manual dates

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  |  | COSTED |  | PLANNED |  | ACTUAL | Difference from costed | Difference from planned
| EXPENDITURE |  | 1461076.77 |  | 1396689.3867 |  | 1332390.74 | 128686.03 | 64298.6467
| No. | Item | Costed Expenditure |  | Planned Expenditure |  | Actual Expenditure | Saving / Overrun | Saving / Overrun | Comments on variations from planned expenditure
| 1 | Panels | 461154.35 |  | 476456.5 |  | 384202.5 | 76951.85 | 92254
| 2 | Inverters | 118044 |  | 121107 |  | 115325.23 | 2718.77 | 5781.77
| 3 | Mounting Structures | 66690 |  | 29643.2 |  | 22391.32 | 44298.68 | 7251.88
| 4 | DC Equipment | 109793.5 |  | 133412 |  | 125312 | -15518.5 | 8100
| 5 | Monitoring | 49000 |  | 80520.5 |  | 107002.01 | -58002.01 | -26481.51
| 6 | AC Equipment | 257521.38 |  | 158246 |  | 158246 | 99275.38 | 0
| 7 | Battery Systems | 0 |  | 0 |  | 0 | 0 | 0
| 8 | Product Add On | 0 |  | 0 |  | 83299.38 | -83299.38 | -83299.38
| 9 | AC & DC Installation | 123500 |  | 103690 |  | 103690 | 19810 | 0
| 10 | Site Logistics | 31594.3 |  | 110446 |  | 93158.2 | -61563.9 | 17287.8
| 11 | Due Dilligence | 89000 |  | 23020 |  | 11867.62 | 77132.38 | 11152.38
| 12 | BDP Commission | 48482.92 |  | 48482.92 |  | 48482.92 | 0 | 0
| 13 | Engineering | 103846.32 |  | 109215.2667 |  | 72067.67 | 31778.65 | 37147.5967 | RV: Matriarch defects percentage 1.25%
| 14 | General Expenses | 2450 |  | 2450 |  | 7345.89 | -4895.89 | -4895.89
| 15 | Service Add On | 0 |  | 0 |  | 0 | 0 | 0
|  | check: | 0 | #REF! | 0 | #REF! | 0
Copy amounts in column H and paste as values at Project review.

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 1461076.77 | 1735813.3394 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY |  |  |  |  | 1332390.74
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | Project Related date | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS | PO NUMBER | COMMENTS
1 | Panels | Longi 570W - Costing Sheet | 260 | 1696.7475 | 441154.35 | 2024-12-22 | 461154.35 | 576442.9375 |  | 1 | 1. Panels | Canadian Solar 555W - Deposit - Herholdts | 266 | 1415.25 | 188228.25 | Herholdts Inv: INV875402 | 2024-07-31 | 260538.2443 | 0.0026438 | 2024-09-27 | 384202.5 | PO3244-SAM-20240719 - RV Approved |  | 19
1 |  | Jinko Solar 575W | [7 empty] | 1 | 1. Panels |  |  |  | 188228.25 | Herholdts Inv: INV875402 | 2024-07-31 | 260538.2443 |  | 2024-10-31 |  |  |  | BUDGET | Installer Allocation
1 | [9 empty] | 1 | 1. Panels | Handling Fee |  |  | 800 | Supply Chain: Inv SCO04502 | 2024-10-31 | 1200.2898 |  | 2024-11-29 |  |  |  | AC Equipment | 257521.38
1 |  | Delivery |  |  | 20000 | 2024-12-22 |  |  |  | 1 | 1. Panels | Delivery |  |  | 5650 | Supply Chain: Inv SCO04533 | 2024-10-31 | 8477.0469 |  | 2024-11-29 |  |  |  | DC Equipment | 50273.5
1 | [9 empty] | 1 | 1. Panels | Storage |  |  | 1296 | Supply Chain: Inv SCO04502 | 2024-10-31 | 45689.1095 |  | 2024-11-29 |  |  |  | AC Labour | 86450
1 | [9 empty] | 1 | 1. Panels | Storage and delivery budget | [5 empty] | 0 | [5 empty] | DC Labour | 37050
[24 empty] | Offloading | 8500
2 | Inverters | Huawei 100KTL | 1 | 78898 | 78898 | 2024-10-25 | 118044 | 147555 |  | 2 | 2. Inverters | Huawei 100KTL | 1 | 68870 | 68870 | Kathea Inv 518635 | 2024-09-30 | 88116.9962 | 0 | 2024-10-31 | 115325.23 |  | MI: Kathea quote | Telehandler | 0
2 |  | Huawei 50KTL | 1 | 39146 | 39146 | 2024-10-25 |  |  |  | 2 | 2. Inverters | Huawei 50KTL | 1 | 45350 | 45350 | Kathea Inv518655 | 2024-10-31 | 58023.8969 |  | 2024-10-31 |  |  | MI: Kathea quote | Storage | 0
2 | [9 empty] | 2 | 2. Inverters | Delivery |  |  | 1105.23 | Kathea Inv 518635 | 2024-09-30 | 1414.107 |  | 2024-10-31 |  |  |  | Scaffolding | 23094.3
2 | [9 empty] | 2 | 2. Inverters | [6 empty] | 0 | [5 empty] | Other | 0
[24 empty] | Total | 462889.18
3 | Mounting Structures | KlipLok Roof | 148000 | 0.45 | 66690 | 2024-10-25 | 66690 | 83362.5 |  | 3 | 3. Mounting Structures | KlipLok Roof | 1 | 27793.2 | 27793.2 | Schletter INV0895 | 2024-09-30 | 78159.9367 | 0 | 2024-09-23 | 22391.32 | PO3363-SAM20-20240918 - RV Approved |  | Less 15% | 393455.803
3 | [9 empty] | 3 | 3. Mounting Structures |  |  |  | 9567 | SCHLETTER - INV1081 | 2024-11-30 | 0 |  | 2024-12-19 |  |  | TC: Added cost for Extra MS and freight | R/Wp | 2.6585
3 | [9 empty] | 3 | 3. Mounting Structures | Delivery |  |  | 1850 | Schletter Inv0893 | 2024-09-30 | 5202.5633 |  | 2024-09-23
[10 empty] | 3 | 3. Mounting Structures | Schletter Credit: MS |  |  | -16818.88 | Schletter Credit Note: CRN0159 | 2024-11-30 | 0 |  | 2024-12-19
3 | [9 empty] | 3 | 3. Mounting Structures | [6 empty] | 0 | [5 empty] | ACTUAL - Cosmic Sun | Installer Price |  | ACTUAL - Thula Moya | Installer Price |  | ACTUAL - CornerStone | Installer Price
[24 empty] | AC Equipment | 69800 |  | AC Equipment | 95446 |  | AC Equipment | 42101.94 | * Excluded R25976,34 for Comms and metering
4 | DC Equipment | DC Cable | 2345 | 16 | 37520 | 2024-11-09 | 109793.5 | 137241.875 |  | 4 | 4. DC Equipment | DC Cable | 3000 | 13.5 | 40500 | Herholdts Inv: INV922149 | 2024-10-31 | 44355.6558 | 0 | 2024-10-31 | 125312 | PO3315-MUL-20240823 - RV Approved | MI: Herholdts quote | DC Equipment | 61872.4 |  | DC Equipment | 84812 |  | DC Equipment | 70901.16
4 |  | DC Surge Arrestor | 4 | 5500 | 22000 | 2024-11-22 |  |  |  | 4 | 4. DC Equipment | Delivery | [5 empty] | 0 | [5 empty] | AC Labour | 37000 |  | AC Labour | 37034 |  | AC Labour | 15154.29
4 |  | DC Cable Tray | 140 | 130 | 18200 | 2024-11-22 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 84812 | 10% | 8481.2 | Thula Moya INV IN04448 | 2024-09-30 | 9288.6219 |  | 2024-10-17 |  | PO3378-SAM20-20240930 - RV Approved |  | DC Labour | 89500 | 0.85473 | DC Labour | 66656 | 0.70061 | DC Labour | 124563.28 | 0.94404
4 |  | Earth Cable | 2345 | 13.5 | 31657.5 | 2024-10-25 |  |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 12721.8 | Thula Moya IN0449 | 2024-10-31 | 13932.9329 |  | 2024-10-17 |  |  |  | Offloading | 8500 |  | Site Logistics | 35954 |  | Site Logistics | 70278
4 |  | Earth clamp | 26 | 16 | 416 | 2024-10-23 |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 16962.4 | Thula Moya IN04519 | 2024-11-30 | 18577.2438 |  | 2024-11-29 |  |  |  | Roof Access | 15000 |  | Sundries | 11544 |  | HSE | 7027.8
4 | [9 empty] | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 21203 | Thula Moya IN04520 | 2024-11-30 | 23221.5548 |  | 2024-11-29 |  |  |  | Container | 0 |  | Accomodation | 40322 |  | COC | 3978
4 | [9 empty] | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 8481.2 | Thula Moya IN04521 | 2024-11-30 | 9288.6219 |  | 2025-02-13 |  |  |  | HSE | 4500 |  | Scaffolding | 0 |  | Travel | 14818.05
4 | [9 empty] | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 8481.2 | Thula Moya IN04537 | 2024-11-30 | 9288.6219 |  | 2024-12-05 |  |  |  | Other | 0 |  | Other | 0 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 4240.6 | Thula Moya IN04538 | 2024-11-30 | 4644.311 |  | 2025-02-13 |  |  |  | Other | 0 |  | Other | 0 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 4240.6 | Thula Moya IN04594 | 2025-01-31 | 4644.311 |  | 2025-03-06 |  |  |  | Other | 0 |  | Other | 0 |  | Other | 0
[24 empty] | Total | 286172.4 |  | Total | 371768 |  | Total | 348822.52
5 | Monitoring | Smartlogger 3000 | 1 | 26000 | 26000 | 2024-10-25 | 49000 | 61250 |  | 5 | 5. Monitoring | Smartlogger 3000 | 1 | 8000 | 8000 | Solarworld SASIV-24-00517 | 2024-08-31 | 6085.4068 | -0.004919 | 2024-09-26 | 107002.01 |  | MI: Kathea quote | R/Wp | 1.9336 |  | R/Wp | 2.5119 |  | R/Wp | 2.3569
5 |  | Comms DB |  |  | 8000 | 2024-10-25 |  |  |  | 5 | 5. Monitoring | CTs |  |  | 13770.5 | AccuEnergy ASAI-003743 | 2024-08-31 | 10474.8868 |  | 2024-09-27
5 |  | Revenue Grade Meter | 1 | 15000 | 15000 | 2024-12-02 |  |  |  | 5 | 5. Monitoring | Revenue Grade Meter | 1 | 11169 | 11169 | MATRIARCH - INV-3278 | 2024-11-30 | 3168.69 |  | 2024-11-30
5 | [9 empty] | 5 | 5. Monitoring | SCADA |  |  | 35750 | Rubicon INVWCRE-0060133 | 2024-08-31 | 27194.1617 |  | 2024-09-27
5 | [9 empty] | 5 | 5. Monitoring | Frontline Comms Equipment |  |  | 2562.51 | Frontline Electrical: INV697940 | 2024-10-31 | 14326.8595 |  | 2024-10-10 |  | PO3387-SAM-20241007 - RV Approved | PO split across the portfolio
5 | [9 empty] | 5 | 5. Monitoring | DNP3 Controller |  |  | 35750 | Rubicon INVWCRE-0062783 | 2024-11-30 | 0 |  | 2025-01-09 |  | PO3476-SAM20-20241122 - RV Approved
6 | AC Equipment | [5 empty] | 257521.38 | 321901.7283 |  | 6 | 6. AC Equipment | [6 empty] | 0 | 0 |  | 158246
[10 empty] | 6 | 6. AC Equipment | AC & Comms Board - Deposit | 40% | 62800 | 25120 | Cosmic Sun CS_SAMPVDB_001 | 2024-09-30 | 51098.7413 |  | 2024-10-03 |  | PO3375-SAMPort-20240930 - RV Approved
[10 empty] | 6 | 6. AC Equipment | AC & Comms Board - Balance | 60% |  | 37680 | Cosmic Sun CS_SAMPVDB_002 | 2024-10-31 | 76648.1119 |  | 2024-10-31
[10 empty] | 6 | 6. AC Equipment | [6 empty] | 0
[10 empty] | 6 | 6. AC Equipment | [6 empty] | 0
6 |  | Project Kick Off |  | 10% | 25752.138 | 2024-12-19 |  |  |  | 6 | 6. AC Equipment | Project Kick Off | 95446 | 10% | 9544.6 | Thula Moya INV IN04448 | 2024-09-30 | 19415.4875 |  | 2024-10-17 |  | PO3378-SAM20-20240930 - RV Approved
6 | 257521.38 | Site Establishment |  | 15% | 38628.207 | 2024-09-25 |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 14316.9 | Thula Moya IN0449 | 2024-10-31 | 29123.2313 |  | 2024-10-17
6 |  | AC Installation Complete |  | 20% | 51504.276 | 2024-11-22 |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 19089.2 | Thula Moya IN04519 | 2024-11-30 | 38830.975 |  | 2024-11-29
6 |  | DC Installation Complete |  | 25% | 64380.345 | 2024-11-21 |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 23861.5 | Thula Moya IN04520 | 2024-11-30 | 48538.7188 |  | 2024-11-29
6 |  | Commissioning Complete |  | 10% | 25752.138 | 2024-11-29 |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 9544.6 | Thula Moya IN04521 | 2024-11-30 | 19415.4875 |  | 2025-02-13
6 |  | Site De-establisment |  | 10% | 25752.138 | 2024-12-11 |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 9544.6 | Thula Moya IN04537 | 2024-11-30 | 19415.4875 |  | 2024-12-05
6 |  | Handover Document Complete |  | 5% | 12876.069 | 2024-12-19 |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 4772.3 | Thula Moya IN04538 | 2024-11-30 | 9707.7438 |  | 2025-02-13
6 |  | End of Defects Period |  | 5% | 12876.069 | 2025-01-18 |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 4772.3 | Thula Moya IN04594 | 2025-01-31 | 9707.7438 |  | 2025-03-06
7 | Battery Systems | [5 empty] | 0 | 0 |  | 7 | Battery Systems | [7 empty] | 0 |  | 0
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
8 | Product Add On | [5 empty] | 0 | 0 |  | 8 | 8. Product Add On | Walkways - Transport |  |  | 4025 | Onvlee Engineering: Inv01048652 | 2024-10-31 | 0 | 0 | 2024-10-10 | 83299.38
8 | [9 empty] | 8 | 8. Product Add On | Mounting Structure for Walkways |  |  | 4244.32 | Schletter INV0951 | 2024-10-31 | 0 |  | 2024-11-29 |  | PO3389-SAM-20241008 - RV Approved
8 | [9 empty] | 8 | 8. Product Add On | Walkways |  |  | 41645.1 | Onvlee Engineering: Inv01048652 | 2024-10-31 | 0 |  | 2024-10-10 |  | PO3390-SAM-20241008 - RV Approved
8 | [9 empty] | 8 | 8. Product Add On | Supply and Install Tie in Breaker - Thula Moya |  |  | 24300.96 | Thula Moya IN04487 | 2024-10-31 | 0 |  | 2024-11-01 |  | PO3433-SAM-20241029 - RV Approved
8 | [9 empty] | 8 | 8. Product Add On | Installation of walkways |  |  | 9084 | Thula Moya IN04597 | 2025-01-31 | 0 |  | 2025-07-31
[10 empty] | 8 | 8. Product Add On | [5 empty] | 2025-01-31 | 49914.42
Only services to be capture below, products above
9 | AC & DC Installation | Project Kick Off |  | 10% | 12350 | 2024-09-18 | 123500 | 145294.1177 |  | 9 | 9. AC & DC installation | Project Kick Off | 103690 | 10% | 10369 | Thula Moya INV IN04448 | 2024-09-30 | 14529.4118 | 0 | 2024-10-17 | 103690 | PO3378-SAM20-20240930 - RV Approved
9 | 37050 | Site Establishment |  | 15% | 18525 | 2024-09-25 |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 15553.5 | Thula Moya IN0449 | 2024-10-31 | 21794.1177 |  | 2024-10-17
9 | 86450 | AC Installation Complete |  | 20% | 24700 | 2024-11-22 |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 20738 | Thula Moya IN04519 | 2024-11-30 | 29058.8235 |  | 2024-11-29
9 |  | DC Installation Complete |  | 25% | 30875 | 2024-11-21 |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 25922.5 | Thula Moya IN04520 | 2024-11-30 | 36323.5294 |  | 2024-11-29
9 |  | Commissioning Complete |  | 10% | 12350 | 2024-11-29 |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 10369 | Thula Moya IN04521 | 2024-11-30 | 14529.4118 |  | 2025-02-13
9 |  | Site De-establisment |  | 10% | 12350 | 2024-12-11 |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 10369 | Thula Moya IN04537 | 2024-11-30 | 14529.4118 |  | 2024-12-05
9 |  | Handover Document Complete |  | 5% | 6175 | 2024-12-19 |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 5184.5 | Thula Moya IN04538 | 2024-11-30 | 7264.7059 |  | 2025-02-13
9 |  | End of Defects Period |  | 5% | 6175 | 2025-01-18 |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 5184.5 | Thula Moya IN04594 | 2025-01-31 | 7264.7059 |  | 2025-03-06
10 | Site Logistics | [5 empty] | 31594.3 | 37169.7647 |  | 10 | 10. Site Logistics | Security | [5 empty] | 0 | 0.0042105 |  | 93158.2
[10 empty] | 10 | 10. Site Logistics | [6 empty] | 0
[10 empty] | 10 | 10. Site Logistics | Project Kick Off | 87820 | 10% | 8782 | Thula Moya INV IN04448 | 2024-09-30 | 3007.4293 |  | 2024-10-17 |  | PO3378-SAM20-20240930 - RV Approved
[10 empty] | 10 | 10. Site Logistics | Site Establishment |  | 15% | 13173 | Thula Moya IN0449 | 2024-10-31 | 4511.144 |  | 2024-10-17
[10 empty] | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 19089.2 | Thula Moya IN04519 | 2024-11-30 | 8791.15 |  | 2024-11-29
[10 empty] | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 23861.5 | Thula Moya IN04520 | 2024-11-30 | 9481.8375 |  | 2024-11-29
[10 empty] | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 9544.6 | Thula Moya IN04521 | 2024-11-30 | 3792.735 |  | 2025-02-13
10 |  | Offloading |  |  | 8500 | 2024-11-29 |  |  |  | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 9544.6 | Thula Moya IN04537 | 2024-11-30 | 3792.735 |  | 2024-12-05
10 | [9 empty] | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 4772.3 | Thula Moya IN04538 | 2024-11-30 | 1896.3675 |  | 2025-02-13
10 | [9 empty] | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 4391 | Thula Moya IN04594 | 2025-01-31 | 1896.3622 |  | 2025-03-06 |  |  | MI: Waiting on revised invoice 1/2
10 |  | Scaffolding |  |  | 23094.3 | 2024-11-29 |  |  |  | 10 | 10. Site Logistics | [6 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2024-11-30 | 89000 | 104705.8824 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 3347.62 | Sun Spot Inv E005 | 2024-11-30 | 40306.8008 | 0.0022772 | 2025-01-16 | 11867.62
11 |  | Structural sign off |  |  | 18000 | 2024-09-25 |  |  |  | 11 | 11. Due Dilligence | Structural sign off |  |  | 2520 | L&B Consulting Inv1742 | 2024-08-31 | 11462.1557 |  | 2024-09-02
11 |  | SCADA - COCT |  |  | 60000 | 2024-10-25 |  |  |  | 11 | 11. Due Dilligence | [6 empty] | 0
11 | [9 empty] | 11 | 11. Due Dilligence | [6 empty] | 0
11 | [9 empty] | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 | MATRIARCH - INV-3413 | 2024-11-30 | 52936.9237 |  | 2024-11-30
12 | BDP Commission | Referral Fee |  |  | 48482.92 | 2024-12-20 | 48482.92 | 0 |  | 12 | BDP Commission | Referral Fee |  |  | 24241.46 | Green Co Inv: INV0000518 | 2024-08-31 |  |  | 2024-09-02 | 48482.92
[10 empty] | 12 | BDP Commission | Referral Fee |  |  | 24241.46 | Green Co Inv: INV0000527 | 2024-11-30 |  |  | 2024-12-12
12 | BDP Commission | [8 empty] | 12 | BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 16328.72 | 2025-01-02 | 103846.32 | 118007.1809 |  | 13 | 13. Engineering | Matriarch Defects Period |  |  | 21667.67 | Matriarch Inv: INV-3417 | 2024-11-30 | 118007.1809 | 0 | 2024-11-30 | 72067.67
13 |  | Management |  |  | 11200 | 2025-01-02 |  |  |  | 13 | 13. Engineering | Management |  |  | 50400 | Matriarch - INV-5021 | 2025-08-31 | 0 |  | 2025-08-31
13 |  | Project manager |  |  | 38080 | 2025-01-02 |  |  |  | 13 | 13. Engineering | Project manager |  |  | 0 |  |  | 0
13 |  | Planner time |  |  | 14560 | 2025-01-02 |  |  |  | 13 | 13. Engineering | Planner time |  |  | 0 |  |  | 0
13 |  | De Snagging |  |  | 23677.6 | 2025-01-02 |  |  |  | 13 | 13. Engineering | De Snagging |  |  | 0 |  |  | 0
13 | [9 empty] | 13 | 13. Engineering
13 | [9 empty] | 13 | 13. Engineering
14 | General Expenses | Car travel to site |  |  | 2450 | 2025-01-02 | 2450 | 2882.3529 |  | 14 | 14. General Expenses | Car travel to site |  |  | 1522.74 | Expense Claim | 2024-08-31 | 540.344 | 0.0032377 | 2024-09-05 | 7345.89
14 | [9 empty] | 14 | 14. General Expenses |  |  | 1 570.98 | 1570.98 | Expense Claim | 2024-09-30 | 568.2484 |  | 2024-10-04
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 1671 | Expense Claim | 2024-10-31 | 591.2541 |  | 2024-11-08
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 53.96 | Expense Claim | 2024-11-30 | 27.1238 |  | 2024-12-06
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 1016.01 | Expense Claim | 2025-01-31 | 399.267 |  | 2025-02-06
[10 empty] | 14 | 14. General Expenses |  |  |  | 423.22 | Expense Claim | 2025-02-28 | 756.1124 |  | 2025-03-06
[10 empty] | 14 | 14. General Expenses |  |  |  | 1087.98 | Expense Claim | 2025-04-30 | 0 |  | 2025-05-08
14 | [9 empty] | 14 | 14. General Expenses
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | Moving inverter and changing tie-in points |  |  | 19463.42 | Thula Moya - IN04750 | 2025-07-31 |  | 0 | 2026-01-31 | 0 |  | TM to CN because CS did work
15 | [9 empty] | 15 | 15. Service Add On |  |  |  | -19463.42 | Thula Moya - IC200104 | 2026-01-31 |  |  | 2026-01-31
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
1785727.752
Note on W32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the date as we have yet to make the payment
Note on R120: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Roedolph Venter and @Mizelda Isaacsplease finilize what is due to them

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2024-07-15 to 2026-08-10
PLANNED |  | CHECK | CHECK
| Planned Revenue | 1735813.3393 | 1735813.3393 | 607534.6687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 433953.3348 | 0 | 0 | 0 | 433953.3348 | 0 | 0 | 0 | 173581.3339 | 0 | 0 | 0 | 86790.667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 1041488.0036 | 1041488.0036 | 1041488.0036 | 1041488.0036 | 1475441.3384 | 1475441.3384 | 1475441.3384 | 1475441.3384 | 1649022.6723 | 1649022.6723 | 1649022.6723 | 1649022.6723 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393 | 1735813.3393
| Planned Expenditure | 1461076.77 | 1461076.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12350 | 75153.207 | 0 | 0 | 0 | 310807.5 | 0 | 37520 | 0 | 211659.621 | 80696.438 | 15000 | 38102.138 | 554440.477 | 0 | 106296.32 | 0 | 19051.069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12350 | 87503.207 | 87503.207 | 87503.207 | 87503.207 | 398310.707 | 398310.707 | 435830.707 | 435830.707 | 647490.328 | 728186.766 | 743186.766 | 781288.904 | 1335729.381 | 1335729.381 | 1442025.701 | 1442025.701 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77 | 1461076.77
| PLANNED CashFlow |  |  | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 595184.6687 | 520031.4617 | 953984.7966 | 953984.7966 | 953984.7966 | 643177.2966 | 1077130.6314 | 1039610.6314 | 1039610.6314 | 827951.0104 | 920835.9063 | 905835.9063 | 867733.7683 | 313293.2913 | 400083.9583 | 293787.6383 | 293787.6383 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693 | 274736.5693
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 1776820.4493 | 1785727.7593 | 607534.6687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 433953.3348 | 0 | 0 | 0 | 433953.3348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223495.7539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86790.667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8907.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 1041488.0036 | 1041488.0036 | 1041488.0036 | 1041488.0036 | 1475441.3384 | 1475441.3384 | 1475441.3384 | 1475441.3384 | 1475441.3384 | 1475441.3384 | 1475441.3384 | 1475441.3384 | 1475441.3384 | 1475441.3384 | 1475441.3384 | 1475441.3384 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1698937.0923 | 1785727.7593 | 1785727.7593 | 1785727.7593 | 1785727.7593 | 1785727.7593 | 1785727.7593 | 1785727.7593 | 1785727.7593 | 1785727.7593 | 1785727.7593 | 1785727.7593 | 1785727.7593 | 1785727.7593 | 1785727.7593 | 1785727.7593 | 1785727.7593 | 1785727.7593 | 1785727.7593 | 1785727.7593 | 1785727.7593 | 1785727.7593 | 1785727.7593 | 1785727.7593 | 1785727.7593 | 1776820.4493 | 1776820.4493 | 1776820.4493 | 1776820.4493 | 1776820.4493 | 1776820.4493 | 1776820.4493 | 1776820.4493 | 1776820.4493 | 1776820.4493 | 1776820.4493 | 1776820.4493 | 1776820.4493 | 1776820.4493 | 1776820.4493 | 1776820.4493 | 1776820.4493 | 1776820.4493 | 1776820.4493 | 1776820.4493
| Actual + Planned Expenditure | 1332390.74 | 1332390.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28284.2 | 0 | 0 | 275391.95 | 26690.98 | 48232.61 | 92942 | 0 | 406034.44 | 1671 | 0 | 0 | 221554.29 | 37993.36 | 24241.46 | -7251.88 | 0 | 0 | 35750 | 3347.62 | 0 | 0 | 1016.01 | 56909.1 | 0 | 0 | 19011.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1087.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9084 | 0 | 0 | 0 | 50400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28284.2 | 28284.2 | 28284.2 | 303676.15 | 330367.13 | 378599.74 | 471541.74 | 471541.74 | 877576.18 | 879247.18 | 879247.18 | 879247.18 | 1100801.47 | 1138794.83 | 1163036.29 | 1155784.41 | 1155784.41 | 1155784.41 | 1191534.41 | 1194882.03 | 1194882.03 | 1194882.03 | 1195898.04 | 1252807.14 | 1252807.14 | 1252807.14 | 1271818.76 | 1271818.76 | 1271818.76 | 1271818.76 | 1271818.76 | 1271818.76 | 1271818.76 | 1271818.76 | 1271818.76 | 1272906.74 | 1272906.74 | 1272906.74 | 1272906.74 | 1272906.74 | 1272906.74 | 1272906.74 | 1272906.74 | 1272906.74 | 1272906.74 | 1272906.74 | 1272906.74 | 1281990.74 | 1281990.74 | 1281990.74 | 1281990.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74 | 1332390.74
| ACTUAL CashFlow |  |  | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 607534.6687 | 579250.4687 | 579250.4687 | 579250.4687 | 303858.5187 | 277167.5387 | 662888.2636 | 569946.2636 | 569946.2636 | 163911.8236 | 596194.1584 | 596194.1584 | 596194.1584 | 374639.8684 | 336646.5084 | 312405.0484 | 319656.9284 | 319656.9284 | 319656.9284 | 283906.9284 | 280559.3084 | 280559.3084 | 504055.0623 | 503039.0523 | 446129.9523 | 446129.9523 | 446129.9523 | 427118.3323 | 427118.3323 | 427118.3323 | 427118.3323 | 427118.3323 | 427118.3323 | 427118.3323 | 427118.3323 | 427118.3323 | 426030.3523 | 426030.3523 | 426030.3523 | 426030.3523 | 426030.3523 | 426030.3523 | 426030.3523 | 426030.3523 | 426030.3523 | 426030.3523 | 426030.3523 | 426030.3523 | 416946.3523 | 416946.3523 | 416946.3523 | 416946.3523 | 366546.3523 | 366546.3523 | 366546.3523 | 366546.3523 | 366546.3523 | 366546.3523 | 366546.3523 | 453337.0193 | 453337.0193 | 453337.0193 | 453337.0193 | 453337.0193 | 453337.0193 | 453337.0193 | 453337.0193 | 453337.0193 | 453337.0193 | 453337.0193 | 453337.0193 | 453337.0193 | 453337.0193 | 453337.0193 | 453337.0193 | 453337.0193 | 453337.0193 | 453337.0193 | 453337.0193 | 453337.0193 | 453337.0193 | 453337.0193 | 453337.0193 | 444429.7093 | 444429.7093 | 444429.7093 | 444429.7093 | 444429.7093 | 444429.7093 | 444429.7093 | 444429.7093 | 444429.7093 | 444429.7093 | 444429.7093 | 444429.7093 | 444429.7093 | 444429.7093 | 444429.7093 | 444429.7093 | 444429.7093 | 444429.7093 | 444429.7093 | 444429.7093
|  | CHECK | CHECK
| Revenue Recognition | -49914.4127 | 1785727.752 | 0 | 0 | 521076.4887 | 0 | 0 | 0 | 55756.9551 | 0 | 0 | 0 | 0 | 270801.5433 | 0 | 0 | 0 | 318673.6502 | 0 | 0 | 0 | 544836.1926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73826.8097 | 0 | 0 | 0 | 756.1124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 1785727.752 | 0 | 0 | 521076.4887 | 521076.4887 | 521076.4887 | 521076.4887 | 576833.4438 | 576833.4438 | 576833.4438 | 576833.4438 | 576833.4438 | 847634.9871 | 847634.9871 | 847634.9871 | 847634.9871 | 1166308.6373 | 1166308.6373 | 1166308.6373 | 1166308.6373 | 1711144.8299 | 1711144.8299 | 1711144.8299 | 1711144.8299 | 1711144.8299 | 1711144.8299 | 1711144.8299 | 1711144.8299 | 1711144.8299 | 1784971.6396 | 1784971.6396 | 1784971.6396 | 1784971.6396 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752 | 1785727.752
| Installer Expenditure |  | 283948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70987 | 0 | 0 | 0 | 0 | 0 | 127776.6 | 28394.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42592.2 | 0 | 0 | 14197.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Installer Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70987 | 70987 | 70987 | 70987 | 70987 | 70987 | 198763.6 | 227158.4 | 227158.4 | 227158.4 | 227158.4 | 227158.4 | 227158.4 | 227158.4 | 227158.4 | 227158.4 | 227158.4 | 269750.6 | 269750.6 | 269750.6 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948 | 283948

## Finance - Revenue
REVENUE RECOGNITION AMOUNT | (All)
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels |  | (blank) | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2025-01-31 | 2025-02-28 | 2025-04-30 | 2025-07-31 | 2025-08-31 | Grand Total
(blank)
Battery Systems
BDP Commission
1. Panels |  | 0 | 521076.4887 |  |  | 55366.4462 | [6 empty] | 576442.9349
2. Inverters | 0 |  |  |  | 89531.1031 | 58023.8969 | [6 empty] | 147555
3. Mounting Structures | 0 |  |  |  | 83362.5 |  | 0 | [5 empty] | 83362.5
4. DC Equipment |  | 0 |  |  | 9288.6219 | 58288.5887 | 65020.3535 | 4644.311 |  |  |  |  | 137241.875
5. Monitoring |  |  |  | 43754.4554 |  | 14326.8595 | 3168.69 | [5 empty] | 61250.0049
6. AC Equipment | 0 | 0 |  |  | 70514.2288 | 105771.3432 | 135908.4125 | 9707.7438 |  |  |  |  | 321901.7283
8. Product Add On | [5 empty] | 0 |  | 49914.42 |  |  |  |  | 49914.42
9. AC & DC installation |  |  |  |  | 14529.4118 | 21794.1177 | 101705.8824 | 7264.7059 |  |  |  |  | 145294.1177
10. Site Logistics | 0 | 0 |  |  | 3007.4293 | 4511.144 | 27754.8251 | 1896.3622 |  |  |  |  | 37169.7605
11. Due Dilligence | 0 |  |  | 11462.1557 |  |  | 93243.7244 | [5 empty] | 104705.8801
13. Engineering |  | 0 |  |  |  |  | 118007.1809 |  |  |  |  | 0 | 118007.1809
14. General Expenses |  |  |  | 540.344 | 568.2484 | 591.2541 | 27.1238 | 399.267 | 756.1124 | 0 |  |  | 2882.3497
15. Service Add On
Grand Total | 0 | 0 | 521076.4887 | 55756.9551 | 270801.5433 | 318673.6502 | 544836.1926 | 73826.8097 | 756.1124 | 0 |  | 0 | 1785727.752
|  |  | 521076.49 | 55756.96 | 270801.54 | 310158.52 | 544836.19 | 73826.81 | 756.11 | 1777212.62
|  |  | -0.0013368 | -0.0049012 | 0.0033446 | 8515.1302 | 0.0025986 | -0.0002684 | 0.0023994
9271.2402

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2025-01-31 | 2025-02-28 | 2025-04-30 | 2025-07-31 | 2025-08-31 | Grand Total
Battery Systems
BDP Commission |  |  | 24241.46 |  |  | 24241.46 | [5 empty] | 48482.92
(blank)
1. Panels |  | 376456.5 |  |  | 7746 | [6 empty] | 384202.5
2. Inverters |  |  |  | 69975.23 | 45350 | [6 empty] | 115325.23
3. Mounting Structures |  |  |  | 29643.2 |  | -7251.88 | [5 empty] | 22391.32
4. DC Equipment |  |  |  | 8481.2 | 53221.8 | 59368.4 | 4240.6 |  |  |  |  | 125312
5. Monitoring |  |  | 57520.5 |  | 2562.51 | 46919 | [5 empty] | 107002.01
6. AC Equipment |  |  |  | 34664.6 | 51996.9 | 66812.2 | 4772.3 |  |  |  |  | 158246
8. Product Add On |  |  |  |  | 74215.38 |  | 9084 |  |  |  |  | 83299.38
9. AC & DC installation |  |  |  | 10369 | 15553.5 | 72583 | 5184.5 |  |  |  |  | 103690
10. Site Logistics |  |  |  | 8782 | 13173 | 66812.2 | 4391 |  |  |  |  | 93158.2
11. Due Dilligence |  |  | 2520 |  |  | 9347.62 | [5 empty] | 11867.62
13. Engineering | 0 |  |  |  |  | 21667.67 |  |  |  |  | 50400 | 72067.67
14. General Expenses |  |  | 1522.74 | 1570.98 | 1671 | 53.96 | 1016.01 | 423.22 | 1087.98 |  |  | 7345.89
15. Service Add On | [9 empty] | 19463.42 |  | 19463.42
Grand Total | 0 | 376456.5 | 85804.7 | 163486.21 | 265490.09 | 360553.63 | 28688.41 | 423.22 | 1087.98 | 19463.42 | 50400 | 1351854.16

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate | [5 empty] | FINANCIAL CLOSE CERTIFICATE
Project Name: | SA Metal - 20 Christiaan
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion: |  |  |  | 1. Financial Close | 1. Financial Close
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | 118044 | 0 | 118044 | 0 | 118044
Inverters | 78898
Optimizers | 39146
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | 66690 | 0 | 66690 | 0 | 66690
Mounting Structure | 66690
Delivery fee
|  | >Name< |  | >Name<
DC Cable | 37520 | 0 | 37520 | 0 | 37520
DC Cable | 37520
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
Smartlogger 3000 | 26000
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | 0 | 0 | #REF! | 0 | #REF!
SCADA | 0
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | 257521.38 | 1.74 | 277892.91 | 1.8777 | -20371.53 |  | 0 | 257521.38
DC Equipment | 50273.5 | 0.33969 | 142158.25 | 0.96053 | -91884.75 |  | 0 | 50273.5
AC Labour | 86450 | 0.58412 | 96174 | 0.64982 | -9724 |  | 0 | 86450
DC Labour | 37050 | 0.25034 | 230160 | 1.5551 | -193110 |  | 0 | 37050
Offloading | 8500 |  | 0 |  | 8500 |  |  | 8500
Roof Access/Scaffolding | 0 |  | 29257.61 |  | -29257.61 |  |  | 0
Storage | 0 |  |  |  | 0 |  |  | 0
Telehandler | 23094.3
HSE | 0
Totals | 462889.18 |  | 775642.77 |  | -335847.89 | 0 |  | 439794.88
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | 257521.38
AC equipment | 0 | 0 |  |  | 0 |  | 0 | 50273.5
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | 86450
DC equipment | 0 | 0 |  |  | 0 |  |  | 37050
Storage | 0 |  |  |  | 0 |  |  | 8500
Panel lifting equipment | 8500 |  |  |  | 8500 |  |  | 0
Offloading | 23094.3 |  |  |  | 23094.3 |  |  | 0
Totals | #REF! |  | 0 |  | #REF! | 0 |  | 439794.88
Budget Summary
Budget | 462889.18
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
Loss | 462889.18
All amounts are exc VAT

## Decision Register (hidden)
SA Metal - 20 Christiaan |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | SA Metal - 20 Christiaan | 0 | 0 | 0