## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate |  |  |  | FINANCIAL CLOSE CERTIFICATE
Project Name: | Blackheath Park
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | Yes
O&M Agreeement | NA
Cost Proposal | Yes
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Change Register
Change Register
ID | Description | Supporting Image (If Applicable) | Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010

## BOQ
Item | Supplier | Description | Quantity | Comments
PV Module
Mounting Structure
DC Cable Red & Black
Inverters
Current Transformers (Production)
Current Transformers (Consumption)
Solar Production Meter
Solar Consumption Meter
Wi-Fi Router & Sim
Switch
Back Up Battery
PVDB
Supplier List
Accuenergy
Krannich
Menlo
Red Pole
Schletter
Switchboard
Techsitter

## Project Plan
[9 empty] | 2026-03-02 | 2026-03-02
| PROJECT PLAN | Blackheath Park | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 800
| PROJECT DEVELOPER | Peet Verreynne
| PROJECT MANAGERS | Justin Franke
| CONTRACT VALUE | 6355349.9168 | [6 empty] | Target Month | 2025-07-31
| Phase: | Compliance Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Expected Status | Comment
|  |  | 85 |  |  | 80 |  | 100% | 100%
1 | Project Initiation | 2025-06-17 | 51 | 2025-08-07 | 2025-06-17 | 65 | 2025-08-21 | 100% | 100%
1.1 | BD Handover | 2025-06-17 | 5 | 2025-06-24 | 2025-06-17 | 5 | 2025-06-24 | 100% | 100%
1.2 | Project Introduction | 2025-07-28 | 1 | 2025-07-29 | 2025-08-08 | 1 | 2025-08-11 | 100% | 100%
1.3 | HSE | 2025-07-28 | 8 | 2025-08-07 | 2025-08-08 | 8 | 2025-08-20 | 100% | 100%
1.4 | Installer Kick Off | 2025-07-28 | 1 | 2025-07-29 | 2025-08-20 | 1 | 2025-08-21 | 100% | 100%
1.5 | Project Review | 2025-07-28 | 1 | 2025-07-29 | 2025-08-20 | 1 | 2025-08-21 | 100% | 100%
2 | Site Establishment | 2025-08-11 | 1 | 2025-08-12 | 2025-09-12 | 1 | 2025-09-13 | 100% | 100%
2.1 | Solar Contractor Establishment | 2025-08-11 | 1 | 2025-08-12 | 2025-09-12 | 1 | 2025-09-13 | 100% | 100% |  | 56 | Net Work Days
3 | AC Installation | 2025-06-30 | 88 | 2025-09-26 | 2025-06-30 | 123 | 2025-10-31 | 100% | 100% |  | 11.2 | Total Weeks
3.1 | Inverters delivered | 2025-06-30 | 1 | 2025-07-01 | 2025-06-30 | 1 | 2025-07-01 | 100% | 100% |  | 71.4286 | kW/Week Installation Rate
3.2 | Inverters Mounted | 2025-08-11 | 1 | 2025-08-12 | 2025-09-12 | 1 | 2025-09-15 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-07-28 | 35 | 2025-09-15 | 2025-08-29 | 35 | 2025-10-20 | 100% | 100%
3.4 | AC Works | 2025-09-15 | 8 | 2025-09-26 | 2025-10-20 | 7 | 2025-10-29 | 100% | 100%
3.5 | AC Tie-In | 2025-09-15 | 2 | 2025-09-17 | 2025-10-29 | 2 | 2025-10-31 | 100% | 100%
4 | DC Works | 2025-06-30 | 123 | 2025-10-31 | 2025-06-30 | 203 | 2026-01-19 | 100% | 100%
4.1 | Lifeline Installation (If Applicable) | [6 empty] | 0% | 0%
4.1 | Mounting Structure delivered | 2025-08-11 | 1 | 2025-08-12 | 2025-09-10 | 1 | 2025-09-11 | 100% | 100%
4.2 | Mounting Structure installation | 2025-08-12 | 25 | 2025-09-16 | 2025-09-11 | 3 | 2025-09-16 | 100% | 100%
4.3 | DC Cable delivered | 2025-06-30 | 1 | 2025-07-01 | 2025-06-30 | 1 | 2025-07-01 | 100% | 100%
4.4 | Re-install 72 panels (shadex) |  |  |  | 2026-01-15 | 2 | 2026-01-19 | 100% | 100%
4.5 | DC Stringing | 2025-10-10 | 15 | 2025-10-31 | 2025-10-24 | 15 | 2025-11-14 | 100% | 100%
5 | Module installation | 2025-06-30 | 105 | 2025-10-13 | 2025-06-30 | 140 | 2025-11-17 | 100% | 100%
5.1 | Module delivery | 2025-06-30 | 1 | 2025-07-01 | 2025-06-30 | 1 | 2025-07-01 | 100% | 100%
5.2 | Module mounting | 2025-09-06 | 25 | 2025-10-13 | 2025-10-02 | 32 | 2025-11-17 | 100% | 100%
6 | Commissioning | 2025-10-31 | 4 | 2025-11-04 | 2025-11-17 | 14 | 2025-12-01 | 100% | 100%
6.1 | Commissioning | 2025-10-31 | 1 | 2025-11-03 | 2025-11-17 | 5 | 2025-11-24 | 100% | 100%
6.2 | Practical Completion | 2025-11-03 | 1 | 2025-11-04 | 2025-11-24 | 5 | 2025-12-01 | 100% | 100%
7 | QA Inspections | 2025-10-31 | 4 | 2025-11-04 | 2025-11-22 | 3 | 2025-11-25 | 100% | 100%
7.1 | Red-Team Inspection | 2025-10-31 | 2 | 2025-11-04 | 2025-11-22 | 2 | 2025-11-25 | 100% | 100%
8 | Project Closure | 2025-11-04 | 15 | 2025-11-19 | 2025-11-25 | 73 | 2026-02-06 | 100% | 100%
8.1 | Equipment serial numbers | 2025-11-04 | 1 | 2025-11-05 | 2025-11-25 | 1 | 2025-11-26 | 100% | 100%
8.2 | Snags completion | 2025-11-04 | 3 | 2025-11-07 | 2025-11-25 | 3 | 2025-11-28 | 100% | 100%
8.3 | System Performance Monitoring | 2025-11-04 | 5 | 2025-11-11 | 2025-12-01 | 5 | 2025-12-08 | 100% | 100%
8.4 | Handover documentation | 2025-11-07 | 1 | 2025-11-10 | 2025-11-28 | 8 | 2025-12-10 | 100% | 100%
8.5 | Handover to Client | 2025-11-10 | 1 | 2025-11-11 | 2026-01-30 | 1 | 2026-02-02 | 100% | 100%
8.6 | Handover to Matriarch | 2025-11-12 | 5 | 2025-11-19 | 2026-02-01 | 5 | 2026-02-06 | 100% | 100%
Formulas:
Planned Start = MIN([Planned Start, row below]:E16)
Planned Start = [Planned Start, row above]
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = [Actual Start, row above]
Actual End = MAX([Actual End, row below]:K16)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C14)
Expected Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW |  |  | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 6355349.9168 |  | 6355349.9168 |  |  |  | Start Date |  |  | 5103597.6646 | 3554777.08 | 1251752.2588 | 1248604.994 | 1246554.3491 | 1247604.994
2 | Planned Expenditure | 5466419.9741 |  | 4803382.074 | VO PM Limit | Current VO Total
3 | Planned Profit | 888929.9428 |  | 1551967.8429 | 44446.4971 | 54973.31 |  | End Date - PC
4 | Planned Margin | 13.99% |  | 24.42%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Acceptance and Initial Deposit |  | 35% | 2224372.4709 |  | 2025-06-27 | 004771 | 2025-06-19 | 2025-06-25
2 | Delivery of Panels |  | 30% | 1906604.975 |  | 2025-07-07 | 004820 | 2025-08-22 | 2025-08-29
3 | Delivery of Inverters |  | 20% | 1271069.9834 |  | 2025-07-07 | 004820 | 2025-08-22 | 2025-08-29
4 | Practical Completion |  | 10% | 635534.9917 |  | 2025-11-11 | 004893 | 2025-12-08 | 2025-12-15
5 | Handover |  | 5% | 317767.4958 |  | 2025-11-17 | 004932 | 2026-02-02 | 2026-02-13
6 | - |  | 0% | 0
7 | - |  | 0% | 0
|  |  | 100% | 6355349.9168
KEY: | contains an error (in result or a check has failed) | [5 empty] | 2558028.3415
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
Formulas:
PAYMENT RECEIVED DATE = [INVOICE RAISED DATE]+6

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 5466419.9741 |  | 4803382.074 | 663037.9001
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 1702080.56 |  | 1591788.4 | 110292.16
2 | 2. Inverters | 420000 |  | 413222.15 | 6777.85
3 | 3. Mounting Structures | 320128 |  | 161835 | 158293
4 | 4. DC Equipment | 635424.2 |  | 941384.25 | -305960.05
5 | 5. Monitoring | 49000 |  | 45787.32 | 3212.68
6 | 6. AC Equipment | 918851.9304 |  | 501939.78 | 416912.1504
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 260000 |  | 93132 | 166868
9 | 9. AC & DC installation | 636320 |  | 840000 | -203680
10 | 10. Site Logistics | 156487.3333 |  | 66798.5 | 89688.8333
11 | 11. Due Dilligence | 290024 |  | 27850 | 262174
12 | 12. BDP Commission | 0 |  | 0 | 0
13 | 13. Engineering | 64103.9503 |  | 79441.874 | -15337.9237
14 | 14. General Expenses | 14000 |  | 3068.72 | 10931.28
15 | 15. Service Add On | 0 |  | 37134.08 | -37134.08
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 5466419.9741 | 6355349.9168 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 4803382.074
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FORECASTED PAYMENT DATE | Total COS | ERROR on REV |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 1702080.56 | 2025-08-29 | 1702080.56 | 1979163.4419 |  | 1 | 1. Panels | Jinko 590W | 1356 | 1168.2 | 1584079.2 | PO4058-SBP-20250629 - RV Approved | Menlo INV0003045 | 2025-06-30 | 1979163.4419 | 0 | 2025-08-31 | 1591788.4
1 |  | Delivery Budget | [7 empty] | 1 | 1. Panels | Jinko 590W - Replacement of damage panels - VO | 6 | 1168.2 | 7009.2 |  | Menlo INV0003423 | 2025-11-30 | 0 |  | 2026-01-15
1 | [9 empty] | 1 | 1. Panels | Transport |  |  | 700 |  | Menlo INV0003423 | 2025-11-30 | 0 |  | 2026-01-15
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 918851.9304
2 | Inverters | Inverter Budget |  |  | 420000 | 2025-08-29 | 420000 | 488372.093 |  | 2 | 2. Inverters | Huawei 100KTL | 6 | 68870.358 | 413222.15 | PO4058-SBP-20250629 - RV Approved | Menlo INV0003045 | 2025-06-30 | 488372.093 | 0 | 2025-08-31 | 413222.15 | DC Equipment | 381324.2
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | AC Labour | 200080
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 436240
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 42120.6667
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 9866.6667
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 320128 | 2025-09-10 | 320128 | 372241.8605 |  | 3 | 3. Mounting Structures | Schletter Structure |  |  | 161835 | PO4142-BLH-20250721 - RV Approved | Schletter - INV1984 | 2025-07-31 | 372241.8605 | 0 | 2025-08-30 | 161835 | Other | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Total | 1996983.4638
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Less 15% | 1697435.9442
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | R/Wp | 2.1218 | Revised Cosmic Sun Pricing - Removed AC Equipment
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL - Cosmic Sun | Installer Price
[23 empty] | AC Equipment | 182300
4 | DC Equipment | DC Cable Budget | 20872.5 |  | 254100 | 2025-08-29 | 635424.2 | 738865.3488 |  | 4 | 4. DC Equipment | DC Cable - To be delivered | 20000 | 13.5 | 270000 | PO4058-SBP-20250629 - RV Approved | Menlo INV0003045 | 2025-06-30 | 371547.0939 | 0.00010557 | 2025-08-31 | 941384.25 | DC Equipment | 356584.25
4 |  | DC Equipment Budget |  |  | 381324.2 | 2025-08-29 |  |  |  | 4 | 4. DC Equipment | Dc cable moved to Milkwood | -6000 | 13.5 | -81000 |  | Allocated to Milkwood | 2025-09-30 | 0 |  | 2025-09-30 |  | AC Labour | 264000
4 | [9 empty] | 4 | 4. DC Equipment | DC Cable | 6000 | 13.65 | 81900 |  | Menlo INV0003324 | 2025-10-31 | 0 |  | 2025-12-12 |  | DC Labour | 576000
4 | [9 empty] | 4 | 4. DC Equipment | DC Cable |  |  | 246400 |  | Menlo INV003399 | 2025-11-30 | 0 |  | 2026-01-09 |  | Offloading | 11000
[10 empty] | 4 | 4. DC Equipment | DC cable from stock - Black | 2000 | 13.5 | 27000 |  | Allocated from Cpt Storeroom | 2025-11-30 | 0 |  | 2025-11-30
[10 empty] | 4 | 4. DC Equipment | DC cable from stock - Red | 3000 | 13.5 | 40500 |  | Allocated from Cpt Storeroom | 2025-11-30 | 0 |  | 2025-11-30
4 | [9 empty] | 4 | 4. DC Equipment | Project Kick Off | 356584.25 | 10% | 35658.43 |  | CS_BHP_001 | 2025-07-31 | 42048.2614 |  | 2025-08-30 |  | Scaffolding | 28050
4 | [9 empty] | 4 | 4. DC Equipment | Site Establishment |  | 15% | 53487.64 |  | CS_BHP_001 | 2025-07-31 | 63072.3862 |  | 2025-10-09 |  | Storage | 0
4 | [9 empty] | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 71316.85 |  | CS_BHP_001 | 2025-07-31 | 84096.511 |  | 2025-11-13 |  | Telehandler | 0
4 | [9 empty] | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 89146.05 |  | CS_BHP_001 | 2025-07-31 | 51956.324 |  | 2025-11-19 |  | HSE | 4500
4 | [9 empty] | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 35658.43 |  | CS_BHP_001 | 2025-07-31 | 42048.2614 |  | 2025-11-28 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 35658.43 |  | CS_BHP_001 | 2025-07-31 | 42048.2614 |  | 2025-11-28 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 17829.21 |  | CS_BHP_001 | 2025-07-31 | 21024.1248 |  | 2025-12-12 |  | Total | 1422434.25
4 | [9 empty] | 4 | 4. DC Equipment | End of Defects Period | 29121.71 | 5% | 17829.21 |  | CS_BHP_001 | 2025-07-31 | 21024.1248 |  | 2026-03-04 |  | R/Wp | 1.778
4 | [9 empty] | 4 | 4. DC Equipment
4 | [9 empty] | 4 | 4. DC Equipment
4 | [9 empty] | 4 | 4. DC Equipment
5 | Monitoring | Monitoring Budget |  |  | 34000 | 2025-07-31 | 49000 | 56976.7442 |  | 5 | 5. Monitoring | Smartlogger |  |  | 8598.34 | PO4058-SBP-20250629 - RV Approved | Menlo INV0003045 | 2025-06-30 | 3373.3923 | 0.0027634 | 2025-08-31 | 45787.32
5 |  | Revenue Metering |  |  | 15000 | 2025-07-31 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 21628 | PO4060-BHL-20250630 - RV Approved | AccuEnergy ASAI-005839 | 2025-06-30 | 8485.3273 |  | 2025-07-29
5 | [9 empty] | 5 | 5. Monitoring | Techsitter |  |  | 11169 |  | Matriarch - INV-4742 | 2025-07-31 | 44834.551 |  | 2025-07-31
5 | [9 empty] | 5 | 5. Monitoring | Delivery of Techsitter Meter |  |  | 206.98 |  | DSV Inv: 180138260 | 2025-07-31 | 283.4709 |  | 2025-08-29
5 | [9 empty] | 5 | 5. Monitoring | Summation CTs |  |  | 2360 | PO4260-BHL-20250821 - RV Approved | Accuenergy - ASAI-006210 | 2025-08-31 | 0 |  | 2025-09-30
5 | [9 empty] | 5 | 5. Monitoring | Battery |  |  | 975 |  | Red Pole - SO-35912 | 2025-09-30 | 0 |  | 2025-09-25
[11 empty] | 5. Monitoring | Power Supply |  |  | 850 |  | Allocated from Freeway Park | 2025-12-31 |  |  | 2025-12-31
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 918851.9304 | 2025-06-30 | 918851.9304 | 1134385.0993 |  | 6 | 6. AC Equipment | [7 empty] | 0 | -0.0027294 |  | 501939.78
6 | [9 empty] | 6 | 6. AC Equipment | PVDB |  |  | 177868.46 | PO4160-BLH-20250725 - RV Approved | Switchboard 2-SOI002245 | 2025-08-31 | 399377.3315 |  | 2025-09-30
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | Tie In kiosk | 148321.32 | 50% | 70885.66 | PO4027-BLH-20250624 - RV Approved | Caltest CLTI1549 | 2025-10-31 | 162840.0306 |  | 2025-07-03
6 | [9 empty] | 6 | 6. AC Equipment |  |  | 50% | 70885.66 |  | Caltest CLTI1621 | 2025-10-31 | 162840.0406 |  | 2025-11-28
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | Project Kick Off | 182300 | 10% | 18230 |  | CS_BHP_001 | 2025-07-31 | 40932.7699 |  | 2025-08-30
6 | [9 empty] | 6 | 6. AC Equipment | Site Establishment |  | 15% | 27345 |  | CS_BHP_001 | 2025-07-31 | 61399.1549 |  | 2025-10-09
6 | [9 empty] | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 36460 |  | CS_BHP_001 | 2025-07-31 | 81865.5399 |  | 2025-11-13
6 | [9 empty] | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 45575 |  | CS_BHP_001 | 2025-07-31 | 102331.9249 |  | 2025-11-19
6 | [9 empty] | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 18230 |  | CS_BHP_001 | 2025-07-31 | 40932.7699 |  | 2025-11-28
6 | [9 empty] | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 18230 |  | CS_BHP_001 | 2025-07-31 | 40932.7699 |  | 2025-11-28
6 | [9 empty] | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 9115 |  | CS_BHP_001 | 2025-07-31 | 20466.385 |  | 2025-12-12
6 | [9 empty] | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 9115 |  | CS_BHP_001 | 2025-07-31 | 20466.385 |  | 2026-03-04
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 260000 | 293798.4496 |  | 8 | 8. Product Add On | [7 empty] | 0 | 0 |  | 93132
8 |  | INVERTER CAGE |  |  | 80000 | 2025-07-31 |  |  |  | 8 | 8. Product Add On | [7 empty] | 0
8 |  | Summation metering |  |  | 85000 | 2025-07-31 |  |  |  | 8 | 8. Product Add On | INVERTER CAGE |  |  | 82302 | PO4198-BLH-20250508 - RV Approved | The Engineering Hub - INV/2025/08/0304 | 2025-08-31 | 293798.4496 |  | 2025-08-30
8 |  | APEX MV Metering Solution |  |  | 95000 | 2025-07-31 |  |  |  | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | Additional Trunking from new roof to DB - VO |  |  | 10830 | PO4474-SBP-20251117 - RV Approved | Cosmic Sun - CS_BHP_008 | 2025-11-30 | 0 |  | 2025-11-19
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 200080 | 2025-11-30 | 636320 | 707022.2222 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0 |  | 840000
9 |  | DC Installation Budget |  |  | 436240 | 2025-08-04 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 840000 | 10% | 84000 |  | CS_BHP_001 | 2025-07-31 | 70702.2222 |  | 2025-08-30
9 | [9 empty] | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 126000 |  | CS_BHP_001 | 2025-07-31 | 106053.3333 |  | 2025-10-09
9 | [9 empty] | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 168000 |  | CS_BHP_002 | 2025-11-30 | 141404.4444 |  | 2025-11-19
9 | [9 empty] | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 193200 |  | CS_BHP_003 | 2025-11-30 | 162615.1111 |  | 2025-11-19
[10 empty] | 9 | 9. AC & DC installation | DC Installation Complete |  |  | 16800 |  | CS_BHP_003 | 2025-11-30 | 14140.4444 |  | 2025-11-19
9 | [9 empty] | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 84000 |  | CS_BHP_004 | 2025-11-30 | 70702.2222 |  | 2025-11-28
9 | [9 empty] | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 84000 |  | CS_BHP_005 | 2025-11-30 | 70702.2222 |  | 2026-02-26
9 | [9 empty] | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 42000 |  | CS_BHP_006 | 2025-12-31 | 35351.1111 |  | 2025-12-12
9 | [9 empty] | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 42000 |  | CS_BHP_011 | 2026-01-31 | 35351.1111 |  | 2026-03-04
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-07-07 | 156487.3333 | 173874.8148 |  | 10 | 10. Site Logistics | Offloading |  |  | 12508.5 |  | Matthews Group:MG INV-1497 | 2025-08-31 | 29556.177 | -0.0031713 | 2025-09-18 | 66798.5
10 |  | Scaffolding |  |  | 42120.6667 | 2025-07-07 |  |  |  | 10 | 10. Site Logistics | Container Rental |  |  | 6400 |  | Container World: PFC02317 | 2025-06-30 | 9662.1722 |  | 2025-06-27
[10 empty] | 10 | 10. Site Logistics |  |  |  | 100 |  | Container World - C581576 | 2025-06-30 | 150.9714 |  | 2025-08-07
[10 empty] | 10 | 10. Site Logistics |  |  |  | 5200 |  | Container World - CM19730 | 2025-07-31 | 12243.0472 |  | 2025-08-21
10 |  | Security |  |  | 96000 | 2025-06-30 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 9866.6667 | 2025-06-30 |  |  |  | 10 | 10. Site Logistics | Container Rental - August |  |  | 620 |  | Container World - C585033 | 2025-07-31 | 1459.7479 |  | 2025-09-01
[10 empty] | 10 | 10. Site Logistics | Container Rental - September |  |  | 600 |  | Container World - C588468 | 2025-08-31 | 11750.6952 |  | 2025-09-30
[10 empty] | 10 | 10. Site Logistics |  |  |  | -5400 |  | Container World - CCM13069 | 2025-08-31 | 0 |  | 2025-09-30
[10 empty] | 10 | 10. Site Logistics |  |  |  | -6400 |  | Container World - PFC02317 | 2025-08-31 | 0 |  | 2025-09-30
[10 empty] | 10 | 10. Site Logistics |  |  |  | 6600 |  | Container World - C580802 | 2025-08-31 | 1642.3652 |  | 2025-09-30
[10 empty] | 10 | 10. Site Logistics | Container Rental - October |  |  | 620 |  | Container World - C591996 | 2025-09-30 | 1589.3856 |  | 2025-09-30
[10 empty] | 10 | 10. Site Logistics | Container Rental - November |  |  | 600 |  | Container World - C595540 | 2025-10-31 | 1694.8657 |  | 2025-11-13
[10 empty] | 10 | 10. Site Logistics | Container Rental - December |  |  | 620 |  | Container World - C599042 | 2025-11-30 | 1589.8701 |  | 2025-12-04
[10 empty] | 10 | 10. Site Logistics | Container Rental - January |  |  | 620 |  | Container World - C602492 | 2025-12-31 | 0 |  | 2026-01-09
[10 empty] | 10 | 10. Site Logistics | Container Rental - February |  |  | 560 |  | Container World - C605863 | 2026-01-31 | 0 |  | 2026-02-05
10 | [9 empty] | 10 | 10. Site Logistics | Project Kick Off | 43550 | 10% | 4355 |  | CS_BHP_001 | 2025-07-31 | 10253.552 |  | 2025-08-30
10 | [9 empty] | 10 | 10. Site Logistics | Site Establishment |  | 15% | 6532.5 |  | CS_BHP_001 | 2025-07-31 | 15380.3281 |  | 2025-10-09
10 | [9 empty] | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 8710 |  | CS_BHP_001 | 2025-07-31 | 20507.1041 |  | 2025-11-13
10 | [9 empty] | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 10887.5 |  | CS_BHP_001 | 2025-07-31 | 25633.8801 |  | 2025-11-19
10 | [9 empty] | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 4355 |  | CS_BHP_001 | 2025-07-31 | 10253.552 |  | 2025-11-28
10 | [9 empty] | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 4355 |  | CS_BHP_001 | 2025-07-31 | 10253.552 |  | 2025-11-28
10 | [9 empty] | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 2177.5 |  | CS_BHP_001 | 2025-07-31 | 5126.776 |  | 2025-12-12
10 | [9 empty] | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 2177.5 |  | CS_BHP_001 | 2025-07-31 | 5126.776 |  | 2026-03-04
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 20008 | 2025-08-25 | 290024 | 322248.8889 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 12250 |  | Sunspot - E032 | 2025-12-31 | 282226.8976 | 0.0014195 | 2026-01-23 | 27850
11 |  | Structural sign off |  |  | 40016 | 2025-08-25 |  |  |  | 11 | 11. Due Dilligence | Structural sign off |  |  | 7500 |  | L&B Consulting: INV-2037 | 2025-07-31 | 13028.3689 |  | 2025-08-30
11 |  | SSEG contingency for ESKOM |  |  | 150000 | 2025-08-25 |  |  |  | 11 | 11. Due Dilligence | SSEG contingency for ESKOM |  |  | 0 |  |  |  | 0
11 |  | Grid Study - Outside of CoCT |  |  | 80000 | 2025-08-25 |  |  |  | 11 | 11. Due Dilligence | Red Team - Completed by Happy Solar |  |  | 8100 | PO4477-SBP-20251118 - RV Approved | HappySolar - INV-0343 | 2025-11-30 | 26993.6209 |  | 2025-12-18
11 | [9 empty] | 11 | 11. Due Dilligence | [7 empty] | 0
12 | BDP Commission | [5 empty] | 0 | 0 |  | 12 | 12. BDP Commission | [10 empty] | 0
12 | BDP Commission | [8 empty] | 12 | 12. BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 64103.9503 | 2025-08-31 | 64103.9503 | 72845.3981 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 79441.874 |  | Matriarch - INV-6570 | 2026-02-28 | 72845.3981 | 0 | 2026-03-31 | 79441.874
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 14000 | 2025-06-30 | 14000 | 15555.5556 |  | 14 | 14. General Expenses | Travel |  |  | 864.48 |  | Expense Claim | 2025-06-30 | 1709.899 | -0.0049699 | 2025-07-04 | 3068.72
14 | [5 empty] | 2025-07-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 309.36 |  | Expense Claim | 2025-07-31 | 4043.2985 |  | 2025-08-07
14 | [5 empty] | 2025-08-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 171.36 |  | Expense Claim | 2025-08-31 | 936.88 |  | 2025-09-05
14 | [5 empty] | 2025-09-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-09-30 | 0 |  | 2025-09-30
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-10-31 | 0 |  | 2025-10-31
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 723.52 |  | Expense Claim | 2025-11-30 | 3667.5733 |  | 2025-12-05
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-12-31 | 0 |  | 2026-01-09
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2026-01-31 | 0 |  | 2026-02-07
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 500 |  |  | 2026-02-28 | 2598.9548 |  | 2026-03-07
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 500 |  |  | 2026-03-31 | 2598.9548 |  | 2026-04-07
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | CS - DC Labour to uninstall and reinstall 72 panels - VO | 50% | 30584.07 | 15292.07 | PO4530-SBP-20251209 - RV Approved | Cosmic Sun - CS_BHP_009 | 2025-12-31 |  | 0 | 2025-12-24 | 37134.08
[10 empty] | 15 | 15. Service Add On |  |  |  | -15292.07 |  | Cosmic Sun - CS_BHP_009 | 2026-01-31 |  |  | 2026-01-31
[10 empty] | 15 | 15. Service Add On |  |  |  | 15292.04 |  | Cosmic Sun - CS_BHP_009 | 2026-01-31 |  |  | 2026-01-31
15 | [9 empty] | 15 | 15. Service Add On | Reinstallation of Panels - VO |  |  | 15292.04 |  | Cosmic Sun - CS_BHP_010 | 2026-01-31 |  |  | 2026-01-29
15 | [9 empty] | 15 | 15. Service Add On | Installation LV Panel - VO |  |  | 6550 |  | Caltest - CLTI1633 | 2026-01-31 |  |  | 2026-01-30
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
| Panel Procurement Budget | 1702080.56 |  | 1979163.4419
| Inverter Procurement Budget | 420000 |  | 488372.093
| Mounting Structure Budget | 320128 |  | 372241.8605
| DC Equipment Budget | 635424.2 |  | 738865.3488
| AC Equipment Budget | 918851.9304 |  | 1134385.0993
| Monitoring Budget | 49000 |  | 56976.7442
| Optional Extras Budget | 0 |  | 0
| MV Equipment Budget | 95000 |  | 110465.1163
| ADD ON | 165000 |  | 183333.3333
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 200080 |  | 222311.1111
| DC Installer Budget | 436240 |  | 484711.1111
| In-House Expense Budget | 64103.9503 |  | 72845.3981
| Compliance Budget | 290024 |  | 322248.8889
| Offloading Budget | 8500 |  | 9444.4444
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 9866.6667 |  | 10962.963
| On Site Security | 96000 |  | 106666.6667
| Roof Access Budget for Installers | 42120.6667 |  | 46800.7407
| EPC Management Fee | 0 |  | 0
| ADD ON | 0 |  | 0
Expenses
| Total EE Expense Budget | 14000 |  | 15555.5556
Note on W35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date
Note on W86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs pls add correct payment date
Note on Q120: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs is this container still onsite?

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2050-12-26
PLANNED |  | CHECK | CHECK
| Planned Revenue | 6355349.9168 | 6355349.9168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2224372.4709 | 0 | 3177674.9584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 635534.9917 | 317767.4958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2224372.4709 | 2224372.4709 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 6037582.421 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168
| Planned Expenditure | 5466419.9741 | 5466419.9741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1038718.5971 | 50620.6667 | 0 | 0 | 309000 | 436240 | 0 | 0 | 3111632.7103 | 0 | 320128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1038718.5971 | 1089339.2638 | 1089339.2638 | 1089339.2638 | 1398339.2638 | 1834579.2638 | 1834579.2638 | 1834579.2638 | 4946211.9741 | 4946211.9741 | 5266339.9741 | 5266339.9741 | 5266339.9741 | 5266339.9741 | 5266339.9741 | 5266339.9741 | 5266339.9741 | 5266339.9741 | 5266339.9741 | 5266339.9741 | 5266339.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741 | 5466419.9741
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2224372.4709 | 1185653.8738 | 4312708.1655 | 4312708.1655 | 4312708.1655 | 4003708.1655 | 3567468.1655 | 3567468.1655 | 3567468.1655 | 455835.4552 | 455835.4552 | 135707.4552 | 135707.4552 | 135707.4552 | 135707.4552 | 135707.4552 | 135707.4552 | 135707.4552 | 135707.4552 | 135707.4552 | 771242.4469 | 1089009.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428 | 888929.9428
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 6355349.9168 | 6355349.9168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2224372.4709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3177674.9584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 635534.9917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317767.4958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2224372.4709 | 2224372.4709 | 2224372.4709 | 2224372.4709 | 2224372.4709 | 2224372.4709 | 2224372.4709 | 2224372.4709 | 2224372.4709 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 5402047.4293 | 6037582.421 | 6037582.421 | 6037582.421 | 6037582.421 | 6037582.421 | 6037582.421 | 6037582.421 | 6037582.421 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168 | 6355349.9168
| Actual + Planned Expenditure | 4803382.074 | 4803382.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6400 | 71750.14 | 0 | 0 | 0 | 32797 | 409.36 | 0 | 5200 | 2669987.1 | 791.36 | 0 | 12508.5 | 975 | 95248.46 | 213365.14 | 0 | 0 | 0 | 0 | 117086.85 | 534438.55 | 338872.52 | 1343.52 | 153021.71 | 8100 | 15292.07 | 850 | 247020 | 7709.2 | 12250 | 21842.01 | 560 | 0 | 0 | 84000 | 71621.71 | 0 | 0 | 0 | 79441.874 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6400 | 78150.14 | 78150.14 | 78150.14 | 78150.14 | 110947.14 | 111356.5 | 111356.5 | 116556.5 | 2786543.6 | 2787334.96 | 2787334.96 | 2799843.46 | 2800818.46 | 2896066.92 | 3109432.06 | 3109432.06 | 3109432.06 | 3109432.06 | 3109432.06 | 3226518.91 | 3760957.46 | 4099829.98 | 4101173.5 | 4254195.21 | 4262295.21 | 4277587.28 | 4278437.28 | 4525457.28 | 4533166.48 | 4545416.48 | 4567258.49 | 4567818.49 | 4567818.49 | 4567818.49 | 4651818.49 | 4723440.2 | 4723440.2 | 4723440.2 | 4723440.2 | 4802882.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074 | 4803382.074
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2217972.4709 | 2146222.3309 | 2146222.3309 | 2146222.3309 | 2146222.3309 | 2113425.3309 | 2113015.9709 | 2113015.9709 | 2107815.9709 | 2615503.8293 | 2614712.4693 | 2614712.4693 | 2602203.9693 | 2601228.9693 | 2505980.5093 | 2292615.3693 | 2292615.3693 | 2292615.3693 | 2292615.3693 | 2292615.3693 | 2175528.5193 | 1641089.9693 | 1302217.4493 | 1300873.9293 | 1147852.2193 | 1775287.211 | 1759995.141 | 1759145.141 | 1512125.141 | 1504415.941 | 1492165.941 | 1470323.931 | 1469763.931 | 1787531.4268 | 1787531.4268 | 1703531.4268 | 1631909.7168 | 1631909.7168 | 1631909.7168 | 1631909.7168 | 1552467.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429 | 1551967.8429
|  | CHECK | CHECK
| Revenue Recognition | -0.0065822 | 6355349.9234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2862464.391 | 0 | 0 | 0 | 1504071.3752 | 0 | 0 | 0 | 737061.8984 | 0 | 0 | 0 | 0 | 1589.3856 | 0 | 0 | 0 | 327374.9369 | 0 | 0 | 0 | 491815.5087 | 0 | 0 | 0 | 0 | 317578.0087 | 0 | 0 | 0 | 35351.1111 | 0 | 0 | 0 | 75444.3529 | 0 | 0 | 0 | 0 | 2598.9548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 6355349.9234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2862464.391 | 2862464.391 | 2862464.391 | 2862464.391 | 4366535.7662 | 4366535.7662 | 4366535.7662 | 4366535.7662 | 5103597.6646 | 5103597.6646 | 5103597.6646 | 5103597.6646 | 5103597.6646 | 5105187.0502 | 5105187.0502 | 5105187.0502 | 5105187.0502 | 5432561.9871 | 5432561.9871 | 5432561.9871 | 5432561.9871 | 5924377.4958 | 5924377.4958 | 5924377.4958 | 5924377.4958 | 5924377.4958 | 6241955.5045 | 6241955.5045 | 6241955.5045 | 6241955.5045 | 6277306.6157 | 6277306.6157 | 6277306.6157 | 6277306.6157 | 6352750.9686 | 6352750.9686 | 6352750.9686 | 6352750.9686 | 6352750.9686 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234 | 6355349.9234

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | 2026-03-31 | Grand Total
(blank)
1. Panels |  | 1979163.4419 |  |  |  |  | 0 |  | 0 |  |  |  | 1979163.4419
2. Inverters |  | 488372.093 | [6 empty] | 0 |  |  |  | 488372.093
3. Mounting Structures |  |  | 372241.8605 | [5 empty] | 0 |  |  |  | 372241.8605
4. DC Equipment |  | 371547.0939 | 367318.2548 |  | 0 | 0 | 0 | [5 empty] | 738865.3487
5. Monitoring |  | 11858.7196 | 45118.0218 | 0 | 0 |  |  |  | 0 |  |  |  | 56976.7414
6. AC Equipment | 0 |  | 409327.6994 | 399377.3315 |  | 325680.0711 |  |  | 0 |  |  |  | 1134385.102
8. Product Add On |  |  |  | 293798.4496 |  |  | 0 |  | 0 |  |  |  | 293798.4496
9. AC & DC installation |  |  | 176755.5556 |  |  |  | 459564.4444 | 35351.1111 | 0 | 35351.1111 |  |  | 707022.2222
10. Site Logistics | 0 | 9813.1437 | 116238.3156 | 42949.2373 | 1589.3856 | 1694.8657 | 1589.8701 | 0 | 0 | 0 |  |  | 173874.818
11. Due Dilligence | 0 |  | 13028.3689 |  |  |  | 26993.6209 | 282226.8976 | 0 |  |  |  | 322248.8875
13. Engineering | 0 | [7 empty] | 0 |  | 72845.3981 |  | 72845.3981
14. General Expenses | 0 | 1709.899 | 4043.2985 | 936.88 | 0 | 0 | 3667.5733 | 0 | 0 | 0 | 2598.9548 | 2598.9548 | 15555.5605
15. Service Add On
12. BDP Commission
7.BESS
Grand Total | 0 | 2862464.391 | 1504071.3752 | 737061.8984 | 1589.3856 | 327374.9369 | 491815.5087 | 317578.0087 | 0 | 35351.1111 | 75444.3529 | 2598.9548 | 6355349.9234
|  | 2862464.39 | 1504071.38 | 737061.9
|  | 0.0010238 | -0.0048338 | -0.0016111

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | Grand Total
(blank)
1. Panels |  | 1584079.2 |  |  |  |  | 7709.2 |  |  |  |  | 1591788.4
2. Inverters |  | 413222.15 | [9 empty] | 413222.15
3. Mounting Structures |  |  | 161835 | [8 empty] | 161835
4. DC Equipment |  | 270000 | 356584.25 |  | -81000 | 81900 | 313900 |  |  |  |  | 941384.25
5. Monitoring |  | 30226.34 | 11375.98 | 2360 | 975 |  |  | 850 |  |  |  | 45787.32
6. AC Equipment |  |  | 182300 | 177868.46 |  | 141771.32 | [5 empty] | 501939.78
8. Product Add On |  |  |  | 82302 |  |  | 10830 |  |  |  |  | 93132
9. AC & DC installation |  |  | 210000 |  |  |  | 546000 | 42000 | 42000 |  |  | 840000
10. Site Logistics |  | 6500 | 49370 | 7908.5 | 620 | 600 | 620 | 620 | 560 |  |  | 66798.5
11. Due Dilligence | 0 |  | 7500 |  |  |  | 8100 | 12250 |  |  |  | 27850
13. Engineering | [9 empty] | 79441.874 |  | 79441.874
14. General Expenses |  | 864.48 | 309.36 | 171.36 | 0 | 0 | 723.52 | 0 | 0 | 500 | 500 | 3068.72
15. Service Add On | [7 empty] | 15292.07 | 21842.01 |  |  | 37134.08
12. BDP Commission
7.BESS
Grand Total | 0 | 2304892.17 | 979274.59 | 270610.32 | -79405 | 224271.32 | 887882.72 | 71012.07 | 64402.01 | 79941.874 | 500 | 4803382.074

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 0.34737 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.1777 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.12022 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 0.2877 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
Blackheath Park |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Blackheath Park | 0 | 0 | 0