## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[9 empty] | 2026-03-02 | 2026-03-02
| PROJECT PLAN | The View | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 166
| PROJECT DEVELOPER | Natasha Watkins-Baker |  |  |  | Target Month | 2025-08-31
| PROJECT MANAGERS | Justin Franke
| CONTRACT VALUE | 1791940.74
| Phase: | Compliance Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Status | Comment
|  |  | 25 |  |  | 99 |  | 100% | 100%
1 | Project Initiation | 2025-07-31 | 12 | 2025-08-12 | 2025-08-04 | 17 | 2025-08-21 | 100% | 100%
1.1 | BD Handover | 2025-08-04 | 1 | 2025-08-05 | 2025-08-04 | 1 | 2025-08-05 | 100% | 100%
1.2 | Project Introduction | 2025-07-31 | 1 | 2025-08-01 | 2025-08-11 | 1 | 2025-08-12 | 100% | 100%
1.3 | HSE | 2025-07-31 | 8 | 2025-08-12 | 2025-08-11 | 8 | 2025-08-21 | 100% | 100%
1.4 | Installer Kick Off | 2025-07-31 | 1 | 2025-08-01 | 2025-08-11 | 1 | 2025-08-12 | 100% | 100%
1.5 | Project Review | 2025-08-07 | 1 | 2025-08-08 | 2025-08-18 | 1 | 2025-08-19 | 100% | 100%
2 | Site Establishment | 2025-08-14 | 1 | 2025-08-15 | 2025-08-25 | 1 | 2025-08-26 | 100% | 100%
2.1 | Solar Contractor Establishment | 2025-08-14 | 1 | 2025-08-15 | 2025-08-25 | 1 | 2025-08-26 | 100% | 100% |  | 71 | Net Work Days
3 | AC Installation | 2025-07-31 | 35 | 2025-09-04 | 2025-07-30 | 119 | 2025-11-26 | 100% | 100% |  | 14.2 | Total Weeks
3.1 | Inverters delivered | 2025-08-15 | 1 | 2025-08-18 | 2025-07-30 | 1 | 2025-07-31 | 100% | 100% |  | 11.6901 | kW/Week Installation Rate
3.2 | Inverters Mounted | 2025-08-18 | 2 | 2025-08-20 | 2025-10-16 | 1 | 2025-10-17 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-07-31 | 20 | 2025-08-28 | 2025-08-11 | 25 | 2025-09-15 | 100% | 100% | DB board delay
3.4 | AC Works | 2025-08-28 | 5 | 2025-09-04 | 2025-10-16 | 19 | 2025-11-12 | 100% | 100%
3.5 | AC Tie-In | 2025-08-28 | 1 | 2025-08-29 | 2025-11-25 | 1 | 2025-11-26 | 100% | 100% | Pending breaker replacement
4 | DC Works | 2025-08-14 | 21 | 2025-09-04 | 2025-08-25 | 92 | 2025-11-25 | 100% | 100%
4.1 | Lifeline Installation |  |  |  | 2025-08-25 | 2 | 2025-10-14 | 100% | 100%
4.1 | Mounting Structure delivered | 2025-08-14 | 1 | 2025-08-15 | 2025-08-25 | 1 | 2025-08-26 | 100% | 100%
4.2 | Mounting Structure installation - Roof A | 2025-08-15 | 3 | 2025-08-20 | 2025-10-05 | 2 | 2025-10-07 | 100% | 100%
4.3 | Mounting Structure installation - Roof B | 2025-08-20 | 1 | 2025-08-29 | 2025-10-07 | 5 | 2025-10-14 | 100% | 100%
4.4 | Mounting Structure installation - Roof C | 2025-08-29 | 2 | 2025-09-02 | 2025-10-08 | 2 | 2025-10-10 | 100% | 100%
4.5 | Mounting Structure installation - Roof D | 2025-09-02 | 1 | 2025-09-03 | 2025-10-10 | 1 | 2025-10-13 | 100% | 100%
4.6 | Mounting Structure installation - Roof E | 2025-09-03 | 1 | 2025-09-04 | 2025-10-13 | 1 | 2025-10-14 | 100% | 100%
4.7 | DC Cable delivered | 2025-08-14 | 1 | 2025-08-15 | 2025-08-25 | 1 | 2025-08-26 | 100% | 100%
4.8 | DC Stringing | 2025-08-23 | 4 | 2025-08-28 | 2025-10-28 | 20 | 2025-11-25 | 100% | 100%
5 | Module installation | 2025-08-14 | 12 | 2025-08-26 | 2025-07-30 | 114 | 2025-11-21 | 100% | 100%
5.1 | Module delivery | 2025-08-14 | 1 | 2025-08-15 | 2025-07-30 | 1 | 2025-07-31 | 100% | 100%
5.2 | Module mounting - Roof A | 2025-08-20 | 4 | 2025-08-26 | 2025-10-14 | 3 | 2025-10-17 | 100% | 100%
5.3 | Module mounting - Roof B | 2025-08-29 | 5 | 2025-09-05 | 2025-11-18 | 3 | 2025-11-21 | 100% | 100%
5.4 | Module mounting - Roof C | 2025-09-02 | 6 | 2025-09-10 | 2025-10-22 | 19 | 2025-11-18 | 100% | 100%
5.5 | Module mounting - Roof D | 2025-09-03 | 7 | 2025-09-12 | 2025-11-18 | 2 | 2025-11-20 | 100% | 100%
5.6 | Module mounting - Roof E | 2025-09-04 | 8 | 2025-09-16 | 2025-10-29 | 2 | 2025-10-31 | 100% | 100%
6 | Commissioning | 2025-09-04 | 4 | 2025-09-08 | 2025-11-26 | 6 | 2025-12-02 | 100% | 100%
6.1 | Commissioning | 2025-09-04 | 1 | 2025-09-05 | 2025-11-26 | 2 | 2025-11-28 | 100% | 100%
6.2 | Practical Completion | 2025-09-05 | 1 | 2025-09-08 | 2025-11-28 | 2 | 2025-12-02 | 100% | 100%
7 | QA Inspections | 2025-09-04 | 1 | 2025-09-05 | 2025-12-09 | 1 | 2025-12-10 | 100% | 100%
7.1 | Red-Team Inspection | 2025-09-04 | 1 | 2025-09-05 | 2025-12-09 | 1 | 2025-12-10 | 100% | 100%
8 | Project Closure | 2025-09-05 | 20 | 2025-09-25 | 2025-12-02 | 83 | 2026-02-23 | 100% | 100%
8.1 | Equipment serial numbers | 2025-09-05 | 1 | 2025-09-08 | 2025-12-10 | 1 | 2025-12-11 | 100% | 100%
8.2 | Snags completion | 2025-09-05 | 5 | 2025-09-12 | 2026-01-12 | 7 | 2026-01-21 | 100% | 100%
8.3 | System Performance Monitoring | 2025-09-08 | 5 | 2025-09-15 | 2025-12-02 | 25 | 2026-01-08 | 100% | 100%
8.4 | Handover documentation | 2025-09-12 | 1 | 2025-09-15 | 2026-01-21 | 16 | 2026-02-12 | 100% | 100%
8.5 | Handover to Client | 2025-09-15 | 1 | 2025-09-16 | 2026-02-16 | 1 | 2026-02-17 | 100% | 100%
8.6 | Handover to Matriarch | 2025-09-17 | 5 | 2025-09-25 | 2026-02-16 | 5 | 2026-02-23 | 100% | 100%
Formulas:
Natasha Watkins-Baker = MIN([Natasha Watkins-Baker, row below]:E16)
Natasha Watkins-Baker = [Natasha Watkins-Baker, row above]
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Natasha Watkins-Baker],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = [Actual Start, row above]
Actual End = MAX([Actual End, row below]:K16)
Actual End = WORKDAY.INTL([Actual Start],[Target Month],1,Data!$C3:C14)
Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )
Note on O56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Justin Franke where are we with snag completion>?

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW
1 | Planned Revenue | 1791940.74 |  | 1791940.74 |  |  |  | Start Date
2 | Planned Expenditure | 1566125.2658 |  | 1865330.23 | VO PM Limit | Current VO Total
3 | Planned Profit | 225815.4742 |  | -73389.49 | 11290.7737 | 57250 |  | End Date - PC
4 | Planned Margin | 12.6% |  | -4.096%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Acceptance and Initial Deposit |  | 50% | 895970.37 |  | 2025-07-31 | 004784 | 2025-07-16 | 2025-07-25 |  | 1900-01-06
2 | Delivery of Panels |  | 10% | 179194.074 |  | 2025-08-21 | 004809 | 2025-08-11 | 2025-08-15
3 | Delivery of Inverters |  | 25% | 447985.185 |  | 2025-08-22 | 004817 | 2025-08-18 | 2025-08-25
4 | Practical Completion |  | 10% | 179194.074 |  | 2025-09-15 | 004899 | 2025-12-10 | 2025-12-15
5 | Handover |  | 5% | 89597.037 |  | 2025-09-22 | 004929 | 2026-01-22 | 2026-01-30 | Has this been received?
6 | - |  | 0% | 0
7 | - |  | 0% | 0
|  |  | 100% | 1791940.74
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 627179.259
2 | Delivery of Panels |  | 30% | 537582.222
3 | Delivery of Inverters |  | 20% | 358388.148
4 | Practical Completion |  | 10% | 179194.074
5 | Handover |  | 5% | 89597.037
| Total |  | 100% | 1791940.74
|  |  | 100% | 1791940.74
Formulas:
PAYMENT RECEIVED DATE = [TIMELINE REVIEW]+7
Note on R14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Thami Cambalele please invoice these for us

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 1566125.2658 |  | 1865330.23 | -299204.9642
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 469263.17 |  | 324441 | 144822.17
2 | 2. Inverters | 140000 |  | 137740.7 | 2259.3
3 | 3. Mounting Structures | 66576 |  | 157679.66 | -91103.66
4 | 4. DC Equipment | 151592.2 |  | 453642.25 | -302050.05
5 | 5. Monitoring | 49000 |  | 36933.71 | 12066.29
6 | 6. AC Equipment | 262993.3826 |  | 184885.08 | 78108.3026
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 4000 |  | 3600 | 400
9 | 9. AC & DC installation | 138700 |  | 315566.4 | -176866.4
10 | 10. Site Logistics | 76280.0333 |  | 161120 | -84839.9667
11 | 11. Due Dilligence | 89000 |  | 20194.13 | 68805.87
12 | 12. BDP Commission | 0 |  | 0 | 0
13 | 13. Engineering | 115920.4798 |  | 69527.3 | 46393.1798
14 | 14. General Expenses | 2800 |  | 0 | 2800
15 | 15. Service Add On | 0 |  | 0 | 0
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 1566125.2658 | 1791940.7415 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 1865330.23
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 469263.17 | 2025-09-25 | 469263.17 | 533253.6023 |  | 1 | 1. Panels | Jinko 590 modules | 282 | 1150.5 | 324441 |  | Menlo INV0003100 | 2025-07-31 | 533253.6023 | 0 | 2025-09-25 | 324441
1 |  | Delivery Budget | [7 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[17 empty] | 45952 | [5 empty] | AC Equipment | 262993.3826
2 | Inverters | Inverter Budget |  |  | 140000 | 2025-09-25 | 140000 | 159090.9091 |  | 2 | 2. Inverters | Huawei 50KTL | 1 | 43606.08 | 43606.08 |  | Menlo INV0003100 | 2025-07-31 | 78238.4976 | 0 | 2025-09-25 | 137740.7 | DC Equipment | 99092.2
2 | [9 empty] | 2 | 2. Inverters | From stock | 1 | 45062.94 | 45062.94 |  | Allocated from Cpt Stock | 2025-07-31 | 80852.4115 |  | 2025-07-31 |  | AC Labour | 41610
[10 empty] | 2 | 2. Inverters | Huawei 50KTL to be credited |  |  | -43606.08 |  | Menlo - CRN0000252 | 2025-09-30 |  |  | 2025-09-26
[10 empty] | 2 | 2. Inverters | To be moved to Waterside |  |  | -45062.94 |  | Allocated to Waterside | 2025-08-31 |  |  | 2025-08-31
2 | [9 empty] | 2 | 2. Inverters | Needs to be replaced with 2 x 100KTLs | [6 empty] | 0 |  |  |  | DC Labour | 97090
2 | [9 empty] | 2 | 2. Inverters | Huawei 100KTL (Menlo | 2 | 68870.35 | 137740.7 |  | Menlo - INV0003227 | 2025-08-31 | 0 |  | 2025-10-31 |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 24446.7
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 4933.3333
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 66576 | 2025-09-25 | 66576 | 75654.5455 |  | 3 | 3. Mounting Structures | Schletter Structure |  |  | 154429.66 | PO4233-SBT-20250818 - RV Approved | Schletter INV2118 | 2025-08-31 | 75654.5455 | 0 | 2025-09-30 | 157679.66 | Other | 0
3 | [9 empty] | 3 | 3. Mounting Structures | Additional Mid and End Clamps - VO |  |  | 3250 | PO4471-SBT-20251114 - RV Approved | Solarworld SASIV-25-00684 | 2025-11-30 | 0 |  | 2026-01-09 |  | Total | 538665.6159
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Less 15% | 457865.7736
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | R/Wp | 2.7582
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL - Boundary Terraces | Installer Price
[23 empty] | AC Equipment | 123026
4 | DC Equipment | DC Cable Budget | 4312.5 |  | 52500 | 2025-09-01 | 151592.2 | 172263.8636 |  | 4 | 4. DC Equipment | DC Cable | 4000 | 14 | 54000 |  | Rubicon Inv:INVWCRE-0069643 | 2025-07-31 | 60762.3944 | 0.0012713 | 2025-09-01 | 453642.25 | DC Equipment | 345642.25
4 |  | DC Equipment Budget |  |  | 99092.2 | 2025-09-01 |  |  |  | 4 | 4. DC Equipment | Additional DC Cable - VO | 4000 |  | 54000 | PO4257-SBT-20250831 - RV Approved | Rubicon Inv:INVWCRE-0070233 | 2025-08-31 | 0 |  | 2025-09-30 |  | AC Labour | 110490
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | DC Labour | 205076.4
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Lifelines
4 | [9 empty] | 4 | 4. DC Equipment | Project Kick Off | 345642.25 | 10% | 34564.225 | PO4244-SBT-20250820 - RV Approved | Happy Solar INV-0331 | 2025-08-31 | 13125.2478 |  | 2025-07-29 |  | Forklift
4 | [9 empty] | 4 | 4. DC Equipment | Site Establishment |  | 15% | 51846.3375 |  | Happy Solar INV-0331 | 2025-08-31 | 19687.8717 |  | 2025-09-05 |  | Geda
4 | [9 empty] | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 69128.45 |  | Happy Solar INV-0331 | 2025-08-31 | 6499.4856 |  | 2025-11-06 |  | Logistics | 161120
4 | [9 empty] | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 86410.5625 |  | Happy Solar INV-0331 | 2025-08-31 | 32813.1195 |  | 2025-12-04 |  | HSE | 0
4 | [9 empty] | 4 | 4. DC Equipment | Commissioning Complete | 94535.465 | 10% | 34564.225 |  | Happy Solar INV-0331 | 2025-08-31 | 13125.2478 |  | 2025-12-24 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 34564.225 |  | Happy Solar INV-0331 | 2025-08-31 | 13125.2478 |  | 2025-12-24 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 17282.1125 |  | Happy Solar INV-0331 | 2025-08-31 | 6562.6239 |  | 2026-01-29 |  | Total | 945354.65
4 | [9 empty] | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 17282.1125 |  | Happy Solar INV-0331 | 2025-08-31 | 6562.6239 |  | 2026-02-26 |  | R/Wp | 5.6949
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 34000 | 2025-09-25 | 49000 | 55681.8182 |  | 5 | 5. Monitoring | Smartlogger |  |  | 8598.34 |  | Menlo INV0003100 | 2025-07-31 | 12837.9814 | 0.00036923 | 2025-09-25 | 36933.71
5 |  | Revenue Metering |  |  | 15000 | 2025-09-25 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 14768 | PO4269-SBT-20250825 - RV Approved | AccuEnergy - ASAI-00620 | 2025-08-31 | 22468.3801 |  | 2025-09-30
5 | [9 empty] | 5 | 5. Monitoring | Techsitter |  |  | 11169 |  | Matriarch - INV-4999 | 2025-08-31 | 17104.0817 |  | 2025-08-31
[10 empty] | 5 | 5. Monitoring | Delivery of Techsitter Meter |  |  | 209.27 |  | DSV Inv: 180145917 | 2025-09-30 | 0 |  | 2025-10-31
5 | [9 empty] | 5 | 5. Monitoring | Battery |  |  | 975 |  | Red Pole Energy: SO-35689 | 2025-08-31 | 1969.6941 |  | 2025-08-30
5 | [9 empty] | 5 | 5. Monitoring | Powersupply |  |  | 850 |  | Mantech-SOR1007853 | 2025-08-31 | 1301.6805 |  | 2025-08-30
5 | [9 empty] | 5 | 5. Monitoring |  |  |  | -850 |  | Mantech - CRN949171 | 2025-09-30 | 0 |  | 2025-09-30
5 | [9 empty] | 5 | 5. Monitoring |  |  |  | 1214.1 |  | Current Automotion - SOQ324142 | 2025-09-30 | 0 |  | 2025-09-09
6 | AC Equipment | AC Equipment Budget |  |  | 262993.3826 | 2025-09-25 | 262993.3826 | 298856.1166 |  | 6 | 6. AC Equipment | [7 empty] | 0 | 0 |  | 184885.08
6 | [9 empty] | 6 | 6. AC Equipment | PVDB |  |  | 61859.08 |  | Switchboard 2-SOI002235 | 2025-08-31 | 99991.6512 |  | 2025-09-30
6 | [9 empty] | 6 | 6. AC Equipment | ABB XT5N 400A TP MCCB |  |  | 10499.85 | PO4445-SBT-20251105 - RV Approved | Switchboard 2-SOI002578 | 2025-11-30 | 0 |  | 2025-12-30
6 | [9 empty] | 6 | 6. AC Equipment | RMA - SWB - ABB XT5N 400A TP MCCB |  |  | -10499.85 |  |  | 2026-02-28 | 0 |  | 2026-03-30
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | Project Kick Off | 123026 | 10% | 7292.92 | PO4244-SBT-20250820 - RV Approved | Happy Solar INV-0331 | 2025-08-31 | 19886.4465 |  | 2025-07-29
[10 empty] | 6 | 6. AC Equipment |  |  |  | 5009.68 |  | Happy Solar INV-0331 | 2025-08-31 | 0 |  | 2025-08-21
6 | [9 empty] | 6 | 6. AC Equipment | Site Establishment |  | 15% | 18453.9 |  | Happy Solar INV-0331 | 2025-08-31 | 29829.6698 |  | 2025-09-05
6 | [9 empty] | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 24605.2 |  | Happy Solar INV-0331 | 2025-08-31 | 39772.8931 |  | 2025-11-06
6 | [9 empty] | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 30756.5 |  | Happy Solar INV-0331 | 2025-08-31 | 49716.1164 |  | 2025-12-04
6 | [9 empty] | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 12302.6 |  | Happy Solar INV-0331 | 2025-08-31 | 19886.4465 |  | 2025-12-24
6 | [9 empty] | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 12302.6 |  | Happy Solar INV-0331 | 2025-08-31 | 19886.4465 |  | 2025-12-24
6 | [9 empty] | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 6151.3 |  | Happy Solar INV-0331 | 2025-08-31 | 9943.2233 |  | 2026-01-29
6 | [9 empty] | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 6151.3 |  | Happy Solar INV-0331 | 2025-08-31 | 9943.2233 |  | 2026-02-26
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 4000 | 4494.382 |  | 8 | 8. Product Add On | [8 empty] | 0 |  | 3600
8 | [9 empty] | 8 | 8. Product Add On
8 |  | Check Meter |  |  | 4000 | 2025-09-11 |  |  |  | 8 | 8. Product Add On | Check Meter |  |  | 3600 | PO4240-ARIM-20250819 - RV Approved | CBB - CBB-5722 | 2025-08-31 | 4494.382 |  | 2025-09-11
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 41610 | 2025-08-21 | 138700 | 163176.4706 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0 |  | 315566.4
9 |  | DC Installation Budget |  |  | 97090 | 2025-08-21 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 315566.4 | 10% | 31556.64 | PO4244-SBT-20250820 - RV Approved | Happy Solar INV-0331 | 2025-08-31 | 16317.6471 |  | 2025-08-21
9 | [9 empty] | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 47334.96 |  | Happy Solar INV-0331 | 2025-08-31 | 24476.4706 |  | 2025-09-05
9 | [9 empty] | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 63113.28 |  | Happy Solar INV-0331 | 2025-08-31 | 32635.2941 |  | 2025-11-06
9 | [9 empty] | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 78891.6 |  | Happy Solar INV-0331 | 2025-08-31 | 40794.1176 |  | 2025-12-04
9 | [9 empty] | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 31556.64 |  | Happy Solar INV-0331 | 2025-08-31 | 16317.6471 |  | 2025-12-24
9 | [9 empty] | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 31556.64 |  | Happy Solar INV-0331 | 2025-08-31 | 16317.6471 |  | 2025-12-24
9 | [9 empty] | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 15778.32 |  | Happy Solar INV-0331 | 2025-08-31 | 8158.8235 |  | 2026-01-29
9 | [9 empty] | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 15778.32 |  | Happy Solar INV-0331 | 2025-08-31 | 8158.8235 |  | 2026-02-26
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-08-21 | 76280.0333 | 89741.2157 |  | 10 | 10. Site Logistics | [7 empty] | 0 | 0 |  | 161120
10 |  | Scaffolding |  |  | 24446.7 | 2025-08-21 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Security |  |  | 38400 | 2025-08-21 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 4933.3333 | 2025-08-21 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | Project Kick Off | 161120 | 10% | 16112 | PO4244-SBT-20250820 - RV Approved | Happy Solar INV-0331 | 2025-08-31 | 8974.1216 |  | 2025-08-21
10 | [9 empty] | 10 | 10. Site Logistics | Site Establishment |  | 15% | 24168 |  | Happy Solar INV-0331 | 2025-08-31 | 13461.1824 |  | 2025-09-05
10 | [9 empty] | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 32224 |  | Happy Solar INV-0331 | 2025-08-31 | 17948.2431 |  | 2025-11-06
10 | [9 empty] | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 40280 |  | Happy Solar INV-0331 | 2025-08-31 | 22435.3039 |  | 2025-12-04
10 | [9 empty] | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 16112 |  | Happy Solar INV-0331 | 2025-08-31 | 8974.1216 |  | 2025-12-24
10 | [9 empty] | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 16112 |  | Happy Solar INV-0331 | 2025-08-31 | 8974.1216 |  | 2025-12-24
10 | [9 empty] | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 8056 |  | Happy Solar INV-0331 | 2025-08-31 | 4487.0608 |  | 2026-01-29
10 | [9 empty] | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 8056 |  | Happy Solar INV-0331 | 2025-08-31 | 4487.0608 |  | 2026-02-26
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2025-08-21 | 89000 | 104705.8824 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 8374.7 |  | Sunspot Inv:E028 | 2025-07-31 | 10934.4706 | -0.004661 | 2026-01-30 | 20194.13
11 |  | Structural sign off |  |  | 18000 | 2025-08-21 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 5819.43 |  | L&B Inv 1701 | 2025-07-31 | 7598.169 |  | 2024-08-22
11 |  | Scada for CoCT |  |  | 60000 | 2025-08-21 |  |  |  | 11 | 11. Due Dilligence | [7 empty] | 0
11 | [9 empty] | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 |  | Matriarch - INV-4987 | 2025-08-31 | 86173.2475 |  | 2025-08-31
11 | [9 empty] | 11 | 11. Due Dilligence | [7 empty] | 0
12 | BDP Commission | [5 empty] | 0 | 0 |  | 12 | 12. BDP Commission | [10 empty] | 0
12 | BDP Commission | [8 empty] | 12 | 12. BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 18042.5598 | 2025-08-31 | 115920.4798 | 131727.818 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 22399.2593 |  | Matriarch - INV-4986 | 2025-08-31 | 131727.818 | 0 | 2025-08-31 | 69527.3
13 |  |  |  |  | 12800 | 2025-08-31 |  |  |  | 13 | 13. Engineering |  |  |  | -22399.2593 |  | Matriarch - CRN-5196 | 2025-08-31 | 0 |  | 2025-08-31
13 |  |  |  |  | 43520 | 2025-08-31 |  |  |  | 13 | 13. Engineering |  |  |  | 69527.3 |  | Matriarch - INV-5195 | 2025-08-31 | 0 |  | 2025-08-31
13 |  |  |  |  | 16640 | 2025-08-31 |  |  |  | 13 | 13. Engineering |  |  |  | 0 |  |  |  | 0
13 |  |  |  |  | 24917.92 | 2025-08-31 |  |  |  | 13 | 13. Engineering |  |  |  | 0 |  |  |  | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 2800 | 2025-09-05 | 2800 | 3294.1176 |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  | 2025-08-31 | 3294.1176 | 0 | 2025-09-05 | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [5 empty] | 2025-09-30 | 0 |  | 2025-09-30
14 | [9 empty] | 14 | 14. General Expenses | Travel | [5 empty] | 2025-10-31 | 0 |  | 2025-10-31
14 | [9 empty] | 14 | 14. General Expenses | Travel | [5 empty] | 2025-11-30 | 0 |  | 2025-11-30
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | [8 empty] | 0 |  | 0
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
| Panel Procurement Budget | 469263.17 |  | 533253.6023
| Inverter Procurement Budget | 140000 |  | 159090.9091
| Mounting Structure Budget | 66576 |  | 75654.5455
| DC Equipment Budget | 151592.2 |  | 172263.8636
| AC Equipment Budget | 262993.3826 |  | 298856.1166
| Monitoring Budget | 49000 |  | 55681.8182
| Optional Extras Budget | 0 |  | 0
| MV Equipment Budget | 0 |  | 0
| ADD ON | 4000 |  | 4494.382
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 41610 |  | 48952.9412
| DC Installer Budget | 97090 |  | 114223.5294
| In-House Expense Budget | 115920.4798 |  | 131727.818
| Compliance Budget | 89000 |  | 104705.8824
| Offloading Budget | 8500 |  | 10000
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 4933.3333 |  | 5803.9216
| On Site Security | 38400 |  | 45176.4706
| Roof Access Budget for Installers | 24446.7 |  | 28760.8235
| EPC Management Fee | 0 |  | 0
| ADD ON | 0 |  | 0
Expenses
| Total EE Expense Budget | 2800 |  | 3294.1176
Note on W36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Mizelda please check the payment date on this
Note on W68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs payment date to be updated

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 1791940.74 | 1791940.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 895970.37 | 0 | 0 | 627179.259 | 0 | 0 | 0 | 179194.074 | 89597.037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 895970.37 | 895970.37 | 895970.37 | 1523149.629 | 1523149.629 | 1523149.629 | 1523149.629 | 1702343.703 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74
| Planned Expenditure | 1566125.2658 | 1566125.2658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 303980.0333 | 115920.4798 | 154392.2 | 4000 | 0 | 987832.5526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 303980.0333 | 419900.5132 | 574292.7132 | 578292.7132 | 578292.7132 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658 | 1566125.2658
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 895970.37 | 895970.37 | 895970.37 | 1219169.5957 | 1103249.1158 | 948856.9158 | 944856.9158 | 1124050.9898 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742 | 225815.4742
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 1791940.74 | 1791940.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 895970.37 | 0 | 0 | 179194.074 | 0 | 447985.185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179194.074 | 0 | 0 | 0 | 0 | 0 | 89597.037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 895970.37 | 895970.37 | 895970.37 | 1075164.444 | 1075164.444 | 1523149.629 | 1523149.629 | 1523149.629 | 1523149.629 | 1523149.629 | 1523149.629 | 1523149.629 | 1523149.629 | 1523149.629 | 1523149.629 | 1523149.629 | 1523149.629 | 1523149.629 | 1523149.629 | 1523149.629 | 1523149.629 | 1702343.703 | 1702343.703 | 1702343.703 | 1702343.703 | 1702343.703 | 1702343.703 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74 | 1791940.74
| Actual + Planned Expenditure | 1865330.23 | 1859510.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86920.085 | 0 | 0 | 52678.32 | 43458.36 | 195803.1975 | 4814.1 | 0 | 333039.34 | 284206.74 | 0 | 0 | 0 | 137949.97 | 189070.93 | 0 | 0 | 0 | 236338.6625 | 0 | 0 | 189070.93 | 10499.85 | 3250 | 0 | 0 | 55642.4325 | 0 | 0 | 0 | 47267.7325 | 0 | 0 | 0 | 0 | -10499.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86920.085 | 86920.085 | 86920.085 | 139598.405 | 183056.765 | 378859.9625 | 383674.0625 | 383674.0625 | 716713.4025 | 1000920.1425 | 1000920.1425 | 1000920.1425 | 1000920.1425 | 1138870.1125 | 1327941.0425 | 1327941.0425 | 1327941.0425 | 1327941.0425 | 1564279.705 | 1564279.705 | 1564279.705 | 1753350.635 | 1763850.485 | 1767100.485 | 1767100.485 | 1767100.485 | 1822742.9175 | 1822742.9175 | 1822742.9175 | 1822742.9175 | 1870010.65 | 1870010.65 | 1870010.65 | 1870010.65 | 1870010.65 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8 | 1859510.8
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 895970.37 | 809050.285 | 809050.285 | 988244.359 | 935566.039 | 1340092.864 | 1144289.6665 | 1139475.5665 | 1139475.5665 | 806436.2265 | 522229.4865 | 522229.4865 | 522229.4865 | 522229.4865 | 384279.5165 | 195208.5865 | 195208.5865 | 195208.5865 | 195208.5865 | -41130.076 | -41130.076 | 138063.998 | -51006.932 | -61506.782 | -64756.782 | -64756.782 | -64756.782 | -30802.1775 | -30802.1775 | -30802.1775 | -30802.1775 | -78069.91 | -78069.91 | -78069.91 | -78069.91 | -78069.91 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06 | -67570.06
|  | CHECK | CHECK
| Revenue Recognition | -0.0045367 | 1791940.7445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 784477.5267 | 0 | 0 | 0 | 1007463.2178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 1791940.7445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 784477.5267 | 784477.5267 | 784477.5267 | 784477.5267 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445 | 1791940.7445

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 |  | 2026-02-28 | Grand Total
(blank)
1. Panels |  | 533253.6023 |  |  |  |  | 0 |  | 533253.6023
2. Inverters | 0 | 159090.9091 | 0 |  |  |  | 0 |  | 159090.9091
3. Mounting Structures |  |  | 75654.5455 |  |  | 0 | 0 |  | 75654.5455
4. DC Equipment |  | 60762.3944 | 111501.468 |  |  |  | 0 |  | 172263.8624
5. Monitoring |  | 12837.9814 | 42843.8364 | 0 |  |  |  |  | 55681.8178
6. AC Equipment |  |  | 298856.1166 |  |  | 0 | 0 | 0 | 298856.1166
8. Product Add On |  |  | 4494.382 | [5 empty] | 4494.382
9. AC & DC installation | 0 |  | 163176.4706 |  |  |  | 0 |  | 163176.4706
10. Site Logistics | 0 |  | 89741.2157 |  |  |  | 0 |  | 89741.2157
11. Due Dilligence |  | 18532.6396 | 86173.2475 |  |  |  | 0 |  | 104705.887
13. Engineering | 0 |  | 131727.818 |  |  |  | 0 |  | 131727.818
14. General Expenses |  |  | 3294.1176 | 0 | 0 | 0 | 0 |  | 3294.1176
15. Service Add On
12. BDP Commission
7.BESS
Grand Total | 0 | 784477.5267 | 1007463.2178 | 0 | 0 | 0 | 0 | 0 | 1791940.7445
1791940.74

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2026-02-28 | Grand Total
(blank)
1. Panels |  | 324441 | [5 empty] | 324441
2. Inverters |  | 88669.02 | 92677.76 | -43606.08 |  |  |  | 137740.7
3. Mounting Structures |  |  | 154429.66 |  |  | 3250 |  | 157679.66
4. DC Equipment |  | 54000 | 399642.25 |  |  |  |  | 453642.25
5. Monitoring |  | 8598.34 | 27762 | 573.37 |  |  |  | 36933.71
6. AC Equipment |  |  | 184885.08 |  |  | 10499.85 | -10499.85 | 184885.08
8. Product Add On |  |  | 3600 |  |  |  |  | 3600
9. AC & DC installation |  |  | 315566.4 |  |  |  |  | 315566.4
10. Site Logistics |  |  | 161120 |  |  |  |  | 161120
11. Due Dilligence |  | 14194.13 | 6000 |  |  |  |  | 20194.13
13. Engineering | 0 |  | 22399.2593 |  |  |  |  | 22399.2593
14. General Expenses |  |  | 0 |  |  |  |  | 0
15. Service Add On
12. BDP Commission
7.BESS
Grand Total | 0 | 489902.49 | 1368082.4093 | -43032.71 |  | 13749.85 | -10499.85 | 1818202.1892

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate | [5 empty] | FINANCIAL CLOSE CERTIFICATE
Project Name: | The View
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion: |  |  |  | 1. Financial Close | 1. Financial Close
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 1.6741 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.85637 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.57936 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 1.3865 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
The View |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | The View | 0 | 0 | 0