## Tasks
Engineering
OPERATIONAL SITES
Task Type | Task ID | Task Name | Status | Task Content | Assignee | Priority | Latest Comment | Comment Count | Assigned Comment Count | Due Date | Start Date | Date Created | Date Updated | Date Closed | Date Done | Created By | Space | Folder | List | Subtask ID's | Subtask URL's | tags | Lists | Sprints | Linked Tasks | Linked Docs | Time Logged | Time Logged Rolled Up | Time Estimate | Time Estimate Rolled Up | Time In Status | Points Estimate | Points Estimate Rolled Up | Approval Signature (signature) | Completion % (automatic progress) | STAGE (drop down) | Site (labels) | Site (short text) | Summary (text) | TRACKING (drop down) | Task Name (text)
Task | 86c4cq20w | Gezina Galleries | OPERATIONAL SITES |  | johan snyman |  | Please remove the circuit breaker here as it is only a signal, and show a relay N/O at the generator switching said signal | 2 | 0 | 2026-02-25 |  | 2025-07-08 19:44 | 2026-02-06 10:06 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 359 hours |  | 0 |  | 100% |  | Gezina Galleries |  |  | Green
Task | 86c6ywwve | Riverside Mall - Project Engineering | OPERATIONAL SITES |  | Gerhard |  | Hi @Paul Dreyer @Gerhard @Mary Boakye , when can we have the updated/latest Techsitter Target File for * Riverside Mall * as this is needed when ordering the meters? | 8 | 0 | 2026-02-26 |  | 2025-12-08 09:42 | 2026-02-17 10:35 |  |  | Gerhard | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 669 hours |  | 0 |  | 100% |  | Riverside Mall |  | - Project for Riverside Mall assigned to [@Gerhard](#88690613). - Status is 'to do' and progress is at 0%. - Due by 12/12/2025 02:00 AM (UTC). | Green
Task | 86c82g6pe | Meraki PH3 | OPERATIONAL SITES |  | johan snyman, Dean Cornelius |  | @johan snyman you can send the EP to LLoyd | 2 | 0 | 2026-02-27 |  | 2026-02-06 08:44 | 2026-02-16 10:05 |  |  | johan snyman | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 49 hours |  | 0 |  | 0% |  | Meraki Ph3 |  | - [@johan snyman](#100552512) is working on this project. - Status is in progress, but 0% is done so far. - Due date was 02/06/2026 at 02:00 AM UTC. | Green
Task | 86c6yvmzu | 7th Avenue - Project Engineering | OPERATIONAL SITES |  | Gerhard |  | Hi @Paul Dreyer @Gerhard @Mary Boakye , when can we have the updated/latest Techsitter Target File for 7th Avenue Park as this is needed when ordering the meters? | 13 | 0 | 2026-03-03 |  | 2025-12-08 07:11 | 2026-02-17 10:36 |  |  | Gerhard | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 517 hours |  | 0 |  | 100% |  | 7th Avenue |  | - Project for 7th Avenue assigned to [@Brandon Watts](#88690611) and [@Gerhard](#88690613). - Due by 12/12/2025 02:00 AM (UTC). - Current progress is 0%. - No comments or updates yet. | Green
Task | 86c7gq4gp | TopSteel - Project Engineering | OPERATIONAL SITES |  | Gerhard |  | @Gerhard when can we have the updated/latest Techsitter Targets File as this is needed when ordering the meters? | 3 | 0 | 2026-03-03 |  | 2026-01-12 09:51 | 2026-02-11 21:20 |  |  | Gerhard | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 387 hours |  | 0 |  | 100% |  | Top Steel |  | - Project for Top Steel is in progress. - Assigned to [@Gerhard](#88690613). - Due by 01/16/2026 02:00 AM (UTC). - Progress is at 0%. | Green
Task | 86c425wba | Steelpark | OPERATIONAL SITES |  | Gerhard |  | @Gerhard when can we have the updated/latest Techsitter Targets File as this is needed when ordering the meters? | 21 | 0 | 2026-03-13 |  | 2025-06-18 07:42 | 2026-02-11 21:18 |  |  | Gerhard | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 187 hours |  | 0 |  | 100% |  | Steelpark |  |  | Green
Task | 86c4a4x3g | Marikana Shoprite | OPERATIONAL SITES |  | johan snyman |  | @johan snyman do is this still in progress? Do you require support? | 4 | 0 |  |  | 2025-07-03 12:40 | 2026-01-14 09:50 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 986 hours |  | 0 |  | 100% |  | Marikana Shoprite |  |  | Green
Task | 86c59z4z0 | BMG Fluid Tech | OPERATIONAL SITES |  | johan snyman |  | ╕±╖ⁿ╢≈-GIV0250-NRS Report.pdf NRS-2017_150T_250T.pdf @Keith Abdulla please see attached the NRS documents as sent on Whatsapp. Let me know if you need anything else | 9 | 0 |  |  | 2025-09-03 08:50 | 2026-02-13 10:06 |  |  | Keith Abdulla | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 2400 hours |  | 0 |  | 100% |  | BMG Fluid Tech |  |  | Green
Task | 86c59awuz | Coega Steel Phase 2 | OPERATIONAL SITES |  | Dean Cornelius |  | DSP-HWE-PVA-EP-MST-003-0A_Rev02.pdf JUPITER-(3000K, 6000K, 9000K)-H1 Smart Transformer Station Installation Guide (with Built-In SACU).pdf FusionSolar8.0 Solution Overview v1.0-202308.pdf | 4 | 0 |  |  | 2025-09-02 08:49 | 2025-12-10 10:01 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 2400 hours |  | 0 |  | 100% |  | Coega Steel |  |  | Green
Task | 86c4cq240 | Pretoria North | OPERATIONAL SITES |  | johan snyman |  |  | 0 | 0 |  |  | 2025-07-08 19:45 | 2026-02-13 10:06 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 2400 hours |  | 0 |  | 0% |  | Shoprite Pretoria North |  |  | Green
Task | 86c4mwwpx | Malvern Engineering | OPERATIONAL SITES |  | johan snyman |  | @Dean Cornelius Hi Dean, updated the EP to show the new inverter location and TIE-IN point. Will share the document. Had to update the DC cable trays and earthing. | 14 | 0 |  |  | 2025-07-22 10:30 | 2025-12-10 10:01 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 2400 hours |  | 0 |  | 100% |  | Malvern Engineering |  |  | Green
Task | 86c3c9ua1 | Upper East Side Hotel | OPERATIONAL SITES |  | Gerhard |  | @Gerhard attached is the SLD from site with comments needed for the GIS Upper Easst Side - GIS SLD.pdf | 15 | 0 |  |  | 2025-05-05 11:17 | 2026-02-17 14:04 |  |  | Gerhard | Emergent Energy | Engineering | Engineering | 86c6dfvrw 86c6p8pdg | https://app.clickup.com/t/86c6dfvrw https://app.clickup.com/t/86c6p8pdg |  | Engineering | [7 empty] | 2352 hours |  | 0 |  | 71.43% |  | Upper East Side Hotel |  |  | Green
Task | 86c5hqzbj | Dipula - Seshego Circle | OPERATIONAL SITES |  | johan snyman |  | @johan snyman , can you please upload the latest EP and PVSOL and remove the old versions | 17 | 0 |  |  | 2025-09-17 14:44 | 2025-12-15 10:12 |  |  | Gerhard | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 1851 hours |  | 0 |  | 100% |  | seshego cicle |  |  | Green
Task | 86c1kz25n | Superspar Despatch | OPERATIONAL SITES |  | johan snyman |  | SLD is correct according to info received from site visit | 23 | 0 |  |  | 2025-01-13 13:06 | 2026-02-13 10:16 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 1728 hours |  | 0 |  | 100% |  | Superspar Despatch PH 2 |  |  | Green
Task | 86c5dq063 | BMG Fluid Tech | OPERATIONAL SITES |  | johan snyman |  | @Dean Cornelius updated it now and attached the image | 8 | 0 |  |  | 2025-09-10 07:12 | 2026-02-13 08:16 |  |  | johan snyman | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 122 hours |  | 0 |  | 0% |  | BMG Fluid Tech |  | - [@johan snyman](#100552512) shared the SLD file and asked [@Dean Cornelius](#88707129) for feedback. - [@Dean Cornelius](#88707129) confirmed the design is good and asked about site constraints. - [@johan snyman](#100552512) confirmed constraints were considered and explained the tie breaker placement. - Task marked 100% complete and status is 'complete' as of 09/15/2025. | Green
Task | 86c4cq2bf | Tsakane Corner | OPERATIONAL SITES |  | johan snyman |  | Hi @Dean Cornelius uploaded the as build. I will load everything into the handover folders once completed. Let me know if I need to change anything. | 1 | 0 |  |  | 2025-07-08 19:45 | 2026-02-13 11:16 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 119 hours |  | 0 |  | 100% |  | Tsakane Corner |  |  | Green
PROVIDE FEEDBACK
Task Type | Task ID | Task Name | Status | Task Content | Assignee | Priority | Latest Comment | Comment Count | Assigned Comment Count | Due Date | Start Date | Date Created | Date Updated | Date Closed | Date Done | Created By | Space | Folder | List | Subtask ID's | Subtask URL's | tags | Lists | Sprints | Linked Tasks | Linked Docs | Time Logged | Time Logged Rolled Up | Time Estimate | Time Estimate Rolled Up | Time In Status | Points Estimate | Points Estimate Rolled Up | Approval Signature (signature) | Completion % (automatic progress) | STAGE (drop down) | Site (labels) | Site (short text) | Summary (text) | TRACKING (drop down) | Task Name (text)
Task | 86c7jq33x | Review PV Reports from Matriarch | PROVIDE FEEDBACK |  | Paul Dreyer |  |  | 0 | 0 | 2026-02-27 |  | 2026-01-14 12:05 | 2026-02-18 10:09 |  |  | Paul Dreyer | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 625 hours |  | 0 |  | 0% |  | Engineering Internal |  | - Review PV reports from Matriarch for Engineering Internal. - Due by 01/16/2026 02:00 AM (UTC). - Status is to do, 0% complete. - No users assigned yet. | Green
QC APPROVED
Task Type | Task ID | Task Name | Status | Task Content | Assignee | Priority | Latest Comment | Comment Count | Assigned Comment Count | Due Date | Start Date | Date Created | Date Updated | Date Closed | Date Done | Created By | Space | Folder | List | Subtask ID's | Subtask URL's | tags | Lists | Sprints | Linked Tasks | Linked Docs | Time Logged | Time Logged Rolled Up | Time Estimate | Time Estimate Rolled Up | Time In Status | Points Estimate | Points Estimate Rolled Up | Approval Signature (signature) | Completion % (automatic progress) | STAGE (drop down) | Site (labels) | Site (short text) | Summary (text) | TRACKING (drop down) | Task Name (text)
Task | 86c6ccnc9 | Inverter room requires cooling/ventilation | QC APPROVED | Portfolio: Dipula PV Phase 1 Site: Black Heath Range Road Category: Critical Discipline: Inverter room environment Snag/Issue: Inverter room requires cooling/ventilation Next Step: Room ventilation cooling assessment Date raised: 2025-10-29 Verified by: V3 Source ID: BLA-013 | Peet Verreynnne | URGENT | Black Heath Range Road_Heatload_calculations_APPROVED.pdf @Dean Cornelius please review and forward to Justin, I opted for the ventilation route. Note these calculations assume we remove 1 of the inverters from the room as per my previous comments on the changes required to match OEM specs | 5 | 0 | 2025-12-04 |  | 2025-10-29 | 2026-01-26 15:25 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 1799 hours |  | 0 |  | 0% | QA | BlackHeath | Black Heath Range Road |  | Green | BLA-013 – Black Heath Range Road – Inverter room environment – Inverter room requires cooling/ventilation
NEEDS APROVAL
Task Type | Task ID | Task Name | Status | Task Content | Assignee | Priority | Latest Comment | Comment Count | Assigned Comment Count | Due Date | Start Date | Date Created | Date Updated | Date Closed | Date Done | Created By | Space | Folder | List | Subtask ID's | Subtask URL's | tags | Lists | Sprints | Linked Tasks | Linked Docs | Time Logged | Time Logged Rolled Up | Time Estimate | Time Estimate Rolled Up | Time In Status | Points Estimate | Points Estimate Rolled Up | Approval Signature (signature) | Completion % (automatic progress) | STAGE (drop down) | Site (labels) | Site (short text) | Summary (text) | TRACKING (drop down) | Task Name (text)
Task | 86c52cck1 | Mondi Engineering tracker | NEEDS APROVAL |  | Johannes Potgieter |  | Updates as per discussion will be ready for internal review by Thursday and printed for the Friday workshop with JA electrical | 5 | 0 | 2026-01-30 |  | 2025-08-19 10:36 | 2026-02-06 10:14 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering | 86c7jja4x | https://app.clickup.com/t/86c7jja4x |  | Engineering | [7 empty] | 289 hours |  | 0 |  | 83.33% |  | Mondi |  |  | Green
HOLD
Task Type | Task ID | Task Name | Status | Task Content | Assignee | Priority | Latest Comment | Comment Count | Assigned Comment Count | Due Date | Start Date | Date Created | Date Updated | Date Closed | Date Done | Created By | Space | Folder | List | Subtask ID's | Subtask URL's | tags | Lists | Sprints | Linked Tasks | Linked Docs | Time Logged | Time Logged Rolled Up | Time Estimate | Time Estimate Rolled Up | Time In Status | Points Estimate | Points Estimate Rolled Up | Approval Signature (signature) | Completion % (automatic progress) | STAGE (drop down) | Site (labels) | Site (short text) | Summary (text) | TRACKING (drop down) | Task Name (text)
Task | 86c0p6bwe | Mega Park SCADA | HOLD |  | Dean Cornelius, Keith Abdulla, Roedolph |  | RTU installed. Awaiting De Cock & Cronje + Spear to install new relays. They are holding op the SSEG progress now. | 43 | 0 | 2026-02-27 | 2025-08-04 | 2024-10-16 08:03 | 2026-02-02 07:58 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering | 86c14rfxn | https://app.clickup.com/t/86c14rfxn |  | Engineering | [7 empty] | 2977 hours |  | 0 |  | 90% |  | Mega Park |  |  | Green
Task | 86c5kyx4z | Mondi Water flow and pressure calcs | HOLD | Use the site development plan to calculate where the best water flow points need to be to ensure that effective cleaning is happening. (show where we tie - in the layout of how water will flow with pressure, for each of the equipment that is going to be used) | Gerhard |  | @Johannes Potgieter please setup session to unblock | 5 | 0 | 2026-02-27 |  | 2025-09-22 14:36 | 2026-02-02 10:08 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 721 hours |  | 0 |  | 100% |  | Mondi |  |  | Green
Task | 86c7ngbzb | Case study to determine accurate irradiance model | HOLD | Request by Dayne: Evaluation of nearby sites currently operating to be compared to PVSol models on various weather models to determine most accurate model. We will start with Cape Town sites. | Paul Dreyer | LOW |  | 0 | 0 | 2026-02-27 |  | 2026-01-19 09:54 | 2026-02-18 10:03 |  |  | Paul Dreyer | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 49 hours |  | 0 |  | 0% |  | Engineering Internal |  | - [@Paul Dreyer](#106514301) will compare data from Cape Town sites to PVSol models using different weather models. - Goal is to find the most accurate irradiance model. - Work has not started yet (0% complete). - Status is 'to do'. | Green
Task | 86c6f8yy1 | M5 Freeway Park | HOLD |  | Brandon Watts |  | PVSol completed | 3 | 0 | 2026-03-31 |  | 2025-11-11 13:44 | 2026-01-19 10:15 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering | 86c6f924g 86c7fjp9k | https://app.clickup.com/t/86c6f924g https://app.clickup.com/t/86c7fjp9k |  | Engineering | [7 empty] | 720 hours |  | 0 |  | 60% |  | M5 Freeway Park |  | - Project is called M5 Freeway Park. - Status is to do, with 0% completed. - Due date is 11/21/2025 at 2:00 AM (UTC). - No updates or comments from users like [@Dean Cornelius](#88707129). | Green
Task | 86c73et86 | Pangea Cutting + Data Analysis Request | HOLD |  | Tanaka Zimuto |  |  | 0 | 0 |  |  | 2025-12-15 12:36 | 2026-01-29 10:18 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 792 hours |  | 0 |  | 0% |  | pangea |  | - Project is at 0% progress and has not started yet. - No comments or updates have been added. - Status is 'to do'. | Green
Task | 86c73et8z | Pangea Finishing + Data Analysis Request | HOLD |  | Tanaka Zimuto |  |  | 0 | 0 |  |  | 2025-12-15 12:36 | 2026-01-29 10:18 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 792 hours |  | 0 |  | 0% |  | pangea |  | - Project is at 0% progress and has not started yet. - Status is set to 'to do'. - No comments or updates from [@Johannes Potgieter](#62645671) or others. | Green
Task | 86c82g6w0 | 25 Superior Road | HOLD |  | johan snyman |  |  | 0 | 0 |  |  | 2026-02-06 08:45 | 2026-02-12 15:17 |  |  | johan snyman | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 139 hours |  | 0 |  | 0% |  | 25 Superior |  | - Project for 25 Superior Road is in progress. - Assigned to [@johan snyman](#100552512). - Due by 02/10/2026 02:00 AM (UTC). - Progress is at 0%.
IN PROGRESS
Task Type | Task ID | Task Name | Status | Task Content | Assignee | Priority | Latest Comment | Comment Count | Assigned Comment Count | Due Date | Start Date | Date Created | Date Updated | Date Closed | Date Done | Created By | Space | Folder | List | Subtask ID's | Subtask URL's | tags | Lists | Sprints | Linked Tasks | Linked Docs | Time Logged | Time Logged Rolled Up | Time Estimate | Time Estimate Rolled Up | Time In Status | Points Estimate | Points Estimate Rolled Up | Approval Signature (signature) | Completion % (automatic progress) | STAGE (drop down) | Site (labels) | Site (short text) | Summary (text) | TRACKING (drop down) | Task Name (text)
Task | 86c7nf5vb | Fairlands Spar Expansion + First Assessment - PowerPoint Template | IN PROGRESS |  | Mary Boakye |  |  | 0 | 0 | 2026-02-02 |  | 2026-01-19 08:39 | 2026-02-09 10:18 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 481 hours |  | 0 |  | 0% |  | Fairlands |  | - Project is at 0% progress and not started yet. - Status is 'to do'. - No updates, comments, or assigned users as of now. | Green
Task | 86c7vxrca | BMG Engineering - Phase 3 + Cost Proposal - Word Template | IN PROGRESS |  | Tanaka Zimuto |  |  | 0 | 0 | 2026-02-13 |  | 2026-01-28 07:40 | 2026-02-09 10:20 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 216 hours |  | 0 |  | 0% |  | BMG Phase 3 |  | - Project is at 0% completion and has not started yet. - No comments or updates from [@Johannes Potgieter](#62645671). - Status is 'to do'. - No subtasks or parent tasks. | Green
Task | 86c6j5vtp | PNP Bethal | IN PROGRESS |  | johan snyman |  | @Dean Cornelius please see EP uploaded. Apologies I see you are not on the group. I have to fix the scale so I can add dims. I'm also getting more info from the other eng so we can complete the SLD | 3 | 0 | 2026-02-16 |  | 2025-11-17 10:34 | 2026-02-13 15:42 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering | 86c7ngtc8 | https://app.clickup.com/t/86c7ngtc8 |  | Engineering | [7 empty] | 384 hours |  | 0 |  | 0% |  | PnP Bethal |  | - Site visit and report for PNP Bethal planned. - Progress is at 0%. - Status is 'to do'. - No updates or comments yet. | Green
Task | 86c5z0m0m | Mahikeng - Builders Express | IN PROGRESS |  | johan snyman |  | @Roedolph I've added the Bluelog. I see that they are busy with the meteocontrol design and there might be changes. I will amend the EP again once we receive everything from IBC | 6 | 0 | 2026-02-18 |  | 2025-10-13 14:34 | 2026-02-12 15:16 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering | 86c6yvm0w | https://app.clickup.com/t/86c6yvm0w |  | Engineering | [7 empty] | 1970 hours |  | 0 | Dean Cornelius | 88.89% |  | Mahikeng |  |  | Green
Task | 86c49ye1f | Red Rocket | IN PROGRESS |  | Gerhard, Paul Dreyer |  | @Gerhard please keep the due date udpated | 20 | 0 | 2026-02-18 |  | 2025-07-03 06:44 | 2026-02-18 10:05 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 553 hours |  | 0 |  | 100% |  | Red Rocket |  |  | Green
Project | 86c84nbp5 | Maynard Mall - Expansion + Sizing Rational Request | IN PROGRESS |  | Tanaka Zimuto |  |  | 0 | 0 | 2026-02-18 |  | 2026-02-10 09:41 | 2026-02-11 09:45 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 169 hours |  | 0 |  | 0% |  |  |  | - Project for Maynard Mall expansion and sizing rationale created. - No progress yet (0% complete). - No comments or updates from [@Johannes Potgieter](#62645671). - Status is to do.
Project | 86c88ax4q | Dennegeur Cost Proposal | IN PROGRESS |  | Paul Dreyer |  |  | 0 | 0 | 2026-02-18 |  | 2026-02-16 10:05 | 2026-02-18 09:20 |  |  | Paul Dreyer | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 49 hours |  | 0 |  | 0% |  | Dennegeur |  | - [@Paul Dreyer](#106514301) is assigned. - Project: Dennegeur. - Status: in progress, 0% complete. - No comments or subtasks yet. | Green
Task | 86c6xxubf | 6th Avenue Shopping Centre + Cost Proposal - Word Template | IN PROGRESS |  | Brandon Watts, Tanaka Zimuto |  | Waiting on client to confirm system size. | 1 | 0 | 2026-02-19 |  | 2025-12-05 12:36 | 2026-02-16 14:29 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 169 hours |  | 0 |  | 0% |  | 6th Avenue |  | - Project is at 0% progress and has not started yet. - Status is 'to do'. - No updates, comments, or subtasks added. - No users assigned. | Green
Task | 86c73fn2w | Fedgroup Site Design Reviews | IN PROGRESS |  | Brandon Watts, Tanaka Zimuto |  |  | 0 | 0 | 2026-02-20 |  | 2025-12-15 13:05 | 2026-02-17 14:24 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering | 86c73fr88 86c73ft9j 86c73ftp0 | https://app.clickup.com/t/86c73fr88 https://app.clickup.com/t/86c73ft9j https://app.clickup.com/t/86c73ftp0 |  | Engineering | [7 empty] | 673 hours |  | 0 |  | 0% |  | Fedgroup |  | - Fedgroup site design reviews planned, not started yet. - Progress is at 0%. - No comments or updates from [@Johannes Potgieter](#62645671). - Status is 'to do'. | Green
Task | 86c6ag7pb | Coega Steels 50 MW BESS + Data Analysis + CP | IN PROGRESS |  | Mary Boakye, Tanaka Zimuto, Paul Dreyer |  | We will need 2 runs per side of 3x 630 1core MV 22kV XLPE Cu cable which will come to 3600 meters | 2 | 0 | 2026-02-24 |  | 2025-11-03 12:32 | 2026-02-17 11:40 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 23 hours |  | 0 |  | 0% |  | Coega Steel |  |  | Green
Project | 86c88akh0 | WERDA Products Cost Proposal | IN PROGRESS |  | Paul Dreyer |  |  | 0 | 0 | 2026-02-25 |  | 2026-02-16 09:54 | 2026-02-16 10:05 |  |  | Paul Dreyer | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 49 hours |  | 0 |  | 0% |  | WERDA |  | - [@Paul Dreyer](#106514301) is working on a cost proposal for WERDA products. - Due date is 02/25/2026 at 02:00 AM UTC. - Status is in progress and completion is at 0%. - No comments or subtasks have been added yet. | Green
Task | 86c6h1p1a | Commissioning QC | IN PROGRESS |  | Dean Cornelius, Peet Verreynnne, Kashmil Samuel |  | Waterside place needs everything | 1 | 0 | 2026-03-09 |  | 2025-11-14 06:53 | 2026-02-17 08:06 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering | 86c6h1pay 86c6h1pgy 86c6h1prd 86c6h1pvp 86c6h1pye 86c6h1q1u 86c6h1q40 86c6j4j3a 86c6j4nbk 86c6j4nwq 86c6j4r00 86c7kd6yx 86c83qhky | https://app.clickup.com/t/86c6h1pay https://app.clickup.com/t/86c6h1pgy https://app.clickup.com/t/86c6h1prd https://app.clickup.com/t/86c6h1pvp https://app.clickup.com/t/86c6h1pye https://app.clickup.com/t/86c6h1q1u https://app.clickup.com/t/86c6h1q40 https://app.clickup.com/t/86c6j4j3a https://app.clickup.com/t/86c6j4nbk https://app.clickup.com/t/86c6j4nwq https://app.clickup.com/t/86c6j4r00 https://app.clickup.com/t/86c7kd6yx https://app.clickup.com/t/86c83qhky |  | Engineering | [7 empty] | 2308 hours |  | 0 |  | 61.76% |  | Dipula and Red Rocket |  | - [@Kashmil Samuel](#88702296) and [@Dean Cornelius](#88707129) are working on this. - Status is in progress, due by 11/18/2025 02:00 AM UTC. - Progress is at 0%. - Related parties: Dipula and Red Rocket. | Green
Task | 86c7gptuv | Swellengrebel - Project Engineering | IN PROGRESS |  | Brandon Watts, johan snyman |  | @Roedolph do we have modules for this site yet? | 2 | 0 | 2026-03-30 |  | 2026-01-12 09:39 | 2026-02-18 10:07 |  |  | Gerhard | Emergent Energy | Engineering | Engineering | 86c7jkj33 86c7jknqv 86c7jkpnc | https://app.clickup.com/t/86c7jkj33 https://app.clickup.com/t/86c7jknqv https://app.clickup.com/t/86c7jkpnc |  | Engineering | [7 empty] | 889 hours |  | 0 |  | 50% |  | Swellengrebel |  | - [@Gerhard](#88690613) is working on project engineering for Swellengrebel. - Status is in progress, but progress is still at 0%. - Due date is January 23, 2026. - No comments or subtasks added yet. | Green
Task | 86c6e8hk0 | De Drift | IN PROGRESS |  | Gerhard |  | De Drift - COMMS DB rev.1_APPROVED.pdf De Drift - SOLAR PV SUB DB 1 rev.1_APPROVED.pdf | 8 | 0 | 2026-06-09 |  | 2025-11-10 09:07 | 2026-01-23 07:16 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering | 86c6xvnmb | https://app.clickup.com/t/86c6xvnmb |  | Engineering | [7 empty] | 888 hours |  | 0 |  | 83.33% |  | De Drift |  |  | Green
Task | 86c7ww90v | Busamed Harrismith | IN PROGRESS |  | johan snyman | HIGH |  | 0 | 0 |  |  | 2026-01-29 08:39 | 2026-02-12 15:16 |  |  | johan snyman | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 482 hours |  | 0 |  | 0% |  | Busamed - Harrismith |  | - Project for Busamed - Harrismith is in progress. - Assigned to [@johan snyman](#100552512). - Due by 02/06/2026 02:00 AM UTC. - Progress is at 0%.
Task | 86c877mg6 | PnP Betahl - GA | IN PROGRESS |  | Brandon Watts |  |  | 0 | 0 |  |  | 2026-02-13 10:10 | 2026-02-16 10:07 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 49 hours |  | 0 |  | 0% |  | PnP Bethal |  | - [@Brandon Watts](#88690611) is assigned. - Site: PnP Bethal. - Progress is at 0%. - Status is to do.
Task | 86c10n9p6 | Trident Steel PE | IN PROGRESS |  | Gerhard, Roedolph | URGENT | Hi @Dean Cornelius , Trident steel AC coms updated based on your input and @Tanaka Zimuto review. please open it in the clinet folder and plot and publish when you are satisfied with it and rede to pass on to the PM | 17 | 0 |  |  | 2024-11-14 08:35 | 2026-02-18 10:12 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering | 86c8a0q7k | https://app.clickup.com/t/86c8a0q7k |  | Engineering |  | Engineering Sign Off: https://app.clickup.com/t/86c22jqc9) | [5 empty] | 2 hours |  | 0 |  | 0% |  | Trident Steel PE |  |  | Green
Project | 86c86hf87 | GQ Fresh Produce + Cost Proposal - Word Template | IN PROGRESS |  | Mary Boakye |  |  | 0 | 0 |  |  | 2026-02-12 10:42 | 2026-02-18 10:04 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 1 hours |  | 0 |  | 0% |  |  |  | - Project is in 'to do' status, not started yet. - Progress is at 0%. - No comments or subtasks added so far.
TO DO
Task Type | Task ID | Task Name | Status | Task Content | Assignee | Priority | Latest Comment | Comment Count | Assigned Comment Count | Due Date | Start Date | Date Created | Date Updated | Date Closed | Date Done | Created By | Space | Folder | List | Subtask ID's | Subtask URL's | tags | Lists | Sprints | Linked Tasks | Linked Docs | Time Logged | Time Logged Rolled Up | Time Estimate | Time Estimate Rolled Up | Time In Status | Points Estimate | Points Estimate Rolled Up | Approval Signature (signature) | Completion % (automatic progress) | STAGE (drop down) | Site (labels) | Site (short text) | Summary (text) | TRACKING (drop down) | Task Name (text)
Task | 86c7xpvxt | Steelcorp - 54 Moore Street + Meter installation | TO DO |  | Kashmil Samuel |  | I have done both site visits as well will upload report later today | 3 | 0 | 2026-02-06 |  | 2026-01-30 08:40 | 2026-02-09 10:58 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 458 hours |  | 0 |  | 0% |  |  |  | - Project is at 0% progress. - Status is 'to do', no work started yet. - No comments or updates from [@Johannes Potgieter](#62645671).
Task | 86c82m639 | Sir Fruit - Water FA + First Assessment - PowerPoint Template | TO DO |  | Tanaka Zimuto |  |  | 0 | 0 | 2026-02-13 |  | 2026-02-06 11:41 | 2026-02-09 10:03 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 287 hours |  | 0 |  | 0% |  | Sir Fruit |  | - Project is at 0% completion and has just been created. - No updates, comments, or activity from [@Johannes Potgieter](#62645671) yet. - Status is 'to do'. - No subtasks or parent tasks linked. | Green
Task | 86c8146mr | Malmesbury Solar Farm (Apollo/PowerX) + FA - Helioscope | TO DO |  | Paul Dreyer |  |  | 0 | 0 | 2026-02-18 | 2026-02-13 | 2026-02-04 13:41 | 2026-02-09 10:58 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 333 hours |  | 0 |  | 0% |  | Malmesbury Solar Farm |  | - Project is at 0% completion. - No updates or comments yet. - Status is 'to do'. | Green
Project | 86c86mvwt | Corporate Park Metering Clarification | TO DO |  | Johannes Potgieter |  |  | 0 | 0 | 2026-02-20 |  | 2026-02-12 12:24 | 2026-02-12 12:24 |  |  | Roedolph | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 142 hours |  | 0 |  | 0% |  | Corporate Park |  | - Assigned to [@Johannes Potgieter](#62645671). - Location: Corporate Park. - Status: to do. Progress: 0%. - Priority: Green. Due by 02/20/2026 02:00 AM (UTC). | Green
Task | 86c6ywu5t | Shoprite Mini Riversdale + Site visit Report | TO DO |  | Paul Dreyer |  | Site inspection delivery date pushed out to after CP approval. Considerations were made for assumptions based on Oswald's inspections. | 2 | 0 | 2026-02-23 |  | 2025-12-08 09:36 | 2026-02-18 10:18 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 673 hours |  | 0 |  | 0% |  | Shoprite Mini Riversdal |  | - Project is at 0% progress and has not started yet. - Status is set to 'to do'. - No updates, comments, or subtasks added so far. | Green
Task | 86c7ng11v | Constantia Glen - Restaurant + Site visit Report | TO DO |  | Roedolph, Paul Dreyer |  |  | 0 | 0 | 2026-02-27 |  | 2026-01-19 09:39 | 2026-02-18 10:17 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 627 hours |  | 0 |  | 0% |  | Constantia Glen |  | - Project is at 0% progress and has not started yet. - Status is 'to do'. - No comments or updates from [@Johannes Potgieter](#62645671). | Green
Task | 86c6p8v5j | Site Inspection form update | TO DO |  | Gerhard |  | Update the form to be more general and friendly top project devs. Lean out the inspection by using standards as references not questions. leave a section for a basic hand drawn SLD to be used as reference. Leave a section for a SDP to be included | 1 | 0 |  |  | 2025-11-24 11:20 | 2026-01-19 10:08 |  |  | Gerhard | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 2063 hours |  | 0 |  | 0% |  | Emergent |  | - Assigned to [@Gerhard](#88690613). - Due by 12/31/2025. - Status: to do. Priority: Green. Urgency: Emergent. - Progress: 0% complete. | Green
Task | 86c6597pp | Universal cooling requirement calculator | TO DO |  | Gerhard |  | Create a multi level cooling calc that can be used by business devs, PMs and Engineers which will all yield a reliable outcome. Rely on libraries and dropdowns for easy selection. Include diagrams to assist people to solve the problem. | 1 | 0 |  |  | 2025-10-24 11:12 | 2026-01-19 10:08 |  |  | Dean Cornelius | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 2808 hours |  | 0 |  | 0% |  | Emergent |  |  | Green
Task | 86c86qc74 | McClelland Adult Centre + First Assessment - PowerPoint Template | TO DO |  | Tanaka Zimuto |  |  | 0 | 0 |  |  | 2026-02-12 13:42 | 2026-02-13 10:05 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 141 hours |  | 0 |  | 0% |  |  |  | - Project for McClelland Adult Centre + First Assessment PowerPoint template. - Status is 'to do', progress is 0%. - No comments, subtasks, or user assignments yet.
Task | 86c86qc7y | 25 Superior - PV Sol + CP - PVSOL | TO DO |  | Tanaka Zimuto |  |  | 0 | 0 |  |  | 2026-02-12 13:42 | 2026-02-13 10:05 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 141 hours |  | 0 |  | 0% |  |  |  | - Project is at 0% completion. - Status is to do, no work started yet. - No comments or updates from [@Johannes Potgieter](#62645671).
Task | 86c875k1z | 369 Umgeni Road + First Assessment - PowerPoint Template | TO DO |  | Tanaka Zimuto |  |  | 0 | 0 |  |  | 2026-02-13 05:42 | 2026-02-13 10:05 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 125 hours |  | 0 |  | 0% |  |  |  | - Project is at 0% completion. - No updates, comments, or subtasks yet. - Status is 'to do'.
Task | 86c875qcb | Altix Medical Centre + First Assessment - PowerPoint Template | TO DO |  | Tanaka Zimuto |  |  | 0 | 0 |  |  | 2026-02-13 06:42 | 2026-02-13 10:05 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 124 hours |  | 0 |  | 0% |  |  |  | - Project for PowerPoint template for Altix Medical Centre and First Assessment. - No work started yet, progress is at 0%. - No comments or updates from [@Johannes Potgieter](#62645671). - Status is 'to do'.
Task | 86c87670j | Dennegeur Phase 3 + Cost Proposal - Word Template | TO DO |  | Tanaka Zimuto |  |  | 0 | 0 |  |  | 2026-02-13 08:42 | 2026-02-13 10:05 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 122 hours |  | 0 |  | 0% |  |  |  | - Project is at 0% completion and has not started yet. - Status is 'to do', no progress or updates so far. - No comments or subtasks have been added. - No users assigned or mentioned yet.
Project | 86c889d8c | Mayo Macs Paddock Site Visit + Site visit Report | TO DO |  | Tanaka Zimuto |  |  | 0 | 0 |  |  | 2026-02-16 08:42 | 2026-02-16 09:48 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 50 hours |  | 0 |  | 0% |  |  |  | - Site visit and report for Mayo Macs Paddock not started yet (0% complete). - No updates or comments from [@Johannes Potgieter](#62645671). - Status is 'to do'.
Project | 86c889d8x | Lulamanzi Berries + Cost Proposal - Word Template | TO DO |  | Tanaka Zimuto |  |  | 0 | 0 |  |  | 2026-02-16 08:42 | 2026-02-16 09:48 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 50 hours |  | 0 |  | 0% |  |  |  | - Project for Lulamanzi Berries Word template and cost proposal. - Progress is at 0%. - Status is to do. - No users assigned or updates from [@Johannes Potgieter](#62645671).
Project | 86c88g521 | Superspar Levyvale + First Assessment - PowerPoint Template | TO DO |  |  |  |  | 0 | 0 |  |  | 2026-02-16 12:42 | 2026-02-16 12:42 |  |  | Johannes Potgieter | Emergent Energy | Engineering | Engineering |  |  |  | Engineering | [7 empty] | 46 hours |  | 0 |  | 0% |  |  |  | - Project for Superspar Levyvale PowerPoint template and first assessment. - Status is to do, 0% complete as of now. - No comments or subtasks added yet. - Created on 02/16/2026.