## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate | [5 empty] | FINANCIAL CLOSE CERTIFICATE
Project Name: | Hungry Lion Citrusdal
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion: |  |  |  | 1. Financial Close | 1. Financial Close
Phase Deliverables Checklist: (Y/N)
Product Agreement
EPC Agreement
O&M Agreeement
Cost Proposal
Deposit Received
Risks / Notes
Acknowledgement and Acceptance:
Role | Name | Signature | Date

## Certificate - Planning
Emergent Energy – Planning Phase Completion Certificate |  |  |  | PLANNING CERTIFICATE
Project Name: | Hungry Lion Citrusdal
Client Representative:
Programme Manager: | Roedolph Venter
Project Manager: | Peet Verreynne
Project Engineer:
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Project Introduction Presentation
Project Brief
Engineering Pack
BOQ
PO – Material & Equipment
PO - Contractors
HSE – NOC
HSE – EE File
HSE – Contractor File
SSEG Application
Risks / Notes
Acknowledgement and Acceptance:
Role | Name | Signature | Date

## Change Register
Change Register
ID | Description | Supporting Image (If Applicable) | Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## BOQ
Item | Supplier | Description | Quantity | Comments
PV Module | Krannich | Longi 610W (LR8-66HGD -595-625M) | 213
Mounting Structure | Schletter
DC Cable Red & Black | Menlo | 6sqmm DC Cable | 4000
Inverters | Menlo | Huawei 100KTL | 1
Current Transformers (Production)
Current Transformers (Consumption)
Solar Production Meter | Techsitter | Techsitter meter | 1
Solar Consumption Meter
Wi-Fi Router & Sim
Switch | Accuenergy | Teltonika TSW200 | 1
Back Up Battery
PVDB
Supplier List
Accuenergy
Krannich
Menlo
Red Pole
Schletter
Switchboard
Techsitter

## Project Plan
[9 empty] | 2026-02-11 | 2026-02-11
| PROJECT PLAN | Hungry Lion Citrusdal |  |  | Net Work Days |  | 19 |  | 0 | 1
| PROJECT SIZE (kWp) | 130 |  |  | Total Weeks |  | 3.8
| PROJECT DEVELOPER | Peet Verreynne |  |  | kW/Week Installation Rate |  | 34.2105
| PROJECT MANAGERS | Peet Verreynne
| CONTRACT VALUE | 1312612.9423
| Phase: | Compliance Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration | Planned End | Actual Start | Duration | Actual End | Status | Expected Status | Comment
|  |  | 35 |  |  | 19 |  | 100% | 100% |  | 2026-02-11 | 2026-02-11
[11 empty] | 1 | 0
1 | Project Initiation | 2025-10-01 | 29 | 2025-10-30 | 2025-10-01 | 37 | 2025-11-07 | 100% | 100%
1.1 | Project Charter Handover | 2025-10-01 | 1 | 2025-10-02 | 2025-10-01 | 1 | 2025-10-02 | 100% | 100% | EPC signed 9 Oct | Milestone | Start Date | Duration | End Date
1.2 | HSE Readiness and Signoff | 2025-10-02 | 20 | 2025-10-30 | 2025-10-02 | 20 | 2025-10-30 | 100% | 100% |  | Project Initiation | 2025-10-01 | 37 | 2025-11-07
1.3 | Project Introduction | 2025-10-23 | 1 | 2025-10-24 | 2025-10-30 | 1 | 2025-10-31 | 100% | 100% |  | Site Establishment | 2025-11-06 | 1 | 2025-11-07
1.4 | Installer Kick Off | 2025-10-24 | 1 | 2025-10-27 | 2025-11-06 | 1 | 2025-11-07 | 100% | 100% |  | AC Installation | 2025-09-24 | 58 | 2025-11-21
1.5 | Project Review | 2025-10-24 | 1 | 2025-10-27 | 2025-10-22 | 1 | 2025-10-23 | 100% | 100% |  | DC Works | 2025-11-10 | 9 | 2025-11-19
[11 empty] | Module installation | 2025-11-06 | 12 | 2025-11-18
2 | Site Establishment | 2025-11-06 | 1 | 2025-11-07 | 2025-11-06 | 1 | 2025-11-07 | 100% | 100% |  | Commissioning | 2025-11-21 | 11 | 2025-12-02
2.1 | Solar Contractor Establishment | 2025-11-06 | 1 | 2025-11-07 | 2025-11-06 | 1 | 2025-11-07 | 100% | 100% | tbc | QA Inspections | 2025-11-25 | 8 | 2025-12-03
[11 empty] | Project Closure | 2025-11-28 | 19 | 2025-12-17
3 | AC Installation | 2025-09-24 | 49 | 2025-11-12 | 2025-09-24 | 58 | 2025-11-21 | 100% | 100%
3.1 | Inverters delivered | 2025-11-07 | 1 | 2025-11-10 | 2025-11-10 | 1 | 2025-11-11 | 100% | 100%
3.2 | Inverters Mounted | 2025-11-10 | 2 | 2025-11-12 | 2025-11-11 | 2 | 2025-11-13 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-09-24 | 30 | 2025-11-05 | 2025-09-24 | 33 | 2025-11-10 | 100% | 100% | added 3 days
3.4 | AC Works | 2025-11-05 | 5 | 2025-11-12 | 2025-11-15 | 5 | 2025-11-21 | 100% | 100%
3.5 | AC Tie-In | 2025-11-05 | 1 | 2025-11-06 | 2025-11-20 | 1 | 2025-11-21 | 100% | 100%
4 | DC Works | 2025-11-06 | 27 | 2025-12-03 | 2025-11-10 | 9 | 2025-11-19 | 100% | 100%
4.1 | Mounting Structure delivered | 2025-11-06 | 1 | 2025-11-07 | 2025-11-10 | 1 | 2025-11-11 | 100% | 100%
4.2 | Mounting Structure installation | 2025-11-07 | 2 | 2025-11-11 | 2025-11-11 | 2 | 2025-11-13 | 100% | 100%
4.3 | DC Cable delivered | 2025-11-06 | 1 | 2025-11-07 | 2025-11-10 | 1 | 2025-11-11 | 100% | 100%
4.4 | DC Stringing | 2025-11-21 | 8 | 2025-12-03 | 2025-11-15 | 3 | 2025-11-19 | 100% | 100%
5 | Module installation | 2025-11-06 | 18 | 2025-11-24 | 2025-11-06 | 12 | 2025-11-18 | 100% | 100%
5.1 | Module delivery | 2025-11-06 | 1 | 2025-11-07 | 2025-11-06 | 1 | 2025-11-07 | 100% | 100%
5.2 | Module mounting | 2025-11-11 | 9 | 2025-11-24 | 2025-11-13 | 3 | 2025-11-18 | 100% | 100%
6 | Commissioning | 2025-12-03 | 16 | 2025-12-19 | 2025-11-21 | 11 | 2025-12-02 | 100% | 100%
6.1 | Commissioning | 2025-12-03 | 1 | 2025-12-04 | 2025-11-21 | 1 | 2025-11-24 | 100% | 100%
6.2 | Practical Completion | 2025-12-04 | 5 | 2025-12-11 | 2025-11-24 | 1 | 2025-11-25 | 100% | 100%
6.3 | System Performance Monitoring | 2025-12-11 | 5 | 2025-12-19 | 2025-11-25 | 5 | 2025-12-02 | 100% | 100%
7 | QA Inspections | 2025-12-11 | 11 | 2025-12-22 | 2025-11-25 | 8 | 2025-12-03 | 100% | 100%
7.1 | Red-Team Inspection | 2025-12-11 | 3 | 2025-12-17 | 2025-11-25 | 3 | 2025-11-28 | 100% | 100%
7.2 | Snags completion | 2025-12-17 | 3 | 2025-12-22 | 2025-11-28 | 3 | 2025-12-03 | 100% | 100%
8 | Project Closure | 2026-01-19 | 11 | 2026-01-30 | 2025-11-28 | 19 | 2025-12-17 | 100% | 99.99%
8.1 | Handover documentation | 2026-01-19 | 3 | 2026-01-22 | 2025-11-28 | 7 | 2025-12-09 | 100% | 100%
8.2 | Handover to Client | 2026-01-29 | 1 | 2026-01-30 | 2025-12-09 | 1 | 2025-12-10 | 100% | 100%
8.3 | Handover to Matriarch | 2026-01-22 | 5 | 2026-01-29 | 2025-12-09 | 5 | 2025-12-17 | 100% | 100%
Formulas:
Planned Start = MIN([Planned Start, row below]:E17)
Planned Start = WORKDAY.INTL([Planned End, row above],0,1,Data!$C3:C60)
Planned End = MAX([Planned End, row below]:G17)
Planned End = WORKDAY.INTL([Planned Start],[Duration],1,Data!$C3:C60)
Actual Start = MIN([Actual Start, row below]:I17)
Actual Start = WORKDAY.INTL([Actual End, row above],0,1,Data!$C3:C60)
Actual End = MAX([Actual End, row below]:K17)
Actual End = WORKDAY.INTL([Actual Start],[Duration],1,Data!$C3:C60)
Expected Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  | FINANCIAL REVIEW | TIMELINE REVIEW |  |  | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 1312612.9423 |  | 1292329.358 |  | 1312612.9423 | Start Date |  |  | 0 | 0 | 1292329.3473 | 889884.7555 | 1312612.9316 | 889884.7555
2 | Planned Expenditure | 997503.4972 |  | 889884.7555 |  | 893355.1418 | 2025-11-06
3 | Planned Profit | 315109.4451 |  | 402444.6025 |  | 419257.8005 | End Date - PC
4 | Planned Margin | 24.01% |  | 31.14% |  | 31.94% | 2025-11-25
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Acceptance and Initial Deposit |  | 50% | 656306.4712 | 2025-09-30 | 004846 + CN004886 + 004887 | 2025-10-01 | 2025-11-10 | [7 empty] | 1900-01-06
2 | Delivery of Panels |  | 25% | 328153.2356 | 2025-11-13 | 004846 + CN004886 + 004887 | 2025-10-01 | 2025-11-14
3 | Delivery of Inverters |  | 10% | 131261.2942 | 2025-11-14 | 004846 + CN004886 + 004887 | 2025-10-01 | 2025-11-14
4 | Practical Completion |  | 10% | 131261.2942 | 2025-12-26 | 004846 + CN004886 + 004887 | 2025-10-01 | 2025-12-11
5 | Handover |  | 5% | 65630.6471 | 2026-07-29 | 004846 + CN004886 + 004887 | 2025-10-01 | 2025-12-11
6 | Reduced system size capex |  | 0% | -20283.5843 |  | CN004886 + 004887 | 2025-12-02 | 2025-12-11
7 | - |  | 0% | 0
|  |  | 100% | 1292329.358
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 452315.2753
2 | Delivery of Panels |  | 30% | 387698.8074
3 | Delivery of Inverters |  | 20% | 258465.8716
4 | Practical Completion |  | 10% | 129232.9358
5 | Handover |  | 5% | 64616.4679
| Total |  | 100% | 1292329.358
|  |  | 100% | 1292329.358
Note on R14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Thami Cambalele please invoice these for us

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 997503.4972 |  | 889884.7555 | 107618.7417
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 329608.245 |  | 237358.05 | 92250.195
2 | 2. Inverters | 70000 |  | 65246 | 4754
3 | 3. Mounting Structures | 52216 |  | 33946 | 18270
4 | 4. DC Equipment | 112097.4 |  | 83728.55 | 28368.85
5 | 5. Monitoring | 49000 |  | 58278 | -9278
6 | 6. AC Equipment | 153726.8609 |  | 94526.15 | 59200.7109
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 40000 |  | 24900 | 15100
9 | 9. AC & DC installation | 103790 |  | 185936.1555 | -82146.1555
10 | 10. Site Logistics | 36017.0667 |  | 68573.54 | -32556.4733
11 | 11. Due Dilligence | 29000 |  | 15565 | 13435
12 | 12. BDP Commission | 8079.73 |  | 0 | 8079.73
13 | 13. Engineering | 11693.1947 |  | 16154.12 | -4460.9253
14 | 14. General Expenses | 2275 |  | 2023.19 | 251.81
15 | 15. Service Add On | 0 |  | 3650 | -3650
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 997503.4972 | 1312612.9423 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 889884.7555
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FORECASTED PAYMENT DATE | Total COS | ERROR on REV |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 329608.245 | 2025-12-31 | 329608.245 | 457789.2292 |  | 1 | 1. Panels | Longi 610W - Krannich | 213 | 1128.5 | 240370.5 |  | Krannich 15-10014209 | 2025-10-31 | 447965.6003 | 20283.5843 | 2025-12-18 | 237358.05
1 |  | Delivery Budget |  | 20283.5843 | [5 empty] | 1 | 1. Panels |  |  |  | 0 |  |  |  | 0
1 | [9 empty] | 1 | 1. Panels | EPR Fees |  |  | 5093.43 |  | Krannich 15-10014209 | 2025-10-31 | 9823.6289 |  | 2025-12-18
1 | [9 empty] | 1 | 1. Panels | Longi 610 to stock - reduction in scope | -12 | 1128.5 | -13542 |  | Allocated to Cpt Storeroom | 2025-11-30 |  |  | 2025-11-30
1 | [9 empty] | 1 | 1. Panels | Delivery Fee |  |  | 5436.12 |  | Krannich 17-01001217 | 2025-11-30 | 0 |  | 2025-12-18
[10 empty] | 1 | 1. Panels | [6 empty] | 2025-12-31 | -20283.5843
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 153726.8609
2 | Inverters | Inverter Budget |  |  | 70000 | 2025-12-31 | 70000 | 97222.2222 |  | 2 | 2. Inverters | Huawei 100KTL | 1 | 65246 | 65246 |  | Krannich 15-10014209 | 2025-10-31 | 97222.2222 | 0 | 2025-12-18 | 65246 | DC Equipment | 77125.4
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | AC Labour | 32635
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 71155
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 11917.0667
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 0
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 52216 | 2025-12-30 | 52216 | 72522.2222 |  | 3 | 3. Mounting Structures | Schletter Structure |  |  | 27460 |  | Schletter INV2383 | 2025-11-30 | 58665.5341 | 0 | 2025-12-30 | 33946 | Other | 0
3 | [9 empty] | 3 | 3. Mounting Structures | Additional Structures |  |  | 6486 |  | Schletter INV2383 | 2025-11-30 | 13856.6881 |  | 2025-12-30 |  | Total | 355059.3275
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Less 15% | 301800.4284
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | R/Wp | 2.3215
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Jasolar |  |  | Cosmic Sun
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL | Installer Price |  | ACTUAL | Installer Price
[23 empty] | AC Equipment | 34122.6 |  | AC Equipment | 47500
4 | DC Equipment | DC Cable Budget | 2872.7 |  | 34972 | 2025-12-30 | 112097.4 | 155690.8333 |  | 4 | 4. DC Equipment | DC Cable - stock CPT | 2000 | 13.5 | 27000 |  | Allocated from Cpt Storeroom | 2025-10-31 | 50199.6988 | 0.0046814 | 2025-10-31 | 83728.55 | DC Equipment | 29738.6 |  | DC Equipment | 45540.55
4 |  | DC Equipment Budget |  |  | 77125.4 | 2025-11-30 |  |  |  | 4 | 4. DC Equipment | DC Cable - Stock CPT Red | 2000 | 13.5 | 27000 |  | Allocated from Cpt Storeroom | 2025-10-31 | 50199.6988 |  | 2025-10-31 |  | AC Labour | 32056.56 | 0.24659 | AC Labour | 51900 | 0.39923
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | DC Labour | 153929.65 | 1.1841 | DC Labour | 103600 | 0.79692
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Offloading | 11410 |  | Offloading | 0
4 | [9 empty] | 4 | 4. DC Equipment | Project Kick Off | 29738.6 | 10% | 2973.86 | PO4379-HLCD-20251017 - RV Approved | JA Electrical Inv 1108 | 2025-10-31 | 5529.1436 |  | 2025-11-06 |  | Geda/scaffholding | 18843 |  | Forklift | 0
4 | [9 empty] | 4 | 4. DC Equipment | Site Establishment |  | 15% | 4460.79 |  | JA Electrical Inv 1118 | 2025-11-30 | 8307.4209 |  | 2025-12-04 |  | Storage | 17679 |  | Geda | 0
4 | [9 empty] | 4 | 4. DC Equipment | AC Installation Complete |  | 10% | 2973.86 |  | JA Electrical Inv 1125 | 2025-11-30 | 5529.8072 |  | 2025-12-04 |  | P&G's | 7173.5 |  | Logistics | 0
[10 empty] | 4 | 4. DC Equipment | AC Installation Complete |  | 10% | 2973.82 |  | JA Electrical Inv 1141 | 2025-12-31 | 5529.7329 |  | 2025-12-18
4 | [9 empty] | 4 | 4. DC Equipment | DC Installation Complete |  | 20% | 5947.72 |  | JA Electrical Inv 1125 | 2025-11-30 | 11059.6145 |  | 2025-12-18 |  | HSE | 0 |  | HSE | 4500
[10 empty] | 4 | 4. DC Equipment | DC Installation Complete |  | 5% | 1486.93 |  | JA Electrical Inv 1130 | 2025-11-30 | 2764.9036 |  | 2026-01-09
4 | [9 empty] | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 2973.86 |  | JA Electrical Inv 1137 | 2025-11-30 | 5529.8072 |  | 2026-01-29 |  | Shuffle Boards | 11935 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 2973.86 |  | JA Electrical Inv 1138 | 2025-11-30 | 5529.8072 |  | 2026-02-05 |  | Other | 0 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 1486.93 |  | JA Electrical Inv 1139 | 2025-11-30 | 2764.9036 |  | 2026-02-05 |  | Total | 316887.91 |  | Total | 253040.55
4 | [9 empty] | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 1476.92 |  | JA Electrical Inv 1140 | 2025-11-30 | 2746.2903 |  | 2026-03-07 |  | R/Wp | 2.4376 |  | R/Wp | 1.9465
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 34000 | 2025-12-30 | 49000 | 68055.5556 |  | 5 | 5. Monitoring | Smartlogger |  |  | 8598.34 |  | Menlo INV0003384 | 2025-11-30 | 10016.0031 | -0.00028811 | 2026-01-09 | 58278
[10 empty] | 5 | 5. Monitoring | Transport |  |  | 100 |  | Menlo INV0003384 | 2025-11-30 | 119.4418 |  | 2026-01-09
5 |  | Revenue Metering |  |  | 15000 | 2025-12-30 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 24561 | PO4370-HLCD-20251015 - RV Approved | AccuEnergy ASAI-006654 | 2025-10-31 | 29559.1702 |  | 2025-11-30
5 | [9 empty] | 5 | 5. Monitoring | Techsitter |  |  | 22338 |  | Matriarch Inv: 5366 | 2025-10-31 | 26710.131 |  | 2025-11-30
[10 empty] | 5 | 5. Monitoring | Delivery of Techsitter |  |  | 343.33 |  | DSV Inv:180153158 | 2025-10-31 | 410.5287 |  | 2025-11-30
5 | [9 empty] | 5 | 5. Monitoring | Battery |  |  | 975 |  | Red Pole - SO-35912 | 2025-10-31 | 1165.833 |  | 2025-11-07
5 | [9 empty] | 5 | 5. Monitoring | Delivery of Comms Equip |  |  | 21.33 |  | Uber | 2025-11-30 | 25.4769 |  | 2025-11-12
5 | [9 empty] | 5 | 5. Monitoring |  |  |  | 41 |  | Uber | 2025-11-30 | 48.9711 |  | 2025-11-29
[10 empty] | 5 | 5. Monitoring | Power Supply |  |  | 1300 |  | Allocated from Cpt Storeroom | 2025-12-31 |  |  | 2025-12-31
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 153726.8609 | 2025-11-30 | 153726.8609 | 213509.529 |  | 6 | 6. AC Equipment | [7 empty] | 0 | 0.0016307 |  | 94526.15
6 | [9 empty] | 6 | 6. AC Equipment | PVDB |  |  | 60403.57 | PO4327-HLCD-20250925 - MI Approved | Switchboard 2-SOI002609 | 2025-11-30 | 136435.6612 |  | 2025-12-30
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | Project Kick Off | 34122.6 | 10% | 3412.26 | PO4379-HLCD-20251017 - RV Approved | JA Electrical Inv 1108 | 2025-10-31 | 7707.3897 |  | 2025-11-06
6 | [9 empty] | 6 | 6. AC Equipment | Site Establishment |  | 15% | 5118.39 |  | JA Electrical Inv 1118 | 2025-11-30 | 11561.0869 |  | 2025-12-04
6 | [9 empty] | 6 | 6. AC Equipment | AC Installation Complete |  | 10% | 3412.26 |  | JA Electrical Inv 1125 | 2025-11-30 | 7707.3913 |  | 2025-12-04
[10 empty] | 6 | 6. AC Equipment | AC Installation Complete |  | 10% | 3412.24 |  | JA Electrical Inv 1141 | 2025-12-31 | 7707.3461 |  | 2025-12-18
6 | [9 empty] | 6 | 6. AC Equipment | DC Installation Complete |  | 20% | 6824.52 |  | JA Electrical Inv 1125 | 2025-11-30 | 15414.7826 |  | 2025-12-18
[10 empty] | 6 | 6. AC Equipment | DC Installation Complete |  | 5% | 1706.13 |  | JA Electrical Inv 1130 | 2025-11-30 | 3853.6956 |  | 2026-01-09
6 | [9 empty] | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 3412.26 |  | JA Electrical Inv 1137 | 2025-11-30 | 7707.3913 |  | 2026-01-29
6 | [9 empty] | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 3412.26 |  | JA Electrical Inv 1138 | 2025-11-30 | 7707.3913 |  | 2026-02-05
6 | [9 empty] | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 1706.13 |  | JA Electrical Inv 1139 | 2025-11-30 | 3853.6956 |  | 2026-02-05
6 | [9 empty] | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 1706.13 |  | JA Electrical Inv 1140 | 2025-11-30 | 3853.6956 |  | 2026-03-07
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 40000 | 44444.4444 |  | 8 | 8. Product Add On | [8 empty] | 0 |  | 24900
8 |  | Inverter Cge |  |  | 40000 | 2025-10-31 |  |  |  | 8 | 8. Product Add On | Inverter Cage | 16450 | 70% | 11515 | PO4359-HLCD-20251007 - RV Approved | Barrier Projects : 507 | 2025-10-31 | 31111.1111 |  | 2025-10-24
8 | [9 empty] | 8 | 8. Product Add On |  |  | 30% | 4935 |  | Barrier Projects : 507 | 2025-10-31 | 13333.3333 |  | 2025-12-04
8 | [9 empty] | 8 | 8. Product Add On |  |  |  | -16450 |  | Barrier Projects Credit : 507 | 2025-11-30 | 0 |  | 2025-12-04
8 | [9 empty] | 8 | 8. Product Add On |  |  |  | 24900 |  | Barrier Projects : 507 | 2025-11-30 | 0 |  | 2025-12-04
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 32635 | 2025-10-31 | 103790 | 115322.2222 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0.0032016 |  | 185936.1555
9 |  | DC Installation Budget |  |  | 71155 | 2025-11-30 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 185986.21 | 10% | 18598.621 | PO4379-HLCD-20251017 - RV Approved | JA Electrical Inv 1108 | 2025-10-31 | 11532.2222 |  | 2025-11-06
9 | [9 empty] | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 27897.9315 |  | JA Electrical Inv 1118 | 2025-11-30 | 17306.0881 |  | 2025-12-04
9 | [9 empty] | 9 | 9. AC & DC installation | AC Installation Complete |  | 10% | 18598.6 |  | JA Electrical Inv 1125 | 2025-11-30 | 11535.3124 |  | 2025-12-04
[10 empty] | 9 | 9. AC & DC installation | AC Installation Complete |  | 10% | 18598.6 |  | JA Electrical Inv 1141 | 2025-12-31 | 11535.3254 |  | 2025-12-18
9 | [9 empty] | 9 | 9. AC & DC installation | DC Installation Complete |  | 20% | 37197.242 |  | JA Electrical Inv 1125 | 2025-11-30 | 23070.6508 |  | 2025-12-18
[10 empty] | 9 | 9. AC & DC installation | DC Installation Complete |  | 5% | 9299.3105 |  | JA Electrical Inv 1130 | 2025-11-30 | 5767.6627 |  | 2026-01-09
9 | [9 empty] | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 18578.62 |  | JA Electrical Inv 1137 | 2025-11-30 | 11522.9203 |  | 2026-01-29
9 | [9 empty] | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 18578.62 |  | JA Electrical Inv 1138 | 2025-11-30 | 11522.9203 |  | 2026-02-05
9 | [9 empty] | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 9289.3 |  | JA Electrical Inv 1139 | 2025-11-30 | 5761.454 |  | 2026-02-05
9 | [9 empty] | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 9299.3105 |  | JA Electrical Inv 1140 | 2025-11-30 | 5767.6627 |  | 2026-03-07
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-11-30 | 36017.0667 | 40018.963 |  | 10 | 10. Site Logistics | Security |  |  | 1533.06 | PO4486-HLCD-20251124 - RV Approved | HP Security Inv 3951 | 2025-11-30 | 894.6814 | 0 | 2025-11-28 | 68573.54
10 |  | Scaffolding |  |  | 11917.0667 | 2025-10-31 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Security |  |  | 15600 | 2025-10-31 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 0 |  |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | Project Kick Off | 67040.5 | 10% | 6704.05 | PO4379-HLCD-20251017 - RV Approved | JA Electrical Inv 1108 | 2025-10-31 | 3912.4293 |  | 2025-11-06
10 | [9 empty] | 10 | 10. Site Logistics | Site Establishment |  | 15% | 10056.075 |  | JA Electrical Inv 1118 | 2025-11-30 | 5868.644 |  | 2025-12-04
10 | [9 empty] | 10 | 10. Site Logistics | AC Installation Complete |  | 10% | 6704.05 |  | JA Electrical Inv 1125 | 2025-11-30 | 3912.4293 |  | 2025-12-04
[10 empty] | 10 | 10. Site Logistics | AC Installation Complete |  | 10% | 6704.03 |  | JA Electrical Inv 1141 | 2025-12-31 | 3912.4177 |  | 2025-12-18
10 | [9 empty] | 10 | 10. Site Logistics | DC Installation Complete |  | 20% | 13408.1 |  | JA Electrical Inv 1125 | 2025-11-30 | 7824.8586 |  | 2025-12-18
[10 empty] | 10 | 10. Site Logistics | DC Installation Complete |  | 5% | 3352.025 |  | JA Electrical Inv 1130 | 2025-11-30 | 1956.2147 |  | 2026-01-09
10 | [9 empty] | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 6704.05 |  | JA Electrical Inv 1137 | 2025-11-30 | 3912.4293 |  | 2026-01-29
10 | [9 empty] | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 6704.05 |  | JA Electrical Inv 1138 | 2025-11-30 | 3912.4293 |  | 2026-02-05
10 | [9 empty] | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 3352.025 |  | JA Electrical Inv 1139 | 2025-11-30 | 1956.2147 |  | 2026-02-05
10 | [9 empty] | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 3352.025 |  | JA Electrical Inv 1140 | 2025-11-30 | 1956.2147 |  | 2026-03-07
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2025-11-30 | 29000 | 32222.2222 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 9565 |  | SunSpot - E034 | 2025-12-31 | 19801.1921 | 0 | 2026-01-23 | 15565
11 |  | Structural sign off |  |  | 18000 | 2025-10-31 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 0 |  |  |  | 0
11 | [9 empty] | 11 | 11. Due Dilligence | [7 empty] | 0
11 | [9 empty] | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 |  | Matriarch - INV-5975 | 2025-12-31 | 12421.0301 |  | 2026-01-30
11 | [9 empty] | 11 | 11. Due Dilligence | [7 empty] | 0
12 | BDP Commission | PD Fee |  |  | 8079.73 | 2025-11-30 | 8079.73 | 0 |  | 12 | 12. BDP Commission | PD Fee |  |  | 0 | [6 empty] | 0
12 | BDP Commission | [8 empty] | 12 | 12. BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 11693.1947 | 2025-10-31 | 11693.1947 | 13287.7212 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 16154.12 |  | Matriarch - INV-6234 | 2026-01-31 | 13287.7212 | 0 | 2026-02-26 | 16154.12
13 | [9 empty] | 13 | 13. Engineering | Management | [6 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | Project manager |  |  | 0 |  |  |  | 0
13 | [9 empty] | 13 | 13. Engineering | Planner time |  |  | 0 |  |  |  | 0
13 | [9 empty] | 13 | 13. Engineering | De Snagging |  |  | 0 |  |  |  | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 2275 | 2025-09-30 | 2275 | 2527.7778 |  | 14 | 14. General Expenses | Travel | [6 empty] | 0 | 0.0015325 |  | 2023.19
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 863.34 |  | Expense Claim | 2025-11-30 | 1960.1664 |  | 2025-12-05
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 1023.4 |  | Expense Claim | 2025-12-31 | 567.6098 |  | 2026-01-08
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 136.45 |  | Expense Claim | 2026-01-31 | 0 |  | 2026-02-05
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | [8 empty] | 0 |  | 3650
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On | Domestic Transport |  |  | 3650 |  | ABL Transport - 0217 | 2025-11-30 |  |  | 2025-11-28
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
| Panel Procurement Budget | 329608.245 |  | 457789.2292
| Inverter Procurement Budget | 70000 |  | 97222.2222
| Mounting Structure Budget | 52216 |  | 72522.2222
| DC Equipment Budget | 112097.4 |  | 155690.8333
| AC Equipment Budget | 153726.8609 |  | 213509.529
| Monitoring Budget | 49000 |  | 68055.5556
| Optional Extras Budget | 0 |  | 0
| MV Equipment Budget | 0 |  | 0
| ADD ON | 40000 |  | 44444.4444
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 32635 |  | 36261.1111
| DC Installer Budget | 71155 |  | 79061.1111
| In-House Expense Budget | 11693.1947 |  | 13287.7212
| Compliance Budget | 29000 |  | 32222.2222
| Offloading Budget | 8500 |  | 9444.4444
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 0 |  | 0
| On Site Security | 15600 |  | 17333.3333
| Roof Access Budget for Installers | 11917.0667 |  | 13241.1852
| EPC Management Fee | 0 |  | 0
| ADD ON | 0 |  | 0
Expenses
| Total EE Expense Budget | 2275 |  | 2527.7778

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-07-07 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 1312612.9423 | 1312612.9423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 656306.4712 | 0 | 0 | 0 | 0 | 0 | 459414.5298 | 0 | 0 | 0 | 0 | 0 | 131261.2942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65630.6471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 656306.4712 | 656306.4712 | 656306.4712 | 656306.4712 | 656306.4712 | 656306.4712 | 1115721.001 | 1115721.001 | 1115721.001 | 1115721.001 | 1115721.001 | 1115721.001 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1246982.2952 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423 | 1312612.9423
| Planned Expenditure | 997503.4972 | 997503.4972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2275 | 0 | 0 | 0 | 129845.2613 | 0 | 0 | 0 | 329586.9909 | 0 | 0 | 0 | 0 | 535796.245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2275 | 2275 | 2275 | 2275 | 132120.2613 | 132120.2613 | 132120.2613 | 132120.2613 | 461707.2522 | 461707.2522 | 461707.2522 | 461707.2522 | 461707.2522 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972 | 997503.4972
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 654031.4712 | 654031.4712 | 654031.4712 | 654031.4712 | 524186.2098 | 524186.2098 | 983600.7396 | 983600.7396 | 654013.7488 | 654013.7488 | 654013.7488 | 654013.7488 | 785275.043 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 249478.798 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451 | 315109.4451
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 1292329.358 | 1292329.358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1115721.001 | 0 | 0 | 0 | 176608.357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1115721.001 | 1115721.001 | 1115721.001 | 1115721.001 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358 | 1292329.358
| Actual + Planned Expenditure | 889884.7555 | 889884.7555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11515 | 54000 | 32663.791 | 21.33 | 0 | 38924.39 | 93470.2965 | 0 | 411212.322 | 0 | 95649.57 | 25566.1355 | 0 | 9565 | 37668.79 | 47639.625 | 0 | 0 | 16154.12 | 15834.3855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11515 | 65515 | 98178.791 | 98200.121 | 98200.121 | 137124.511 | 230594.8075 | 230594.8075 | 641807.1295 | 641807.1295 | 737456.6995 | 763022.835 | 763022.835 | 772587.835 | 810256.625 | 857896.25 | 857896.25 | 857896.25 | 874050.37 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555 | 889884.7555
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11515 | -65515 | -98178.791 | 1017520.88 | 1017520.88 | 978596.49 | 885126.1935 | 1061734.5505 | 650522.2285 | 650522.2285 | 554872.6585 | 529306.523 | 529306.523 | 519741.523 | 482072.733 | 434433.108 | 434433.108 | 434433.108 | 418278.988 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025 | 402444.6025
|  | CHECK | CHECK
| Revenue Recognition | 20283.595 | 1292329.3473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 786382.1412 | 0 | 0 | 0 | 451468.4151 | 0 | 0 | 0 | 0 | 41191.0698 | 0 | 0 | 0 | 13287.7212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 1292329.3473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 786382.1412 | 786382.1412 | 786382.1412 | 786382.1412 | 1237850.5563 | 1237850.5563 | 1237850.5563 | 1237850.5563 | 1237850.5563 | 1279041.6261 | 1279041.6261 | 1279041.6261 | 1279041.6261 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473 | 1292329.3473

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | Grand Total
(blank)
1. Panels | 0 | 457789.2292 | 0 | -20283.5843 | 0 |  | 437505.6449
2. Inverters |  | 97222.2222 |  |  | 0 |  | 97222.2222
3. Mounting Structures |  |  | 72522.2222 |  | 0 |  | 72522.2222
4. DC Equipment |  | 105928.5412 | 44232.5546 | 5529.7329 | 0 |  | 155690.8287
5. Monitoring |  | 57845.6629 | 10209.893 |  | 0 |  | 68055.5558
6. AC Equipment |  | 7707.3897 | 198094.7916 | 7707.3461 | 0 |  | 213509.5274
8. Product Add On | 0 | 44444.4444 | 0 |  |  |  | 44444.4444
9. AC & DC installation | 0 | 11532.2222 | 92254.6714 | 11535.3254 | 0 |  | 115322.219
10. Site Logistics |  | 3912.4293 | 32194.116 | 3912.4177 | 0 |  | 40018.963
11. Due Dilligence | 0 |  |  | 32222.2222 | 0 |  | 32222.2222
13. Engineering | 0 |  |  |  |  | 13287.7212 | 13287.7212
14. General Expenses | 0 |  | 1960.1664 | 567.6098 | 0 | 0 | 2527.7762
15. Service Add On
12. BDP Commission
7.BESS
Grand Total | 0 | 786382.1412 | 451468.4151 | 41191.0698 | 0 | 13287.7212 | 1292329.3473

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | Grand Total
(blank)
1. Panels | 0 | 245463.93 | -8105.88 |  |  | 237358.05
2. Inverters |  | 65246 |  |  |  | 65246
3. Mounting Structures |  |  | 33946 |  |  | 33946
4. DC Equipment |  | 56973.86 | 23780.87 | 2973.82 |  | 83728.55
5. Monitoring |  | 48217.33 | 8760.67 | 1300 |  | 58278
6. AC Equipment |  | 3412.26 | 87701.65 | 3412.24 |  | 94526.15
8. Product Add On |  | 16450 | 8450 |  |  | 24900
9. AC & DC installation |  | 18598.621 | 148738.9345 | 18598.6 |  | 185936.1555
10. Site Logistics |  | 6704.05 | 55165.46 | 6704.03 |  | 68573.54
11. Due Dilligence | 0 |  |  | 15565 |  | 15565
13. Engineering | 0 |  |  |  | 16154.12 | 16154.12
14. General Expenses |  |  | 863.34 | 1023.4 | 136.45 | 2023.19
15. Service Add On |  |  | 3650 |  |  | 3650
12. BDP Commission | 0 |  |  |  |  | 0
7.BESS
Grand Total | 0 | 461066.051 | 362951.0445 | 49577.09 | 16290.57 | 889884.7555

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | #REF! | #REF! |  | #REF! | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | #REF! | #REF! |  | #REF! | #REF!
AC Labour | #REF! | #REF! | 96174 | #REF! | #REF! |  | #REF! | #REF!
DC Labour | #REF! | #REF! | 230160 | #REF! | #REF! |  | #REF! | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | #REF! | #REF! |  | #REF! | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF!
DC installation | #REF! | #REF! |  | #REF! | #REF! |  | #REF! | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
#REF! |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
#REF!