## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate |  |  |  | FINANCIAL CLOSE CERTIFICATE
Project Name: | Westway BESS
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Product Agreement
EPC Agreement
O&M Agreeement
Cost Proposal
Deposit Received
Risks / Notes
Acknowledgement and Acceptance:
Role | Name | Signature | Date

## Certificate - Planning
Emergent Energy – Planning Phase Completion Certificate |  |  |  | PLANNING CERTIFICATE
Project Name: | Westway BESS
Client Representative:
Programme Manager: | Roedolph Venter
Project Manager: | Lloyd Brown
Project Engineer:
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Project Introduction Presentation
Project Brief
Engineering Pack
BOQ
PO – Material & Equipment
PO - Contractors
HSE – NOC
HSE – EE File
HSE – Contractor File
SSEG Application
Risks / Notes
Acknowledgement and Acceptance:
Role | Name | Signature | Date

## Change Register
Change Register
ID | Description | Supporting Image (If Applicable) | Impact | Proposed Date | Proposed By | Status | Approved By | Approved Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
DEC011
DEC012
DEC013
DEC014
DEC015
DEC016
DEC017
DEC018
DEC019
DEC020
DEC021
DEC022
DEC023
DEC024
DEC025
DEC026
DEC027
DEC028
DEC029
DEC030

## BOQ
Item | Supplier | Description | Quantity | Comments
PV Module
DC Cable Red & Black
Inverters
Mounting Structure
Current Transformers (Production)
Current Transformers (Consumption)
Solar Production Meter (Techistter)
Grid Consumption Meter
Wi-Fi Router & Sim
Switch
Back Up Battery
PVDB
Supplier List
Accuenergy
Krannich
Menlo
Red Pole
Schletter
Switchboard
Techsitter

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC |  |  |  | In progress
7.1 Agreement |  |  |  | In progress
13.2 Agreement |  |  |  | In progress
EE File |  |  |  | In progress
Subbie File |  |  |  | Not appointed yet
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING | [10 empty] | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
|  | COSTED |  | ACTUAL |  | FINANCIAL REVIEW | TIMELINE REVIEW |  |  |  | 823858.2648 | 585065.5112 | 0 | 0
1 | Planned Revenue | 823858.487 |  | 823858.487 |  |  | Start Date
2 | Planned Expenditure | 725014.913 |  | 585065.5112 | VO vs Costed Margin
3 | Planned Profit | 98843.574 |  | 238792.9758 | 4942.1787 |  | End Date - PC
4 | Planned Margin | 12% |  | 28.98% | 0
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE REQUIREMENTS & COMMENTS | MILESTONE DOCUMENTS RECEIVED
1 | Acceptance and Initial Deposit |  | 20% | 164771.6974 | 2025-12-24 | 004900 | 2025-12-12 | 2025-12-29 |  | FALSE |  |  |  |  | 1900-01-06
2 | Delivery of batteries |  | 0% | 0 | [5 empty] | FALSE
3 | Delivery of Inverter |  | 0% | 0 | [5 empty] | FALSE
4 | Practical Completion |  | 0% | 0 | [5 empty] | FALSE
5 | Handover |  | 80% | 659086.7896 | 2026-03-07 | 004948 | 2026-02-26 | 2026-03-07 |  | FALSE
6 | - |  | 0% | 0 | [5 empty] | FALSE
7 | - |  | 0% | 0 | [5 empty] | FALSE
|  |  | 100% | 823858.487
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 288350.4705
2 | Delivery of Panels |  | 30% | 247157.5461
3 | Delivery of Inverters |  | 20% | 164771.6974
4 | Practical Completion |  | 10% | 82385.8487
5 | Handover |  | 5% | 41192.9244
| Total |  | 100% | 823858.487
|  |  | 100% | 823858.487

## Project Plan
[9 empty] | 2026-02-24 | 2026-02-24
| PROJECT PLAN | Westway BESS |  |  | Net Work Days |  | 15 |  | 0 | 1
| PROJECT SIZE (kWh) | 100 |  |  | Total Weeks |  | 3
| PROJECT DEVELOPER | Gordon Upton |  |  | kW/Week Installation Rate |  | 33.3333
| PROJECT MANAGERS | Lloyd Brown
| CONTRACT VALUE | 823858.487
| Phase: | Construction
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration | Planned End | Actual Start | Duration | Actual End | Status | Expected Status | Comment
|  |  | 18 |  |  | 18 |  | 32.99% | 42.99% |  | 2026-02-24 | 2026-02-24
[11 empty] | 1 | 0
1 | Project Initiation | 2026-01-16 | 20 | 2026-02-05 | 2026-01-16 | 34 | 2026-02-19 | 90.91% | 90.91%
1.1 | Project Charter Handover | 2026-01-16 | 1 | 2026-01-19 | 2026-01-16 | 1 | 2026-01-19 | 100% | 100% |  | Milestone | Start Date | Duration | End Date
1.2 | HSE Readiness and Signoff | 2026-01-19 | 10 | 2026-02-02 | 2026-02-09 | 5 | 2026-02-16 | 100% | 100% |  | Project Initiation | 2026-01-16 | 34 | 2026-02-19
1.3 | Project Introduction | 2026-02-02 | 1 | 2026-02-03 | 2026-02-16 | 1 | 2026-02-17 | 100% | 100% |  | Site Establishment | 2026-02-23 | 1 | 2026-02-24
1.4 | Technical Meeting | 2026-01-18 | 10 | 2026-01-30 | 2026-01-18 | 10 | 2026-01-30 | 100% | 100% |  | AC Installation | 2026-02-23 | 2 | 2026-02-25
| Post Tests Review |  |  |  | 2026-02-05 | 2 | 2026-02-09
1.5 | Project Review | 2026-02-02 | 3 | 2026-02-05 | 2026-02-16 | 3 | 2026-02-19 | 100% | 100% |  | BESS Works | 2026-02-21 | 4 | 2026-02-25
[11 empty] | 0 | 0 | 0 | 0
2 | Site Establishment | 2026-02-23 | 1 | 2026-02-24 | 2026-02-23 | 1 | 2026-02-24 | 100% | 100% |  | Commissioning | 2026-02-25 | 16 | 2026-03-13
2.1 | Solar Contractor Establishment | 2026-02-23 | 1 | 2026-02-24 | 2026-02-23 | 1 | 2026-02-24 | 100% | 100% |  | QA Inspections | 2026-03-13 | 5 | 2026-03-18
[11 empty] | Project Closure | 2026-03-16 | 10 | 2026-03-26
3 | AC Installation | 2026-02-23 | 2 | 2026-02-25 | 2026-02-23 | 2 | 2026-02-25 | 20% | 60%
3.1 | Inverters delivered | 2026-02-23 | 1 | 2026-02-24 | 2026-02-23 | 1 | 2026-02-24 | 100% | 100%
3.2 | Inverters Mounted | 2026-02-24 | 1 | 2026-02-25 | 2026-02-24 | 1 | 2026-02-25 | 0% | 0%
3.3 | DB Lead Time - N/A
3.4 | AC Works | 2026-02-23 | 2 | 2026-02-25 | 2026-02-23 | 2 | 2026-02-25 | 0% | 50% | not started
3.5 | AC Tie-In | 2026-02-23 | 1 | 2026-02-24 | 2026-02-23 | 1 | 2026-02-24 | 0% | 100%
4 | BESS Works | 2026-02-21 | 4 | 2026-02-25 | 2026-02-21 | 4 | 2026-02-25 | 20% | 50%
4.1 | Batteries delivered | 2026-02-23 | 1 | 2026-02-24 | 2026-02-23 | 1 | 2026-02-24 | 100% | 100%
4.2 | Batteries Installation | 2026-02-24 | 1 | 2026-02-25 | 2026-02-24 | 1 | 2026-02-25 | 0% | 0%
4.3 | DC Cable Material delivered | 2026-02-23 | 1 | 2026-02-24 | 2026-02-23 | 1 | 2026-02-24 | 0% | 100% | n/a
4.4 | DC Cable Installation | 2026-02-21 | 2 | 2026-02-24 | 2026-02-21 | 2 | 2026-02-24 | 0% | 100% | n/a
6 | Commissioning | 2026-02-25 | 16 | 2026-03-13 | 2026-02-25 | 16 | 2026-03-13 | 0% | 0%
6.1 | Commissioning | 2026-02-25 | 1 | 2026-02-26 | 2026-02-25 | 1 | 2026-02-26 | 0% | 0%
6.2 | Practical Completion | 2026-02-26 | 1 | 2026-02-27 | 2026-02-26 | 1 | 2026-02-27 | 0% | 0%
6.3 | System Performance Monitoring | 2026-02-27 | 10 | 2026-03-13 | 2026-02-27 | 10 | 2026-03-13 | 0% | 0%
7 | QA Inspections | 2026-03-13 | 5 | 2026-03-18 | 2026-03-13 | 5 | 2026-03-18 | 0% | 0%
7.1 | Red-Team Inspection | 2026-03-13 | 1 | 2026-03-16 | 2026-03-13 | 1 | 2026-03-16 | 0% | 0%
7.2 | Snags completion | 2026-03-16 | 2 | 2026-03-18 | 2026-03-16 | 2 | 2026-03-18 | 0% | 0%
8 | Project Closure | 2026-03-16 | 10 | 2026-03-26 | 2026-03-16 | 10 | 2026-03-26 | 0% | 0%
8.1 | Handover documentation | 2026-03-16 | 3 | 2026-03-19 | 2026-03-16 | 3 | 2026-03-19 | 0% | 0%
8.2 | Handover to Client | 2026-03-19 | 1 | 2026-03-20 | 2026-03-19 | 1 | 2026-03-20 | 0% | 0%
8.3 | Handover to Matriarch | 2026-03-19 | 5 | 2026-03-26 | 2026-03-19 | 5 | 2026-03-26 | 0% | 0%
Formulas:
Planned Start = MIN([Planned Start, row below]:E18)
Planned Start = [Planned End, row above]
Planned End = MAX([Planned End, row below]:G18)
Planned End = WORKDAY.INTL([Planned Start],[Duration],1,Data!$C3:C60)
Actual Start = MIN([Actual Start, row below]:I18)
Actual Start = WORKDAY.INTL([Actual End, row above],0,1,Data!$C3:C60)
Actual End = MAX([Actual End, row below]:K18)
Actual End = WORKDAY.INTL([Actual Start],[Duration],1,Data!$C3:C60)
Expected Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 725014.913 | 823858.2648 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 585065.5112
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FORECASTED PAYMENT DATE | Total COS | ERROR on REV |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | [5 empty] | 0 | 0 |  | 1 | 1. Panels | [8 empty] | 0 |  | 0
1 | [9 empty] | 1 | 1. Panels
1 | [9 empty] | 1 | 1. Panels
1 | [9 empty] | 1 | 1. Panels
1 | [9 empty] | 1 | 1. Panels
1 | [9 empty] | 1 | 1. Panels | [11 empty] | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 0
2 | Inverters | [5 empty] | 0 | 0 |  | 2 | 2. Inverters | [8 empty] | 0 |  | 0 | DC Equipment | 0
2 | [9 empty] | 2 | 2. Inverters | [11 empty] | AC Labour | 0
2 | [9 empty] | 2 | 2. Inverters | [11 empty] | DC Labour | 0
2 | [9 empty] | 2 | 2. Inverters | [11 empty] | Offloading | 0
2 | [9 empty] | 2 | 2. Inverters | [11 empty] | Scaffolding | 0
2 | [9 empty] | 2 | 2. Inverters | [11 empty] | Storage | 0
2 | [9 empty] | 2 | 2. Inverters | [11 empty] | Telehandler | 0
[23 empty] | Trenching | 0
3 | Mounting Structures | [5 empty] | 0 | 0 |  | 3 | 3. Mounting Structures | [8 empty] | 0 |  | 0 | Other | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [11 empty] | Total | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [11 empty] | Less 15% | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [11 empty] | R/Wp | 0
3 | [9 empty] | 3 | 3. Mounting Structures
3 | [9 empty] | 3 | 3. Mounting Structures | [11 empty] | ACTUAL | Installer Price
[23 empty] | AC Equipment | 151265.4261
4 | DC Equipment | [5 empty] | 0 | 0 |  | 4 | 4. DC Equipment | [8 empty] | 0 |  | 0 | DC Equipment | 79942.7
4 | [9 empty] | 4 | 4. DC Equipment | [11 empty] | AC Labour | 44530
4 | [9 empty] | 4 | 4. DC Equipment | [11 empty] | DC Labour | 91980
4 | [9 empty] | 4 | 4. DC Equipment | [11 empty] | Lifelines | 8500
4 | [9 empty] | 4 | 4. DC Equipment | [11 empty] | Forklift | 17023.903
4 | [9 empty] | 4 | 4. DC Equipment | [11 empty] | Geda | 1788.3333
4 | [9 empty] | 4 | 4. DC Equipment | [11 empty] | Logistics | 0
4 | [9 empty] | 4 | 4. DC Equipment | [11 empty] | Trenching | 0
4 | [9 empty] | 4 | 4. DC Equipment | [11 empty] | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | [11 empty] | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | [11 empty] | Total | 395030.3625
4 | [9 empty] | 4 | 4. DC Equipment | [11 empty] | R/Wp | 3.9503
4 | [9 empty] | 4 | 4. DC Equipment
4 | [9 empty] | 4 | 4. DC Equipment
4 | [9 empty] | 4 | 4. DC Equipment
5 | Monitoring | [5 empty] | 0 | 0 |  | 5 | 5. Monitoring | [10 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring
5 | [9 empty] | 5 | 5. Monitoring
5 | [9 empty] | 5 | 5. Monitoring
5 | [9 empty] | 5 | 5. Monitoring
5 | [9 empty] | 5 | 5. Monitoring
5 | [9 empty] | 5 | 5. Monitoring
6 | AC Equipment | [5 empty] | 0 | 0 |  | 6 | 6. AC Equipment | [10 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
6 | [9 empty] | 6 | 6. AC Equipment
7 | BESS | Battery Inverter + Battery Bank | 1 |  | 559066 | 2026-03-31 | 724139.913 | 822886.2648 |  | 7 | 7.BESS | Battery Inverter + Battery Bank | [6 empty] | 0 |  |  | 573781
7 |  | Ps and Gs | 1 |  | 19400 | 2026-02-28 |  |  |  | 7 | 7.BESS | SigenStack 50kW Hybrid Inverter | 1 | 69250 | 69250 | PO4615-WWB-20260209 - RV Approved |  | 2026-02-28 | 99314.6755 |  | 2026-04-29
7 |  | Installation | 1 |  | 53200 | 2026-02-28 |  |  |  | 7 | 7.BESS | SigenStack Battery 12kWh | 8 | 38500 | 308000 |  |  | 2026-02-28 | 441717.2572 |  | 2026-04-29
7 |  | AC+DC Equipment | 1 |  | 64400 | 2026-02-28 |  |  |  | 7 | 7.BESS | Sigen Power Sensor | 2 | 3650 | 7300 |  |  | 2026-02-28 | 10469.2727 |  | 2026-04-29
7 |  | Inverter Cables | 2 |  | 7500 | 2026-02-28 |  |  |  | 7 | 7.BESS | SigenStack Battery controller | 1 | 57800 | 57800 |  |  | 2026-02-28 | 82893.6931 |  | 2026-04-29
7 |  | Main Gateway Cable (Tie-In) | 40 |  | 20573.913 | 2026-02-28 |  |  |  | 7 | 7.BESS | SigenStack Accessories | 1 | 29300 | 29300 |  |  | 2026-02-28 | 42020.5053 |  | 2026-04-29
7.BESS
7 | [9 empty] | 7 | 7.BESS | Installation - Deposit | 70567 | 50% | 35283.5 | PO4630-WWB-20260219 - RV Approved |  | 2026-02-28 | 50601.7235 |  | 2026-03-02
7 | [9 empty] | 7 | 7.BESS | Installation - Commissioning Complete |  | 30% | 21170.1 |  |  | 2026-02-28 | 30361.0341 |  | 2026-03-06
7 | [9 empty] | 7 | 7.BESS | Installation - End of Defects - 30 Days |  | 20% | 14113.4 |  |  | 2026-02-28 | 20240.6894 |  | 2026-04-05
7 | [9 empty] | 7 | 7.BESS | [7 empty] | 0
7 | [9 empty] | 7 | 7.BESS | [7 empty] | 0
7 | [9 empty] | 7 | 7.BESS | Installer Equipment - Deposit | 27594 | 50% | 13797 |  |  | 2026-02-28 | 19786.9253 |  | 2026-03-02
7 | [9 empty] | 7 | 7.BESS | Installer Equipment - Balance |  | 30% | 8278.2 |  |  | 2026-02-28 | 11872.1552 |  | 2026-03-25
7 | [9 empty] | 7 | 7.BESS | Installer Equipment - End of Defects - 30 Days |  | 20% | 5518.8 |  |  | 2026-02-28 | 7914.7701 |  | 2026-04-24
7 | [9 empty] | 7 | 7.BESS | [7 empty] | 0
7 | [9 empty] | 7 | 7.BESS | [7 empty] | 0
7 | [9 empty] | 7 | 7.BESS | [7 empty] | 0
7 | [9 empty] | 7 | 7.BESS | CTs |  |  | 3970 | PO4628-WWB-20260217 - RV Approved |  | 2026-02-28 | 5693.5633 |  | 2026-03-30
7 | [9 empty] | 7 | 7.BESS | [7 empty] | 0
7 | [9 empty] | 7 | 7.BESS | [7 empty] | 0
7 | [9 empty] | 7 | 7.BESS | [7 empty] | 0
7 | [9 empty] | 7 | 7.BESS | [7 empty] | 0
7 | [9 empty] | 7 | 7.BESS | [7 empty] | 0
7 | [9 empty] | 7 | 7.BESS | [7 empty] | 0
7 | [9 empty] | 7 | 7.BESS | [7 empty] | 0
7 | [9 empty] | 7 | 7.BESS | [7 empty] | 0
7 | [9 empty] | 7 | 7.BESS | [7 empty] | 0
7 | [9 empty] | 7 | 7.BESS | [7 empty] | 0
8 | Product Add On | [5 empty] | 0 | 0 |  | 8 | 8. Product Add On | [10 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
Only services to be capture below, products above
9 | AC & DC Installation | [5 empty] | 0 | 0 |  | 9 | 9. AC & DC installation | [10 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation
9 | [9 empty] | 9 | 9. AC & DC installation
9 | [9 empty] | 9 | 9. AC & DC installation
9 | [9 empty] | 9 | 9. AC & DC installation
9 | [9 empty] | 9 | 9. AC & DC installation
9 | [9 empty] | 9 | 9. AC & DC installation
9 | [9 empty] | 9 | 9. AC & DC installation
9 | [9 empty] | 9 | 9. AC & DC installation
9 | [9 empty] | 9 | 9. AC & DC installation
9 | [9 empty] | 9 | 9. AC & DC installation
9 | [9 empty] | 9 | 9. AC & DC installation
10 | Site Logistics | [5 empty] | 0 | 0 |  | 10 | 10. Site Logistics | [10 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
11 | Due Dilligence | [5 empty] | 0 | 0 |  | 11 | 11. Due Dilligence | [10 empty] | 0
11 | [9 empty] | 11 | 11. Due Dilligence
11 | [9 empty] | 11 | 11. Due Dilligence
11 | [9 empty] | 11 | 11. Due Dilligence
11 | [9 empty] | 11 | 11. Due Dilligence
12 | BDP Commission | [5 empty] | 0 | 0 |  | 12 | 12. BDP Commission | [10 empty] | 0
12 | BDP Commission | [8 empty] | 12 | 12. BDP Commission
13 | Engineering | [5 empty] | 0 | 0 |  | 13 | 13. Engineering | Matriarch Defects Period |  |  | 10409.5113 |  |  | 2026-03-31 |  |  | 2026-04-30 | 10409.5113
13 | [9 empty] | 13 | 13. Engineering
13 | [9 empty] | 13 | 13. Engineering
13 | [9 empty] | 13 | 13. Engineering
13 | [9 empty] | 13 | 13. Engineering
13 | [9 empty] | 13 | 13. Engineering
14 | General Expenses | Travel |  |  | 875 | 2026-03-31 | 875 | 972 |  | 14 | 14. General Expenses | Travel |  |  | 291.6667 |  |  | 2026-02-28 | 324 | 0 | 2026-03-07 | 875
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 291.6667 |  |  | 2026-03-31 | 324 |  | 2026-04-07
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 291.6667 |  |  | 2026-04-30 | 324 |  | 2026-05-07
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | [8 empty] | 0 |  | 0
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from Costed
EXPENDITURE |  | 725014.913 |  | 585065.5112 | 139949.4018
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 0 |  | 0 | 0
2 | 2. Inverters | 0 |  | 0 | 0
3 | 3. Mounting Structures | 0 |  | 0 | 0
4 | 4. DC Equipment | 0 |  | 0 | 0
5 | 5. Monitoring | 0 |  | 0 | 0
6 | 6. AC Equipment | 0 |  | 0 | 0
7 | 7.BESS | 724139.913 |  | 573781 | 150358.913
8 | 8. Product Add On | 0 |  | 0 | 0
9 | 9. AC & DC installation | 0 |  | 0 | 0
10 | 10. Site Logistics | 0 |  | 0 | 0
11 | 11. Due Dilligence | 0 |  | 0 | 0
12 | 12. BDP Commission | 0 |  | 0 | 0
13 | 13. Engineering | 0 |  | 10409.5113 | -10409.5113
14 | 14. General Expenses | 875 |  | 875 | 0
15 | 15. Service Add On | 0 |  | 0 | 0
| check: | 0 | #REF! | 0

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-12-15 to 2031-06-09
PLANNED |  | CHECK | CHECK
| Planned Revenue | 823858.487 | 823858.487 | 0 | 164771.6974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 659086.7896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487
| Planned Expenditure | 725014.913 | 725014.913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165073.913 | 0 | 0 | 0 | 0 | 559941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165073.913 | 165073.913 | 165073.913 | 165073.913 | 165073.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913 | 725014.913
| PLANNED CashFlow |  |  | 0 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | -302.2156 | 658784.574 | 658784.574 | 658784.574 | 658784.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574 | 98843.574
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 823858.487 | 823858.487 | 0 | 0 | 164771.6974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 659086.7896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487 | 823858.487
| Actual + Planned Expenditure | 585065.5112 | 585065.5112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70542.2667 | 0 | 0 | 8278.2 | 18083.4 | 291.6667 | 0 | 5518.8 | 482059.5112 | 291.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70542.2667 | 70542.2667 | 70542.2667 | 78820.4667 | 96903.8667 | 97195.5333 | 97195.5333 | 102714.3333 | 584773.8446 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112 | 585065.5112
| ACTUAL CashFlow |  |  | 0 | 0 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | 164771.6974 | 753316.2204 | 753316.2204 | 753316.2204 | 745038.0204 | 726954.6204 | 726662.9537 | 726662.9537 | 721144.1537 | 239084.6425 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758 | 238792.9758
|  | CHECK | CHECK
| Revenue Recognition | 0.22222 | 823858.2648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 823210.2648 | 0 | 0 | 0 | 0 | 324 | 0 | 0 | 0 | 324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 823858.2648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 823210.2648 | 823210.2648 | 823210.2648 | 823210.2648 | 823210.2648 | 823534.2648 | 823534.2648 | 823534.2648 | 823534.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648 | 823858.2648

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-03-30 | Grand Total
(blank)
1. Panels | 0 |  | 0 | 577060.675 |  |  |  |  | 577060.675
2. Inverters | 0 |  | 0 | 175000 |  |  |  |  | 175000
3. Mounting Structures |  |  | 0 | 188842.5 |  |  |  |  | 188842.5
4. DC Equipment |  |  | 0 | 21928.2157 | 100913.8006 | 21928.2157 | 4385.6431 |  | 149155.875
5. Monitoring |  |  | 0 | 10517.6768 | 50732.3232 |  |  |  | 61250
6. AC Equipment |  |  | 0 | 30740.9935 | 196451.5969 | 30740.9935 | 6148.1987 |  | 264081.7826
8. Product Add On | 0 |  | 0 |  | 144498.7669 |  |  | 18670.5387 | 163169.3056
9. AC & DC installation |  |  | 0 | 37919.4444 | 68255 | 37919.4444 | 7583.8889 |  | 151677.7778
10. Site Logistics |  |  | 0 | 7089.9731 | 12761.9515 | 7089.9731 | 1417.9946 |  | 28359.8923
11. Due Dilligence |  | 11164.1093 | 0 |  |  | 87724.7796 |  |  | 98888.8889
13. Engineering |  |  | 0 |  |  | 19649.8092 |  |  | 19649.8092
14. General Expenses |  | 534.7222 | 0 | 534.7222 | 534.7222 | 534.7222 |  |  | 2138.8889
15. Service Add On
12. BDP Commission
7.BESS
Grand Total | 0 | 11698.8315 | 0 | 1049634.2007 | 574148.1613 | 205587.9377 | 19535.7253 | 18670.5387 | 1879275.3952

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-03-30 | Grand Total
(blank)
1. Panels | 0 |  |  | 356240 |  |  |  |  | 356240
2. Inverters |  |  |  | 137740 |  |  |  |  | 137740
3. Mounting Structures |  |  |  | 151074 |  |  |  |  | 151074
4. DC Equipment |  |  |  | 19985.675 | 91974.215 | 19985.675 | 3997.135 |  | 135942.7
5. Monitoring |  |  |  | 8500 | 41000 |  |  |  | 49500
6. AC Equipment |  |  |  | 17608.369 | 112527.0142 | 17608.369 | 3521.6738 |  | 151265.4261
8. Product Add On |  |  |  |  | 116091 |  |  | 15000 | 131091
9. AC & DC installation |  |  |  | 34127.5 | 61429.5 | 34127.5 | 6825.5 |  | 136510
10. Site Logistics |  |  |  | 6828.0591 | 12290.5064 | 6828.0591 | 1365.6118 |  | 27312.2364
11. Due Dilligence |  | 10000 |  |  |  | 78577.5 |  |  | 88577.5
13. Engineering | [5 empty] | 23490.9424 |  |  | 23490.9424
14. General Expenses |  | 481.25 |  | 481.25 | 481.25 | 481.25 |  |  | 1925
15. Service Add On
12. BDP Commission |  |  | 0 | [5 empty] | 0
7.BESS
Grand Total | 0 | 10481.25 | 0 | 732584.8531 | 435793.4856 | 181099.2956 | 15709.9206 | 15000 | 1390668.8049

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill
2025-12-15 | Builders Break
2025-12-16 | Builders Break
2025-12-17 | Builders Break
2025-12-18 | Builders Break
2025-12-19 | Builders Break
2025-12-20 | Builders Break
2025-12-21 | Builders Break
2025-12-22 | Builders Break
2025-12-23 | Builders Break
2025-12-24 | Builders Break
2025-12-25 | Builders Break
2025-12-26 | Builders Break
2025-12-27 | Builders Break
2025-12-28 | Builders Break
2025-12-29 | Builders Break
2025-12-30 | Builders Break
2025-12-31 | Builders Break
2026-01-01 | Builders Break
2026-01-02 | Builders Break
2026-01-03 | Builders Break
2026-01-04 | Builders Break
2026-01-05 | Builders Break
2026-01-06 | Builders Break
2026-01-07 | Builders Break
2026-01-08 | Builders Break
Builders Break
Builders Break
Builders Break
Builders Break
Builders Break
Builders Break
Builders Break
Builders Break
2026-03-21 | Human Rights day
2026-04-03 | Good Friday
2026-04-06 | Family Day
2026-04-27 | Freedom Day
2026-05-01 | Workers day
2026-06-16 | Youth Day Holiday
2026-08-09 | Womens Day
2026-08-10 | Womens Day Observerd
2026-09-24 | Heritage Day
2026-12-16 | Day of Reconciliation
2026-12-25 | Christmas Day
2026-12-26 | Day of Goodwill