## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate |  |  |  | FINANCIAL CLOSE CERTIFICATE
Project Name: | Steelpark
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Product Agreement
EPC Agreement
O&M Agreeement
Cost Proposal
Deposit Received
Risks / Notes
Acknowledgement and Acceptance:
Role | Name | Signature | Date

## Certificate - Planning
Emergent Energy – Planning Phase Completion Certificate |  |  |  | PLANNING CERTIFICATE
Project Name: | Steelpark
Client Representative:
Programme Manager: | Roedolph Venter
Project Manager: | Justin Franke
Project Engineer:
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Project Introduction Presentation
Project Brief | Completed
Engineering Pack | Completed
BOQ | Partially Completed
PO – Material & Equipment
PO - Contractors
HSE – NOC
HSE – EE File
HSE – Contractor File
SSEG Application
Risks / Notes
Acknowledgement and Acceptance:
Role | Name | Signature | Date

## Change Register
Change Register
ID | Description | Supporting Image (If Applicable) | Impact | Proposed Date | Proposed By | Status | Approved By | Approved Date | Results / Comments
DEC001 | Change inverters from 2x 50KTL to 1x100KTL |  | Engineering change, drawings updated | 2025-12-01 | Dean | Approved | Simon & JP | 2025-12-01
DEC002 | Roof profile confirmation - Solar compatible |  | Roof replacement
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
DEC011
DEC012
DEC013
DEC014
DEC015
DEC016
DEC017
DEC018
DEC019
DEC020
DEC021
DEC022
DEC023
DEC024
DEC025
DEC026
DEC027
DEC028
DEC029
DEC030

## BOQ
Item | Supplier | Description | Quantity | Comments
PV Module | Menlo | Jinko 590W - JKM590N-72HL4-BDV | 221
DC Cable Red & Black | Menlo | Enco PV Cable | 4000
Inverters | Menlo | Huawei 100KTL - SUN2000-100-KTL-M2 | 1 | Take note, this has changed to 1x 100KTL
Mounting Structure | Schletter
Current Transformers (Production)
Current Transformers (Consumption)
Solar Production Meter (Techistter)
Grid Consumption Meter
Wi-Fi Router & Sim
Switch
Back Up Battery
PVDB | Switchboard
Supplier List
Accuenergy
Krannich
Menlo
Red Pole
Schletter
Switchboard
Techsitter
Note on D5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Mizelda Isaacs please take note here

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC |  |  |  | In Progress
7.1 Agreement |  |  |  | In Progress
13.2 Agreement |  |  |  | In Progress
EE File |  |  |  | In Progress
Subbie File |  |  |  | Not appointed
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[9 empty] | 2026-02-25 | 2026-02-25
| PROJECT PLAN | Steelpark |  |  | Net Work Days |  | 27 |  | 0 | 1
| PROJECT SIZE (kWp) | 130 |  |  | Total Weeks |  | 5.4
| PROJECT DEVELOPER | Natasha Watkins-Baker |  |  | kW/Week Installation Rate |  | 24.0741
| PROJECT MANAGERS | Justin Franke
| CONTRACT VALUE | 1441230.4772
| Phase: | Construction
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration | Planned End | Actual Start | Duration | Actual End | Status | Expected Status | Comment
|  |  | 35 |  |  | 36 |  | 27.11% | 27.11% |  | 2026-02-25 | 2026-02-25
[11 empty] | 1 | 0
1 | Project Initiation | 2025-11-25 | 97 | 2026-03-02 | 2025-11-25 | 99 | 2026-03-04 | 31.25% | 31.25%
1.1 | Project Charter Handover | 2025-11-25 | 1 | 2025-11-26 | 2025-11-25 | 1 | 2025-11-26 | 100% | 100% |  | Milestone | Start Date | Duration | End Date
1.2 | Client Roof Replacement | 2026-01-31 | 21 | 2026-03-02 | 2026-01-31 | 23 | 2026-03-04 | 40% | 78.12% | Start date 19 Feb | Project Initiation | 2025-11-25 | 99 | 2026-03-04
1.3 | DB Works on Client side | 2025-12-12 | 10 | 2026-01-30 | 2025-12-12 | 10 | 2026-01-30 | 100% | 100% |  | Site Establishment | 2026-02-23 | 1 | 2026-02-24
1.4 | HSE Readiness and Signoff | 2026-02-09 | 5 | 2026-02-16 | 2026-02-09 | 11 | 2026-02-24 | 100% | 100% |  | AC Installation | 2026-01-17 | 45 | 2026-03-03
1.5 | Project Introduction | 2026-02-16 | 1 | 2026-02-17 | 2026-02-16 | 1 | 2026-02-17 | 100% | 100% |  | DC Works | 2026-02-26 | 22 | 2026-03-20
1.6 | Installer Kick Off | 2026-02-16 | 1 | 2026-02-17 | 2026-02-16 | 1 | 2026-02-17 | 100% | 100% |  | Module installation | 2026-02-23 | 24 | 2026-03-19
1.7 | Project Review | 2026-02-16 | 1 | 2026-02-17 | 2026-02-16 | 1 | 2026-02-17 | 100% | 100% |  | Commissioning | 2026-03-20 | 11 | 2026-03-31
[11 empty] | QA Inspections | 2026-03-24 | 8 | 2026-04-01
2 | Site Establishment | 2026-02-23 | 1 | 2026-02-24 | 2026-02-23 | 1 | 2026-02-24 | 100% | 100% |  | Project Closure | 2026-03-24 | 20 | 2026-04-13
2.1 | Solar Contractor Establishment | 2026-02-23 | 1 | 2026-02-24 | 2026-02-23 | 1 | 2026-02-24 | 100% | 100%
3 | AC Installation | 2026-01-17 | 45 | 2026-03-03 | 2026-01-17 | 45 | 2026-03-03 | 65.67% | 65.67%
3.1 | Inverters delivered | 2026-02-23 | 1 | 2026-02-24 | 2026-02-23 | 1 | 2026-02-24 | 100% | 100%
3.2 | Inverters Mounted | 2026-02-24 | 1 | 2026-02-25 | 2026-02-24 | 1 | 2026-02-25 | 0% | 100%
3.3 | Solar DB Lead Time | 2026-01-17 | 20 | 2026-02-13 | 2026-01-17 | 22 | 2026-02-17 | 85% | 100%
3.4 | AC Works | 2026-02-24 | 5 | 2026-03-03 | 2026-02-24 | 5 | 2026-03-03 | 0% | 14.29%
3.5 | AC Tie-In | 2026-02-24 | 1 | 2026-02-25 | 2026-02-24 | 1 | 2026-02-25 | 0% | 100%
4 | DC Works | 2026-02-23 | 24 | 2026-03-19 | 2026-02-26 | 22 | 2026-03-20 | 0% | 0%
4.1 | Mounting Structure delivered | 2026-02-23 | 1 | 2026-02-24 | 2026-02-26 | 1 | 2026-02-27 | 0% | 0% | justin to deliver
4.2 | Mounting Structure installation | 2026-03-09 | 2 | 2026-03-11 | 2026-03-11 | 2 | 2026-03-13 | 0% | 0%
4.3 | DC Cable delivered | 2026-02-23 | 1 | 2026-02-24 | 2026-02-26 | 1 | 2026-02-27 | 0% | 0%
4.4 | DC Stringing | 2026-03-14 | 4 | 2026-03-19 | 2026-03-16 | 4 | 2026-03-20 | 0% | 0% | justin to deliver
5 | Module installation | 2026-02-23 | 22 | 2026-03-17 | 2026-02-23 | 24 | 2026-03-19 | 20% | 20%
5.1 | Module delivery | 2026-02-23 | 1 | 2026-02-24 | 2026-02-23 | 1 | 2026-02-24 | 100% | 100%
5.2 | Module mounting | 2026-03-11 | 4 | 2026-03-17 | 2026-03-13 | 4 | 2026-03-19 | 0% | 0%
6 | Commissioning | 2026-03-19 | 11 | 2026-03-30 | 2026-03-20 | 11 | 2026-03-31 | 0% | 0%
6.1 | Commissioning | 2026-03-19 | 1 | 2026-03-20 | 2026-03-20 | 1 | 2026-03-23 | 0% | 0%
6.2 | Practical Completion | 2026-03-20 | 1 | 2026-03-23 | 2026-03-23 | 1 | 2026-03-24 | 0% | 0%
6.3 | System Performance Monitoring | 2026-03-23 | 5 | 2026-03-30 | 2026-03-24 | 5 | 2026-03-31 | 0% | 0%
7 | QA Inspections | 2026-03-23 | 8 | 2026-03-31 | 2026-03-24 | 8 | 2026-04-01 | 0% | 0%
7.1 | Red-Team Inspection | 2026-03-23 | 3 | 2026-03-26 | 2026-03-24 | 3 | 2026-03-27 | 0% | 0%
7.2 | Snags completion | 2026-03-26 | 3 | 2026-03-31 | 2026-03-27 | 3 | 2026-04-01 | 0% | 0%
8 | Project Closure | 2026-03-26 | 20 | 2026-04-15 | 2026-03-24 | 20 | 2026-04-13 | 0% | 0%
8.1 | Handover documentation | 2026-03-26 | 7 | 2026-04-08 | 2026-03-24 | 7 | 2026-04-02 | 0% | 0%
8.2 | Handover to Client | 2026-04-08 | 1 | 2026-04-09 | 2026-04-02 | 1 | 2026-04-07 | 0% | 0%
8.3 | Handover to Matriarch | 2026-04-08 | 5 | 2026-04-15 | 2026-04-02 | 5 | 2026-04-13 | 0% | 0%
Formulas:
Planned Start = MIN([Planned Start, row below]:E19)
Planned Start = [Planned Start, row above]
Planned End = MAX([Planned End, row below]:G19)
Planned End = WORKDAY.INTL([Planned Start],[Duration],1,Data!$C3:C60)
Actual Start = MIN([Actual Start, row below]:I19)
Actual Start = [Actual Start, row above]
Actual End = MAX([Actual End, row below]:K19)
Actual End = WORKDAY.INTL([Actual Start],[Duration],1,Data!$C3:C60)
Expected Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 1194452.4559 | 1399380.6072 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 827940.6935
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FORECASTED PAYMENT DATE | Total COS | ERROR on REV |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 370794.53 | 2026-04-24 | 370794.53 | 452188.4512 |  | 1 | 1. Panels | Jinko 590W - JKM590N-72HL4-BDV - Menlo | 221 | 1180 | 260780 |  | MSA Energy - INV0003648 | 2026-02-28 | 451495.9197 | 0 | 2026-04-24 | 261180
1 |  | Delivery Budget | [7 empty] | 1 | 1. Panels | Transport for broken two broken panels |  |  | 400 |  | MSA Energy INV0003653 | 2026-02-28 | 692.5315 |  | 2026-04-24
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 198443.487
2 | Inverters | Inverter Budget |  |  | 95000 | 2026-04-24 | 95000 | 115853.6585 |  | 2 | 2. Inverters | [7 empty] | 0 | 0 |  | 68870.35 | DC Equipment | 50822.8
2 | [9 empty] | 2 | 2. Inverters | Huawei 100KTL - Use stock from Mayo Macs | 1 | 68870.35 | 68870.35 |  | MSA Energy - INV0003648 | 2026-02-28 | 115853.6585 |  | 2026-04-24 |  | AC Labour | 32490
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 75810
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 21741.9
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 0
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 58482 | 2026-03-25 | 58482 | 71319.5122 |  | 3 | 3. Mounting Structures | Schletter Structure | [6 empty] | 0 | 0 |  | 15616.04 | Other | 0
3 | [9 empty] | 3 | 3. Mounting Structures | Clampfit Pro | 400 | 22.73 | 9092 |  |  | 2026-02-28 | 41523.7797 |  | 03/31/2026 |  | Total | 387808.187
[10 empty] | 3 | 3. Mounting Structures | Clampfit Pro | 74 | 23.96 | 1773.04 |  | Allocated from Joburg Streroom | 2026-02-28 | 8097.5937 |  | 2026-02-28
[10 empty] | 3 | 3. Mounting Structures | Clampfit Pro | 126 |  |  |  | Joburg Storeroom | 2026-02-28 | 0 |  | 2026-02-28
3 | [9 empty] | 3 | 3. Mounting Structures | Mid Clamps | 100 | 10.95 | 1095 |  | Allocated from Cpt Storeroom | 2026-02-28 | 5000.9392 |  | 2026-02-28 |  | Less 15% | 329636.9589
[10 empty] | 3 | 3. Mounting Structures | Mid Clamps | 100 | 11.52 | 1152 |  | Allocated from Cpt Storeroom | 2026-02-28 | 5261.262 |  | 2026-02-28
[10 empty] | 3 | 3. Mounting Structures | Mid Clamps | 200 |  |  |  | Joburg Storeroom | 2026-02-28 | 0 |  | 2026-02-28
3 | [9 empty] | 3 | 3. Mounting Structures | End Clamps | 200 | 12.52 | 2504 |  |  | 2026-02-28 | 11435.9376 |  | 03/31/2026 |  | R/Wp | 2.5357
[10 empty] | 3 | 3. Mounting Structures | [6 empty] | 2026-02-28 | 0 |  | 2026-02-28
3 | [9 empty] | 3 | 3. Mounting Structures | Screws | 200 |  | 0 |  | Joburg Storeroom | 2026-02-28 | 0 |  | 2026-02-28
3 | [9 empty] | 3 | 3. Mounting Structures | Screws | 1000 |  | 0 |  | Joburg Storeroom | 2026-02-28 | 0 |  | 2026-02-28 |  | ACTUAL - Leading Edge Power | Installer Price |  | ACTUAL - Happy Solar | Installer Price |  | ACTUAL - Cosmic Sun | Installer Price
[23 empty] | AC Equipment | 35629.45 |  | AC Equipment | 85150 |  | AC Equipment | 41000
4 | DC Equipment | DC Cable Budget | 1328 |  | 18592 | 2026-04-24 | 69414.8 | 84652.1951 |  | 4 | 4. DC Equipment | DC Cable - Menlo | 2000 | 13.65 | 27300 |  | Allocated from Joburg Streroom | 2026-02-28 | 24114.0498 | 0 | 2026-02-28 | 95836.45 | DC Equipment | 72341.45 |  | DC Equipment | 54990 |  | DC Equipment | 69107.78
4 |  | DC Equipment Budget |  |  | 50822.8 | 2026-03-19 |  |  |  | 4 | 4. DC Equipment | Check DC Cable Stock | [6 empty] | 0 |  |  |  | AC Labour | 41239.56 | 0.31723 | AC Labour | 84500 | 0.65 | AC Labour | 42900 | 0.33
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | DC Labour | 90230.36 | 0.69408 | DC Labour | 106210 | 0.817 | DC Labour | 93600 | 0.72
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Offloading | 12000 |  | Logistics | 114000 |  | Offloading | 7150
4 | [9 empty] | 4 | 4. DC Equipment | Project Kick Off | 68536.45 | 10% | 6853.645 | PO4620-SSP-20260212 - RV Approved | Leading Edge Energy Inv: INV-0186 | 2026-02-28 | 6053.8145 |  | 2026-02-20 |  | Geda Lift | 12397 |  | Forklift | 0 |  | Roof Access | 5775
4 | [9 empty] | 4 | 4. DC Equipment | Site Establishment |  | 15% | 10280.4675 |  | Leading Edge Energy Inv: INV-0187 | 2026-02-28 | 9080.7218 |  | 2026-02-23 |  | Storage | 9450 |  | Geda | 0 |  | Site Container | 6600
4 | [9 empty] | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 13707.29 |  |  | 2026-02-28 | 12107.6291 |  | 2026-03-10 |  | Toilet Rental | 1600 |  | Logistics | 0 |  | HSE Compliance | 4500
4 | [9 empty] | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 17134.1125 |  |  | 2026-03-31 | 15134.5363 |  | 2026-03-27 |  | Travel | 9345.93 |  | HSE | 0 |  | HSE | 0
4 | [9 empty] | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 6853.645 |  |  | 2026-04-30 | 6053.8145 |  | 2026-04-07 |  | COC | 4500 |  | Other | 0 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 6853.645 |  |  | 2026-04-30 | 6053.8145 |  | 2026-04-08 |  | HSE | 6750 |  | Other | 0 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 3426.8225 |  |  | 2026-04-30 | 3026.9073 |  | 2026-04-08 |  | Total | 295483.75 |  | Total | 444850 |  | Total | 270632.78
4 | [9 empty] | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 3426.8225 |  |  | 2026-05-31 | 3026.9073 |  | 2026-05-01 |  | R/Wp | 2.273 |  | R/Wp | 3.4219 |  | R/Wp | 2.0818
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | After Negotiations
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
[23 empty] | ACTUAL - Leading Edge Power | Installer Price |  | ACTUAL - Happy Solar | Installer Price |  | ACTUAL - Cosmic Sun | Installer Price
5 | Monitoring | Smartlogger 3000 |  |  | 26000 | 2026-03-15 | 49000 | 59756.0976 |  | 5 | 5. Monitoring | Smartlogger 3000 - Menlo |  |  | 8598.34 |  | MSA Energy - INV0003648 | 2026-02-28 | 10830.2624 | 0 | 2026-04-24 | 47441.44 | AC Equipment | 33557.29 |  | AC Equipment | 42300 |  | AC Equipment | 41000
5 |  | Comms DB |  |  | 8000 | 2026-03-15 |  |  |  | 5 | 5. Monitoring | CTs |  |  | 15184 | PO4617-SSP-20260211 - RV Approved |  | 2026-02-28 | 19125.4014 |  | 2026-03-30 |  | DC Equipment | 68536.45 |  | DC Equipment | 54989 |  | DC Equipment | 69107.78
5 |  | Revenue Grade Meter |  |  | 15000 | 2026-03-15 |  |  |  | 5 | 5. Monitoring | Revenue Grade Meter |  |  | 15000 |  |  | 2026-02-28 | 18893.6395 |  | 2026-03-30 |  | AC Labour | 39997.83 | 0.30768 | AC Labour | 63375 | 0.4875 | AC Labour | 42900 | 0.33
5 | [9 empty] | 5 | 5. Monitoring | Check meter |  |  | 3600 | PO4051-STLP-20250627 - RV Approved | CBB Inv: CBB-5722 | 2026-02-28 | 4534.4735 |  | 2025-09-11 |  | DC Labour | 79230.36 | 0.60946 | DC Labour | 106210 | 0.817 | DC Labour | 93600 | 0.72
5 | [9 empty] | 5 | 5. Monitoring | Check Meter CT's |  |  | 2870 |  | Accuenergy Inv: ASAI-006974 | 2026-02-28 | 3614.983 |  | 2026-01-07 |  | Offloading | 12000 |  | Logistics | 62300 |  | Offloading | 7150
[10 empty] | 5 | 5. Monitoring | Lithium Battery |  |  | 975 |  | Red Pole:SO-35689 | 2026-02-28 | 1228.0866 |  | 2025-08-30 |  | Geda Lift | 6198.5 |  | Forklift | 0 |  | Roof Access | 1650
5 | [9 empty] | 5 | 5. Monitoring | Power Supply |  |  | 1214.1 |  | current Automation Inv: SOQ324142 | 2026-02-28 | 1529.2512 |  | 2025-09-10 |  | Storage | 9450 |  | Geda | 0 |  | Site Container | 6600
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0 |  |  |  | Toilet Rental | 1600 |  | Logistics | 0 |  | HSE Compliance | 4500
[23 empty] | Travel | 9345.93 |  | HSE | 0 |  | HSE | 0
6 | AC Equipment | AC Equipment Budget |  |  | 198443.487 | 2026-03-15 | 198443.487 | 200154.3824 |  | 6 | 6. AC Equipment | [7 empty] | 0 | 0 |  | 58297.93 | COC | 4500 |  | Other | 0 |  | Other | 0
6 | [9 empty] | 6 | 6. AC Equipment | Comms DB |  |  | 24740.64 |  | Switchboard Inv: 2-SOI002868 | 2026-02-28 | 84942.0815 |  | 2026-03-30 |  | HSE | 6750 |  | Other | 0 |  | Other | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0 |  |  |  | Total | 271166.36 |  | Total | 329174 |  | Total | 266507.78
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0 |  |  |  | R/Wp | 2.0859 |  | R/Wp | 2.5321 |  | R/Wp | 2.0501
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | Project Kick Off | 33557.29 | 10% | 3355.729 | PO4620-SSP-20260212 - RV Approved | Leading Edge Energy Inv: INV-0186 | 2026-02-28 | 11521.2301 |  | 2026-02-20
6 | [9 empty] | 6 | 6. AC Equipment | Site Establishment |  | 15% | 5033.5935 |  | Leading Edge Energy Inv: INV-0187 | 2026-02-28 | 17281.8451 |  | 2026-02-23
6 | [9 empty] | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 6711.458 |  |  | 2026-02-28 | 23042.4602 |  | 2026-03-10
6 | [9 empty] | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 8389.3225 |  |  | 2026-03-31 | 28803.0752 |  | 2026-03-27
6 | [9 empty] | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 3355.729 |  |  | 2026-04-30 | 11521.2301 |  | 2026-04-07
6 | [9 empty] | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 3355.729 |  |  | 2026-04-30 | 11521.2301 |  | 2026-04-08
6 | [9 empty] | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 1677.8645 |  |  | 2026-04-30 | 5760.615 |  | 2026-04-08
6 | [9 empty] | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 1677.8645 |  |  | 2026-05-31 | 5760.615 |  | 2026-05-01
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | Check Meter |  |  | 4000 | 2026-03-10 | 4000 | 4494.382 |  | 8 | 8. Product Add On | Check meter |  |  | 3600 | PO4051-STLP-20250627 - RV Approved | CBB Inv: CBB-5722 | 2026-02-28 | 4494.382 | 0 | 2025-09-11 | 3600
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 32490 | 2026-03-10 | 108300 | 127411.7647 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0 |  | 119228.19
9 |  | DC Installation Budget |  |  | 75810 | 2026-03-26 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 119228.19 | 10% | 11922.819 | PO4620-SSP-20260212 - RV Approved | Leading Edge Energy Inv: INV-0186 | 2026-02-28 | 12741.1765 |  | 2026-02-20
9 | [9 empty] | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 17884.2285 |  | Leading Edge Energy Inv: INV-0187 | 2026-02-28 | 19111.7647 |  | 2026-02-23
9 | [9 empty] | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 23845.638 |  |  | 2026-02-28 | 25482.3529 |  | 2026-03-10
9 | [9 empty] | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 29807.0475 |  |  | 2026-03-31 | 31852.9412 |  | 2026-03-27
9 | [9 empty] | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 11922.819 |  |  | 2026-04-30 | 12741.1765 |  | 2026-04-07
9 | [9 empty] | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 11922.819 |  |  | 2026-04-30 | 12741.1765 |  | 2026-04-08
9 | [9 empty] | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 5961.4095 |  |  | 2026-04-30 | 6370.5882 |  | 2026-04-08
9 | [9 empty] | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 5961.4095 |  |  | 2026-05-31 | 6370.5882 |  | 2026-05-01
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2026-03-10 | 59041.9 | 69461.0588 |  | 10 | 10. Site Logistics | [7 empty] | 0 | 0 |  | 49844.4325
10 |  | Scaffolding |  |  | 21741.9 | 2026-03-10 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Security |  |  | 28800 | 2026-03-10 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 0 | 2026-03-10 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | Project Kick Off | 49844.43 | 10% | 4984.43 | PO4620-SSP-20260212 - RV Approved | Leading Edge Energy Inv: INV-0186 | 2026-02-28 | 6946.0874 |  | 2026-02-20
10 | [9 empty] | 10 | 10. Site Logistics | Site Establishment |  | 15% | 7476.68 |  | Leading Edge Energy Inv: INV-0187 | 2026-02-28 | 10419.1799 |  | 2026-02-23
10 | [9 empty] | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 9968.886 |  |  | 2026-02-28 | 13892.2111 |  | 2026-03-10
10 | [9 empty] | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 12461.1075 |  |  | 2026-03-31 | 17365.2638 |  | 2026-03-27
10 | [9 empty] | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 4984.443 |  |  | 2026-04-30 | 6946.1055 |  | 2026-04-07
10 | [9 empty] | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 4984.443 |  |  | 2026-04-30 | 6946.1055 |  | 2026-04-08
10 | [9 empty] | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 2492.2215 |  |  | 2026-04-30 | 3473.0528 |  | 2026-04-08
10 | [9 empty] | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 2492.2215 |  |  | 2026-05-31 | 3473.0528 |  | 2026-05-01
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2026-03-30 | 89000 | 104705.8824 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 12577.5 |  |  | 2026-04-30 | 14980.4464 | 0 | 2026-04-14 | 87910.48
11 |  | Structural sign off |  |  | 18000 | 2026-03-30 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 7690.9 |  | L&B Consulting: Inv 1701 | 2026-01-31 | 9160.2556 |  | 2024-08-22
11 |  | Scada for CoCT |  |  | 60000 | 2026-03-30 |  |  |  | 11 | 11. Due Dilligence | Scada for CoCT |  |  | 50000 | PO4627-SSP-20260217 - RV Approved | Rubicon - INVRED-0139914 | 2026-02-28 | 59552.5598 |  | 2026-03-30
11 | [9 empty] | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 |  |  | 2026-03-31 | 7146.3072 |  | 2026-04-30
[10 empty] | 11 | 11. Due Dilligence | Roof inspection |  |  | 9900 |  | HappySolar Inv: 0346 | 2026-01-31 | 11791.4068 |  | 2025-12-24
11 | [9 empty] | 11 | 11. Due Dilligence | Roof inspection |  |  | 1742.08 |  | Leading Edge INV0171 | 2026-01-31 | 2074.9065 |  | 2025-11-28
12 | BDP Commission | PD Fee |  |  | 0 |  | 0 | 0 |  | 12 | 12. BDP Commission | PD Fee |  |  | 0 | [6 empty] | 0
12 | BDP Commission | [8 empty] | 12 | 12. BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 13718.459 | 2026-04-15 | 90875.739 | 106912.6341 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 18015.381 |  |  | 2026-04-30 | 106912.6341 | 0 | 2026-04-30 | 18015.381
13 |  | Management |  |  | 9600 | 2026-03-11 |  |  |  | 13 | 13. Engineering | Management | [6 empty] | 0
13 |  | Project manager |  |  | 32640 | 2026-03-11 |  |  |  | 13 | 13. Engineering | Project manager | [6 empty] | 0
13 |  | Planner time |  |  | 12480 | 2026-03-11 |  |  |  | 13 | 13. Engineering | Planner time | [6 empty] | 0
13 |  | De Snagging |  |  | 22437.28 | 2026-03-11 |  |  |  | 13 | 13. Engineering | De Snagging | [6 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 2100 | 2026-04-15 | 2100 | 2470.5882 |  | 14 | 14. General Expenses | Travel |  |  | 525 |  |  | 2026-02-28 | 617.6471 | 0 | 2026-03-07 | 2100
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 525 |  |  | 2026-03-31 | 617.6471 |  | 2026-04-07
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 525 |  |  | 2026-04-30 | 617.6471 |  | 2026-05-07
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 525 |  |  | 2026-05-31 | 617.6471 |  | 2026-06-07
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | [8 empty] | 0 |  | 0
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
| Panel Procurement Budget | 370794.53 |  | 452188.4512
| Inverter Procurement Budget | 95000 |  | 115853.6585 | [14 empty] | 1399380.6072
| Mounting Structure Budget | 58482 |  | 71319.5122
| DC Equipment Budget | 69414.8 |  | 84652.1951
| AC Equipment Budget | 198443.487 |  | 200154.3824
| Monitoring Budget | 49000 |  | 59756.0976
| Optional Extras Budget | 0 |  | 0
| MV Equipment Budget | 0 |  | 0
| ADD ON | 4000 |  | 4494.382
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 32490 |  | 38223.5294
| DC Installer Budget | 75810 |  | 89188.2353
| In-House Expense Budget | 90875.739 |  | 106912.6341
| Compliance Budget | 89000 |  | 104705.8824
| Offloading Budget | 8500 |  | 10000
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 0 |  | 0
| On Site Security | 28800 |  | 33882.3529
| Roof Access Budget for Installers | 21741.9 |  | 25578.7059
| EPC Management Fee | 0 |  | 0
| ADD ON | 0 |  | 0
Expenses
| Total EE Expense Budget | 2100 |  | 2470.5882

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW |  |  | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 1441230.4772 |  | 1399380.6092 |  |  |  | Start Date |  |  | 1399380.6072 | 827940.6935 | 897424.4234 | 544093.0425
2 | Planned Expenditure | 1194452.4559 |  | 827940.6935 | VO PM LIMIT | CURRENT VO Total
3 | Planned Profit | 246778.0213 |  | 571439.9158 | 12338.9011 | 0 |  | End Date - PC
4 | Planned Margin | 17.12% |  | 40.84%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Acceptance and Initial Deposit |  | 50% | 699690.3046 |  | 2026-01-31 | 004942 | 2026-02-13 | 2026-02-27 | [5 empty] | 1900-01-06
2 | Delivery of Panels |  | 25% | 349845.1523 |  | 2026-03-03 |  |  | 2026-03-03
3 | Delivery of Inverters |  | 10% | 139938.0609 |  | 2026-03-03 |  |  | 2026-03-03
4 | Practical Completion |  | 10% | 139938.0609 |  | 2026-04-06 |  |  | 2026-04-07
5 | Handover |  | 5% | 69969.0305 |  | 2026-04-16 |  |  | 2026-04-14
6 |  |  | 0% |  |  | 2026-04-16 |  |  | 2026-04-14
7 | - |  | 0% | 0
|  |  | 100% | 1399380.6092
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 489783.2132
2 | Delivery of Panels |  | 30% | 419814.1828
3 | Delivery of Inverters |  | 20% | 279876.1218
4 | Practical Completion |  | 10% | 139938.0609
5 | Handover |  | 5% | 69969.0305
| Total |  | 100% | 1399380.6092
|  |  | 100% | 1399380.6092
Formulas:
PLANNED PAYMENT DATE = [PLANNED PAYMENT DATE, row above]
PAYMENT RECEIVED DATE = [PAYMENT RECEIVED DATE, row above]
Note on R14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Thami Cambalele please invoice these for us

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from Costed
EXPENDITURE |  | 1194452.4559 |  | 827940.6935 | 366511.7625
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 370794.53 |  | 261180 | 109614.53
2 | 2. Inverters | 95000 |  | 68870.35 | 26129.65
3 | 3. Mounting Structures | 58482 |  | 15616.04 | 42865.96
4 | 4. DC Equipment | 69414.8 |  | 95836.45 | -26421.65
5 | 5. Monitoring | 49000 |  | 47441.44 | 1558.56
6 | 6. AC Equipment | 198443.487 |  | 58297.93 | 140145.557 | Check with Natasha reduction of price
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 4000 |  | 3600 | 400
9 | 9. AC & DC installation | 108300 |  | 119228.19 | -10928.19
10 | 10. Site Logistics | 59041.9 |  | 49844.4325 | 9197.4675
11 | 11. Due Dilligence | 89000 |  | 87910.48 | 1089.52
12 | 12. BDP Commission | 0 |  | 0 | 0
13 | 13. Engineering | 90875.739 |  | 18015.381 | 72860.358
14 | 14. General Expenses | 2100 |  | 2100 | 0
15 | 15. Service Add On | 0 |  | 0 | 0
| check: | 0 | #REF! | 0

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-11-10 to 2031-05-05
PLANNED |  | CHECK | CHECK
| Planned Revenue | 1441230.4772 | 1399380.6092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 699690.3046 | 0 | 0 | 0 | 0 | 489783.2132 | 0 | 0 | 0 | 0 | 139938.0609 | 69969.0305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 699690.3046 | 699690.3046 | 699690.3046 | 699690.3046 | 699690.3046 | 1189473.5178 | 1189473.5178 | 1189473.5178 | 1189473.5178 | 1189473.5178 | 1329411.5788 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092
| Planned Expenditure | 1194452.4559 | 1194452.4559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420132.667 | 50822.8 | 134292 | 89000 | 0 | 15818.459 | 484386.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420132.667 | 470955.467 | 605247.467 | 694247.467 | 694247.467 | 710065.9259 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 699690.3046 | 699690.3046 | 699690.3046 | 699690.3046 | 699690.3046 | 1189473.5178 | 769340.8509 | 718518.0509 | 584226.0509 | 495226.0509 | 635164.1118 | 689314.6833 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533 | 204928.1533
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 1399380.6092 | 1399380.6092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 699690.3046 | 489783.2132 | 0 | 0 | 0 | 0 | 139938.0609 | 69969.0305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 699690.3046 | 1189473.5178 | 1189473.5178 | 1189473.5178 | 1189473.5178 | 1189473.5178 | 1329411.5788 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092 | 1399380.6092
| Actual + Planned Expenditure | 827940.6935 | 799264.6935 | 0 | 0 | 1742.08 | 0 | 0 | 0 | 9900 | 0 | 2870 | 0 | 0 | 0 | 0 | 0 | 27116.623 | 71995.0095 | 525 | 54233.272 | 0 | 67791.59 | 104924.64 | 68316.59 | 12577.5 | 338648.69 | 37573.699 | 525 | 0 | 0 | 0 | 525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 1742.08 | 1742.08 | 1742.08 | 1742.08 | 11642.08 | 11642.08 | 14512.08 | 14512.08 | 14512.08 | 14512.08 | 14512.08 | 14512.08 | 41628.703 | 113623.7125 | 114148.7125 | 168381.9845 | 168381.9845 | 236173.5745 | 341098.2145 | 409414.8045 | 421992.3045 | 760640.9945 | 798214.6935 | 798739.6935 | 798739.6935 | 798739.6935 | 798739.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935 | 799264.6935
| ACTUAL CashFlow |  |  | 0 | 0 | -1742.08 | -1742.08 | -1742.08 | -1742.08 | -11642.08 | -11642.08 | -14512.08 | -14512.08 | -14512.08 | -14512.08 | -14512.08 | -14512.08 | -41628.703 | 586066.5921 | 1075324.8053 | 1021091.5333 | 1021091.5333 | 953299.9433 | 848375.3033 | 919996.7743 | 977388.3047 | 638739.6147 | 601165.9158 | 600640.9158 | 600640.9158 | 600640.9158 | 600640.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158 | 600115.9158
|  | CHECK | CHECK
| Revenue Recognition | 41849.87 | 1399380.6072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23026.569 | 0 | 0 | 0 | 1040518.913 | 0 | 0 | 0 | 0 | 100919.7708 | 0 | 0 | 0 | 215666.5441 | 0 | 0 | 0 | 19248.8104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 1399380.6072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23026.569 | 23026.569 | 23026.569 | 23026.569 | 1063545.4819 | 1063545.4819 | 1063545.4819 | 1063545.4819 | 1063545.4819 | 1164465.2527 | 1164465.2527 | 1164465.2527 | 1164465.2527 | 1380131.7969 | 1380131.7969 | 1380131.7969 | 1380131.7969 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072 | 1399380.6072

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) |  | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | Grand Total
(blank)
1. Panels |  | 0 |  | 452188.4512 |  |  |  | 452188.4512
2. Inverters | 0 | 0 |  | 115853.6585 |  |  |  | 115853.6585
3. Mounting Structures |  | 0 |  | 71319.5122 |  |  |  | 71319.5122
4. DC Equipment |  | 0 |  | 39577.8144 | 27044.6285 | 18029.7523 |  | 84652.1951
5. Monitoring |  | 0 | 10964.5738 | 37903.8873 |  | 10887.6365 |  | 59756.0976
6. AC Equipment |  | 0 |  | 137527.8986 | 62685.8123 | 41790.5415 |  | 242004.2524
8. Product Add On
9. AC & DC installation |  | 0 |  | 31852.9412 | 57335.2941 | 38223.5294 |  | 127411.7647
10. Site Logistics |  | 0 |  | 17365.2647 | 31257.4765 | 20838.3176 |  | 69461.0588
11. Due Dilligence |  |  | 23026.569 | 59552.5598 | 7146.3072 | 14980.4464 |  | 104705.8824
13. Engineering |  | 0 |  |  | 106912.6341 |  |  | 106912.6341
14. General Expenses |  | 0 |  | 617.6471 | 617.6471 | 617.6471 | 617.6471 | 2470.5882
15. Service Add On
12. BDP Commission
7.BESS
Grand Total | 0 | 0 | 33991.1427 | 963759.635 | 292999.7996 | 145367.8708 | 617.6471 | 1436736.0952

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) |  | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | Grand Total
(blank)
1. Panels |  |  |  | 260780 |  |  |  | 260780
2. Inverters |  |  |  | 69000 |  |  |  | 69000
3. Mounting Structures |  |  |  | 29315.1 |  |  |  | 29315.1
4. DC Equipment |  |  |  | 45134.1125 | 30841.4025 | 20560.935 |  | 96536.45
5. Monitoring |  |  | 8659.1 | 29934 |  | 8598.34 |  | 47191.44
6. AC Equipment |  |  |  | 33129.9625 | 15100.7805 | 10067.187 |  | 58297.93
8. Product Add On
9. AC & DC installation |  |  |  | 29807.0475 | 53652.6855 | 35768.457 |  | 119228.19
10. Site Logistics |  |  |  | 12461.1075 | 22429.9935 | 14953.329 |  | 49844.43
11. Due Dilligence |  |  | 19332.98 | 50000 | 6000 | 12577.5 |  | 87910.48
13. Engineering |  |  |  |  | 95172.661 |  |  | 95172.661
14. General Expenses |  |  |  | 525 | 525 | 525 | 525 | 2100
15. Service Add On
12. BDP Commission |  | 0 | [5 empty] | 0
7.BESS
Grand Total |  | 0 | 27992.08 | 560086.33 | 223722.523 | 103050.748 | 525 | 915376.681

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill
2025-12-15 | Builders Break
2025-12-16 | Builders Break
2025-12-17 | Builders Break
2025-12-18 | Builders Break
2025-12-19 | Builders Break
2025-12-20 | Builders Break
2025-12-21 | Builders Break
2025-12-22 | Builders Break
2025-12-23 | Builders Break
2025-12-24 | Builders Break
2025-12-25 | Builders Break
2025-12-26 | Builders Break
2025-12-27 | Builders Break
2025-12-28 | Builders Break
2025-12-29 | Builders Break
2025-12-30 | Builders Break
2025-12-31 | Builders Break
2026-01-01 | Builders Break
2026-01-02 | Builders Break
2026-01-03 | Builders Break
2026-01-04 | Builders Break
2026-01-05 | Builders Break
2026-01-06 | Builders Break
2026-01-07 | Builders Break
2026-01-08 | Builders Break
2026-01-09 | Builders Break
2026-01-10 | Builders Break
2026-01-11 | Builders Break
2026-01-12 | Builders Break
2026-01-13 | Builders Break
2026-01-14 | Builders Break
2026-01-15 | Builders Break
2026-01-16 | Builders Break
2026-03-21 | Human Rights day
2026-04-03 | Good Friday
2026-04-06 | Family Day
2026-04-27 | Freedom Day
2026-05-01 | Workers day
2026-06-16 | Youth Day Holiday
2026-08-09 | Womens Day
2026-08-10 | Womens Day Observerd
2026-09-24 | Heritage Day
2026-12-16 | Day of Reconciliation
2026-12-25 | Christmas Day
2026-12-26 | Day of Goodwill