## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate |  |  |  | FINANCIAL CLOSE CERTIFICATE
Project Name: | Trident Steel GP
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[10 empty] | 2026-03-02 | 2026-03-02
| PROJECT PLAN |  | Trident Steel GP | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) |  | 1875 | [7 empty] | What is required next? Johannes mentioned SSEG approval
| PROJECT DEVELOPER |  | Natasha Watkins-Baker
| PROJECT MANAGERS |  | JT Moorosi
| CONTRACT VALUE |  | 16024328.9397
| Phase: |  | Commercial Close Out
No. | HIGH LEVEL PROGRAMME |  | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Expected Status | Comment
|  |  |  | 53 |  |  | 85 |  | 100% | 100%
1 | Project Initiation |  | 2024-10-29 | 25 | 2024-11-23 | 2024-10-29 | 25 | 2024-11-23 | 100% | 100%
1.1 | Handover |  | 2024-10-29 | 1 | 2024-10-30 | 2024-10-29 | 1 | 2024-10-30 | 100% | 100%
1.2 | Project Introduction |  | 2024-11-08 | 1 | 2024-11-11 | 2024-11-08 | 1 | 2024-11-11 | 100% | 100%
1.3 | HSE |  | 2024-11-08 | 15 | 2024-11-23 | 2024-11-08 | 15 | 2024-11-23 | 100% | 100%
1.4 | Installer Kick Off |  | 2024-11-16 | 1 | 2024-11-18 | 2024-11-16 | 1 | 2024-11-18 | 100% | 100%
1.5 | Project Review |  | 2024-11-16 | 1 | 2024-11-18 | 2024-11-16 | 1 | 2024-11-18 | 100% | 100%
2 | Site Establishment |  | 2025-01-06 | 8 | 2025-01-14 | 2025-01-06 | 36 | 2025-02-11 | 100% | 100%
2.1 | TSS - Roof Assessment |  | 2025-01-06 | 1 | 2025-01-07 | 2025-01-06 | 1 | 2025-01-07 | 100% | 100% |  | 134
2.2 | CPD1 - Roof Assessment |  | 2025-01-13 | 1 | 2025-01-14 | 2025-02-10 | 1 | 2025-02-11 | 100% | 100% |  | 139
3 | Roof Replacement - Paul |  | 2024-11-11 | 46 | 2024-12-27 | 2024-11-11 | 95 | 2025-02-14 | 100% | 100% |  | 26.8
3.1 | Activity Start Date |  | 2024-11-11 | 1 | 2024-11-12 | 2024-11-11 | 1 | 2024-11-12 | 100% | 100%
3.2 | First Phase | 3. Construction | 2024-11-12 | 15 | 2024-12-03 | 2024-11-12 | 15 | 2024-12-03 | 100% | 100% |  | 69.9627
3.3 | Second Phase |  | 2024-12-03 | 15 | 2024-12-27 | 2024-12-03 | 50 | 2025-02-14 | 100% | 100%
4 | AC Installation |  | 2025-01-09 | 1 | 2025-01-10 | 2024-12-12 | 118 | 2025-04-09 | 100% | 100%
4.1 | Inverters delivered - TSS & CPD |  | 2025-01-09 | 1 | 2025-01-10 | 2025-02-04 | 1 | 2025-02-05 | 100% | 100%
4.2 | Steel Structure - TSS |  |  |  |  | 2025-01-20 | 35 | 2025-03-10 | 100% | 100%
4.3 | Steel Structure - CPD |  |  |  |  | 2025-01-20 | 42 | 2025-03-19 | 100% | 100%
4.4 | Mounting Inverters - TSS |  |  |  |  | 2025-03-15 | 5 | 2025-03-21 | 100% | 100%
4.5 | Mounting Inverters - CPD1 |  |  |  |  | 2025-03-24 | 6 | 2025-04-01 | 100% | 100%
4.6 | Mounting Cable Trays - TSS |  |  |  |  | 2025-03-21 | 2 | 2025-03-25 | 100% | 100%
4.7 | Mounting Cable Trays - CPD |  |  |  |  | 2025-04-01 | 4 | 2025-04-07 | 100% | 100%
4.8 | Solar DB Lead Time - TSS & CPD |  |  |  |  | 2024-12-12 | 46 | 2025-02-19 | 100% | 100%
4.9 | Installing Solar DB - TSS |  |  |  |  | 2025-02-19 | 2 | 2025-02-21 | 100% | 100%
4.10 | Installing Solar DB - CPD |  |  |  |  | 2025-02-19 | 2 | 2025-02-21 | 100% | 100%
4.11 | AC Cabling (DB to Inverter) - TSS |  |  |  |  | 2025-03-25 | 4 | 2025-03-31 | 100% | 100%
4.12 | AC Cabling (DB to Inverter) - CPD |  |  |  |  | 2025-04-04 | 3 | 2025-04-09 | 100% | 100%
4.13 | AC Cabling (DB to Tie In) - TSS |  |  |  |  | 2025-02-22 | 12 | 2025-03-11 | 100% | 100%
4.14 | AC Cabling (DB to Tie In) - CPD |  |  |  |  | 2025-02-22 | 2 | 2025-02-25 | 100% | 100%
4.15 | Tie In Breaker Installation - TSS |  |  |  |  | 2025-02-22 | 11 | 2025-03-10 | 100% | 100%
4.16 | Tie In Breaker Installation - CPD |  |  |  |  | 2025-02-22 | 1 | 2025-02-22 | 100% | 100%
4.17 | AC Commissioning - TSS |  |  |  |  | 2025-03-11 | 4 | 2025-03-17 | 100% | 100%
4.18 | AC Commissioning - CPD |  |  |  |  | 2025-02-25 | 10 | 2025-03-11 | 100% | 100%
5 | DC Works - TSS |  | 2025-01-06 | 49 | 2025-02-24 | 2025-01-14 | 64 | 2025-03-19 | 100% | 100%
5.1 | Mounting Structure Delivered |  | 2025-01-06 | 1 | 2025-01-07 | 2025-01-14 | 1 | 2025-01-15 | 100% | 100% | Optimiser Delivery early Dec
5.2 | DC Cable Delivered |  | 2025-01-06 | 35 | 2025-02-24 | 2025-03-06 | 1 | 2025-03-07 | 100% | 100%
5.3 | TSS - Module Delivery |  | 2025-01-14 | 1 | 2025-01-15 | 2025-01-28 | 3 | 2025-01-31 | 100% | 100%
5.4 | TSS - Mounting Structure installation |  | 2025-01-06 | 20 | 2025-02-03 | 2025-01-15 | 4 | 2025-01-21 | 100% | 100%
5.5 | TSS - Module Lifting |  | 2025-01-27 | 7 | 2025-02-05 | 2025-01-29 | 35 | 2025-03-19 | 100% | 100%
5.6 | TSS - Module Mounting |  | 2025-01-06 | 35 | 2025-02-24 | 2025-01-29 | 35 | 2025-03-19 | 100% | 100% | 1400 on 11 Mar of 1400
6 | DC Works - CPD1 |  | #REF! | #REF! | #REF! | 2025-01-14 | 87 | 2025-04-11 | 100% | 100%
6.1 | Mounting Structure Delivered |  | #REF! | 1 | #REF! | 2025-01-14 | 1 | 2025-01-15 | 100% | 100%
6.2 | DC Cable Delivered |  | #REF! | 35 | #REF! | 2025-03-06 | 1 | 2025-03-07 | 100% | 100%
6.3 | CPD1 - Module Delivery |  | 2025-01-21 | 1 | 2025-01-22 | 2025-01-28 | 3 | 2025-01-31 | 100% | 100%
6.4 | CPD1 - Mounting Structure installation |  | 2024-12-03 | 45 | 2025-02-07 | 2025-02-07 | 11 | 2025-02-24 | 100% | 100%
6.5 | CPD1 - Module Lifting |  | 2025-01-14 | 10 | 2025-01-28 | 2025-02-20 | 36 | 2025-04-11 | 100% | 100%
6.6 | CPD1 - Module Mounting |  | 2025-01-14 | 45 | 2025-03-18 | 2025-02-20 | 36 | 2025-04-11 | 100% | 100% | 1483 on 17 Mar of 1800
7 | Extras |  | 0 | 0 | 0 | 2025-02-17 | 62 | 2025-04-20 | 100% | 100%
7.1 | TSS - Fixed Anchor Point & Lifeline Approvals |  |  |  |  | 2025-02-27 | 1 | 2025-02-28 | 100% | 100% |  | 1
7.2 | TSS - Fixed Anchor Point & Lifeline Installation |  |  |  |  | 2025-08-13 | 5 | 2025-08-20 | 100% | 100% | Awaiting Mauro to feedback, contact he said he'll advise tomorrow latest - 03/07/25 | 1
7.3 | TSS - Fixed Anchor Point & Lifeline Sign Off |  |  |  |  | 2025-08-20 | 1 | 2025-08-21 | 100% | 100% |  | 1
7.4 | CPD1 - Fixed Anchor Point & Lifeline Approvals |  |  |  |  | 2025-02-27 | 1 | 2025-02-28 | 100% | 100% |  | 1
7.5 | CPD1 - Fixed Anchor Point & Lifeline Installation |  |  |  |  | 2025-08-20 | 5 | 2025-08-27 | 100% | 100% | Awaiting Mauro to feedback, contact he said he'll advise tomorrow latest - 03/07/25 | 1
7.6 | CPD1 - Fixed Anchor Point & Lifeline Sign Off |  |  |  |  | 2025-08-27 | 1 | 2025-08-28 | 100% | 100% |  | 1
7.7 | TSS - Walkway Installation |  |  |  |  | 2025-04-11 | 10 | 2025-07-04 | 100% | 100% | Pending sign off, works completed. | 1
7.8 | CPD1 - Walkway Installation |  |  |  |  | 2025-04-11 | 10 | 2025-07-04 | 100% | 100% | Pending sign off, works completed. | 1
7.9 | TSS - Waterpoint Installation |  |  |  |  | 2025-07-23 | 2 | 2025-07-25 | 100% | 100% | Awaiting LOG for the Subby to submit for approval then commence works | 1
7.10 | CPD1 - Waterpoint Installation |  |  |  |  | 2025-08-15 | 5 | 2025-08-22 | 100% | 100% | Awaiting LOG for the Subby to submit for approval then commence works | 1
7.11 | MV Metering |  |  |  |  | 2025-04-18 | 7 | 2025-04-25 | 100% | 100%
8 | Commissioning |  | #REF! | #REF! | #REF! | 2025-03-19 | 113 | 2025-07-10 | 100% | 100%
8.1 | TSS - Practical Completion |  | 2025-02-24 | 3 | 2025-02-27 | 2025-03-19 | 4 | 2025-03-25 | 100% | 100%
8.2 | TSS - Commissioning |  | 2025-02-27 | 1 | 2025-02-28 | 2025-03-25 | 5 | 2025-04-01 | 100% | 100%
8.3 | CPD1 - Commissioning |  | #REF! | 3 | #REF! | 2025-04-09 | 4 | 2025-04-15 | 100% | 100%
8.4 | CPD1 - Practical Completion |  | #REF! | 1 | #REF! | 2025-04-15 | 62 | 2025-07-10 | 100% | 100%
9 | QA Inspections |  | #REF! | #REF! | #REF! | 2025-04-02 | 113 | 2025-07-24 | 100% | 100%
9.1 | TSS - Red-Team Inspection & Snag Completion |  | 2025-02-24 | 15 | 2025-03-17 | 2025-04-02 | 15 | 2025-04-23 | 100% | 100%
9.2 | CPD1 - Red-Team Inspection & Snag Completion |  | #REF! | 15 | #REF! | 2025-07-10 | 10 | 2025-07-24 | 100% | 100%
10 | Project Closure |  | #REF! | #REF! | #REF! | 2025-03-19 | 190 | 2025-09-25 | 100% | 100%
10.1 | Equipment serial numbers |  | #REF! | 2 | #REF! | 2025-03-19 | 2 | 2025-03-21 | 100% | 100%
10.2 | Client Snag completion |  | #REF! | 10 | #REF! | 2025-07-10 | 35 | 2025-08-28 | 100% | 100%
10.3 | System Performance Monitoring |  | #REF! | 10 | #REF! | 2025-07-10 | 30 | 2025-08-21 | 100% | 100%
10.4 | Handover documentation |  | #REF! | 10 | #REF! | 2025-07-10 | 55 | 2025-09-25 | 100% | 100%
10.5 | Handover to Client |  | #REF! | 1 | #REF! | 2025-08-18 | 20 | 2025-09-15 | 100% | 100%
10.6 | Handover to Matriarch |  | #REF! | 5 | #REF! | 2025-07-24 | 45 | 2025-09-25 | 100% | 100%
Formulas:
Planned Start = MIN([Planned Start, row below]:E16)
Planned Start = [Planned Start, row above]
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = [Actual Start, row above]
Actual End = MAX([Actual End, row below]:K16)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C14)

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | PLANNED |  | ACTUAL |  | FINANCIAL REVIEW | TIMELINE REVIEW
1 | Planned Revenue | 16024328.9397 |  | 16024328.9397 |  | 16024328.9397 | Start Date
2 | Planned Expenditure | 13780793.7463 |  | 14799893.8717 |  | 15134526.9749 | 2025-01-06
3 | Planned Profit | 2243535.1934 |  | 1224435.0679 |  | 889801.9648 | End Date - PC
4 | Planned Margin | 14% |  | 7.641% |  | 5.553% | 2025-05-21
CONTRACT
No. | PAYMENT MILESTONE TSS |  | % | VALUE | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Acceptance and initial Deposit |  | 35% | 2804257.5644 | 2024-11-18 | 004644 | 2024-11-13 | 2024-12-17
2 | Delivery of Inverters |  | 20% | 1602432.894 | 2024-11-15 | 004648 | 2025-02-07 | 2025-02-14 | Receipt of solar panels on site
3 | Delivery of Panels |  | 30% | 2403649.341 | 2025-02-05 | 004657 | 2025-01-30 | 2025-02-05 | Receipt of inverters of site
4 | Practical Completion |  | 10% | 801216.447 | 2025-04-25 | 004697 | 2025-02-27 | 2025-04-25 | All provisional test successfully finalised
5 | Handover Partial |  | 2.5% | 200304.1117 | 2026-02-25 | 004697 | 2025-02-27 | 2026-02-25 | All documentation provided
6 | Handover Partial |  | 2.5% | 200304.1117 | 2026-02-28 | 004697 | 2025-02-27 | 2026-08-31
7 | - |  | 0% | 0
No. | PAYMENT MILESTONE CDP |  | % | VALUE | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Acceptance and initial Deposit |  | 35% | 2804257.5644 | 2024-11-18 | 004631 | 2024-11-13 | 2024-12-17
2 | Delivery of Inverters |  | 20% | 1602432.894 | 2024-11-18 | 004649 | 2025-02-07 | 2025-02-14 | Receipt of solar panels on site
3 | Delivery of Panels |  | 30% | 2403649.341 | 2025-02-05 | 004658 | 2025-01-30 | 2025-02-05 | Receipt of inverters of site
4 | Practical Completion |  | 10% | 801216.447 | 2025-03-03 | 004696 | 2025-02-27 | 2025-11-03 | All provisional test successfully finalised
5 | Handover |  | 2.5% | 200304.1117 | 2026-02-25 | 004696 | 2025-02-27 | 2026-02-25 | All documentation provided
6 | Handover Partial |  | 2.5% | 200304.1117 | 2026-02-28 | 004696 | 2025-02-27 | 2026-08-31
7 | - |  | 0% | 0
|  |  | 100% | 16024328.9397
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 5608515.1289
2 | Delivery of Panels |  | 30% | 4807298.6819
3 | Delivery of Inverters |  | 20% | 3204865.7879
4 | Practical Completion |  | 10% | 1602432.894
5 | Handover |  | 5% | 801216.447
| Total |  | 100% | 16024328.9397
|  |  | 100% | 16024328.9397
Formulas:
PLANNED PAYMENT DATE = [PAYMENT RECEIVED DATE]
PAYMENT RECEIVED DATE = [TIMELINE REVIEW]+7
Note on P25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Johannes Potgieter was this received

## Data (hidden)
Public holidays |  | Drop down list
2024-01-01 | New Years Day | Approved
2024-03-21 | Human Rights day | Pending
2024-03-29 | Good Friday | Declined
2024-04-01 | Family Day | Abanded
2024-05-01 | Workers day
2024-06-17 | Youth Day Holiday
2024-08-09 | Womens Day
2024-09-24 | Heritage Day
2024-12-16 | Day of Reconciliation
2024-12-25 | Christmas Day
2024-12-26 | Day of Goodwill |  | Manual dates

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  |  | COSTED |  | PLANNED |  | ACTUAL | Difference from costed | Difference from planned
| EXPENDITURE |  | 13780793.7463 |  | 15134526.9749 |  | 14799893.8717 | -1019100.1255 | 334633.1032
| No. | Item | Costed Expenditure |  | Planned Expenditure |  | Actual Expenditure | Saving / Overrun | Saving / Overrun | Comments on variations from planned expenditure
| 1 | Panels | 4370925.632 |  | 4254751.8 |  | 4255658.94 | 115266.692 | -907.14
| 2 | Inverters | 3000818 |  | 3103440 |  | 3159240 | -158422 | -55800
| 3 | Mounting Structures | 656096 |  | 346295 |  | 385343 | 270753 | -39048
| 4 | DC Equipment | 1512771.2 |  | 1835752.5 |  | 1702752.5 | -189981.3 | 133000
| 5 | Monitoring | 550800 |  | 403365.26 |  | 419582.98 | 131217.02 | -16217.72
| 6 | AC Equipment | 978811.0178 |  | 1388068.87 |  | 1529166.87 | -550355.8522 | -141098
| 7 | Battery Systems | 0 |  | 0 |  | 0 | 0 | 0
| 8 | Product Add On | 608000 |  | 890823.0032 |  | 492321.82 | 115678.18 | 398501.1832
| 9 | AC & DC Installation | 1003132 |  | 2052500 |  | 2052500 | -1049368 | 0
| 10 | Site Logistics | 234820.18 |  | 462630 |  | 424330 | -189509.82 | 38300
| 11 | Due Dilligence | 167000 |  | 161100 |  | 120447.39 | 46552.61 | 40652.61
| 12 | BDP Commission | 0 |  | 0 |  | 0 | 0 | 0
| 13 | Engineering | 664894.7165 |  | 200304.1117 |  | 165600.0017 | 499294.7147 | 34704.11 | RV: Matriarch defects percentage 1.25%
| 14 | General Expenses | 32725 |  | 35496.43 |  | 37052.37 | -4327.37 | -1555.94
| 15 | Service Add On | 0 |  | 0 |  | 55898 | -55898 | -55898
|  | check: | 0 | #REF! | 0 | #REF! | 0
Copy amounts in column H and paste as values at Project review.

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 13780793.7463 | 16024328.9397 |  | ACTUAL EXPENDITURE BREAKDOWN | [6 empty] | FINANCE ONLY |  |  |  |  | 14799893.8717
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | Project Related date | Total COS | ERROR on REV |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS | COMMENTS
1 | Panels | Jinko 580W | 3232 | 1333.826 | 4310925.632 | 2024-12-11 | 4370925.632 | 4699920.0344 |  | 1 | 1. Panels | Jinko 585W - TSS (1400) | 1602 | 1327.95 | 2127375.9 |  | Menlo Inv IN0002290 | 2024-12-31 | 2349960.0172 | 0 | 2025-02-07 | 4255658.94 | Menlo quote | 19
1 | [9 empty] | 1 | 1. Panels | Jinko 585W - CPD1 (1804) | 1602 |  | 2127375.9 |  | Menlo Inv IN0002363 | 2024-12-31 | 2349960.0172 |  | 2025-02-20 |  |  | BUDGET - Solar | Installer Allocation
1 |  | Module delivery to site |  |  | 60000 | 2024-12-11 |  |  |  | 1 | 1. Panels | [7 empty] | 0 |  |  |  |  | AC Equipment | 1505863.1043
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  |  | DC Equipment | 955571.2
1 | [9 empty] | 1 | 1. Panels | Storage |  |  | 685.71 |  | Supply Chain - Inv SCO05052 | 2025-05-31 | 0 |  | 2025-06-27 |  | TC: Added cost | AC Labour | 1074640 | 7.676
[10 empty] | 1 | 1. Panels | [9 empty] | 2025-09-30
1 | [9 empty] | 1 | 1. Panels |  |  |  | 221.43 |  | Supply Chain - SCO05164 | 2025-07-31 | 0 |  | 2025-08-30 |  |  | DC Labour | 468640 | 3.3474
[24 empty] | Offloading | 8500
2 | Inverters | SolarEdge 100kW | 18 | 66161 | 1190898 | 2024-12-11 | 3000818 | 3226686.0215 |  | 2 | 2. Inverters | SolarEdge 100kW | 18 | 18950 | 341100 | PO3553-TSD-20250121 - RV Approved | HERHOLDT'S - INV995250 | 2025-02-28 | 354646.0063 | 0 | 2025-03-28 | 3159240 | Herholdts quote | Roof Access/Scaffolding | 74707.68
[10 empty] | 2 | 2. Inverters | Solar Edge Synergy unit | 54 | 15710 | 848340 |  | HERHOLDT'S - INV995250 | 2025-02-28 | 882029.8828 |  | 2025-03-28
2 | [9 empty] | 2 | 2. Inverters | S1200 Optimiser - TSS | 825 | 1160 | 957000 | PO3554-TSD-20250121 | HERHOLDT'S - INV987265 | 2025-01-31 | 995005.0662 |  | 2025-02-27 |  |  | Storage | 51892.5
2 |  | S1200 Optimiser | 1616 | 1120 | 1809920 | 2024-12-11 |  |  |  | 2 | 2. Inverters | S1200 Optimiser - CPD1 | 825 | 1160 | 957000 |  | HERHOLDT'S - INV987265 | 2025-01-31 | 995005.0662 |  | 2025-02-27 |  | Delivery early Dec Herholdts quote | Telehandler | 32400
[10 empty] | 2 | 2. Inverters | Spare Optimizer 1200W/80V | 60 |  | 55800 | PO4193-TSG-20250804 - RV Approved | Herholdts - INV1113245 | 2025-08-31 | 0 |  | 2025-09-30
2 | [9 empty] | 2 | 2. Inverters |  |  |  | 0 |  |  |  | 0 |  |  |  |  | Other | 0
[24 empty] | Total | 4172214.4843
3 | Mounting Structures | IBR Roof |  |  | 656096 | 2025-02-05 | 656096 | 705479.5699 |  | 3 | 3. Mounting Structures | IBR Roof |  |  | 346295 | PO3465-TRID-20241115 - RV Approved | SCHLETTER - INV1261 | 2025-01-31 | 705479.5699 | 0 | 2025-02-26 | 385343 |  | Less 15% | 3546382.3117 | [SM: Target Installation Price]
3 | [9 empty] | 3 | 3. Mounting Structures | Delivery |  |  | 0 |  |  |  | 0 |  |  |  |  | R/Wp | 1.8914
3 | [9 empty] | 3 | 3. Mounting Structures | MS Top Up - Trunking Incl - Schletter |  |  | 39048 | PO3774-TSG-20250328 - RV Approved | Schletter - INV1643 | 2025-04-30 |  |  | 2025-04-30
3 | [9 empty] | 3 | 3. Mounting Structures | [12 empty] | ACTUAL | Installer Price
[24 empty] | AC Equipment | 1388068.87
4 | DC Equipment | DC Cable | 39800 | 14 | 557200 | 2025-02-13 | 1512771.2 | 1626635.6989 |  | 4 | 4. DC Equipment | DC Cable | 46000 | 13.3 | 611800 |  | Menlo Inv IN0002363 | 2024-12-31 | 542107.7845 | 0.0027792 | 2025-02-20 | 1702752.5 | Menlo quote | DC Equipment | 1090952.5
4 | [9 empty] | 4 | 4. DC Equipment | DC Cable Budget | 10000 | 13.3 | 0 |  |  |  | 0 |  |  |  |  | AC Labour | 633750 | 0.338
4 |  | DC Cable Tray | 270 | 1530 | 413100 | 2025-02-13 |  |  |  | 4 | 4. DC Equipment | Deposit - TSS | 484867.78 | 30% | 145460.334 | PO3527-TSG-20241212 | Cosmic Sun CS_TRS_001 | 2025-01-31 | 290003.5188 |  | 2025-01-09 |  |  | DC Labour | 1418750 | 0.75667
4 | [9 empty] | 4 | 4. DC Equipment | All AC & DC Equipment Onsite |  | 20% | 96973.556 |  | Cosmic Sun CS_TRS_003 | 2025-02-28 | 193335.6792 |  | 2025-02-20 |  |  | Offloading | 39600
4 | [9 empty] | 4 | 4. DC Equipment | Pracitcal Completion - TSS |  | 30% | 145460.334 |  | Cosmic Sun CS_TRS_008 | 2025-03-31 | 128890.4534 |  | 2025-04-10 |  |  | Roof Access/Scaffolding | 194150
4 | [9 empty] | 4 | 4. DC Equipment | Site Fully Commissioned - TSS |  | 15% | 72730.167 |  | Cosmic Sun CS_TRS_009 | 2025-04-30 | 159642.9077 |  | 2025-04-17 |  |  | Trenching | 15000
4 |  | Earth Cable | 39800 | 13.5 | 537300 | 2025-02-13 |  |  |  | 4 | 4. DC Equipment | Retention |  | 5% | 24243.389 |  | Cosmic Sun CS_TRS_013 | 2025-06-30 | 23159.6559 |  | 2025-08-21 |  |  | HSE | 18800
[10 empty] | 4 | 4. DC Equipment | CPD1
[10 empty] | 4 | 4. DC Equipment | Deposit - CPD1 | 606084.72 | 30% | 181825.416 |  | Cosmic Sun CS_TRS_001 | 2025-01-31 |  |  | 2025-01-09
[10 empty] | 4 | 4. DC Equipment | All AC & DC Equipment Onsite |  | 20% | 121216.944 |  | Cosmic Sun CS_TRS_003 | 2025-02-28 |  |  | 2025-02-20
[10 empty] | 4 | 4. DC Equipment | Practical Completion |  | 30% | 181825.416 |  | Cosmic Sun CS_TRS_010 | 2025-04-30 | 173697.4179 |  | 2025-05-08
[10 empty] | 4 | 4. DC Equipment | Site Fully Commissioned |  | 15% | 90912.708 |  | Cosmic Sun CS_TRS_010 | 2025-04-30 | 86848.709 |  | 2025-05-08
4 |  | Earth clamp | 323.2 | 16 | 5171.2 | 2025-02-27 |  |  |  | 4 | 4. DC Equipment | Retention |  | 5% | 30304.236 |  | Cosmic Sun CS_TRS_012 | 2025-06-30 | 28949.5697 |  | 2025-08-21 |  |  | Other | 0
[24 empty] | Total | 4799071.37
5 | Monitoring | SolarEdge Gateway |  |  | 4300 | 2024-12-11 | 550800 | 592258.0645 |  | 5 | 5. Monitoring | SolarEdge Energy Meter | 2 | 1740 | 3480 | PO3553-TSD-20250121 - RV Approved | HERHOLDT'S - INV995250 | 2025-02-28 | 5722.9894 | -0.0025619 | 2025-03-28 | 419582.98 |  | R/Wp | 2.5595
5 |  | Comms DB |  |  | 64000 | 2024-12-11 |  |  |  | 5 | 5. Monitoring | CTs & Router: TSS & CPD - AccuEnergy |  |  | 21463 | PO3565-TSG-20250127 - RV Approved | Accuenergy - Inv ASAI-004650 | 2025-01-31 | 31475.0959 |  | 2025-02-27
5 |  | Fibre run |  |  | 162500 | 2024-12-11 |  |  |  | 5 | 5. Monitoring | Revenue Grade Meter - Techsitter | 2 | 14934 | 29868 |  | Matriarch INV-3710 | 2025-01-31 | 43800.8743 |  | 2025-01-31
5 |  | Generator Integration SEDG |  |  | 250000 | 2024-12-11 |  |  |  | 5 | 5. Monitoring | Fibre - Volkirk Deposit |  |  | 40101 | PO3696-TSG-20250226 - RV Approved | Volkirk Fibre INV0001116 | 2025-02-28 | 62163.262 |  | 2025-03-06 |  |  |  | 4272214.48
[10 empty] | 5 | 5. Monitoring | Fibre - Volkirk - Balance |  |  | 40101 |  | Volkirk Fibre - INV0001138 | 2025-03-31 | 62163.262 |  | 2025-04-03
5 |  | Janitza UMG 604 pro (MV Metering) | 2 |  | 70000 | 2024-12-11 |  |  |  | 5 | 5. Monitoring | Solar Edge PPC-DG |  |  | 61210 | PO3553-TSD-20250121 - RV Approved | HERHOLDT'S - INV995250 | 2025-02-28 | 125742.7913 |  | 2025-03-28
[10 empty] | 5 | 5. Monitoring | 24V PSU |  |  | 1460 | PO3648-TSG-20250211 - RV Approved | Accuenergy - Inv ASAI-004783 | 2025-02-28 | 2401.0243 |  | 2025-03-28
[10 empty] | 5 | 5. Monitoring | Janitza UMG 604 (moved from Trident PE) |  |  | 18571.36 |  | Harmonius Technical Inv: INV21620 | 2025-02-28 | 30541.2922 |  | 2025-02-27
[10 empty] | 5 | 5. Monitoring | Shipping of Janitza |  |  | 559.63 |  | DSV Inv: 180121124 | 2025-03-31 | 0 |  | 2025-04-30
[10 empty] | 5 | 5. Monitoring | Janitza UMG 604 - Harmonious |  |  | 18571.36 | PO3738-TSG-20250312 - RV Approved | Harmonius Technical QU100577 | 2025-03-31 | 0 |  | 2025-03-13
[10 empty] | 5 | 5. Monitoring | Delivery of Janitza |  |  | 559.63 |  | DSV Inv: 180121124 | 2025-05-31 | 822.1799
[10 empty] | 5 | 5. Monitoring | Fibre - Volkirk : Main Sub - Deposit |  |  | 23617.5 | PO3752-TSG-20250317 - RV Approved | Volkirk Properties INV0001127 | 2025-03-31 | 36619.658 |  | 2025-03-28
[10 empty] | 5 | 5. Monitoring | Fibre - Volkirk : Main Sub - Balance |  |  | 23617.5 |  | Volkirk Properties INV0001139 | 2025-03-31 | 36611.078 |  | 2025-04-03
[10 empty] | 5 | 5. Monitoring | SE Hark EMS Package - Herholdts | 1 | 97750 | 97750 | PO3952-TSG-20250523 - RV Approved | Herholdts - INV1071481 | 2025-05-31 | 121579.4487 |  | 2025-06-27
[10 empty] | 5 | 5. Monitoring | Commisioning - Solar Edge Hours | 4 | 5550 | 22200 | PO3861-TSG-20250509 - RV Approved | Herholdts - INV1058643 | 2025-05-31 | 32615.111 |  | 2025-06-27
5 | [9 empty] | 5 | 5. Monitoring | Fiber - Gensets |  |  | 16453 | PO4074-TSG-20250630 - RV Approved | VP Fibre - INV0001201 | 2025-06-30 | 0 |  | 2025-07-11 |  |  |  | -526856.89
6 | AC Equipment | Project Kick Off |  | 10% | 150586.3104 | 2024-12-30 | 978811.0178 | 1619207.6391 |  | 6 | 6. AC Equipment | [7 empty] | 0 | 0.0013183 |  | 1529166.87
6 | [9 empty] | 6 | 6. AC Equipment | DB Board Fast Track Fee |  |  | 14956 | PO3612-TRID-20210131 - RV Approved | CS_TRS_002 | 2025-02-28 | 15836.6428 |  | 2025-02-13
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | VO - AC Cable : Cosmic Sun |  |  | 126142 | PO3675-TSG-20250219 - RV Approved | Cosmic Sun CS_TRS_005 | 2025-02-28 | 93925.8134 |  | 2025-02-20
6 | [9 empty] | 6 | 6. AC Equipment | Deposit - TSS | 616919.5 | 30% | 185075.85 | PO3527-TSG-20241212 | Cosmic Sun CS_TRS_001 | 2025-01-31 | 480584.1506 |  | 2025-01-09
6 | 1505863.1043 | Site Establishment |  | 15% | 225879.4657 | 2025-01-06 |  |  |  | 6 | 6. AC Equipment | All AC & DC Equipment Onsite |  | 20% | 123383.9 |  | Cosmic Sun CS_TRS_003 | 2025-02-28 | 293960.2946 |  | 2025-02-20
6 |  | AC Installation Complete |  | 20% | 301172.6209 | 2024-12-27 |  |  |  | 6 | 6. AC Equipment | Pracitcal Completion - TSS |  | 30% | 185075.85 |  | Cosmic Sun CS_TRS_008 | 2025-03-31 | 195973.5304 |  | 2025-04-10
6 |  | Commissioning Complete |  | 10% | 150586.3104 | #REF! |  |  |  | 6 | 6. AC Equipment | Site Fully Commissioned - TSS |  | 15% | 92537.925 |  | Cosmic Sun CS_TRS_009 | 2025-04-30 | 97986.7652 |  | 2025-04-17
6 |  | Handover Document Complete |  | 5% | 75293.1552 | #REF! |  |  |  | 6 | 6. AC Equipment | Retention |  | 5% | 30845.975 |  | Cosmic Sun CS_TRS_013 | 2025-06-30 | 32662.2551 |  | 2025-08-21
[10 empty] | 6 | 6. AC Equipment | CPD1
[10 empty] | 6 | 6. AC Equipment | Deposit - CPD1 | 771149.37 | 30% | 231344.811 |  | Cosmic Sun CS_TRS_001 | 2025-01-31 |  |  | 2025-01-09
[10 empty] | 6 | 6. AC Equipment | All AC & DC Equipment Onsite |  | 20% | 154229.874 |  | Cosmic Sun CS_TRS_003 | 2025-02-28 |  |  | 2025-02-20
[10 empty] | 6 | 6. AC Equipment | Practical Completion |  | 30% | 231344.811 |  | Cosmic Sun CS_TRS_010 | 2025-04-30 | 244966.9114 |  | 2025-05-08
[10 empty] | 6 | 6. AC Equipment | Site Fully Commissioned |  | 15% | 115672.4055 |  | Cosmic Sun CS_TRS_010 | 2025-04-30 | 122483.4557 |  | 2025-05-08
6 |  | End of Defects Period |  | 5% | 75293.1552 | #REF! |  |  |  | 6 | 6. AC Equipment | Retention |  | 5% | 38557.4685 |  | Cosmic Sun CS_TRS_012 | 2025-06-30 | 40827.8186 |  | 2025-08-21
7 | Battery Systems | [5 empty] | 0 | 0 |  | 7 | Battery Systems | [8 empty] | 0 |  | 0
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
8 | Product Add On | Inverter cages (1 close to TSS transformer, 1 at CPD1) |  |  | 100000 | #REF! | 608000 | 645840.4075 |  | 8 | 8. Product Add On | RUT Power Supply - AccuEnergy |  |  | 99 | PO3858-TSG-20250508 | ASAI - 005420 | 2025-05-31 | 132.7062 | 0.0031842 | 2025-06-27 | 492321.82 | Team lost power supply somehow.
8 |  | Permanent anchors and temporary/permanent lifelines |  |  | 250000 | #REF! |  |  |  | 8 | 8. Product Add On | Plug point Fibre and Comms at Sub - Cosmic Sun |  |  | 1500 | PO3939-TSG-20250520 - RV Approved | Cosmic Sun: CS_TRS_011 | 2025-05-31 | 2010.6993 |  | 2025-05-29
8 |  | Walkways | 120 | 750 | 90000 | #REF! |  |  |  | 8 | 8. Product Add On | Permanent Anchor Points - ATS Africa | 171800 | 50% | 85900 | PO3803-TSG-20250414 - RV Approved | ATS AFRICA - INV-0386 | 2025-04-30 | 172789.3022 |  | 2025-05-08
[10 empty] | 8 | 8. Product Add On |  |  | 50% | 85900 |  | ATS AFRICA - INV-0386 | 2025-04-30 | 172789.3022 |  | 2025-06-19
8 |  | Water Points | 4 | 12000 | 48000 | #REF! |  |  |  | 8 | 8. Product Add On | Walkways- Cosmic Sun = 120m |  |  | 16800 | PO3676-TSG-20250219 - RV Approved | Cosmic Sun CS_TRS_006 | 2025-02-28 | 39344.3872 |  | 2025-06-12
8 |  | Cat Ladders | 4 | 30000 | 120000 | #REF! |  |  |  | 8 | 8. Product Add On | Walkways - Onvlee | 21.0526 | 2974.66 | 62467.86 | PO3697-TSG-20250226 - RV Approved | Onvlee PO-3697-TSG-20250226 | 2025-03-31 | 39459.6298 |  | 2025-03-13 |  | Must place order before 25 Nov, delivery must be set for 4 Dec - Cash payment
8 | [9 empty] | 8 | 8. Product Add On | Walkways Fastners | 23 | 94.8 | 2180.4 |  | Onvlee PO-3697-TSG-20250226 | 2025-03-31 | 1377.3127 |  | 2025-03-13
8 | [9 empty] | 8 | 8. Product Add On | Delivery |  |  | 5175 |  | Onvlee PO-3697-TSG-20250226 | 2025-03-31 | 3268.9384 |  | 2025-03-13
8 | [9 empty] | 8 | 8. Product Add On | Cat6 Cable - Cosmic Sun |  |  | 10519 | PO4086-TSG-20250702 - RV Approved | Cosmic Sun CS_TRS_014 | 2025-06-30 | 0 |  | 2025-07-03
8 | [9 empty] | 8 | 8. Product Add On | Lifting & Rigging | [6 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | Additional Courier |  |  | 1100 | PO3923-TSG-20250516 - RV Approved | Supply Chain - INV SCO05026 | 2025-05-31 | 0 |  | 2025-06-19
8 | [9 empty] | 8 | 8. Product Add On | Temp Fence Transport & Labour |  |  | 12000 | PO3552-TRID-20250121 - RV Approved | Supply Chain Optimiser Inv SCO04728 | 2025-01-31 | 8098.8322 |  | 2025-02-20
8 | [9 empty] | 8 | 8. Product Add On | Waterpoints - Deposit | 50% | 47900 | 23950 | PO3621-TSG-20250205 - RV Approved | Plumbryt INV 3621-250314/01 | 2025-03-31 | 0 |  | 2025-03-20
[10 empty] | 8 | 8. Product Add On | Waterpoints - Balance | 50% |  | 23950 |  | Plumbryt INV 3621-250314/01 | 2025-03-31 | 0 |  | 2025-08-07
8 | [9 empty] | 8 | 8. Product Add On | MV Shutdown |  |  | 0 |  |  |  | 0
[10 empty] | 8 | 8. Product Add On | VO - Inverter Stands, Fence works: Cosmic Sun | 60% | 106215.56 | 63729.336 | PO3661-TSG-20250214 - RV Approved | Cosmic Sun CS_TRS_004 | 2025-02-28 | 41161.5916 |  | 2025-02-20
[10 empty] | 8 | 8. Product Add On |  | 40% |  | 42486.224 |  | Cosmic Sun CS_TRS_007 | 2025-03-31 | 26939.0917 |  | 2025-04-03
[10 empty] | 8 | 8. Product Add On | MV Metering - Malaysian Swittchgear | 75% | 44655 | 33491.25 | PO3725-TSG-20250306 - RV Approved | Malaysian Inv SJ-11558 | 2025-04-30 | 39856.7327 |  | 2025-04-10
[10 empty] | 8 | 8. Product Add On |  | 25% |  | 11163.75 |  | Malaysian Inv SJ-11558 | 2025-04-30 | 13285.5776 |  | 2025-05-15
[10 empty] | 8 | 8. Product Add On | Domestic Transport |  |  | 3500 | PO3865-TSG-20250509 - RV Approved | Supply Chain - INV SCO05008 | 2025-05-31 | 76733.9118 |  | 2025-06-12
[10 empty] | 8 | 8. Product Add On | Walkways Mount Kits Top Up - Onvlee | 50 | 94.8 | 4740 | PO3914-TSG-20250515 - RV Approved | Onvlee INV01050372 | 2025-05-31 | 6353.8099 |  | 2025-05-29
8 | [9 empty] | 8 | 8. Product Add On | Walkways Mount Kits Top Up Delivery - Onvlee | 1 | 1670 | 1670 |  | Onvlee INV01050372 | 2025-05-31 | 2238.5786 |  | 2025-05-29
Only services to be capture below, products above
9 | AC & DC Installation | Project Kick Off |  | 10% | 154328 | 2024-12-30 | 1003132 | 1677478.2609 |  | 9 | 9. AC & DC installation | Deposit - TSS | 912222.22 | 30% | 273666.666 | PO3527-TSG-20241212 | Cosmic Sun CS_TRS_001 | 2025-01-31 | 503243.4783 | 0 | 2025-01-09 | 2052500
9 | 468640 | Site Establishment |  | 15% | 231492 | 2025-01-06 |  |  |  | 9 | 9. AC & DC installation | All AC & DC Equipment Onsite |  | 20% | 182444.444 |  | Cosmic Sun CS_TRS_003 | 2025-02-28 | 335495.6522 |  | 2025-02-20
9 | 1074640 | AC Installation Complete |  | 20% | 308656 | 2024-12-27 |  |  |  | 9 | 9. AC & DC installation | Pracitcal Completion - TSS |  | 30% | 273666.666 |  | Cosmic Sun CS_TRS_008 | 2025-03-31 | 223663.7676 |  | 2025-04-10
9 |  | Commissioning Complete |  | 10% | 154328 | #REF! |  |  |  | 9 | 9. AC & DC installation | Site Fully Commissioned - TSS |  | 15% | 136833.333 |  | Cosmic Sun CS_TRS_009 | 2025-04-30 | 111831.8838 |  | 2025-04-17
9 |  | Handover Document Complete |  | 5% | 77164 | #REF! |  |  |  | 9 | 9. AC & DC installation | Retention |  | 5% | 45611.111 |  | Cosmic Sun CS_TRS_013 | 2025-06-30 | 37277.2946 |  | 2025-08-21
[10 empty] | 9 | 9. AC & DC installation | CPD1
[10 empty] | 9 | 9. AC & DC installation | Deposit - CPD1 | 1140277.78 | 30% | 342083.334 |  | Cosmic Sun CS_TRS_001 | 2025-01-31 |  |  | 2025-01-09
[10 empty] | 9 | 9. AC & DC installation | All AC & DC Equipment Onsite |  | 20% | 228055.556 |  | Cosmic Sun CS_TRS_003 | 2025-02-28 |  |  | 2025-02-20
[10 empty] | 9 | 9. AC & DC installation | Practical Completion |  | 30% | 342083.334 |  | Cosmic Sun CS_TRS_010 | 2025-04-30 | 279579.7107 |  | 2025-05-08
[10 empty] | 9 | 9. AC & DC installation | Site Fully Commissioned |  | 15% | 171041.667 |  | Cosmic Sun CS_TRS_010 | 2025-04-30 | 139789.8553 |  | 2025-05-08
9 |  | End of Defects Period |  | 5% | 77164 | #REF! |  |  |  | 9 | 9. AC & DC installation | Retention |  | 5% | 57013.889 |  | Cosmic Sun CS_TRS_012 | 2025-06-30 | 46596.6184 |  | 2025-08-21
10 | Site Logistics | Telehandler |  |  | 32400 | 2025-01-06 | 234820.18 | 255239.3261 |  | 10 | 10. Site Logistics | [7 empty] | 0 | 0.002534 |  | 424330
10 |  | Offloading |  |  | 8500 | #REF! |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
[10 empty] | 10 | 10. Site Logistics | [7 empty] | 0
[10 empty] | 10 | 10. Site Logistics | Security - Jan |  |  | 1950 | PO3582-TSG-20250129 - RV Approved | Infantry - INV-2558 | 2025-01-31 | 1151.6421 |  | 2025-01-30
[10 empty] | 10 | 10. Site Logistics | Security - April |  |  | 650 | PO3810-TSG-20250416 - RV Approved | Infantry - INV-2759 | 2025-04-30 | 0 |  | 2025-04-17
[10 empty] | 10 | 10. Site Logistics | Security - Feb |  |  | 27600 | PO3583-TSG-20250129 - RV Approved | Infantry - INV-2559 | 2025-01-31 | 16300.1652 |  | 2025-02-07
[10 empty] | 10 | 10. Site Logistics | Security - Mar |  |  | 31500 | PO3710-TSG-20250303 - RV Approved | Infantry - INV-2670 | 2025-03-31 | 18947.6086 |  | 2025-03-13
10 |  | Storage |  |  | 51892.5 | #REF! |  |  |  | 10 | 10. Site Logistics | Deposit -TSS | 161168.89 | 30% | 48350.667 |  | Cosmic Sun CS_TRS_001 | 2025-01-31 | 64249.2273 |  | 2025-01-09
10 |  | Scaffolding |  |  | 74707.68 | #REF! |  |  |  | 10 | 10. Site Logistics | All AC & DC Equipment Onsite |  | 20% | 32233.778 |  | Cosmic Sun CS_TRS_003 | 2025-02-28 | 45331.2535 |  | 2025-02-20
10 |  | On site security |  |  | 67320 | #REF! |  |  |  | 10 | 10. Site Logistics | Pracitcal Completion - TSS |  | 30% | 48350.667 |  | Cosmic Sun CS_TRS_008 | 2025-03-31 | 29279.8667 |  | 2025-04-10
10 | [9 empty] | 10 | 10. Site Logistics | Site Fully Commissioned - TSS |  | 15% | 24175.3335 |  | Cosmic Sun CS_TRS_009 | 2025-04-30 | 14541.7383 |  | 2025-04-17
10 | [9 empty] | 10 | 10. Site Logistics | Retention |  | 5% | 8058.4445 |  | Cosmic Sun CS_TRS_013 | 2025-06-30 | 4847.2461 |  | 2025-08-21
[10 empty] | 10 | 10. Site Logistics | CPD1
[10 empty] | 10 | 10. Site Logistics | Deposit - CPD1 | 201461.11 | 30% | 60438.333 |  | Cosmic Sun CS_TRS_001 | 2025-01-31 |  |  | 2025-01-09
[10 empty] | 10 | 10. Site Logistics | All AC & DC Equipment Onsite |  | 20% | 40292.222 |  | Cosmic Sun CS_TRS_003 | 2025-02-28 |  |  | 2025-02-20
[10 empty] | 10 | 10. Site Logistics | Practical Completion |  | 30% | 60438.333 |  | Cosmic Sun CS_TRS_010 | 2025-04-30 | 36354.3454 |  | 2025-05-08
[10 empty] | 10 | 10. Site Logistics | Site Fully Commissioned |  | 15% | 30219.1665 |  | Cosmic Sun CS_TRS_010 | 2025-04-30 | 18177.1727 |  | 2025-05-08
10 | [9 empty] | 10 | 10. Site Logistics | Retention |  | 5% | 10073.0555 |  | Cosmic Sun CS_TRS_012 | 2025-06-30 | 6059.0576 |  | 2025-08-21
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 30000 | 2025-01-06 | 167000 | 181521.7391 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 17500 |  | Sunspot E024 | 2025-05-31 | 26373.5929 | 0.0016732 | 2025-06-05 | 120447.39
[10 empty] | 11 | 11. Due Dilligence | Travel to site |  |  | 2147.39 |  | Sunspot E024 | 2025-05-31 | 3236.2508 |  | 2025-06-05
11 |  | Structural sign off |  |  | 50000 | 2025-01-06 |  |  |  | 11 | 11. Due Dilligence | Structural sign off |  |  | 0 |  | L&B Consulting Inv: 1617 | 2024-12-31 | 0 |  | 2024-04-12
11 |  | Grid Study - Outside of CoCT |  |  | 80000 | 2025-01-06 |  |  |  | 11 | 11. Due Dilligence | Grid Study - Outside of CoCT |  |  | 79700 | PO3689-TSG-20250220 - RV Approved | Okusha Engineering Inv EE14 | 2025-04-30 | 111937.3162 |  | 2025-07-03
11 |  | Lightning Risk Assessment |  |  | 7000 | 2025-01-06 |  |  |  | 11 | 11. Due Dilligence | Lightning Risk Assessment - LPS |  |  | 5100 | PO3564-TSG-20250127 - RV Approved | LPS INV 306601 | 2025-01-31 | 5746.4983 |  | 2025-03-06
11 | [9 empty] | 11 | 11. Due Dilligence | Red Team Inspection | 2 | 8000 | 16000 |  | Matriarch - INV-4423 | 2025-05-31 | 34228.0793 |  | 2025-05-31
12 | BDP Commission | [5 empty] | 0 | 0 |  | 12 | BDP Commission | Referral Fee |  |  | 0 | [6 empty] | 0
12 | BDP Commission | [8 empty] | 12 | BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 167999.6765 | 2025-10-15 | 664894.7165 | 755562.1778 |  | 13 | 13. Engineering | Matriarch Defects Period |  |  | 200304.1117 |  | Matriarch - INV-4422 | 2025-05-31 | 755562.1778 | 0 | 2025-05-31 | 165600.0017
13 |  | Management |  |  | 74800 | 2025-10-15 |  |  |  | 13 | 13. Engineering |  |  |  | -200304.11 |  | Matriarch -CN-4996 | 2025-08-31 | 0 |  | 2025-08-31
13 |  | Project manager |  |  | 254320 | 2025-10-15 |  |  |  | 13 | 13. Engineering | MAM Performance Gaurantee |  |  | 165600 |  | Matriarch - INV-4997 | 2025-08-31 | 0 |  | 2025-08-31
13 |  | Planner time |  |  | 97240 | 2025-10-15 |  |  |  | 13 | 13. Engineering | [6 empty] | 2025-05-31 | 0 |  | 2025-05-31
13 |  | De Snagging |  |  | 70535.04 | 2025-10-15 |  |  |  | 13 | 13. Engineering | [6 empty] | 2025-05-31 | 0 |  | 2025-05-31
13 | [9 empty] | 13 | 13. Engineering
13 | [9 empty] | 13 | 13. Engineering
14 | General Expenses | Car travel to site |  |  | 32725 | 2025-10-15 | 32725 | 38500 |  | 14 | 14. General Expenses | Travel to site |  |  | 7446.43 |  | Expense Claims | 2024-12-31 | 8076.518 | 0.0049992 | 2025-01-09 | 37052.37
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 2931 |  | Expense Claims | 2025-01-31 | 3343.2704 |  | 2025-02-07
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 12977.95 |  | Expense Claims | 2025-02-28 | 9543.7985 |  | 2025-03-06
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 3958.29 |  | Expense Claims | 2025-03-31 | 4057.1696 |  | 2025-04-07
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 1491.59 |  | Expense Claims | 2025-04-30 | 1505.0668 |  | 2025-05-08
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 1352.79 |  | Expense Claims | 2025-05-31 | 1495.2011 |  | 2025-06-09
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 194.68 |  | Expense Claims | 2025-06-30 | 239.0599 |  | 2025-07-04
[10 empty] | 14 | 14. General Expenses |  |  |  | 2331.4 |  | Expense Claims | 2025-07-31 | 2704.8743 |  | 2025-08-07
[10 empty] | 14 | 14. General Expenses |  |  |  | 4368.24 |  | Expense Claims | 2025-08-31 | 7535.0364 |  | 2025-09-07
14 | [9 empty] | 14 | 14. General Expenses
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | Gen Sync Fix - AfrikEnergy |  |  | 4500 | PO4081-TSG-20250701 - RV Approved | AfrikEnergy - INV032882 | 2025-07-31 |  | 0 | 2025-07-24 | 55898
15 | [9 empty] | 15 | 15. Service Add On | Plugs for switchgear - Cosmic Sun |  |  | 4347.83 | PO4140-TSG-20250721 - RV Approved | Cosmic Sun CS_TRS_015 | 2025-07-31 |  |  | 2025-07-24
15 | [9 empty] | 15 | 15. Service Add On | Gen integration onsite support - AfrikEnergy |  |  | 5305 | PO4141-TSG-20250721 - RV Approved | AfrikEnergy - INV032885 | 2025-07-31 |  |  | 2025-07-17
[10 empty] | 15 | 15. Service Add On | SSEG Additional Tests - Cosmic Sun |  |  | 17160 | PO4584-TSG-20260127 - RV Approved | Cosmic Sun: CS_TRS_999 | 2026-01-31 |  |  | 2026-02-05
[10 empty] | 15 | 15. Service Add On | Roof repairs |  |  | 19085.17 |  | A&I Sheeting - Inv 6502 | 2025-07-31 |  |  | 2025-07-24
15 | [9 empty] | 15 | 15. Service Add On | COC fdor Waterpoints - Plumbryt |  |  | 5500 | PO4245-TSG-20250820 - RV Approved | Plumryt - 25/08/2025 | 2025-08-31 |  |  | 2025-08-30
Plugs for switchgear
16024328.9258
Note on Y55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Thami Cambalele this must be captured under Mega Park, this specific one is not for Trident Steel GP.
Note on W95: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date
Note on W168: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date
Note on W169: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2024-11-04 to 2026-11-02
PLANNED |  | CHECK | CHECK
| Planned Revenue | 16024328.9397 | 16024328.9397 | 0 | 1602432.894 | 7210948.0229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4807298.6819 | 0 | 0 | 0 | 801216.447 | 0 | 0 | 0 | 0 | 0 | 0 | 801216.447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801216.447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 1602432.894 | 8813380.9168 | 8813380.9168 | 8813380.9168 | 8813380.9168 | 8813380.9168 | 8813380.9168 | 8813380.9168 | 8813380.9168 | 8813380.9168 | 8813380.9168 | 8813380.9168 | 13620679.5987 | 13620679.5987 | 13620679.5987 | 13620679.5987 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397
| Planned Expenditure | 13780793.7463 | 12360544.9454 | 0 | 0 | 0 | 0 | 0 | 7922543.632 | 0 | 609828.6209 | 304914.3104 | 656771.4657 | 0 | 0 | 0 | 656096 | 1507600 | 0 | 5171.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 697619.7165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 7922543.632 | 7922543.632 | 8532372.2529 | 8837286.5633 | 9494058.029 | 9494058.029 | 9494058.029 | 9494058.029 | 10150154.029 | 11657754.029 | 11657754.029 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 11662925.229 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454 | 12360544.9454
| PLANNED CashFlow |  |  | 0 | 1602432.894 | 8813380.9168 | 8813380.9168 | 8813380.9168 | 890837.2848 | 890837.2848 | 281008.664 | -23905.6465 | -680677.1121 | -680677.1121 | -680677.1121 | -680677.1121 | 3470525.5698 | 1962925.5698 | 1962925.5698 | 1957754.3698 | 2758970.8168 | 2758970.8168 | 2758970.8168 | 2758970.8168 | 2758970.8168 | 2758970.8168 | 2758970.8168 | 3560187.2637 | 3560187.2637 | 3560187.2637 | 3560187.2637 | 3560187.2637 | 3560187.2637 | 3560187.2637 | 3560187.2637 | 3560187.2637 | 3560187.2637 | 3560187.2637 | 3560187.2637 | 3560187.2637 | 3560187.2637 | 3560187.2637 | 3560187.2637 | 3560187.2637 | 3560187.2637 | 3560187.2637 | 3560187.2637 | 3560187.2637 | 3560187.2637 | 3560187.2637 | 3560187.2637 | 3560187.2637 | 2862567.5473 | 2862567.5473 | 2862567.5473 | 2862567.5473 | 2862567.5473 | 2862567.5473 | 2862567.5473 | 2862567.5473 | 2862567.5473 | 2862567.5473 | 2862567.5473 | 2862567.5473 | 2862567.5473 | 2862567.5473 | 2862567.5473 | 2862567.5473 | 2862567.5473 | 2862567.5473 | 2862567.5473 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943 | 3663783.9943
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 16024328.9397 | 15623720.7162 | 0 | 0 | 0 | 0 | 0 | 0 | 5608515.1289 | 0 | 0 | 0 | 0 | 0 | 0 | 4807298.6819 | 3204865.7879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801216.447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801216.447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400608.2235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400608.2235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5608515.1289 | 5608515.1289 | 5608515.1289 | 5608515.1289 | 5608515.1289 | 5608515.1289 | 5608515.1289 | 10415813.8108 | 13620679.5987 | 13620679.5987 | 13620679.5987 | 13620679.5987 | 13620679.5987 | 13620679.5987 | 13620679.5987 | 13620679.5987 | 13620679.5987 | 13620679.5987 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 14421896.0457 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15223112.4927 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 15623720.7162 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397 | 16024328.9397
| Actual + Planned Expenditure | 14799893.8717 | 14799334.2417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1475691.841 | 0 | 0 | 31818 | 2157906.9 | 14956 | 3919877.51 | 2300329.36 | 58178.95 | 119894.62 | 23950 | 1279207.5 | 106204.724 | 690003.057 | 326926.7585 | 0 | 39607.63 | 1310929.431 | 11163.75 | 0 | 224214.1117 | 19647.39 | 21652.79 | 87000 | 120734.71 | 90413.68 | 16453 | 5305 | 27933 | 0 | 26281.4 | 0 | 244707.5685 | -28982.68 | 4368.24 | 0 | 0 | 0 | 55800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1475691.841 | 1475691.841 | 1475691.841 | 1507509.841 | 3665416.741 | 3680372.741 | 7600250.251 | 9900579.611 | 9958758.561 | 10078653.181 | 10102603.181 | 11381810.681 | 11488015.405 | 12178018.462 | 12504945.2205 | 12504945.2205 | 12544552.8505 | 13855482.2815 | 13866646.0315 | 13866646.0315 | 14090860.1432 | 14110507.5332 | 14132160.3232 | 14219160.3232 | 14339895.0332 | 14430308.7132 | 14446761.7132 | 14452066.7132 | 14479999.7132 | 14479999.7132 | 14506281.1132 | 14506281.1132 | 14750988.6817 | 14722006.0017 | 14726374.2417 | 14726374.2417 | 14726374.2417 | 14726374.2417 | 14782174.2417 | 14782174.2417 | 14782174.2417 | 14782174.2417 | 14782174.2417 | 14782174.2417 | 14782174.2417 | 14782174.2417 | 14782174.2417 | 14782174.2417 | 14782174.2417 | 14782174.2417 | 14782174.2417 | 14782174.2417 | 14782174.2417 | 14782174.2417 | 14782174.2417 | 14782174.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417 | 14799334.2417
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5608515.1289 | 5608515.1289 | 5608515.1289 | 4132823.2879 | 4132823.2879 | 4132823.2879 | 4101005.2879 | 6750397.0698 | 9940306.8577 | 6020429.3477 | 3720099.9877 | 3661921.0377 | 3542026.4177 | 3518076.4177 | 2238868.9177 | 2132664.1937 | 1442661.1367 | 1115734.3782 | 1916950.8252 | 1877343.1952 | 566413.7642 | 555250.0142 | 555250.0142 | 331035.9025 | 311388.5125 | 289735.7225 | 202735.7225 | 82001.0125 | -8412.6675 | -24865.6675 | -30170.6675 | -58103.6675 | -58103.6675 | -84385.0675 | -84385.0675 | -329092.636 | -300109.956 | -304478.196 | -304478.196 | -304478.196 | -304478.196 | -360278.196 | -360278.196 | -360278.196 | -360278.196 | -360278.196 | 440938.2509 | 440938.2509 | 440938.2509 | 440938.2509 | 440938.2509 | 440938.2509 | 440938.2509 | 440938.2509 | 440938.2509 | 440938.2509 | 440938.2509 | 440938.2509 | 440938.2509 | 423778.2509 | 423778.2509 | 423778.2509 | 824386.4744 | 824386.4744 | 824386.4744 | 824386.4744 | 824386.4744 | 824386.4744 | 824386.4744 | 824386.4744 | 824386.4744 | 824386.4744 | 824386.4744 | 824386.4744 | 824386.4744 | 824386.4744 | 824386.4744 | 824386.4744 | 824386.4744 | 824386.4744 | 824386.4744 | 824386.4744 | 824386.4744 | 824386.4744 | 824386.4744 | 824386.4744 | 824386.4744 | 824386.4744 | 824386.4744 | 1224994.6979 | 1224994.6979 | 1224994.6979 | 1224994.6979 | 1224994.6979 | 1224994.6979 | 1224994.6979 | 1224994.6979 | 1224994.6979 | 1224994.6979
|  | CHECK | CHECK
| Revenue Recognition | 0.013926 | 16024328.9258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5250104.3369 | 0 | 0 | 0 | 4143486.4556 | 0 | 0 | 0 | 2531182.3613 | 0 | 0 | 0 | 0 | 807251.3671 | 0 | 0 | 0 | 1998064.1711 | 0 | 0 | 0 | 1063381.7473 | 0 | 0 | 0 | 0 | 220618.5758 | 0 | 0 | 0 | 2704.8743 | 0 | 0 | 0 | 7535.0364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 16024328.9258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5250104.3369 | 5250104.3369 | 5250104.3369 | 5250104.3369 | 9393590.7924 | 9393590.7924 | 9393590.7924 | 9393590.7924 | 11924773.1537 | 11924773.1537 | 11924773.1537 | 11924773.1537 | 11924773.1537 | 12732024.5208 | 12732024.5208 | 12732024.5208 | 12732024.5208 | 14730088.6919 | 14730088.6919 | 14730088.6919 | 14730088.6919 | 15793470.4392 | 15793470.4392 | 15793470.4392 | 15793470.4392 | 15793470.4392 | 16014089.015 | 16014089.015 | 16014089.015 | 16014089.015 | 16016793.8893 | 16016793.8893 | 16016793.8893 | 16016793.8893 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258 | 16024328.9258

## Finance - Revenue
REVENUE RECOGNITION AMOUNT | (All)
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels |  | (blank) | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | Grand Total
(blank)
Battery Systems
BDP Commission
1. Panels | 0 | 0 | 4699920.0344 |  |  |  |  | 0 |  | 0 |  | 4699920.0344
2. Inverters |  | 0 |  | 1990010.1324 | 1236675.8891 | [5 empty] | 0 | 3226686.0215
3. Mounting Structures |  | 0 |  | 705479.5699 | [7 empty] | 705479.5699
4. DC Equipment |  | 0 | 542107.7845 | 290003.5188 | 193335.6792 | 128890.4534 | 420189.0347 |  | 52109.2256 |  |  | 1626635.6961
5. Monitoring |  |  |  | 75275.9702 | 226571.3592 | 135393.9981 |  | 155016.7396 | 0 |  |  | 592258.0671
6. AC Equipment | 0 |  |  | 480584.1506 | 403722.7507 | 195973.5304 | 465437.1324 |  | 73490.0736 |  |  | 1619207.6378
8. Product Add On | 0 | 0 |  | 8098.8322 | 80505.9788 | 71044.9726 | 398720.9148 | 87469.7058 | 0 |  |  | 645840.4043
9. AC & DC installation |  |  |  | 503243.4783 | 335495.6522 | 223663.7676 | 531201.4498 |  | 83873.913 |  |  | 1677478.2609
10. Site Logistics | 0 | 0 |  | 81701.0346 | 45331.2535 | 48227.4753 | 69073.2564 |  | 10906.3037 |  |  | 255239.3236
11. Due Dilligence |  |  | 0 | 5746.4983 |  |  | 111937.3162 | 63837.923 |  |  |  | 181521.7375
13. Engineering | [7 empty] | 755562.1778 |  |  | 0 | 755562.1778
14. General Expenses |  |  | 8076.518 | 3343.2704 | 9543.7985 | 4057.1696 | 1505.0668 | 1495.2011 | 239.0599 | 2704.8743 | 7535.0364 | 38499.995
15. Service Add On
Grand Total | 0 | 0 | 5250104.3369 | 4143486.4556 | 2531182.3613 | 807251.3671 | 1998064.1711 | 1063381.7473 | 220618.5758 | 2704.8743 | 7535.0364 | 16024328.9258
|  |  | 5306329.45 | 4143486.46 | 2534966.69 | 807251.37 | 1998064.17 | 1063381.75 | 160609.13
|  |  | -56225.1131 | -0.0044445 | -3784.3287 | -0.0029091 | 0.001052 | -0.0026663 | 60009.4458 |  |  | -0.0049548

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) |  | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2026-01-31 | Grand Total
Battery Systems
BDP Commission |  | 0 | [10 empty] | 0
(blank)
1. Panels |  |  | 2024-12-31: 4254751.8; 2025-05-31: 685.71; 2025-07-31: 221.43 | 4255658.94
2. Inverters | 0 |  | 2025-01-31: 1914000; 2025-02-28: 1189440; 2025-08-31: 55800 | 3159240
3. Mounting Structures | 0 |  | 2025-01-31: 346295; 2025-04-30: 39048 | 385343
4. DC Equipment | 0 |  | 611800 | 327285.75 | 218190.5 | 145460.334 | 345468.291 |  | 54547.625 |  |  |  | 1702752.5
5. Monitoring |  |  | 2025-01-31: 51331; 2025-02-28: 124822.36; 2025-03-31: 106466.99; 2025-05-31: 120509.63; 2025-06-30: 16453 | 419582.98
6. AC Equipment |  |  | 2025-01-31: 416420.661; 2025-02-28: 418711.774; 2025-03-31: 185075.85; 2025-04-30: 439555.1415; 2025-06-30: 69403.4435 | 1529166.87
8. Product Add On | 0 |  |  | 12000 | 80529.336 | 160209.484 | 216455 | 12609 | 10519 |  |  |  | 492321.82
9. AC & DC installation |  |  | 2025-01-31: 615750; 2025-02-28: 410500; 2025-03-31: 273666.666; 2025-04-30: 649958.334; 2025-06-30: 102625 | 2052500
10. Site Logistics |  |  | 2025-01-31: 138339; 2025-02-28: 72526; 2025-03-31: 79850.667; 2025-04-30: 115482.833; 2025-06-30: 18131.5 | 424330
11. Due Dilligence |  |  | 2024-12-31: 0; 2025-01-31: 5100; 2025-04-30: 79700; 2025-05-31: 35647.39 | 120447.39
13. Engineering |  |  | 2025-05-31: 200304.1117; 2025-08-31: -34704.11 | 165600.0017
14. General Expenses |  |  | 7446.43 | 2931 | 12977.95 | 3958.29 | 1491.59 | 1352.79 | 194.68 | 2331.4 | 4368.24 |  | 37052.37
15. Service Add On |  |  | 2025-07-31: 33238; 2025-08-31: 5500; 2026-01-31: 17160 | 55898
Grand Total | 0 | 0 | 4873998.23 | 3829452.411 | 2527697.92 | 954688.281 | 1887159.1895 | 371108.6317 | 271874.2485 | 35790.83 | 30964.13 | 17160 | 14799893.8717

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | 1190898 | 0 | 1190898 | 0 | 1190898
Inverters | 1190898
Optimizers | 0
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | 656096 | 0 | 656096 | 0 | 656096
Mounting Structure | 656096
Delivery fee
|  | >Name< |  | >Name<
DC Cable | 557200 | 0 | 557200 | 0 | 557200
DC Cable | 557200
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
SolarEdge Gateway | 4300
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | 100000 | 0 | #REF! | 0 | #REF!
SCADA | 100000
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | 1505863.1043 | 0.80313 | 277892.91 | 0.14821 | 1227970.1943 |  | 0 | 1505863.1043
DC Equipment | 955571.2 | 0.50964 | 142158.25 | 0.075818 | 813412.95 |  | 0 | 955571.2
AC Labour | 1074640 | 0.57314 | 96174 | 0.051293 | 978466 |  | 0 | 1074640
DC Labour | 468640 | 0.24994 | 230160 | 0.12275 | 238480 |  | 0 | 468640
Offloading | 8500 |  | 0 |  | 8500 |  |  | 8500
Roof Access/Scaffolding | 74707.68 |  | 29257.61 |  | 45450.07 |  |  | 74707.68
Storage | 51892.5 |  |  |  | 51892.5 |  |  | 51892.5
Telehandler | 32400
HSE | 0
Totals | 4172214.4843 |  | 775642.77 |  | 3364171.7143 | 0 |  | 4139814.4843
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | 1505863.1043
AC equipment | 0 | 0 |  |  | 0 |  | 0 | 955571.2
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | 1074640
DC equipment | 537300 | 0.28656 |  |  | 537300 |  |  | 468640
Storage | 0 |  |  |  | 0 |  |  | 8500
Panel lifting equipment | 92792.5 |  |  |  | 92792.5 |  |  | 74707.68
Offloading | 0 |  |  |  | 0 |  |  | 51892.5
Totals | #REF! |  | 0 |  | #REF! | 0 |  | 4139814.4843
Budget Summary
Budget | 4172214.4843
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
Loss | 4172214.4843
All amounts are exc VAT

## Decision Register (hidden)
Trident Steel GP |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Trident Steel GP | 0 | 0 | 0