## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[9 empty] | 2026-02-25 | 2026-02-25
| PROJECT PLAN | Ridgeview Mall | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 600
| PROJECT DEVELOPER | Peet Verenney
| PROJECT MANAGERS | JT Moorosi
| CONTRACT VALUE | 5813800
| Phase: | Compliance Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Status | Comment
|  |  | 74 |  |  | 133 |  | 100% | 100%
1 | Project Initiation | 2025-01-28 | 35 | 2025-03-04 | 2025-01-28 | 57 | 2025-03-26 | 100% | 100%
1.1 | BD Handover | 2025-01-28 | 1 | 2025-01-29 | 2025-01-28 | 1 | 2025-01-29 | 100% | 100%
1.2 | Project Introduction | 2025-02-11 | 1 | 2025-02-12 | 2025-02-11 | 1 | 2025-02-12 | 100% | 100%
1.3 | HSE | 2025-02-11 | 20 | 2025-03-03 | 2025-02-11 | 43 | 2025-03-26 | 100% | 100%
1.4 | Engineering Sign Off
1.5 | Installer Kick Off | 2025-03-03 | 1 | 2025-03-04 | 2025-03-03 | 1 | 2025-03-04 | 100% | 100%
1.6 | Project Review | 2025-03-03 | 1 | 2025-03-04 | 2025-03-03 | 1 | 2025-03-04 | 100% | 100%
2 | Site Establishment | 2025-03-10 | 1 | 2025-03-11 | 2025-03-10 | 1 | 2025-03-11 | 100% | 100%
2.1 | Installer on site & Roof Assessment | 2025-03-10 | 1 | 2025-03-11 | 2025-03-10 | 1 | 2025-03-11 | 100% | 100% |  | 91 | Net Work Days
3 | AC Installation | 2025-03-10 | 60 | 2025-05-09 | 2025-03-10 | 127 | 2025-07-15 | 100% | 100% |  | 18.2 | Total Weeks
3.1 | Inverters delivered | 2025-03-11 | 1 | 2025-03-12 | 2025-03-11 | 1 | 2025-03-12 | 100% | 100% |  | 32.967 | kW/Week Installation Rate
3.2 | Inverters Mounted | 2025-03-11 | 5 | 2025-03-18 | 2025-06-09 | 5 | 2025-06-17 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-03-10 | 25 | 2025-04-15 | 2025-03-10 | 25 | 2025-04-15 | 100% | 100%
3.4 | AC Works | 2025-04-15 | 15 | 2025-05-09 | 2025-06-09 | 12 | 2025-06-26 | 100% | 100%
3.5 | AC Tie-In | 2025-04-15 | 3 | 2025-04-22 | 2025-07-14 | 1 | 2025-07-15 | 100% | 100%
4 | DC Works | 2025-03-10 | 60 | 2025-05-09 | 2025-03-10 | 63 | 2025-05-12 | 100% | 100%
4.1 | Lifeline Installation (If Applicable) | [6 empty] | 0% | 0%
4.1 | Mounting Structure delivered | 2025-03-11 | 1 | 2025-03-12 | 2025-03-11 | 1 | 2025-03-12 | 100% | 100%
4.2 | Mounting Structure installation | 2025-03-10 | 10 | 2025-03-25 | 2025-03-10 | 10 | 2025-03-25 | 100% | 100%
4.3 | DC Cable delivered | 2025-03-11 | 1 | 2025-03-12 | 2025-03-11 | 1 | 2025-03-12 | 100% | 100%
4.3 | DC Stringing | 2025-04-21 | 13 | 2025-05-09 | 2025-04-29 | 8 | 2025-05-12 | 100% | 100%
5 | Module installation | 2025-03-10 | 45 | 2025-04-24 | 2025-03-25 | 38 | 2025-05-02 | 100% | 100%
5.1 | Module delivery | 2025-03-10 | 1 | 2025-03-11 | 2025-03-25 | 1 | 2025-03-26 | 100% | 100%
5.2 | Module mounting | 2025-03-25 | 20 | 2025-04-24 | 2025-03-25 | 20 | 2025-05-02 | 100% | 100%
6 | Commissioning | 2025-05-09 | 14 | 2025-05-23 | 2025-07-17 | 4 | 2025-07-21 | 100% | 100%
6.1 | Commissioning | 2025-05-09 | 5 | 2025-05-16 | 2025-07-17 | 1 | 2025-07-18 | 100% | 100%
6.2 | Practical Completion | 2025-05-16 | 5 | 2025-05-23 | 2025-07-18 | 1 | 2025-07-21 | 100% | 100%
7 | QA Inspections | 2025-05-23 | 7 | 2025-05-30 | 2025-07-21 | 7 | 2025-07-28 | 100% | 100%
7.1 | Red-Team Inspection | 2025-05-23 | 5 | 2025-05-30 | 2025-07-21 | 5 | 2025-07-28 | 100% | 100%
8 | Project Closure | 2025-05-30 | 39 | 2025-07-08 | 2025-07-21 | 11 | 2025-08-01 | 100% | 100%
8.1 | Equipment serial numbers | 2025-05-30 | 2 | 2025-06-03 | 2025-07-28 | 2 | 2025-07-30 | 100% | 100%
8.2 | Snags completion | 2025-05-30 | 10 | 2025-06-13 | 2025-07-28 | 1 | 2025-07-29 | 100% | 100%
8.3 | System Performance Monitoring | 2025-06-13 | 5 | 2025-06-23 | 2025-07-21 | 5 | 2025-07-28 | 100% | 100%
8.4 | Handover documentation | 2025-06-23 | 10 | 2025-07-07 | 2025-07-28 | 3 | 2025-07-31 | 100% | 100%
8.5 | Handover to Client | 2025-07-07 | 1 | 2025-07-08 | 2025-07-31 | 1 | 2025-08-01 | 100% | 100%
8.6 | Handover to Matriarch | 2025-06-15 | 5 | 2025-06-23 | 2025-07-23 | 5 | 2025-07-30 | 100% | 100%
Formulas:
Planned Start = MIN([Planned Start, row below]:E17)
Planned Start = [Planned Start, row above]+14
Planned End = MAX([Planned End, row below]:G17)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I17)
Actual Start = [Actual Start, row above]+14
Actual End = MAX([Actual End, row below]:K17)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C14)

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | PLANNED |  | ACTUAL |  | FINANCIAL REVIEW | TIMELINE REVIEW
1 | Planned Revenue | 5813800 |  | 5852178.26 |  | 5813800 | Start Date
2 | Planned Expenditure | 5151610.7211 |  | 4046134.0475 |  | 4227923.8759 | 2025-03-10
3 | Planned Profit | 662189.2789 |  | 1806044.2125 |  | 1585876.1241 | End Date - PC
4 | Planned Margin | 11.39% |  | 30.86% |  | 27.28% | 2025-05-23
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Acceptance and initial Deposit |  | 35% | 2034830 | 2025-02-28 | 004715 |  | 2025-04-04
2 | Delivery of Panels |  | 20% | 1162760 | 2025-04-09 | 004715 |  | 2025-04-17
3 | Delivery of Inverters |  | 30% | 1744140 | 2025-04-10 | 004715 |  | 2025-03-19
4 | Practical Completion |  | 10% | 581380 | 2025-06-22 | 004715 |  | 2025-07-17
5 | Handover |  | 5% | 290690 | 2025-08-07 | 004715 |  | 2025-08-08
6 | Inverter Cage |  | 0% | 38378.26 | 2025-09-20 | 004835 | 2025-08-31 | 31/03/2026
7 | - |  | 0% | 0
|  |  | 100% | 5852178.26
KEY: | contains an error (in result or a check has failed)
| Red Font - IF TEXT : content not yet confirmed |  |  |  | 5682989.5
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 2048262.391
2 | Delivery of Panels |  | 30% | 1755653.478
3 | Delivery of Inverters |  | 20% | 1170435.652
4 | Practical Completion |  | 10% | 585217.826
5 | Handover |  | 5% | 292608.913
| Total |  | 100% | 5852178.26
|  |  | 100% | 5852178.26

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  |  | COSTED |  | PLANNED |  | ACTUAL | Difference from costed | Difference from planned
| EXPENDITURE |  | 5151610.7211 |  | 4227923.8759 |  | 4046134.0475 | 1105476.6736 | 181789.8284
| No. | Item | Costed Expenditure |  | Planned Expenditure |  | Actual Expenditure | Saving / Overrun | Saving / Overrun | Comments on variations from planned expenditure
| 1 | Panels | 1496537.005 |  | 1189073.9059 |  | 1208550.89 | 287986.115 | -19476.9841
| 2 | Inverters | 350000 |  | 344350 |  | 344350 | 5650 | 0
| 3 | Mounting Structures | 270229.5 |  | 92905.88 |  | 93481.82 | 176747.68 | -575.94
| 4 | DC Equipment | 548101.2 |  | 558749.25 |  | 671199.2575 | -123098.0575 | -112450.0075
| 5 | Monitoring | 49000 |  | 36654.33 |  | 33421.96 | 15578.04 | 3232.37
| 6 | AC Equipment | 842399.3696 |  | 357261 |  | 390951.5 | 451447.8696 | -33690.5
| 7 | Battery Systems | 0 |  | 0 |  | 0 | 0 | 0
| 8 | Product Add On | 350000 |  | 440000 |  | 138014.52 | 211985.48 | 301985.48
| 9 | AC & DC Installation | 509892.5 |  | 600000 |  | 600000 | -90107.5 | 0
| 10 | Site Logistics | 214099.5 |  | 91407 |  | 77457 | 136642.5 | 13950
| 11 | Due Dilligence | 132038.25 |  | 95212.75 |  | 102050 | 29988.25 | -6837.25
| 12 | BDP Commission | 0 |  | 0 |  | 304347.83 | -304347.83 | -304347.83
| 13 | Engineering | 378813.3966 |  | 400707.18 |  | 72672.5 | 306140.8966 | 328034.68 | RV: Matriarch defects percentage 1.25%
| 14 | General Expenses | 10500 |  | 21602.58 |  | 6386.77 | 4113.23 | 15215.81
| 15 | Service Add On | 0 |  | 0 |  | 3250 | -3250 | -3250
|  | check: | 0 | #REF! | 0 | #REF! | 0
Copy amounts in column H and paste as values at Project review.

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 5151610.7211 | 5813800 |  | ACTUAL EXPENDITURE BREAKDOWN | [6 empty] | FINANCE ONLY |  |  |  |  | 4046134.0475
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | Project Related date | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS | COMMENTS
1 | Panels | Longi 555W | 1082 | 1346.1525 | 1456537.005 | 2025-04-09 | 1496537.005 | 1689109.4328 |  | 1 | 1. Panels | Longi 575W | 1044 | 1138.9597 | 1189070.9 | PO3611-RSV-20210131 - RV Approved | Krannich - Inv 15-10012162 | 2025-03-31 | 1666674.4449 | 0 | 2025-05-22 | 1208550.89 |  | 19
1 | [9 empty] | 1 | 1. Panels | ChemiTek |  |  | 5526 |  | Krannich - Inv 15-10012162 | 2025-03-31 | 7745.5793 |  | 2025-05-22 |  |  | BUDGET | Installer Allocation
1 |  | Delivery |  |  | 40000 | 2025-04-09 |  |  |  | 1 | 1. Panels | Freight |  |  | 10480 |  | Krannich - Inv 15-10012162 | 2025-03-31 | 14689.4085 |  | 2025-05-22 |  |  | AC Equipment | 842399.3696
1 | [9 empty] | 1 | 1. Panels | 580W Panel |  |  | 3473.99 |  | Krannich - Inv 15-10013490 | 2025-08-31 | 0 |  | 2025-10-02 |  |  | DC Equipment | 338269.2
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  |  | AC Labour | 150127.5 | 0.25021
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  |  | DC Labour | 359765 | 0.59961
[24 empty] | Offloading | 8500
2 | Inverters | Huawei 100KTL | 5 | 70000 | 350000 | 2025-04-10 | 350000 | 395037.543 |  | 2 | 2. Inverters | Huawei 100KTL | 5 | 68870 | 344350 | PO3611-RSV-20210131 - RV Approved | Krannich - Inv 15-10011997 | 2025-03-31 | 395037.543 | 0 | 2025-05-08 | 344350 |  | Roof Access/Scaffolding | 54199.5
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  |  | Storage | 7400
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  |  | Telehandler | 0
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  |  | Other | 0
[24 empty] | Total | 1760660.5696
3 | Mounting Structures | Lumax Pitch Roof |  |  | 270229.5 | 2025-04-10 | 270229.5 | 305002.2792 |  | 3 | 3. Mounting Structures | KlipLock - Schletter |  |  | 71546.52 | PO3719-RSC-20250305 - RV Approved | Schletter - INV1531 | 2025-03-31 | 234881.4786 | 0.00148 | 2025-04-30 | 93481.82 |  | Less 15% | 1496561.4841 | [SM: Target Installation Price]
3 | [9 empty] | 3 | 3. Mounting Structures | Delivery |  |  | 2750 |  | Schletter - INV1531 | 2025-03-31 | 9028.0291 |  | 2025-04-30 |  |  | R/Wp | 2.4943
[10 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
[10 empty] | 3 | 3. Mounting Structures | KlipLock Seam Clamps - JHB Storage | 434 | 24.88 | 10797.92 |  | Allocated from Stock | 2025-03-31 | 35448.7041 |  | 2025-03-31
[10 empty] | 3 | 3. Mounting Structures |  | 166 | 28.35 | 4706.1 |  | Allocated from Stock | 2025-07-31 | 13558.7194 |  | 2025-07-31
[10 empty] | 3 | 3. Mounting Structures | End Clamps - JHB Storage | 146 | 11.48 | 1676.08 |  | Allocated from Stock | 2025-03-31 | 5502.436 |  | 2025-03-31
3 | [9 empty] | 3 | 3. Mounting Structures | Mid Clamps - JHB Storage | 180 | 11.14 | 2005.2 |  | Allocated from Stock | 2025-03-31 | 6582.9105 |  | 2025-03-31
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  |  | ACTUAL - Cosmic Sun | Installer Price
[24 empty] | AC Equipment | 357261
4 | DC Equipment | DC Cabling (Total Cable Length) | 14988 | 14 | 209832 | 2025-04-10 | 548101.2 | 618630.1468 |  | 4 | 4. DC Equipment | [7 empty] | 0 | 0.0018644 |  | 671199.2575 |  | DC Equipment | 336509.25
[10 empty] | 4 | 4. DC Equipment | DC Cable | 16000 | 13.89 | 222240 | PO3611-RSV-20210131 - RV Approved | Krannich - Inv 15-10011997 | 2025-03-31 | 205240.5956 |  | 2025-05-08 |  |  | AC Labour | 180000 | 0.3
[10 empty] | 4 | 4. DC Equipment |  | 2000 |  | 111120 |  | Krannich Inv: 15-10012069 | 2025-03-31 | 102620.2978 |  | 2025-05-08 |  |  | DC Labour | 420000 | 0.7
4 |  | Project Kick Off |  | 10% | 33826.92 | 2025-03-03 |  |  |  | 4 | 4. DC Equipment | DC Cable - JHB Stock | 100 | 13.3 | 1330 |  | Allocated from JHB Storeroom | 2025-08-31 | 1225.8328 |  | 2025-08-31 |  |  | Offloading | 8800
4 | 338269.2 | Site Establishment |  | 15% | 50740.38 | 2025-03-17 |  |  |  | 4 | 4. DC Equipment | Deposit | 336509.25 | 30% | 100952.775 | PO3717-RSC-20250305 - RV Approved | Cosmic Sun - CS_RSC_001 | 2025-03-31 | 93230.776 |  | 2025-03-13 |  |  | Roof Access/Scaffolding | 34100
4 |  | AC Installation Complete |  | 20% | 67653.84 | 2025-05-16 |  |  |  | 4 | 4. DC Equipment | All DC and AC Equipment on site |  | 20% | 67301.85 |  | Cosmic Sun - CS_RSC_002 | 2025-04-30 | 62153.8507 |  | 2025-05-08 |  |  | Storage | 8657
4 |  | DC Installation Complete |  | 25% | 84567.3 | 2025-05-16 |  |  |  | 4 | 4. DC Equipment | Practical completion |  | 30% | 100952.78 |  | Cosmic Sun - CS_RSC_003 | 2025-06-30 | 93230.7696 |  | 2025-07-17 |  |  | HSE | 4500
4 |  | Commissioning Complete |  | 10% | 33826.92 | 2025-05-30 |  |  |  | 4 | 4. DC Equipment | Site fully commissioned |  | 15% | 50476.39 |  | Cosmic Sun - CS_RSC_004 | 2025-06-30 | 46615.3898 |  | 2025-07-24 |  |  | Other | 0
4 |  | Site De-establisment |  | 10% | 33826.92 | 2025-08-05 |  |  |  | 4 | 4. DC Equipment | Retention |  | 5% | 16825.4625 |  | Cosmic Sun - CS_RSC_007 | 2025-08-31 | 14312.6326 |  | 2025-08-21 |  |  | Other | 0
4 |  | Handover Document Complete |  | 5% | 16913.46 | 2025-06-10 |  |  |  | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  |  | Other | 0
4 |  | End of Defects Period |  | 5% | 16913.46 | 2025-07-10 |  |  |  | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  |  | Total | 1349827.25
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  |  | R/Wp | 2.2497
5 | Monitoring | Smartlogger 3000 |  |  | 26000 | 2025-04-10 | 49000 | 55305.256 |  | 5 | 5. Monitoring | [7 empty] | 0 | 0 |  | 33421.96
5 |  | Comms DB |  |  | 8000 | 2025-04-10 |  |  |  | 5 | 5. Monitoring | CTs, Meters, Router - AccuEnergy |  |  | 13396 | PO3718-RSC-20250305 - RV Approved | AccuEnergy Inv ASAI-004973 | 2025-03-31 | 22167.1383 |  | 2025-04-30
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | Smartlogger 3000 |  |  | 8333.33 | PO3611-RSV-20210131 - RV Approved | Krannich - Inv 15-10011997 | 2025-03-31 | 13789.6446 |  | 2025-05-08
5 |  | Revenue Grade Meter |  |  | 15000 | 2025-07-10 |  |  |  | 5 | 5. Monitoring | Revenue Grade Meter |  |  | 11169 |  | Matriarch - INV-4082 | 2025-03-31 | 18481.9922 |  | 2025-04-30
5 | [9 empty] | 5 | 5. Monitoring | Delivery of Techsitter |  |  | 523.63 |  | DSV Inv: 180122089 | 2025-03-31 | 866.4809 |  | 2025-04-30
6 | AC Equipment | [5 empty] | 842399.3696 | 950798.2205 |  | 6 | 6. AC Equipment | [8 empty] | -0.0024493 |  | 390951.5
6 |  | Project Kick Off |  | 10% | 84239.937 | 2025-03-03 |  |  |  | 6 | 6. AC Equipment | Deposit | 357261 | 30% | 107178.3 | PO3717-RSC-20250305 - RV Approved | Cosmic Sun - CS_RSC_001 | 2025-03-31 | 285239.4662 |  | 2025-03-13
6 | 842399.3696 | Site Establishment |  | 15% | 126359.9054 | 2025-03-17 |  |  |  | 6 | 6. AC Equipment | All DC and AC Equipment on site |  | 20% | 71452.2 |  | Cosmic Sun - CS_RSC_002 | 2025-04-30 | 190159.6441 |  | 2025-05-08
6 |  | AC Installation Complete |  | 20% | 168479.8739 | 2025-05-16 |  |  |  | 6 | 6. AC Equipment | Practical completion |  | 30% | 107178.3 |  | Cosmic Sun - CS_RSC_003 | 2025-06-30 | 208441.9923 |  | 2025-07-17
6 |  | DC Installation Complete |  | 25% | 210599.8424 | 2025-05-16 |  |  |  | 6 | 6. AC Equipment | Site fully commissioned |  | 15% | 53589.15 |  | Cosmic Sun - CS_RSC_004 | 2025-06-30 | 92421.5112 |  | 2025-07-24
6 |  | Commissioning Complete |  | 10% | 84239.937 | 2025-05-30 |  |  |  | 6 | 6. AC Equipment | Retention |  | 5% | 17863.05 |  | Cosmic Sun - CS_RSC_007 | 2025-08-31 | 40855.6082 |  | 2025-08-21
6 |  | Site De-establisment |  | 10% | 84239.937 | 2025-08-05 |  |  |  | 6 | 6. AC Equipment | 3P Breaker moved to Stock |  |  | -24757 |  | Allocated to Jhb Storeroom | 2025-08-31 | 0 |  | 2025-08-31
6 |  | Handover Document Complete |  | 5% | 42119.9685 | 2025-06-10 |  |  |  | 6 | 6. AC Equipment | AC Cable for Tie In VO - Cosmic Sun |  |  | 29881.5 | PO4026-RSC-20250524 - RV Approved | Cosmic Sun - CS_RSC_005 | 2025-07-31 | 68344.3937 |  | 2025-07-11
6 |  | End of Defects Period |  | 5% | 42119.9685 | 2025-07-10 |  |  |  | 6 | 6. AC Equipment | 4P Breaker VO- Cosmic Sun |  |  | 28566 | PO4084-RSC-20250702 - RV Approved | Cosmic Sun - CS_RSC_006 | 2025-07-31 | 65335.6073 |  | 2025-07-11
7 | Battery Systems | [5 empty] | 0 | 0 |  | 7 | Battery Systems | [8 empty] | 0 |  | 0
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
8 | Product Add On | [5 empty] | 350000 | 350000 |  | 8 | 8. Product Add On | PV DB Cage/Enclosure Add on - JRL Eng | 89800 | 80% | 71840 | PO3924-RSC-20250516 - RV Approved | JRL Engineering - INV00322 | 2025-05-31 | 0 | 0 | 2025-05-22 | 138014.52 | Client to be invoiced Variation of R44358,35 incl VAT
8 |  | Extra Capex |  |  | 350000 | 2025-05-30 |  |  |  | 8 | 8. Product Add On | PV DB Cage/Enclosure Add on - JRL Eng |  | 20% | 17960 |  | JRL Engineering - INV00322 | 2025-05-31 | 0 |  | 2025-06-19
8 | [9 empty] | 8 | 8. Product Add On | PV DB Cage/Enclosure - JRL - Deposit | 61258 | 50% | 30629 | PO3802-RSC-20250414 - RV Approved | JRL Engineering - INV 2025063 | 2025-04-30 | 175000 |  | 2025-04-17
8 | [9 empty] | 8 | 8. Product Add On | PV DB Cage/Enclosure - JRL - Balance |  | 30% | 18377.4 |  | JRL Engineering - INV 2025063 | 2025-04-30 | 0 |  | 2025-04-25
[10 empty] | 8 | 8. Product Add On | PV DB Cage/Enclosure - JRL - Balance |  | 20% | 12251.6 |  | JRL Engineering - INV 2025063 | 2025-04-30 | 0 |  | 2025-06-19
8 | [9 empty] | 8 | 8. Product Add On | PV DB Cage/Enclosure - JRL - Credit |  |  | -13043.48 |  | JRL Engineering - Credit ICA10016 | 2025-06-30 |  |  | 2025-06-30
8 | [9 empty] | 8 | 8. Product Add On | [6 empty] | 2025-08-31 | 175000 |  | 2025-06-30
Only services to be capture below, products above
9 | AC & DC Installation | Project Kick Off |  | 10% | 50989.25 | 2025-03-03 | 509892.5 | 599873.5294 |  | 9 | 9. AC & DC installation | Deposit | 600000 | 30% | 180000 | PO3717-RSC-20250305 - RV Approved | Cosmic Sun - CS_RSC_001 | 2025-03-31 | 179962.0588 | 0 | 2025-03-13 | 600000
9 | 150127.5 | Site Establishment |  | 15% | 76483.875 | 2025-03-17 |  |  |  | 9 | 9. AC & DC installation | All DC and AC Equipment on site |  | 20% | 120000 |  | Cosmic Sun - CS_RSC_002 | 2025-04-30 | 119974.7059 |  | 2025-05-08
9 | 359765 | AC Installation Complete |  | 20% | 101978.5 | 2025-05-16 |  |  |  | 9 | 9. AC & DC installation | Practical completion |  | 30% | 180000 |  | Cosmic Sun - CS_RSC_003 | 2025-06-30 | 179962.0588 |  | 2025-07-17
9 |  | DC Installation Complete |  | 25% | 127473.125 | 2025-05-16 |  |  |  | 9 | 9. AC & DC installation | Site fully commissioned |  | 15% | 90000 |  | Cosmic Sun - CS_RSC_004 | 2025-06-30 | 89981.0294 |  | 2025-07-24
9 |  | Commissioning Complete |  | 10% | 50989.25 | 2025-05-30 |  |  |  | 9 | 9. AC & DC installation | Retention |  | 5% | 30000 |  | Cosmic Sun - CS_RSC_007 | 2025-08-31 | 29993.6765 |  | 2025-08-21
9 |  | Site De-establisment |  | 10% | 50989.25 | 2025-08-05 |  |  |  | 9 | 9. AC & DC installation | [7 empty] | 0
9 |  | Handover Document Complete |  | 5% | 25494.625 | 2025-06-10 |  |  |  | 9 | 9. AC & DC installation | [7 empty] | 0
9 |  | End of Defects Period |  | 5% | 25494.625 | 2025-07-10 |  |  |  | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Security |  |  | 144000 | 2025-07-10 | 214099.5 | 251881.7647 |  | 10 | 10. Site Logistics | [8 empty] | 0.0028607 |  | 77457
[10 empty] | 10 | 10. Site Logistics | Security - March |  |  | 4050 | PO3584-RSV-20250129 - RV Approved | INFANTRY - IN-2560 | 2025-01-31 | 4810.7689 |  | 2025-03-28 |  | Credit note requested
[10 empty] | 10 | 10. Site Logistics | Security - April |  |  | 5350 | PO3585-RSV-20250129 - RV Approved | INFANTRY - IN-2561 | 2025-01-31 | 6354.9664 |  | 2025-03-28 |  | Credit note requested
[10 empty] | 10 | 10. Site Logistics | Security - Credit Note - Late start |  |  | -5350 |  | INFANTRY-CN-2643 | 2025-03-31 | 0 |  | 2025-03-31
[10 empty] | 10 | 10. Site Logistics | Security - Credit Note - Late start |  |  | -4050 |  | INFANTRY - CN-2642 | 2025-03-31 | 0 |  | 2025-03-31
[10 empty] | 10 | 10. Site Logistics | Security March - Infantry |  |  | 8250 |  | INFANTRY - IN-2688 | 2025-03-31 | -5807.1211 |  | 2025-03-28
[10 empty] | 10 | 10. Site Logistics | Security - April |  |  | 2250 | PO3811-RSC-20250416 - RV Approved | Infantry - IN-2689 | 2025-04-30 | 5480.6151 |  | 2025-04-17
10 |  | Scaffolding |  |  | 54199.5 | 2025-05-30 |  |  |  | 10 | 10. Site Logistics | Deposit | 56057 | 30% | 16817.1 | PO3717-RSC-20250305 - RV Approved | Cosmic Sun - CS_RSC_001 | 2025-03-31 | 40963.5791 |  | 2025-03-13
10 |  | Site Storage |  |  | 7400 | 2025-05-30 |  |  |  | 10 | 10. Site Logistics | All DC and AC Equipment on site |  | 20% | 11211.4 |  | Cosmic Sun - CS_RSC_002 | 2025-04-30 | 27309.0527 |  | 2025-05-08
10 | [9 empty] | 10 | 10. Site Logistics | Practical completion |  | 30% | 16817.1 |  | Cosmic Sun - CS_RSC_003 | 2025-06-30 | 54687.3856 |  | 2025-07-17
10 | [9 empty] | 10 | 10. Site Logistics | Site fully commissioned |  | 15% | 8408.55 |  | Cosmic Sun - CS_RSC_004 | 2025-06-30 | 27343.6928 |  | 2025-07-24
10 |  | Offloading |  |  | 8500 | 2025-05-30 |  |  |  | 10 | 10. Site Logistics | Retention |  | 5% | 2802.85 |  | Cosmic Sun - CS_RSC_007 | 2025-08-31 | 9114.5643 |  | 2025-08-21
10 | [9 empty] | 10 | 10. Site Logistics | Crane Hire - SCO |  |  | 10900 | PO3724-RSC-20250306 - RV Approved | Supply Chain Inv: SCO05072 | 2025-06-30 | 81624.258 |  | 2025-07-17
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
11 | Due Dilligence | Electrical PrEng sign off |  |  | 15012.75 | 2025-06-06 | 132038.25 | 155339.1176 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 15750 |  | Sunspot E026 | 2025-06-30 | 22754.8699 | -0.0013731 | 2025-07-29 | 102050
11 |  | Structural sign off |  |  | 30025.5 | 2025-02-24 |  |  |  | 11 | 11. Due Dilligence | Structural sign off - LnB Eng |  |  | 7500 | PO3586-RSV-20250129 - RV Approved | L&B Consulting INV-1893 | 2025-01-31 | 10638.4269 |  | 2025-02-07
11 | [9 empty] | 11 | 11. Due Dilligence | Red Team |  |  | 8000 |  | Matriarch - IN-4753 | 2025-07-31 | 13703.8808 |  | 2025-07-31
11 |  | Grid Study - Outside of CoCT |  |  | 80000 | 2025-07-08 |  |  |  | 11 | 11. Due Dilligence | Grid Study - Outside of CoCT |  |  | 65700 | PO3687-RSC-20250220 - RV Approved | Okusha Electrical Inv EE10 | 2025-04-30 | 98881.0009 |  | 2026-03-31
11 |  | Lightning Risk Assessment |  |  | 7000 | 2025-07-08 |  |  |  | 11 | 11. Due Dilligence | Lightning Risk Assessment - LPS |  |  | 5100 | PO4199-RSC-20250805 - RV Approved | LPS In307224 | 2025-08-31 | 9360.9404 |  | 2025-09-11
12 | BDP Commission | [5 empty] | 0 | 0 |  | 12 | BDP Commission | Termination Fee |  |  | 304347.83 |  | Terra Firma Inv: INA6021290 | 2025-03-31 |  |  | 2025-03-27 | 304347.83
12 | BDP Commission | [8 empty] | 12 | BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 50778.7166 | 2025-07-08 | 378813.3966 | 430469.7688 |  | 13 | 13. Engineering | Matriarch Defects Period (PG Cost R9190) |  |  | 72672.5 |  | Matriarch - INV-4752 | 2025-07-31 | 430469.7688 | 0 | 2025-07-31 | 72672.5
13 |  | Management |  |  | 48000 | 2025-07-08 |  |  |  | 13 | 13. Engineering | Management |  |  | 0 |  |  | 2025-07-31 | 0 |  | 2025-07-31
13 |  | Project manager |  |  | 163200 | 2025-07-08 |  |  |  | 13 | 13. Engineering | Project manager |  |  | 0 |  |  | 2025-07-31 | 0 |  | 2025-07-31
13 |  | Planner time |  |  | 62400 | 2025-07-08 |  |  |  | 13 | 13. Engineering | Planner time |  |  | 0 |  |  | 2025-07-31 | 0 |  | 2025-07-31
13 |  | De Snagging |  |  | 54434.68 | 2025-07-08 |  |  |  | 13 | 13. Engineering | De Snagging |  |  | 0 |  |  | 2025-07-31 | 0 |  | 2025-07-31
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Car travel to site |  |  | 10500 | 2025-07-08 | 10500 | 12352.9412 |  | 14 | 14. General Expenses | Car travel to site |  |  | 602.58 |  | Expense Claims | 2025-01-31 | 455.068 | 0.0020646 | 2025-02-07 | 6386.77
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 514.98 |  | Expense Claims | 2025-02-28 | 286.4445 |  | 2025-03-06
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 2896.82 |  | Expense Claims | 2025-03-31 | 2011.2568 |  | 2025-04-04
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 639.27 |  | Expense Claims | 2025-04-30 | 521.1196 |  | 2025-05-08
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 421.74 |  | Expense Claims | 2025-05-31 | 431.4336 |  | 2025-06-09
[10 empty] | 14 | 14. General Expenses |  |  |  | 704.96 |  | Expense Claims | 2025-06-30 | 2502.1022 |  | 2025-07-04
[10 empty] | 14 | 14. General Expenses |  |  |  | 606.42 |  | Expense Claims | 2025-07-31 | 6145.5144 |  | 2025-08-07
14 | [9 empty] | 14 | 14. General Expenses
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | [8 empty] | 0 |  | 3250
15 | [9 empty] | 15 | 15. Service Add On | Solar Panel Clean - Cosmic Sun |  |  | 3250 | PO4149-RSC-20250722 | Cosmic Sun - CS_RSC_008 | 2025-08-31 |  |  | 2025-08-21
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
| Panel Procurement Budget | 1689109.4328 | [16 empty] | 5813799.9956
| Inverter Procurement Budget | 395037.543
| Mounting Structure Budget | 305002.2792
| DC Equipment Budget | 618630.1468
| AC Equipment Budget | 950798.2205
| Monitoring Budget | 55305.256
| Optional Extras Budget | 0
| MV Metering Budget | 0
| ADD ON | 350000
| Battery System | 0
| Generator | 0
Services
| AC Installer Budget | 176620.5882
| DC Installer Budget | 423252.9412
| In-House Expense Budget | 430469.7688
| Compliance Budget | 155339.1176
| Offloading Budget | 10000
| Roof Access Budget for Equipment | 0
| Site storage | 8705.8824
| On Site Security | 169411.7647
| Roof Access Budget for Installers | 63764.1176
| EPC Management Fee | 0
| ADD ON | 0
Expenses
| Total EE Expense Budget | 12352.9412
Note on Q23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs Reply: @Tasneema van Harte I will check and advise
Note on W103: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2026-09-28
PLANNED |  | CHECK | CHECK
| Planned Revenue | 5813800 | 5852178.26 | 0 | 0 | 0 | 0 | 0 | 2034830 | 0 | 0 | 0 | 0 | 0 | 2906900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 581380 | 0 | 0 | 0 | 0 | 0 | 0 | 290690 | 0 | 0 | 0 | 0 | 0 | 38378.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 2034830 | 2034830 | 2034830 | 2034830 | 2034830 | 2034830 | 4941730 | 4941730 | 4941730 | 4941730 | 4941730 | 4941730 | 4941730 | 4941730 | 4941730 | 4941730 | 5523110 | 5523110 | 5523110 | 5523110 | 5523110 | 5523110 | 5523110 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26 | 5852178.26
| Planned Expenditure | 5151610.7211 | 5151610.7211 | 0 | 0 | 0 | 0 | 0 | 30025.5 | 169056.107 | 0 | 253584.1604 | 0 | 0 | 2360598.505 | 0 | 0 | 0 | 0 | 760752.4813 | 0 | 589155.607 | 15012.75 | 84528.0535 | 0 | 0 | 0 | 719841.45 | 0 | 0 | 0 | 169056.107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 30025.5 | 199081.607 | 199081.607 | 452665.7674 | 452665.7674 | 452665.7674 | 2813264.2724 | 2813264.2724 | 2813264.2724 | 2813264.2724 | 2813264.2724 | 3574016.7537 | 3574016.7537 | 4163172.3607 | 4178185.1107 | 4262713.1641 | 4262713.1641 | 4262713.1641 | 4262713.1641 | 4982554.6142 | 4982554.6142 | 4982554.6142 | 4982554.6142 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211 | 5151610.7211
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 2004804.5 | 1835748.3931 | 1835748.3931 | 1582164.2326 | 1582164.2326 | 1582164.2326 | 2128465.7276 | 2128465.7276 | 2128465.7276 | 2128465.7276 | 2128465.7276 | 1367713.2463 | 1367713.2463 | 778557.6394 | 763544.8894 | 679016.8359 | 1260396.8359 | 1260396.8359 | 1260396.8359 | 540555.3859 | 540555.3859 | 540555.3859 | 540555.3859 | 662189.2789 | 662189.2789 | 662189.2789 | 662189.2789 | 662189.2789 | 662189.2789 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389 | 700567.5389
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 5852178.26 | 5813800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1744140 | 0 | 2034830 | 0 | 1162760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 581380 | 0 | 0 | 290690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1744140 | 1744140 | 3778970 | 3778970 | 4941730 | 4941730 | 4941730 | 4941730 | 4941730 | 4941730 | 4941730 | 4941730 | 4941730 | 4941730 | 4941730 | 4941730 | 4941730 | 5523110 | 5523110 | 5523110 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800 | 5813800
| Actual + Planned Expenditure | 4046134.0475 | 4046134.0475 | 0 | 0 | 8102.58 | 0 | 0 | 0 | 514.98 | 404948.175 | 0 | 321997.83 | 7976.02 | 0 | 32879 | 18377.4 | 99385.15 | 956648.05 | 0 | 1276916.9 | 0 | 0 | 421.74 | 30211.6 | 0 | -12338.52 | 58447.5 | 415848.18 | 202474.09 | 101128.6 | 606.42 | 0 | 70741.3625 | -23427 | 0 | 5100 | 0 | 0 | 3473.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 8102.58 | 8102.58 | 8102.58 | 8102.58 | 8617.56 | 413565.735 | 413565.735 | 735563.565 | 743539.585 | 743539.585 | 776418.585 | 794795.985 | 894181.135 | 1850829.185 | 1850829.185 | 3127746.085 | 3127746.085 | 3127746.085 | 3128167.825 | 3158379.425 | 3158379.425 | 3146040.905 | 3204488.405 | 3620336.585 | 3822810.675 | 3923939.275 | 3924545.695 | 3924545.695 | 3995287.0575 | 3971860.0575 | 3971860.0575 | 3976960.0575 | 3976960.0575 | 3976960.0575 | 3980434.0475 | 3980434.0475 | 3980434.0475 | 3980434.0475 | 3980434.0475 | 3980434.0475 | 3980434.0475 | 3980434.0475 | 3980434.0475 | 3980434.0475 | 3980434.0475 | 3980434.0475 | 3980434.0475 | 3980434.0475 | 3980434.0475 | 3980434.0475 | 3980434.0475 | 3980434.0475 | 3980434.0475 | 3980434.0475 | 3980434.0475 | 3980434.0475 | 3980434.0475 | 3980434.0475 | 3980434.0475 | 3980434.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475 | 4046134.0475
| ACTUAL CashFlow |  |  | 0 | 0 | -8102.58 | -8102.58 | -8102.58 | -8102.58 | -8617.56 | -413565.735 | 1330574.265 | 1008576.435 | 3035430.415 | 3035430.415 | 4165311.415 | 4146934.015 | 4047548.865 | 3090900.815 | 3090900.815 | 1813983.915 | 1813983.915 | 1813983.915 | 1813562.175 | 1783350.575 | 1783350.575 | 1795689.095 | 1737241.595 | 1902773.415 | 1700299.325 | 1599170.725 | 1889254.305 | 1889254.305 | 1818512.9425 | 1841939.9425 | 1841939.9425 | 1836839.9425 | 1836839.9425 | 1836839.9425 | 1833365.9525 | 1833365.9525 | 1833365.9525 | 1833365.9525 | 1833365.9525 | 1833365.9525 | 1833365.9525 | 1833365.9525 | 1833365.9525 | 1833365.9525 | 1833365.9525 | 1833365.9525 | 1833365.9525 | 1833365.9525 | 1833365.9525 | 1833365.9525 | 1833365.9525 | 1833365.9525 | 1833365.9525 | 1833365.9525 | 1833365.9525 | 1833365.9525 | 1833365.9525 | 1833365.9525 | 1833365.9525 | 1833365.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525 | 1767665.9525
|  | CHECK | CHECK
| Revenue Recognition | 0.0044473 | 5813799.9956 | 0 | 22259.2302 | 0 | 0 | 0 | 286.4445 | 0 | 0 | 0 | 0 | 3334356.6992 | 0 | 0 | 0 | 679479.9891 | 0 | 0 | 0 | 431.4336 | 0 | 0 | 0 | 0 | 899565.0597 | 0 | 0 | 0 | 597557.8844 | 0 | 0 | 0 | 279863.2548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 5813799.9956 | 0 | 22259.2302 | 22259.2302 | 22259.2302 | 22259.2302 | 22545.6746 | 22545.6746 | 22545.6746 | 22545.6746 | 22545.6746 | 3356902.3739 | 3356902.3739 | 3356902.3739 | 3356902.3739 | 4036382.363 | 4036382.363 | 4036382.363 | 4036382.363 | 4036813.7966 | 4036813.7966 | 4036813.7966 | 4036813.7966 | 4036813.7966 | 4936378.8563 | 4936378.8563 | 4936378.8563 | 4936378.8563 | 5533936.7407 | 5533936.7407 | 5533936.7407 | 5533936.7407 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956 | 5813799.9956
| Installer Expenditure |  | 1327460.7575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388131.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258754.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58447.5 | 388131.08 | 194065.54 | 0 | 0 | 0 | 64688.5125 | -24757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Installer Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388131.075 | 388131.075 | 388131.075 | 388131.075 | 388131.075 | 388131.075 | 388131.075 | 388131.075 | 646885.125 | 646885.125 | 646885.125 | 646885.125 | 646885.125 | 646885.125 | 646885.125 | 646885.125 | 646885.125 | 705332.625 | 1093463.705 | 1287529.245 | 1287529.245 | 1287529.245 | 1287529.245 | 1352217.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575 | 1327460.7575

## Finance - Revenue
REVENUE RECOGNITION AMOUNT | (All)
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels |  | (blank) | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | Grand Total
(blank)
Battery Systems
BDP Commission
1. Panels | 0 |  |  |  | 1689109.4328 |  |  |  |  | 0 | 1689109.4328
2. Inverters | 0 | 0 |  |  | 395037.543 | [5 empty] | 395037.543
3. Mounting Structures | 0 | 0 |  |  | 291443.5583 |  |  |  | 13558.7194 |  | 305002.2777
4. DC Equipment |  | 0 |  |  | 401091.6694 | 62153.8507 |  | 139846.1594 |  | 15538.4654 | 618630.1449
5. Monitoring |  | 0 |  |  | 55305.256 | [5 empty] | 55305.256
6. AC Equipment |  |  |  |  | 285239.4662 | 190159.6441 |  | 300863.5035 | 133680.0009 | 40855.6082 | 950798.223
8. Product Add On | [5 empty] | 175000 | 0 |  |  | 175000 | 350000 | 4363882.8774
9. AC & DC installation |  | 0 |  |  | 179962.0588 | 119974.7059 |  | 269943.0882 |  | 29993.6765 | 599873.5294
10. Site Logistics |  |  | 11165.7353 |  | 35156.458 | 32789.6679 |  | 163655.3364 |  | 9114.5643 | 251881.7618
11. Due Dilligence |  |  | 10638.4269 |  |  | 98881.0009 |  | 22754.8699 | 13703.8808 | 9360.9404 | 155339.119
13. Engineering | 0 | [7 empty] | 430469.7688 |  | 430469.7688
14. General Expenses |  |  | 455.068 | 286.4445 | 2011.2568 | 521.1196 | 431.4336 | 2502.1022 | 6145.5144 |  | 12352.9391
15. Service Add On
Grand Total | 0 | 0 | 22259.2302 | 286.4445 | 3334356.6992 | 679479.9891 | 431.4336 | 899565.0597 | 597557.8844 | 279863.2548 | 5813799.9956
|  |  | 22148.73 | 286.44 | 3334356.7 | 679479.99 | 431.43 | 899565.06 | 597557.88 | 318352.03 | 5852178.26
|  |  | 110.5002 | 0.0044888 | -0.00079137 | -0.00086035 | 0.0036358 | -0.00032972 | 0.0044359 | -38488.7752 | -38378.2644
5852178.26
5852178.26
2.9039e-05
318352.03

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | Grand Total
Battery Systems
BDP Commission |  | 2025-03-31: 304347.83 | 304347.83
(blank)
1. Panels |  | 2025-03-31: 1205076.9; 2025-08-31: 3473.99 | 1208550.89
2. Inverters |  | 2025-03-31: 344350 | 344350
3. Mounting Structures |  | 2025-03-31: 88775.72; 2025-07-31: 4706.1 | 93481.82
4. DC Equipment |  | 2025-03-31: 434312.775; 2025-04-30: 67301.85; 2025-06-30: 151429.17; 2025-08-31: 18155.4625 | 671199.2575
5. Monitoring |  | 2025-03-31: 33421.96 | 33421.96
6. AC Equipment |  |  |  | 107178.3 | 71452.2 |  | 160767.45 | 58447.5 | -6893.95 | 390951.5
8. Product Add On |  | 2025-04-30: 61258; 2025-05-31: 89800; 2025-06-30: -13043.48 | 138014.52
9. AC & DC installation |  | 2025-03-31: 180000; 2025-04-30: 120000; 2025-06-30: 270000; 2025-08-31: 30000 | 600000
10. Site Logistics |  | 9400 |  | 15667.1 | 13461.4 |  | 36125.65 |  | 2802.85 | 77457
11. Due Dilligence |  | 7500 |  |  | 65700 |  | 15750 | 8000 | 5100 | 102050
13. Engineering |  | 2025-07-31: 72672.5 | 72672.5
14. General Expenses |  | 602.58 | 514.98 | 2896.82 | 639.27 | 421.74 | 704.96 | 606.42 |  | 6386.77
15. Service Add On |  | 2025-08-31: 3250 | 3250
Grand Total |  | 17502.58 | 514.98 | 2716027.405 | 399812.72 | 90221.74 | 621733.75 | 144432.52 | 55888.3525 | 4046134.0475

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate | [5 empty] | FINANCIAL CLOSE CERTIFICATE
Project Name: | Ridgeview Mall
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion: |  |  |  | 1. Financial Close | 1. Financial Close
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | 350000 | 0 | 350000 | 0 | 350000
Inverters | 350000
Optimizers | 0
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | 270229.5 | 0 | 270229.5 | 0 | 270229.5
Mounting Structure | 270229.5
Delivery fee
|  | >Name< |  | >Name<
DC Cable | 209832 | 0 | 209832 | 0 | 209832
DC Cable | 209832
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
Smartlogger 3000 | 26000
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | 0 | 0 | #REF! | 0 | #REF!
SCADA | 0
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | 842399.3696 | 1.404 | 277892.91 | 0.46315 | 564506.4596 |  | 0 | 842399.3696
DC Equipment | 338269.2 | 0.56378 | 142158.25 | 0.23693 | 196110.95 |  | 0 | 338269.2
AC Labour | 150127.5 | 0.25021 | 96174 | 0.16029 | 53953.5 |  | 0 | 150127.5
DC Labour | 359765 | 0.59961 | 230160 | 0.3836 | 129605 |  | 0 | 359765
Offloading | 8500 |  | 0 |  | 8500 |  |  | 8500
Roof Access/Scaffolding | 54199.5 |  | 29257.61 |  | 24941.89 |  |  | 54199.5
Storage | 7400 |  |  |  | 7400 |  |  | 7400
Telehandler | 0
HSE | 0
Totals | 1760660.5696 |  | 775642.77 |  | 985017.7996 | 0 |  | 1760660.5696
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | 842399.3696
AC equipment | 0 | 0 |  |  | 0 |  | 0 | 338269.2
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | 150127.5
DC equipment | 33826.92 | 0.056378 |  |  | 33826.92 |  |  | 359765
Storage | 7000 |  |  |  | 7000 |  |  | 8500
Panel lifting equipment | 214099.5 |  |  |  | 214099.5 |  |  | 54199.5
Offloading | 0 |  |  |  | 0 |  |  | 7400
Totals | #REF! |  | 0 |  | #REF! | 0 |  | 1760660.5696
Budget Summary
Budget | 1760660.5696
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
Loss | 1760660.5696
All amounts are exc VAT

## Decision Register (hidden)
Ridgeview Mall |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Ridgeview Mall | 0 | 0 | 0