## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate |  |  |  | FINANCIAL CLOSE CERTIFICATE
Project Name: | Steelpark
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Product Agreement
EPC Agreement
O&M Agreeement
Cost Proposal
Deposit Received
Risks / Notes
Acknowledgement and Acceptance:
Role | Name | Signature | Date

## Certificate - Planning
Emergent Energy – Planning Phase Completion Certificate |  |  |  | PLANNING CERTIFICATE
Project Name: | Steelpark
Client Representative:
Programme Manager: | Roedolph Venter
Project Manager: | Justin Franke
Project Engineer:
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Project Introduction Presentation
Project Brief
Engineering Pack
BOQ
PO – Material & Equipment
PO - Contractors
HSE – NOC
HSE – EE File
HSE – Contractor File
SSEG Application
Risks / Notes
Acknowledgement and Acceptance:
Role | Name | Signature | Date

## Change Register
Change Register
ID | Description | Supporting Image (If Applicable) | Impact | Proposed Date | Proposed By | Status | Approved By | Approved Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
DEC011
DEC012
DEC013
DEC014
DEC015
DEC016
DEC017
DEC018
DEC019
DEC020
DEC021
DEC022
DEC023
DEC024
DEC025
DEC026
DEC027
DEC028
DEC029
DEC030

## BOQ
Item | Supplier | Description | Quantity | Comments
PV Module | Menlo | Jinko 590W - JKM590N-72HL4-BDV | 221
DC Cable Red & Black | Menlo | Enco PV Cable | 4000
Inverters | Menlo | Huawei 100KTL - SUN2000-100-KTL-M2 | 1 | Take note, this has changed to 1x 100KTL
Mounting Structure | Schletter
Current Transformers (Production)
Current Transformers (Consumption)
Solar Production Meter (Techistter)
Grid Consumption Meter
Wi-Fi Router & Sim
Switch
Back Up Battery
PVDB | Switchboard
Supplier List
Accuenergy
Krannich
Menlo
Red Pole
Schletter
Switchboard
Techsitter
Note on D5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Mizelda Isaacs please take note here

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC |  |  |  | In Progress
7.1 Agreement |  |  |  | In Progress
13.2 Agreement |  |  |  | In Progress
EE File |  |  |  | In Progress
Subbie File |  |  |  | Not appointed
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[9 empty] | 2026-02-11 | 2026-02-11
| PROJECT PLAN | Steelpark |  |  | Net Work Days |  | 26 |  | 0 | 1
| PROJECT SIZE (kWp) | 130 |  |  | Total Weeks |  | 5.2
| PROJECT DEVELOPER | Natasha Watkins-Baker |  |  | kW/Week Installation Rate |  | 25
| PROJECT MANAGERS | Justin Franke
| CONTRACT VALUE | 1441230.4772
| Phase: | Planning
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration | Planned End | Actual Start | Duration | Actual End | Status | Expected Status | Comment
|  |  | 35 |  |  | 35 |  | 7.455% | 7.455% |  | 2026-02-11 | 2026-02-11
[11 empty] | 1 | 0
1 | Project Initiation | 2025-11-25 | 97 | 2026-03-02 | 2025-11-25 | 97 | 2026-03-02 | 2.5% | 2.5%
1.1 | Project Charter Handover | 2025-11-25 | 1 | 2025-11-26 | 2025-11-25 | 1 | 2025-11-26 | 100% | 100% |  | Milestone | Start Date | Duration | End Date
1.2 | Client Roof Replacement | 2026-01-31 | 21 | 2026-03-02 | 2026-01-31 | 21 | 2026-03-02 | 25% | 36.67% | Start date 19 Feb | Project Initiation | 2025-11-25 | 97 | 2026-03-02
1.3 | DB Works on Client side | 2025-12-12 | 10 | 2026-01-30 | 2025-12-12 | 10 | 2026-01-30 | 100% | 100% |  | Site Establishment | 2026-02-23 | 1 | 2026-02-24
1.4 | HSE Readiness and Signoff | 2026-02-09 | 5 | 2026-02-16 | 2026-02-09 | 5 | 2026-02-16 | 0% | 28.57% |  | AC Installation | 2026-01-17 | 46 | 2026-03-04
1.5 | Project Introduction | 2026-02-16 | 1 | 2026-02-17 | 2026-02-16 | 1 | 2026-02-17 | 0% | 0% |  | DC Works | 2026-02-23 | 24 | 2026-03-19
1.6 | Installer Kick Off | 2026-02-16 | 1 | 2026-02-17 | 2026-02-16 | 1 | 2026-02-17 | 0% | 0% |  | Module installation | 2026-03-11 | 6 | 2026-03-17
1.7 | Project Review | 2026-02-16 | 1 | 2026-02-17 | 2026-02-16 | 1 | 2026-02-17 | 0% | 0% |  | Commissioning | 2026-03-19 | 11 | 2026-03-30
[11 empty] | QA Inspections | 2026-03-23 | 8 | 2026-03-31
2 | Site Establishment | 2026-02-23 | 1 | 2026-02-24 | 2026-02-23 | 1 | 2026-02-24 | 0% | 0% |  | Project Closure | 2026-03-26 | 20 | 2026-04-15
2.1 | Solar Contractor Establishment | 2026-02-23 | 1 | 2026-02-24 | 2026-02-23 | 1 | 2026-02-24 | 0% | 0%
3 | AC Installation | 2026-01-17 | 46 | 2026-03-04 | 2026-01-17 | 46 | 2026-03-04 | 57.14% | 57.14%
3.1 | Inverters delivered | 2026-02-24 | 1 | 2026-02-25 | 2026-02-24 | 1 | 2026-02-25 | 0% | 0%
3.2 | Inverters Mounted | 2026-02-25 | 1 | 2026-02-26 | 2026-02-25 | 1 | 2026-02-26 | 0% | 0%
3.3 | Solar DB Lead Time | 2026-01-17 | 20 | 2026-02-13 | 2026-01-17 | 20 | 2026-02-13 | 80% | 92.59%
3.4 | AC Works | 2026-02-25 | 5 | 2026-03-04 | 2026-02-25 | 5 | 2026-03-04 | 0% | 0%
3.5 | AC Tie-In | 2026-02-25 | 1 | 2026-02-26 | 2026-02-25 | 1 | 2026-02-26 | 0% | 0%
4 | DC Works | 2026-02-23 | 24 | 2026-03-19 | 2026-02-23 | 24 | 2026-03-19 | 0% | 0%
4.1 | Mounting Structure delivered | 2026-02-23 | 1 | 2026-02-24 | 2026-02-23 | 1 | 2026-02-24 | 0% | 0%
4.2 | Mounting Structure installation | 2026-03-09 | 2 | 2026-03-11 | 2026-03-09 | 2 | 2026-03-11 | 0% | 0%
4.3 | DC Cable delivered | 2026-02-23 | 1 | 2026-02-24 | 2026-02-23 | 1 | 2026-02-24 | 0% | 0%
4.4 | DC Stringing | 2026-03-14 | 4 | 2026-03-19 | 2026-03-14 | 4 | 2026-03-19 | 0% | 0%
5 | Module installation | 2026-03-11 | 6 | 2026-03-17 | 2026-03-11 | 6 | 2026-03-17 | 0% | 0%
5.1 | Module delivery | 2026-03-11 | 1 | 2026-03-12 | 2026-03-11 | 1 | 2026-03-12 | 0% | 0%
5.2 | Module mounting | 2026-03-11 | 4 | 2026-03-17 | 2026-03-11 | 4 | 2026-03-17 | 0% | 0%
6 | Commissioning | 2026-03-19 | 11 | 2026-03-30 | 2026-03-19 | 11 | 2026-03-30 | 0% | 0%
6.1 | Commissioning | 2026-03-19 | 1 | 2026-03-20 | 2026-03-19 | 1 | 2026-03-20 | 0% | 0%
6.2 | Practical Completion | 2026-03-20 | 1 | 2026-03-23 | 2026-03-20 | 1 | 2026-03-23 | 0% | 0%
6.3 | System Performance Monitoring | 2026-03-23 | 5 | 2026-03-30 | 2026-03-23 | 5 | 2026-03-30 | 0% | 0%
7 | QA Inspections | 2026-03-23 | 8 | 2026-03-31 | 2026-03-23 | 8 | 2026-03-31 | 0% | 0%
7.1 | Red-Team Inspection | 2026-03-23 | 3 | 2026-03-26 | 2026-03-23 | 3 | 2026-03-26 | 0% | 0%
7.2 | Snags completion | 2026-03-26 | 3 | 2026-03-31 | 2026-03-26 | 3 | 2026-03-31 | 0% | 0%
8 | Project Closure | 2026-03-26 | 20 | 2026-04-15 | 2026-03-26 | 20 | 2026-04-15 | 0% | 0%
8.1 | Handover documentation | 2026-03-26 | 7 | 2026-04-08 | 2026-03-26 | 7 | 2026-04-08 | 0% | 0%
8.2 | Handover to Client | 2026-04-08 | 1 | 2026-04-09 | 2026-04-08 | 1 | 2026-04-09 | 0% | 0%
8.3 | Handover to Matriarch | 2026-04-08 | 5 | 2026-04-15 | 2026-04-08 | 5 | 2026-04-15 | 0% | 0%
Formulas:
Planned Start = MIN([Planned Start, row below]:E19)
Planned Start = [Planned Start, row above]
Planned End = MAX([Planned End, row below]:G19)
Planned End = WORKDAY.INTL([Planned Start],[Duration],1,Data!$C3:C60)
Actual Start = MIN([Actual Start, row below]:I19)
Actual Start = [Actual Start, row above]
Actual End = MAX([Actual End, row below]:K19)
Actual End = WORKDAY.INTL([Actual Start],[Duration],1,Data!$C3:C60)
Expected Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW |  |  | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 1441230.4772 |  | 1441230.4772 |  |  |  | Start Date |  |  | 1408948.9719 | 873450.211 | 39067.3343 | 27992.08
2 | Planned Expenditure | 1194452.4559 |  | 888450.211 | VO PM LIMIT | CURRENT VO Total
3 | Planned Profit | 246778.0213 |  | 552780.2663 | 12338.9011 | 0 |  | End Date - PC
4 | Planned Margin | 17.12% |  | 38.35%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Acceptance and Initial Deposit |  | 50% | 720615.2386 |  | 2026-01-31 | 004914 | 2026-01-14 | 2026-02-20 | [5 empty] | 1900-01-06
2 | Delivery of Panels |  | 25% | 360307.6193 |  | 2026-03-19 |  |  | 2026-03-19
3 | Delivery of Inverters |  | 10% | 144123.0477 |  | 2026-03-04 |  |  | 2026-03-04
4 | Practical Completion |  | 10% | 144123.0477 |  | 2026-04-06 |  |  | 2026-04-06
5 | Handover |  | 5% | 72061.5239 |  | 2026-04-16 |  |  | 2026-04-16
6 | - |  | 0% | 0
7 | - |  | 0% | 0
|  |  | 100% | 1441230.4772
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 504430.667
2 | Delivery of Panels |  | 30% | 432369.1432
3 | Delivery of Inverters |  | 20% | 288246.0954
4 | Practical Completion |  | 10% | 144123.0477
5 | Handover |  | 5% | 72061.5239
| Total |  | 100% | 1441230.4772
|  |  | 100% | 1441230.4772
Note on R14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Thami Cambalele please invoice these for us

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from Costed
EXPENDITURE |  | 1194452.4559 |  | 888450.211 | 306002.245
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 370794.53 |  | 260780 | 110014.53
2 | 2. Inverters | 95000 |  | 69000 | 26000
3 | 3. Mounting Structures | 58482 |  | 29315.1 | 29166.9
4 | 4. DC Equipment | 69414.8 |  | 89548.89 | -20134.09
5 | 5. Monitoring | 49000 |  | 32257.44 | 16742.56
6 | 6. AC Equipment | 198443.487 |  | 69740.64 | 128702.847
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 4000 |  | 0 | 4000
9 | 9. AC & DC installation | 108300 |  | 128600 | -20300
10 | 10. Site Logistics | 59041.9 |  | 24025 | 35016.9
11 | 11. Due Dilligence | 89000 |  | 87910.48 | 1089.52
12 | 12. BDP Commission | 0 |  | 0 | 0
13 | 13. Engineering | 90875.739 |  | 95172.661 | -4296.922
14 | 14. General Expenses | 2100 |  | 2100 | 0
15 | 15. Service Add On | 0 |  | 0 | 0
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 1194452.4559 | 1441230.4772 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 888450.211
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FORECASTED PAYMENT DATE | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 370794.53 | 2026-05-10 | 370794.53 | 452188.4512 |  | 1 | 1. Panels | Jinko 590W - JKM590N-72HL4-BDV - Menlo | 221 | 1180 | 260780 |  |  | 2026-02-28 | 452188.4512 | 0 | 2026-05-10 | 260780
1 |  | Delivery Budget | [7 empty] | 1 | 1. Panels |  |  | 2 |  |  |  |  | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 198443.487
2 | Inverters | Inverter Budget |  |  | 95000 | 2026-04-25 | 95000 | 115853.6585 |  | 2 | 2. Inverters | [7 empty] | 0 | 0 |  | 69000 | DC Equipment | 50822.8
2 | [9 empty] | 2 | 2. Inverters | Huawei 100KTL | 1 | 69000 | 69000 |  |  | 2026-02-28 | 115853.6585 |  | 2026-05-10 |  | AC Labour | 32490
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 75810
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 21741.9
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 0
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 58482 | 2026-03-25 | 58482 | 71319.5122 |  | 3 | 3. Mounting Structures | Schletter Structure |  |  | 29315.1 |  |  | 2026-02-28 | 71319.5122 | 0 | 2026-03-30 | 29315.1 | Other | 0
3 | [9 empty] | 3 | 3. Mounting Structures | IBR Clamps | 600 | [5 empty] | 0 |  |  |  | Total | 387808.187
3 | [9 empty] | 3 | 3. Mounting Structures | Mid Clamps | 400 | [5 empty] | 0 |  |  |  | Less 15% | 329636.9589
3 | [9 empty] | 3 | 3. Mounting Structures | End Clamps | 200 | [5 empty] | 0 |  |  |  | R/Wp | 2.5357
3 | [9 empty] | 3 | 3. Mounting Structures | Screws | 1200 | [5 empty] | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL - Leading Edge Power | Installer Price |  | ACTUAL - Happy Solar | Installer Price |  | ACTUAL - Cosmic Sun | Installer Price
[23 empty] | AC Equipment | 45000 |  | AC Equipment | 85150 |  | AC Equipment | 41000
4 | DC Equipment | DC Cable Budget | 1328 |  | 18592 | 2026-04-24 | 69414.8 | 84652.1951 |  | 4 | 4. DC Equipment | DC Cable - Menlo | 2000 | 13.75 | 27500 |  |  | 2026-02-28 | 25996.2504 | 0 | 2026-05-10 | 89548.89 | DC Equipment | 62048.89 |  | DC Equipment | 54990 |  | DC Equipment | 69107.78
4 |  | DC Equipment Budget |  |  | 50822.8 | 2026-03-19 |  |  |  | 4 | 4. DC Equipment | Check DC Cable Stock | [6 empty] | 0 |  |  |  | AC Labour | 35000 | 0.26923 | AC Labour | 84500 | 0.65 | AC Labour | 42900 | 0.33
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | DC Labour | 93600 | 0.72 | DC Labour | 106210 | 0.817 | DC Labour | 93600 | 0.72
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Offloading | 7150 |  | Logistics | 114000 |  | Offloading | 7150
4 | [9 empty] | 4 | 4. DC Equipment | Project Kick Off | 62048.89 | 10% | 6204.889 |  |  | 2026-02-28 | 5865.5945 |  | 2026-02-23 |  | Roof Access | 5775 |  | Forklift | 0 |  | Roof Access | 5775
4 | [9 empty] | 4 | 4. DC Equipment | Site Establishment |  | 15% | 9307.3335 |  |  | 2026-02-28 | 8798.3917 |  | 2026-02-23 |  | Site Container | 6600 |  | Geda | 0 |  | Site Container | 6600
4 | [9 empty] | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 12409.778 |  |  | 2026-03-31 | 11731.1889 |  | 2026-03-11 |  | HSE Compliance | 4500 |  | Logistics | 0 |  | HSE Compliance | 4500
4 | [9 empty] | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 15512.2225 |  |  | 2026-03-31 | 14663.9862 |  | 2026-03-26 |  | HSE | 0 |  | HSE | 0 |  | HSE | 0
4 | [9 empty] | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 6204.889 |  |  | 2026-04-30 | 5865.5945 |  | 2026-04-06 |  | Other | 0 |  | Other | 0 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 6204.889 |  |  | 2026-04-30 | 5865.5945 |  | 2026-04-07 |  | Other | 0 |  | Other | 0 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 3102.4445 |  |  | 2026-04-30 | 2932.7972 |  | 2026-04-07 |  | Total | 259673.89 |  | Total | 444850 |  | Total | 270632.78
4 | [9 empty] | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 3102.4445 |  |  | 2026-04-30 | 2932.7972 |  | 2026-04-30 |  | R/Wp | 1.9975 |  | R/Wp | 3.4219 |  | R/Wp | 2.0818
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Smartlogger 3000 |  |  | 26000 | 2026-03-15 | 49000 | 59756.0976 |  | 5 | 5. Monitoring | Smartlogger 3000 - Menlo |  |  | 8598.34 |  |  | 2026-05-31 | 15928.2089 | 0 | 2026-05-10 | 32257.44
5 |  | Comms DB |  |  | 8000 | 2026-03-15 |  |  |  | 5 | 5. Monitoring | [7 empty] | 0
5 |  | Revenue Grade Meter |  |  | 15000 | 2026-03-15 |  |  |  | 5 | 5. Monitoring | Revenue Grade Meter |  |  | 15000 |  |  |  | 27787.1233 |  | 0
5 | [9 empty] | 5 | 5. Monitoring | Check meter |  |  | 3600 | PO4051-STLP-20250627 - RV Approved | CBB Inv: CBB-5722 | 2026-01-31 | 6668.9096 |  | 2025-09-11
5 | [9 empty] | 5 | 5. Monitoring | Check Meter CT's |  |  | 2870 |  | Accuenergy Inv: ASAI-006974 | 2026-01-31 | 5316.6029 |  | 2026-01-07
[10 empty] | 5 | 5. Monitoring | Lithium Battery |  |  | 975 |  | Red Pole:SO-35689 | 2026-01-31 | 1806.163 |  | 2025-08-30
5 | [9 empty] | 5 | 5. Monitoring | Power Supply |  |  | 1214.1 |  | current Automation Inv: SOQ324142 | 2026-01-31 | 2249.0898 |  | 2025-09-10
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 198443.487 | 2026-03-15 | 198443.487 | 242004.2524 |  | 6 | 6. AC Equipment | [7 empty] | 0 | 0 |  | 69740.64
6 | [9 empty] | 6 | 6. AC Equipment | Comms DB |  |  | 24740.64 |  |  | 2026-02-28 | 85851.522 |  | 2026-03-30
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | Project Kick Off | 45000 | 10% | 4500 |  |  | 2026-02-28 | 15615.273 |  | 2026-02-23
6 | [9 empty] | 6 | 6. AC Equipment | Site Establishment |  | 15% | 6750 |  |  | 2026-02-28 | 23422.9096 |  | 2026-02-23
6 | [9 empty] | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 9000 |  |  | 2026-03-31 | 31230.5461 |  | 2026-03-11
6 | [9 empty] | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 11250 |  |  | 2026-03-31 | 39038.1826 |  | 2026-03-26
6 | [9 empty] | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 4500 |  |  | 2026-04-30 | 15615.273 |  | 2026-04-06
6 | [9 empty] | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 4500 |  |  | 2026-04-30 | 15615.273 |  | 2026-04-07
6 | [9 empty] | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 2250 |  |  | 2026-04-30 | 7807.6365 |  | 2026-04-07
6 | [9 empty] | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 2250 |  |  | 2026-04-30 | 7807.6365 |  | 2026-04-30
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | Check Meter |  |  | 4000 | 2026-03-11 | 4000 | 4494.382 |  | 8 | 8. Product Add On | [8 empty] | 4494.382 |  | 0
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 32490 | 2026-03-11 | 108300 | 127411.7647 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0 |  | 128600
9 |  | DC Installation Budget |  |  | 75810 | 2026-03-26 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 128600 | 10% | 12860 |  |  | 2026-02-28 | 12741.1765 |  | 2026-02-23
9 | [9 empty] | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 19290 |  |  | 2026-02-28 | 19111.7647 |  | 2026-02-23
9 | [9 empty] | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 25720 |  |  | 2026-03-31 | 25482.3529 |  | 2026-03-11
9 | [9 empty] | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 32150 |  |  | 2026-03-31 | 31852.9412 |  | 2026-03-26
9 | [9 empty] | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 12860 |  |  | 2026-04-30 | 12741.1765 |  | 2026-04-06
9 | [9 empty] | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 12860 |  |  | 2026-04-30 | 12741.1765 |  | 2026-04-07
9 | [9 empty] | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 6430 |  |  | 2026-04-30 | 6370.5882 |  | 2026-04-07
9 | [9 empty] | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 6430 |  |  | 2026-04-30 | 6370.5882 |  | 2026-04-30
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2026-03-11 | 59041.9 | 69461.0588 |  | 10 | 10. Site Logistics | [7 empty] | 0 | 0 |  | 24025
10 |  | Scaffolding |  |  | 21741.9 | 2026-03-11 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Security |  |  | 28800 | 2026-03-11 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 0 | 2026-03-11 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | Project Kick Off | 24025 | 10% | 2402.5 |  |  | 2026-02-28 | 6946.1059 |  | 2026-02-23
10 | [9 empty] | 10 | 10. Site Logistics | Site Establishment |  | 15% | 3603.75 |  |  | 2026-02-28 | 10419.1588 |  | 2026-02-23
10 | [9 empty] | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 4805 |  |  | 2026-03-31 | 13892.2118 |  | 2026-03-11
10 | [9 empty] | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 6006.25 |  |  | 2026-03-31 | 17365.2647 |  | 2026-03-26
10 | [9 empty] | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 2402.5 |  |  | 2026-04-30 | 6946.1059 |  | 2026-04-06
10 | [9 empty] | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 2402.5 |  |  | 2026-04-30 | 6946.1059 |  | 2026-04-07
10 | [9 empty] | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 1201.25 |  |  | 2026-04-30 | 3473.0529 |  | 2026-04-07
10 | [9 empty] | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 1201.25 |  |  | 2026-04-30 | 3473.0529 |  | 2026-04-30
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2026-03-30 | 89000 | 104705.8824 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 12577.5 |  |  | 2026-04-30 | 14980.4464 | 0 | 2026-04-13 | 87910.48
11 |  | Structural sign off |  |  | 18000 | 2026-03-30 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 7690.9 |  | L&B Consulting: Inv 1701 | 2026-01-31 | 9160.2556 |  | 2024-08-22
11 |  | Scada for CoCT |  |  | 60000 | 2026-03-30 |  |  |  | 11 | 11. Due Dilligence | Scada for CoCT |  |  | 50000 |  |  | 2026-02-28 | 59552.5598 |  | 2026-03-30
11 | [9 empty] | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 |  |  | 2026-03-31 | 7146.3072 |  | 2026-04-07
[10 empty] | 11 | 11. Due Dilligence | Roof inspection |  |  | 9900 |  | HappySolar Inv: 0346 | 2026-01-31 | 11791.4068 |  | 2025-12-24
11 | [9 empty] | 11 | 11. Due Dilligence | Roof inspection |  |  | 1742.08 |  | Leading Edge INV0171 | 2026-01-31 | 2074.9065 |  | 2025-11-28
12 | BDP Commission | PD Fee |  |  | 0 |  | 0 | 0 |  | 12 | 12. BDP Commission | PD Fee |  |  | 0 | [6 empty] | 0
12 | BDP Commission | [8 empty] | 12 | 12. BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 13718.459 | 2026-04-15 | 90875.739 | 106912.6341 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 18015.381 |  |  | 2026-03-31 | 20237.6587 | 0 | 2026-03-30 | 95172.661
13 |  | Management |  |  | 9600 | 2026-03-11 |  |  |  | 13 | 13. Engineering | Management |  |  | 9600 |  |  | 2026-03-31 | 10784.2029 |  | 2026-03-30
13 |  | Project manager |  |  | 32640 | 2026-03-11 |  |  |  | 13 | 13. Engineering | Project manager |  |  | 32640 |  |  | 2026-03-31 | 36666.2899 |  | 2026-03-30
13 |  | Planner time |  |  | 12480 | 2026-03-11 |  |  |  | 13 | 13. Engineering | Planner time |  |  | 12480 |  |  | 2026-03-31 | 14019.4638 |  | 2026-03-30
13 |  | De Snagging |  |  | 22437.28 | 2026-03-11 |  |  |  | 13 | 13. Engineering | De Snagging |  |  | 22437.28 |  |  | 2026-03-31 | 25205.0188 |  | 2026-03-30
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 2100 | 2026-04-15 | 2100 | 2470.5882 |  | 14 | 14. General Expenses | Travel |  |  | 525 |  |  | 2026-02-28 | 617.6471 | 0 | 2026-03-07 | 2100
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 525 |  |  | 2026-03-31 | 617.6471 |  | 2026-04-07
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 525 |  |  | 2026-04-30 | 617.6471 |  | 2026-05-07
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 525 |  |  | 2026-05-31 | 617.6471 |  | 2026-06-07
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | [8 empty] | 0 |  | 0
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
| Panel Procurement Budget | 370794.53 |  | 452188.4512
| Inverter Procurement Budget | 95000 |  | 115853.6585
| Mounting Structure Budget | 58482 |  | 71319.5122
| DC Equipment Budget | 69414.8 |  | 84652.1951
| AC Equipment Budget | 198443.487 |  | 242004.2524
| Monitoring Budget | 49000 |  | 59756.0976
| Optional Extras Budget | 0 |  | 0
| MV Equipment Budget | 0 |  | 0
| ADD ON | 4000 |  | 4494.382
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 32490 |  | 38223.5294
| DC Installer Budget | 75810 |  | 89188.2353
| In-House Expense Budget | 90875.739 |  | 106912.6341
| Compliance Budget | 89000 |  | 104705.8824
| Offloading Budget | 8500 |  | 10000
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 0 |  | 0
| On Site Security | 28800 |  | 33882.3529
| Roof Access Budget for Installers | 21741.9 |  | 25578.7059
| EPC Management Fee | 0 |  | 0
| ADD ON | 0 |  | 0
Expenses
| Total EE Expense Budget | 2100 |  | 2470.5882

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-11-10 to 2031-05-05
PLANNED |  | CHECK | CHECK
| Planned Revenue | 1441230.4772 | 1441230.4772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720615.2386 | 0 | 0 | 0 | 0 | 144123.0477 | 0 | 360307.6193 | 0 | 0 | 144123.0477 | 72061.5239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720615.2386 | 720615.2386 | 720615.2386 | 720615.2386 | 720615.2386 | 864738.2863 | 864738.2863 | 1225045.9056 | 1225045.9056 | 1225045.9056 | 1369168.9534 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772
| Planned Expenditure | 1194452.4559 | 1194452.4559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420132.667 | 50822.8 | 134292 | 89000 | 0 | 15818.459 | 113592 | 0 | 370794.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420132.667 | 470955.467 | 605247.467 | 694247.467 | 694247.467 | 710065.9259 | 823657.9259 | 823657.9259 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559 | 1194452.4559
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720615.2386 | 720615.2386 | 720615.2386 | 720615.2386 | 720615.2386 | 864738.2863 | 444605.6194 | 754090.4387 | 619798.4387 | 530798.4387 | 674921.4864 | 731164.5513 | 617572.5513 | 617572.5513 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213 | 246778.0213
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 1441230.4772 | 1441230.4772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720615.2386 | 0 | 144123.0477 | 0 | 360307.6193 | 0 | 0 | 144123.0477 | 72061.5239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720615.2386 | 720615.2386 | 864738.2863 | 864738.2863 | 1225045.9056 | 1225045.9056 | 1225045.9056 | 1369168.9534 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772 | 1441230.4772
| Actual + Planned Expenditure | 888450.211 | 859970.211 | 0 | 0 | 1742.08 | 0 | 0 | 0 | 9900 | 0 | 2870 | 0 | 0 | 0 | 0 | 0 | 0 | 64918.4725 | 525 | 51934.778 | 0 | 64918.4725 | 199228.401 | 71443.4725 | 12577.5 | 0 | 12983.6945 | 366403.34 | 0 | 0 | 0 | 525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 1742.08 | 1742.08 | 1742.08 | 1742.08 | 11642.08 | 11642.08 | 14512.08 | 14512.08 | 14512.08 | 14512.08 | 14512.08 | 14512.08 | 14512.08 | 79430.5525 | 79955.5525 | 131890.3305 | 131890.3305 | 196808.803 | 396037.204 | 467480.6765 | 480058.1765 | 480058.1765 | 493041.871 | 859445.211 | 859445.211 | 859445.211 | 859445.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211 | 859970.211
| ACTUAL CashFlow |  |  | 0 | 0 | -1742.08 | -1742.08 | -1742.08 | -1742.08 | -11642.08 | -11642.08 | -14512.08 | -14512.08 | -14512.08 | -14512.08 | -14512.08 | -14512.08 | 706103.1586 | 641184.6861 | 784782.7338 | 732847.9558 | 1093155.5751 | 1028237.1026 | 829008.7017 | 901688.2769 | 961172.3008 | 961172.3008 | 948188.6063 | 581785.2663 | 581785.2663 | 581785.2663 | 581785.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663 | 581260.2663
|  | CHECK | CHECK
| Revenue Recognition | 32281.5053 | 1408948.9719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39067.3343 | 0 | 0 | 0 | 914299.9758 | 0 | 0 | 0 | 0 | 299933.2627 | 0 | 0 | 0 | 139102.5431 | 0 | 0 | 0 | 16545.856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 1408948.9719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39067.3343 | 39067.3343 | 39067.3343 | 39067.3343 | 953367.3101 | 953367.3101 | 953367.3101 | 953367.3101 | 953367.3101 | 1253300.5728 | 1253300.5728 | 1253300.5728 | 1253300.5728 | 1392403.1159 | 1392403.1159 | 1392403.1159 | 1392403.1159 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719 | 1408948.9719

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) |  | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | Grand Total
(blank)
1. Panels |  | 0 |  | 452188.4512 |  |  | 452188.4512
2. Inverters | 0 | 0 |  | 115853.6585 |  |  | 115853.6585
3. Mounting Structures |  | 0 |  | 71319.5122 |  |  | 71319.5122
4. DC Equipment |  | 0 |  | 54160.6925 | 28458.7358 | 2032.7668 | 84652.1951
5. Monitoring |  | 0 | 8881.8531 | 42054.7144 |  | 8819.5301 | 59756.0976
6. AC Equipment |  | 0 |  | 35857.1759 | 198975.6413 | 7171.4352 | 242004.2524
8. Product Add On | 0 | 0 |  | 4494.382 |  |  | 4494.382
9. AC & DC installation |  | 0 |  | 31852.9412 | 89188.2353 | 6370.5882 | 127411.7647
10. Site Logistics |  | 0 |  | 17365.2647 | 48622.7412 | 3473.0529 | 69461.0588
11. Due Dilligence |  |  | 22610.8818 | 68954.4721 |  | 13140.5284 | 104705.8824
13. Engineering |  | 0 |  |  | 106912.6341 |  | 106912.6341
14. General Expenses |  | 0 | 617.6471 | 617.6471 | 617.6471 | 617.6471 | 2470.5882
15. Service Add On
12. BDP Commission
7.BESS
Grand Total | 0 | 0 | 32110.382 | 894718.9118 | 472775.6347 | 41625.5487 | 1441230.4772

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) |  | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | Grand Total
(blank)
1. Panels |  |  |  | 260780 |  |  | 260780
2. Inverters |  |  |  | 87212.16 |  |  | 87212.16
3. Mounting Structures |  |  |  | 58482 |  |  | 58482
4. DC Equipment |  |  |  | 67705.7 | 35575.96 | 2541.14 | 105822.8
5. Monitoring |  |  | 8659.1 | 41000 |  | 8598.34 | 58257.44
6. AC Equipment |  |  |  | 29402.8842 | 163160.0259 | 5880.5768 | 198443.487
8. Product Add On |  |  |  | 4000 |  |  | 4000
9. AC & DC installation |  |  |  | 27075 | 75810 | 5415 | 108300
10. Site Logistics |  |  |  | 8189.475 | 22930.53 | 1637.895 | 32757.9
11. Due Dilligence |  |  | 21642.08 | 66000 |  | 12577.5 | 100219.58
13. Engineering |  |  |  |  | 95172.661 |  | 95172.661
14. General Expenses |  |  | 525 | 525 | 525 | 525 | 2100
15. Service Add On
12. BDP Commission |  | 0 |  |  |  |  | 0
7.BESS
Grand Total |  | 0 | 30826.18 | 650372.2192 | 393174.1768 | 37175.4518 | 1111548.0279

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill
2025-12-15 | Builders Break
2025-12-16 | Builders Break
2025-12-17 | Builders Break
2025-12-18 | Builders Break
2025-12-19 | Builders Break
2025-12-20 | Builders Break
2025-12-21 | Builders Break
2025-12-22 | Builders Break
2025-12-23 | Builders Break
2025-12-24 | Builders Break
2025-12-25 | Builders Break
2025-12-26 | Builders Break
2025-12-27 | Builders Break
2025-12-28 | Builders Break
2025-12-29 | Builders Break
2025-12-30 | Builders Break
2025-12-31 | Builders Break
2026-01-01 | Builders Break
2026-01-02 | Builders Break
2026-01-03 | Builders Break
2026-01-04 | Builders Break
2026-01-05 | Builders Break
2026-01-06 | Builders Break
2026-01-07 | Builders Break
2026-01-08 | Builders Break
2026-01-09 | Builders Break
2026-01-10 | Builders Break
2026-01-11 | Builders Break
2026-01-12 | Builders Break
2026-01-13 | Builders Break
2026-01-14 | Builders Break
2026-01-15 | Builders Break
2026-01-16 | Builders Break
2026-03-21 | Human Rights day
2026-04-03 | Good Friday
2026-04-06 | Family Day
2026-04-27 | Freedom Day
2026-05-01 | Workers day
2026-06-16 | Youth Day Holiday
2026-08-09 | Womens Day
2026-08-10 | Womens Day Observerd
2026-09-24 | Heritage Day
2026-12-16 | Day of Reconciliation
2026-12-25 | Christmas Day
2026-12-26 | Day of Goodwill