## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[9 empty] | 2026-02-15 | 2026-02-15
| PROJECT PLAN | Dobsonpoint | [7 empty] | 1
| PROJECT SIZE (kWp) | 422 | [7 empty] | Snaglist in hand with installer
| PROJECT DEVELOPER | Natasha Watkins-Baker
| PROJECT MANAGERS | JT Moorosi
| CONTRACT VALUE | 3894207.6831
| Phase: | QA
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Excepted Status | Comment
|  |  | 59 |  |  | 177 |  | 91.51% | 94.84%
1 | Project Initiation | 2025-04-22 | 42 | 2025-06-03 | 2025-04-22 | 43 | 2025-06-04 | 100% | 100%
1.1 | BD Handover | 2025-04-22 | 1 | 2025-04-23 | 2025-04-22 | 1 | 2025-04-23 | 100% | 100% | [5 empty] | 2026-02-15 | 2026-02-15
1.2 | Project Introduction | 2025-06-02 | 1 | 2025-06-03 | 2025-06-03 | 1 | 2025-06-04 | 100% | 100% |  | Milestone | Start Date | Total Duration | End Date | 1 | 0
1.3 | HSE | 2025-04-22 | 10 | 2025-05-07 | 2025-04-22 | 10 | 2025-05-07 | 100% | 100% |  | Project Initiation | 2025-04-22 | 43 | 2025-06-04
1.4 | Installer Kick Off | 2025-05-26 | 1 | 2025-05-27 | 2025-05-27 | 1 | 2025-05-28 | 100% | 100% |  | Site Establishment | 2025-06-10 | 1 | 2025-06-11
1.5 | Project Review | 2025-05-26 | 1 | 2025-05-27 | 2025-05-27 | 1 | 2025-05-28 | 100% | 100% |  | AC Installation | 2025-05-20 | 142 | 2025-10-09
[11 empty] | DC Works | 2025-05-20 | 195 | 2025-12-01
2 | Site Establishment | 2025-06-09 | 1 | 2025-06-10 | 2025-06-10 | 1 | 2025-06-11 | 100% | 100% |  | Module installation | 2025-06-10 | 168 | 2025-11-25
2.1 | Solar Contractor Establishment | 2025-06-09 | 1 | 2025-06-10 | 2025-06-10 | 1 | 2025-06-11 | 100% | 100% |  | Commissioning | 2025-12-01 | 3 | 2025-12-04
[11 empty] | QA Inspections | 2025-12-04 | 1 | 2025-12-05
3 | AC Installation | 2025-05-19 | 57 | 2025-07-15 | 2025-05-20 | 142 | 2025-10-09 | 100% | 100% |  | Project Closure | 2025-12-05 | 81 | 2026-02-24
3.1 | Inverters delivered | 2025-06-10 | 1 | 2025-06-11 | 2025-05-20 | 1 | 2025-05-21 | 100% | 100%
3.2 | Inverters Mounted | 2025-06-11 | 5 | 2025-06-19 | 2025-07-23 | 2 | 2025-07-25 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-05-19 | 25 | 2025-06-24 | 2025-05-20 | 35 | 2025-07-09 | 100% | 100%
3.4 | AC Works | 2025-06-24 | 15 | 2025-07-15 | 2025-08-02 | 2 | 2025-08-05 | 100% | 100%
3.5 | AC Tie-In | 2025-06-24 | 3 | 2025-06-27 | 2025-10-07 | 2 | 2025-10-09 | 100% | 100% | “⚠️ Two size-5 glands were short on 06 Aug—awaiting delivery; complete final cable connections to the breaker ASAP.”
4 | DC Works | 2025-06-09 | 56 | 2025-08-04 | 2025-05-20 | 195 | 2025-12-01 | 100% | 100%
4.1 | Lifeline Installation (If Applicable) | [6 empty] | 0% | 0%
4.1 | Mounting Structure delivered | 2025-06-09 | 1 | 2025-06-10 | 2025-05-26 | 1 | 2025-05-27 | 100% | 100% | 100%
4.2 | Mounting Structure installation | 2025-06-10 | 15 | 2025-07-02 | 2025-10-08 | 15 | 2025-10-29 | 100% | 100%
4.3 | DC Cable delivered | 2025-06-09 | 1 | 2025-06-10 | 2025-05-20 | 1 | 2025-05-21 | 100% | 100%
4.3 | DC Stringing | 2025-07-21 | 10 | 2025-08-04 | 2025-10-26 | 26 | 2025-12-01 | 100% | 100%
5 | Module installation | 2025-06-25 | 29 | 2025-07-24 | 2025-06-10 | 168 | 2025-11-25 | 100% | 100%
5.1 | Module delivery | 2025-06-25 | 1 | 2025-06-26 | 2025-06-10 | 1 | 2025-06-11 | 100% | 100% | 100%
5.2 | Module mounting | 2025-06-26 | 20 | 2025-07-24 | 2025-10-29 | 19 | 2025-11-25 | 100% | 100%
6 | Commissioning | 2025-08-04 | 3 | 2025-08-07 | 2025-12-01 | 3 | 2025-12-04 | 100% | 100%
6.1 | Commissioning | 2025-08-04 | 1 | 2025-08-05 | 2025-12-01 | 1 | 2025-12-02 | 100% | 100%
6.2 | Practical Completion | 2025-08-05 | 2 | 2025-08-07 | 2025-12-02 | 2 | 2025-12-04 | 100% | 100%
7 | QA Inspections | 2025-08-07 | 1 | 2025-08-08 | 2025-12-04 | 1 | 2025-12-05 | 100% | 100%
7.1 | Red-Team Inspection | 2025-08-07 | 1 | 2025-08-08 | 2025-12-04 | 1 | 2025-12-05 | 100% | 100%
8 | Project Closure | 2025-08-08 | 14 | 2025-08-22 | 2025-12-05 | 81 | 2026-02-24 | 32.08% | 58.7%
8.1 | Equipment serial numbers | 2025-08-08 | 2 | 2025-08-12 | 2025-12-05 | 2 | 2025-12-09 | 100% | 100%
8.2 | Snags completion | 2025-08-08 | 5 | 2025-08-15 | 2026-02-03 | 14 | 2026-02-23 | 10% | 60% | QC snags in progress
8.3 | System Performance Monitoring | 2025-08-15 | 5 | 2025-08-22 | 2026-01-13 | 5 | 2026-01-20 | 100% | 100%
8.4 | Handover documentation | 2025-08-08 | 6 | 2025-08-18 | 2026-02-03 | 9 | 2026-02-16 | 35% | 92.31%
8.5 | Handover to Client | 2025-08-18 | 1 | 2025-08-19 | 2026-02-20 | 1 | 2026-02-23 | 0% | 0% | Dipula Handover
8.6 | Handover to Matriarch | 2025-08-10 | 5 | 2025-08-15 | 2026-02-17 | 5 | 2026-02-24 | 0% | 0%
Formulas:
Planned Start = MIN([Planned Start, row below]:E16)
Planned Start = WORKDAY.INTL([Planned End, row above],0,1,Data!$C3:C14)
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = WORKDAY.INTL([Actual End, row above],0,1,Data!$C3:C14)
Actual End = MAX([Actual End, row below]:K16)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C14)
Excepted Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )
Note on O26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs is this something we can assist with, do you want comments here or on Click up Reply: @Johannes Potgieter lets keep it on ClickUp. I have no idea where this is coming from

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 3894207.6831 |  | 3894207.6831 |  |  |  | Start Date | 3143242.0706 | 2434540.1678 | 686671.8626 | 582623.2382 | 488140.2674 | 533945.6422
2 | Planned Expenditure | 3473977.0262 |  | 3017163.406 | VO PM Limit | Current VO Total
3 | Planned Profit | 420230.6568 |  | 877044.2771 | 21011.5328 | 91474.565 |  | End Date - PC
4 | Planned Margin | 10.79% |  | 22.52%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE |  | MILESTONE NOTES & COMMENTS
1 | Deposit |  | 20% | 778841.5366 |  | 2025-04-30 | 004729 | 2025-05-01 | 2025-04-30
2 | Delivery of Panels |  | 20% | 778841.5366 |  | 2025-07-02 | 004729 | 2025-05-01 | 2025-06-20
3 | Delivery of Inverters |  | 15% | 584131.1525 |  | 2025-06-17 | 004729 | 2025-05-01 | 2025-05-30
4 | Commissioning Complete |  | 15% | 584131.1525 |  | 2025-08-14 | 004729 | 2025-05-01 | 2025-12-11
5 | Final Completion Issued |  | 25% | 973551.9208 |  | 2025-08-15 | 004729 | 2025-05-01 | 2025-12-11
6 | Handover |  | 5% | 194710.3842 |  | 2026-03-02 | 004729 | 2025-05-01 | 2026-01-02
7 | - |  | 0% | 0
|  |  | 100% | 3894207.6831
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 1362972.6891
2 | Delivery of Panels |  | 30% | 1168262.3049
3 | Delivery of Inverters |  | 20% | 778841.5366
4 | Practical Completion |  | 10% | 389420.7683
5 | Handover |  | 5% | 194710.3842
| Total |  | 100% | 3894207.6831
|  |  | 100% | 3894207.6831

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 3473977.0262 |  | 3017163.406 | 456813.6202
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 1194235.4425 |  | 845753 | 348482.4425
2 | 2. Inverters | 210000 |  | 275481.4 | -65481.4
3 | 3. Mounting Structures | 178321.5 |  | 78183.6 | 100137.9
4 | 4. DC Equipment | 320835.6 |  | 347949.7097 | -27114.1097
5 | 5. Monitoring | 49000 |  | 35927.14 | 13072.86
6 | 6. AC Equipment | 472703.7261 |  | 286432.6399 | 186271.0862
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 0 |  | 79000 | -79000
9 | 9. AC & DC installation | 320512.5 |  | 558566.4221 | -238053.9221
10 | 10. Site Logistics | 86776.2 |  | 238550.5983 | -151774.3983
11 | 11. Due Dilligence | 117813.5 |  | 30898.04 | 86915.46
12 | 12. BDP Commission | 92245.7539 |  | 0 | 92245.7539
13 | 13. Engineering | 174707.8037 |  | 48677.596 | 126030.2077
14 | 14. General Expenses | 6825 |  | 8794.13 | -1969.13
15 | 15. Service Add On | 250000 |  | 182949.13 | 67050.87
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 3473977.0262 | 3894207.6831 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 3017163.406
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 1194235.4425 | 2025-07-28 | 1194235.4425 | 1388645.8634 |  | 1 | 1. Panels | Jinko 620W = MENLO | 681 | 1233.8 | 840217.8 | PO3903-DIP-PH2-DOB-20250514 | Menlo: INV0002939 | 2025-05-31 | 1388645.8634 | 0 | 2025-07-28 | 845753
1 |  | Delivery Budget | [7 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | Jinko 620W = MENLO - Replacements | 4 |  | 4935.2 |  | MSA Energy INV0003444 | 2025-11-30 | 0 |  | 2026-01-23
1 | [9 empty] | 1 | 1. Panels | Transport |  |  | 600 |  | MSA Energy INV0003444 | 2025-11-30 | 0 |  | 2026-01-23
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 472703.7261
2 | Inverters | Inverter Budget |  |  | 210000 | 2025-07-17 | 210000 | 244186.0465 |  | 2 | 2. Inverters | Huawei 100KTL - MENLO | 4 | 68870.35 | 275481.4 | PO3903-DIP-PH2-DOB-20250514 | Menlo: Inv0002912 | 2025-05-31 | 244186.0465 | 0 | 2025-07-17 | 275481.4 | DC Equipment | 191083.6
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | AC Labour | 99067.5
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 221445
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 26666.2
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 4810
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 178321.5 | 2025-06-27 | 178321.5 | 207350.5814 |  | 3 | 3. Mounting Structures | Schletter Structure |  |  | 78183.6 | PO3944-DDC-20250521 - RV Approved | Schletter INV1794 | 2025-05-31 | 143056.8331 | -0.001735 | 2025-06-27 | 78183.6 | Other | 0
3 | [9 empty] | 3 | 3. Mounting Structures | Contigency | [5 empty] | 2025-08-31 | 64293.75 |  |  |  | Total | 1024276.0261
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Less 15% | 870634.6222
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | R/Wp | 2.0631
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL - Thula Moya | Installer Price
[23 empty] | AC Equipment | 106823.2699
4 | DC Equipment | DC Cable Budget | 10658.2 |  | 129752 | 2025-07-17 | 320835.6 | 373064.6512 |  | 4 | 4. DC Equipment | DC Cable - MENLO | 10000 | 13.4 | 134000 | PO3903-DIP-PH2-DOB-20250514 | Menlo: Inv0002912 | 2025-05-31 | 143672.0936 | 0 | 2025-07-17 | 347949.7097 | DC Equipment | 213949.7097
4 |  | DC Equipment Budget |  |  | 191083.6 | 2025-07-17 |  |  |  | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | AC Labour | 172647.8032
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | DC Labour | 385918.6189
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Offloading | 10510.2153
4 | [5 empty] | 2025-05-15 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 213949.7097 | 10% | 21394.971 | PO3877-DDC-20250513 - RV Approved | Thula Moya Inv: IN04720 | 2025-05-31 | 22939.2558 |  | 2025-05-15 |  | Scaffolding | 38332.5275
4 | [5 empty] | 0 |  |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 32092.4565 |  | Thula Moya Inv: IN04720 | 2025-05-31 | 34408.8836 |  | 2025-05-15 |  | Storage | 6328.7983
4 | [5 empty] | 0 |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 42789.9419 |  | Thula Moya Inv: IN04800 | 2025-07-31 | 45878.5115 |  | 2025-08-14 |  | Telehandler | 0
4 | [5 empty] | 0 |  |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 17% | 36371.4506 |  | Thula Moya IN04777 | 2025-07-31 | 38996.7348 |  | 2025-07-11 |  | HSE | 2329.0573
[6 empty] | 0 |  |  |  | 4. | 4. DC Equipment | DC Installation Complete |  | 8% | 17115.9768 |  | Thula Moya IN04851 | 2025-08-31 | 18351.4046 |  | 2025-12-18
4 | [9 empty] | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 21394.971 |  | Thula Moya IN04852 | 2025-08-31 | 22939.2558 |  | 2025-12-18 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 21394.971 |  | Thula Moya IN04964 | 2025-11-30 | 22939.2558 |  | 2026-01-29 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 10697.4855 |  | Thula Moya IN04965 | 2025-11-30 | 11469.6279 |  | 2026-02-05 |  | Total | 936840
4 | [9 empty] | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 10697.4855 |  | Thula Moya IN05014 | 2026-01-31 | 11469.6279 |  | 2026-03-07 |  | R/Wp | 2.22
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 34000 | 2025-07-17 | 49000 | 56976.7442 |  | 5 | 5. Monitoring | Smartlogger - MENLO |  |  | 8598.35 | PO3903-DIP-PH2-DOB-20250514 | Menlo: Inv0002912 | 2025-05-31 | 12388.93 | 0.0017938 | 2025-07-17 | 35927.14
5 |  | Revenue Metering |  |  | 15000 | 2025-05-29 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 13695 | PO3834-DIP-Ph2-Dobs-20250429 - RV Approved | Accuenergy - INV ASAI-005360 | 2025-04-30 | 19558.7545 |  | 2025-05-29
[6 empty] | 2025-07-29 |  |  |  | 5 | 5. Monitoring |  |  |  | 214.29 |  | Accenergy - INV ASAI-005800 | 2025-06-30 | 339.8419 |  | 2025-07-29
5 | [5 empty] | 0 |  |  |  | 5 | 5. Monitoring | Techsitter |  |  | 11169 |  | Matriarch Inv: 4451 | 2025-06-30 | 21272.9038 |  | 2025-06-30
5 | [5 empty] | 2025-05-22 |  |  |  | 5 | 5. Monitoring | UPS |  |  | 2250.5 | PO3863-DIP Ph2-20250509 - RV Approved | Frontline INV725690 | 2025-05-31 | 3416.3122 |  | 2025-05-22
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 472703.7261 | 2025-07-29 | 472703.7261 | 549655.4954 |  | 6 | 6. AC Equipment | [7 empty] | 0 | -0.0028141 |  | 286432.6399
6 | [5 empty] | 2025-07-29 |  |  |  | 6 | 6. AC Equipment | PVDB |  |  | 179609.37 | PO3885-DIP-Ph2-Dobson-20250513 - RV Approved | Switchboard Inv: 2-SOI002096 | 2025-06-30 | 344664.9002 |  | 2025-07-29
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | Project Kick Off | 106823.2699 | 10% | 10682.327 | PO3877-DDC-20250513 - RV Approved | Thula Moya Inv: IN04720 | 2025-05-31 | 20825.5286 |  | 2025-05-15
6 | [9 empty] | 6 | 6. AC Equipment | Site Establishment |  | 15% | 16023.4905 |  | Thula Moya Inv: IN04720 | 2025-05-31 | 31238.293 |  | 2025-05-15
6 | [9 empty] | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 21364.654 |  | Thula Moya Inv: IN04800 | 2025-07-31 | 40181.949 |  | 2025-08-14
6 | [9 empty] | 6 | 6. AC Equipment | DC Installation Complete |  | 17% | 18159.9559 |  | Thula Moya IN04777 | 2025-07-31 | 34848.4012 |  | 2025-07-11
[10 empty] | 6 | 6. AC Equipment | DC Installation Complete |  | 8% | 8545.8616 |  | Thula Moya IN04851 | 2025-08-31 | 16399.2476 |  | 2025-12-18
6 | [9 empty] | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 10682.327 |  | Thula Moya IN04852 | 2025-08-31 | 20499.0595 |  | 2025-12-18
6 | [9 empty] | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 10682.327 |  | Thula Moya IN04964 | 2025-11-30 | 20499.0595 |  | 2026-01-29
6 | [9 empty] | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 5341.1635 |  | Thula Moya IN04965 | 2025-11-30 | 10249.5298 |  | 2026-02-05
6 | [9 empty] | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 5341.1635 |  | Thula Moya IN05014 | 2026-01-31 | 10249.5298 |  | 2026-03-07
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 0 | 0 |  | 8 | 8. Product Add On | [8 empty] | 0 |  | 79000
8 | [9 empty] | 8 | 8. Product Add On | Site Delay |  | 13400 | 13400 |  | Thula Moya IN04757 | 2025-06-30 |  |  | 2025-06-26
8 | [9 empty] | 8 | 8. Product Add On | Inverter Cage with Roof - JRL Engineering - Deposit | 46480 | 80% | 37184 | PO4016-DDC-20250620 - RV Approved | JRL Engineering INV00338 | 2025-06-30 |  |  | 2025-06-26
8 | [9 empty] | 8 | 8. Product Add On | Inverter Cage with Roof - JRL Engineering - Balance |  | 20% | 9296 |  | JRL Engineering INV00338 | 2025-06-30 |  |  | 2025-08-07
8 | [9 empty] | 8 | 8. Product Add On | Inverter Cage Amends- JRL Engineering |  | 100% | 3900 | PO4250-DDC-20250820 - RV Approved | JRL Engineering INV00359 | 2025-08-31 |  |  | 2025-08-21
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On | Waterpoints |  |  | 15220 | PO4354-DDC-20251006 - RV Approved | Lutendo Construction: Inv INV00826 | 2025-09-30 |  |  | 2025-10-09
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 99067.5 | 2025-05-15 | 320512.5 | 377073.5294 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0 |  | 558566.4221
9 |  | DC Installation Budget |  |  | 221445 | 2025-05-15 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 558566.4221 | 10% | 55856.6422 | PO3877-DDC-20250513 - RV Approved | Thula Moya Inv: IN04720 | 2025-05-31 | 37707.3529 |  | 2025-05-15
9 | [9 empty] | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 83784.9633 |  | Thula Moya Inv: IN04720 | 2025-05-31 | 56561.0294 |  | 2025-05-15
9 | [9 empty] | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 111713.2844 |  | Thula Moya Inv: IN04800 | 2025-07-31 | 75414.7059 |  | 2025-08-14
9 | [9 empty] | 9 | 9. AC & DC installation | DC Installation Complete |  | 17% | 94956.2918 |  | Thula Moya Inv : IN04777 | 2025-07-31 | 64102.5 |  | 2025-07-11
[10 empty] | 9. | 9. AC & DC installation | DC Installation Complete |  | 8% | 44685.3138 |  | Thula Moya IN04851 | 2025-08-31 | 30165.8824 |  | 2025-12-18
9 | [9 empty] | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 55856.6422 |  | Thula Moya IN04852 | 2025-11-30 | 37707.3529 |  | 2025-12-18
9 | [9 empty] | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 55856.6422 |  | Thula Moya IN04964 | 2025-11-30 | 37707.3529 |  | 2026-01-29
9 | [9 empty] | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 27928.3211 |  | Thula Moya IN04965 | 2025-11-30 | 18853.6765 |  | 2026-02-05
9 | [9 empty] | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 27928.3211 |  | Thula Moya IN05014 | 2026-01-31 | 18853.6765 |  | 2026-03-07
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-07-30 | 86776.2 | 102089.6471 |  | 10 | 10. Site Logistics | [7 empty] | 0 | 0.0011746 |  | 238550.5983
10 |  | Scaffolding |  |  | 26666.2 | 2025-07-31 |  |  |  | 10 | 10. Site Logistics | Security - May: JeeryG & Sons |  |  | 25500 | PO3978-DDC-20250603 - RV Approved | JerryG & Sons InvPO3978-DDC-20250603 | 2025-06-30 | 6312.0266 |  | 2025-07-31
[10 empty] | 10 | 10. Site Logistics | [7 empty] | 0
[6 empty] | 2025-07-11 |  |  |  | 10 | 10. Site Logistics | Security - June |  |  | 25500 |  | JerryG & Sons INV 5 | 2025-06-30 | 23548.3664 |  | 2025-07-11
[6 empty] | 2025-07-31 |  |  |  | 10 | 10. Site Logistics | Security - July |  |  | 26350 |  | JerryG & Sons INV 8 | 2025-07-31 | 24039.7481 |  | 2025-07-31
[6 empty] | 2025-09-01 |  |  |  | 10 | 10. Site Logistics | Security - August |  |  | 26350 |  | JerryG & Sons INV11 | 2025-08-31 | 3799.4302 |  | 2025-09-01
[6 empty] | 2025-10-02 |  |  |  | 10 | 10. Site Logistics | Security - September |  |  | 25500 |  | JerryG & Sons INV13 | 2025-09-30 | 2203.7704 |  | 2025-10-02
[6 empty] | 2025-10-03 |  |  |  | 10 | 10. Site Logistics | Security - October |  |  | 26350 |  | JerryG & Sons INV17 | 2025-10-31 | 1384.28 |  | 2025-11-06
10 |  | Security |  |  | 46800 | 2025-10-04 |  |  |  | 10 | 10. Site Logistics | Security - November |  |  | 25500 |  | JerryG & Sons INV21 | 2025-11-30 | 0 |  | 2025-11-28
10 |  | Storage |  |  | 4810 | 2025-10-05 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [5 empty] | 2025-10-06 |  |  |  | 10 | 10. Site Logistics | Project Kick Off | 57500.5983 | 10% | 5750.0598 | PO3877-DDC-20250513 - RV Approved | Thula Moya Inv: IN04720 | 2025-05-31 | 3727.107 |  | 2025-05-15
10 | [5 empty] | 0 |  |  |  | 10 | 10. Site Logistics | Site Establishment |  | 15% | 8625.0897 |  | Thula Moya Inv: IN04720 | 2025-05-31 | 5590.6605 |  | 2025-05-15
10 | [5 empty] | 0 |  |  |  | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 11500.1197 |  | Thula Moya Inv: IN04800 | 2025-07-31 | 10019.1799 |  | 2025-08-14
10 | [5 empty] | 0 |  |  |  | 10 | 10. Site Logistics | DC Installation Complete |  | 17% | 9775.1017 |  | Thula Moya Inv: IN04777 | 2025-07-31 | 8918.0639 |  | 2025-07-11
[6 empty] | 0 |  |  |  | 10 | 10. Site Logistics | DC Installation Complete |  | 8% | 4600.0479 |  | Thula Moya IN04851 | 2025-08-31 | 3396.8552 |  | 2025-12-18
10 | [5 empty] | 0 |  |  |  | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 5750.0598 |  | Thula Moya IN04852 | 2025-08-31 | 4246.069 |  | 2025-12-18
10 | [5 empty] | 0 |  |  |  | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 5750.0598 |  | Thula Moya IN04964 | 2025-11-30 | 2443.3043 |  | 2026-01-29
10 | [5 empty] | 0 |  |  |  | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 2875.0299 |  | Thula Moya IN04965 | 2025-11-30 | 1230.3922 |  | 2026-02-05
10 | [5 empty] | 0 |  |  |  | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 2875.0299 |  | Thula Moya IN05014 | 2026-01-31 | 1230.3922 |  | 2026-03-07
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2025-04-09 | 117813.5 | 138604.1176 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 11585.8 |  | Sunspot Investments E027 | 2025-07-31 | 50818.1553 | 0.0018918 | 2026-01-29 | 30898.04
11 |  | Structural Sign Off |  |  | 19813.5 | 2025-04-10 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 8212.24 | PO3745-DIP-Ph2-20250313 - RV Approved | L&B Consulting - Invoice 1934 | 2025-04-30 | 37550.8468 |  | 2025-04-10
11 |  | Grid Study |  |  | 80000 | 2025-04-11 |  |  |  | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 |  | Matriarch - INV-5975 | 2025-12-31 | 26915.1281 |  | 2026-01-30
11 |  | Lightning Risk Assessment |  |  | 7000 | 2025-06-26 |  |  |  | 11 | 11. Due Dilligence | Lightning Risk Assessment |  |  | 5100 | PO3844-Dipula Ph2-20250430 - RV Approved | LPS Inv: IN306837 | 2025-04-30 | 23319.9856 |  | 2025-06-26
11 | [5 empty] | 2025-06-27 |  |  |  | 11 | 11. Due Dilligence | [7 empty] | 0
2025-06-28
12 | BDP Commission | Referral Fee |  |  | 76871.4616 | 2025-06-29 | 92245.7539 | 0 |  | 12 | 12. BDP Commission | Referral Fee | [9 empty] | 0
12 | BDP Commission | PD Fee |  |  | 15374.2923 | 2025-06-30 |  |  |  | 12 | 12. BDP Commission | PD Fee
2025-07-01
13 | Engineering | Matriarch Defects Period |  |  | 36877.4809 | 2025-07-02 | 174707.8037 | 198531.5951 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 48677.596 |  |  | 2026-02-28 | 198531.5951 | 0 | 2026-02-26 | 48677.596
13 |  | Management |  |  | 22285.7143 | 2025-07-03 |  |  |  | 13 | 13. Engineering | Management |  |  | 0 |  |  | 2026-02-28 | 0 |  | 2026-02-26
13 |  | Project manager |  |  | 66300 | 2025-07-04 |  |  |  | 13 | 13. Engineering | Project manager |  |  | 0 |  |  | 2026-02-28 | 0 |  | 2026-02-26
13 |  | Planner time |  |  | 28971.4286 | 2025-07-05 |  |  |  | 13 | 13. Engineering | Planner time |  |  | 0 |  |  | 2026-02-28 | 0 |  | 2026-02-26
13 |  | De Snagging |  |  | 20273.18 | 2025-07-06 |  |  |  | 13 | 13. Engineering | De Snagging |  |  | 0 |  |  | 2026-02-28 | 0 |  | 2026-02-26
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 6825 | 2025-03-31 | 6825 | 8029.4118 |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  | 2025-04-30 | 0 | -0.0004171 | 2025-03-31 | 8794.13
14 | [5 empty] | 2025-04-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  | 2025-04-30 | 0 |  | 2025-04-30
14 | [5 empty] | 2025-06-09 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 1399.46 |  | Expense Claim | 2025-05-31 | 1819.1539 |  | 2025-06-09
14 | [5 empty] | 2025-07-04 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 1610.1 |  | Expense Claim | 2025-06-30 | 2264.0643 |  | 2025-07-04
14 | [5 empty] | 2025-08-07 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 2045.03 |  | Expense Claim | 2025-07-31 | 1130.3353 |  | 2025-08-07
14 | [5 empty] | 2025-09-05 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 72.87 |  | Expense Claim | 2025-08-31 | 81.5479 |  | 2025-09-05
14 | [5 empty] | 2025-09-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-09-30 | 0 |  | 2025-09-30
14 | [5 empty] | 2025-10-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 3363.46 |  | Expense Claim | 2025-10-31 | 1613.8362 |  | 2025-11-06
14 | [5 empty] | 2025-11-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 59.5 |  | Expense Claim | 2025-11-30 | 676.8776 |  | 2025-12-05
14 | [5 empty] | 2025-12-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 154.7 |  | Expense Claim | 2025-12-31 | 201.3772 |  | 2026-01-08
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 89.01 |  | Expense Claim | 2026-01-31 | 242.2199 |  | 2026-02-05
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | Welcome Bonus |  |  | 250000 | 2025-09-08 | 250000 | 250000 |  | 15 | 15. Service Add On | [8 empty] | 0 |  | 182949.13
15 | [5 empty] | 2025-09-09 |  |  |  | 15 | 15. Service Add On
15 | [5 empty] | 2025-09-10 |  |  |  | 15 | 15. Service Add On
15 | [5 empty] | 2025-09-11 |  |  |  | 15 | 15. Service Add On | VO - Installation of DC | 50% | 182949.13 | 91474.565 |  | Thula Moya - IN04887 | 2025-09-30 | 125000 |  | 2025-09-11
15 | [5 empty] | 2025-10-15 |  |  |  | 15 | 15. Service Add On |  |  |  | 91474.565 |  | Thula Moya - IN04887 | 2025-09-30 | 125000 |  | 2025-12-12
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
| Panel Procurement Budget | 1194235.4425 |  | 1388645.8634
| Inverter Procurement Budget | 210000 |  | 244186.0465
| Mounting Structure Budget | 178321.5 |  | 207350.5814
| DC Equipment Budget | 320835.6 |  | 373064.6512
| AC Equipment Budget | 472703.7261 |  | 549655.4954
| Monitoring Budget | 49000 |  | 56976.7442
| Optional Extras Budget | 0 |  | 0
| MV Metering Budget | 0 |  | 0
| ADD ON | 0 |  | 0
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 99067.5 |  | 116550
| DC Installer Budget | 221445 |  | 260523.5294
| In-House Expense Budget | 174707.8037 |  | 198531.5951
| Compliance Budget | 117813.5 |  | 138604.1176
| Offloading Budget | 8500 |  | 10000
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 4810 |  | 5658.8235
| On Site Security | 46800 |  | 55058.8235
| Roof Access Budget for Installers | 26666.2 |  | 31372
| EPC Management Fee | 0 |  | 0
| ADD ON | 250000 |  | 250000
Expenses
| Total EE Expense Budget | 6825 |  | 8029.4118
Note on W162: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 3894207.6831 | 3894207.6831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 778841.5366 | 0 | 0 | 0 | 0 | 0 | 0 | 584131.1525 | 0 | 778841.5366 | 0 | 0 | 0 | 0 | 0 | 1557683.0732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194710.3842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 778841.5366 | 778841.5366 | 778841.5366 | 778841.5366 | 778841.5366 | 778841.5366 | 778841.5366 | 1362972.6891 | 1362972.6891 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831
| Planned Expenditure | 3473977.0262 | 3473977.0262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6825 | 110813.5 | 0 | 0 | 0 | 0 | 320512.5 | 0 | 15000 | 0 | 0 | 0 | 262192.9616 | 190082.096 | 0 | 564835.6 | 0 | 1702105.3686 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 51610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6825 | 117638.5 | 117638.5 | 117638.5 | 117638.5 | 117638.5 | 438151 | 438151 | 453151 | 453151 | 453151 | 453151 | 715343.9616 | 905426.0577 | 905426.0577 | 1470261.6577 | 1470261.6577 | 3172367.0262 | 3172367.0262 | 3172367.0262 | 3172367.0262 | 3172367.0262 | 3172367.0262 | 3422367.0262 | 3422367.0262 | 3422367.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262 | 3473977.0262
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6825 | -117638.5 | -117638.5 | -117638.5 | 661203.0366 | 661203.0366 | 340690.5366 | 340690.5366 | 325690.5366 | 325690.5366 | 325690.5366 | 909821.6891 | 647628.7275 | 1236388.168 | 1236388.168 | 671552.568 | 671552.568 | -1030552.8005 | -1030552.8005 | 527130.2727 | 527130.2727 | 527130.2727 | 527130.2727 | 277130.2727 | 277130.2727 | 277130.2727 | 225520.2727 | 225520.2727 | 225520.2727 | 225520.2727 | 225520.2727 | 225520.2727 | 225520.2727 | 225520.2727 | 225520.2727 | 225520.2727 | 225520.2727 | 225520.2727 | 225520.2727 | 225520.2727 | 225520.2727 | 225520.2727 | 225520.2727 | 225520.2727 | 225520.2727 | 225520.2727 | 225520.2727 | 225520.2727 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568 | 420230.6568
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 3894207.6831 | 3894207.6831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 778841.5366 | 0 | 0 | 0 | 584131.1525 | 0 | 0 | 778841.5366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1557683.0732 | 0 | 0 | 194710.3842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 778841.5366 | 778841.5366 | 778841.5366 | 778841.5366 | 1362972.6891 | 1362972.6891 | 1362972.6891 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 2141814.2257 | 3699497.2989 | 3699497.2989 | 3699497.2989 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831 | 3894207.6831
| Actual + Planned Expenditure | 3017163.406 | 3017163.406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8212.24 | 0 | 0 | 0 | 0 | 234210 | 2250.5 | 13695 | 0 | 1399.46 | 0 | 133867.6 | 12779.1 | 184762.8 | 418079.75 | 0 | 1071891.46 | 11341.03 | 187368 | 3900 | 0 | 26422.87 | 91474.565 | 0 | 0 | 25500 | 15220 | 0 | 0 | 0 | 29713.46 | 0 | 0 | 25500 | 59.5 | 91474.565 | 168631.2 | 0 | 0 | 154.7 | 0 | 5535.2 | 111269.8 | 46931.01 | 0 | 0 | 48677.596 | 46842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8212.24 | 8212.24 | 8212.24 | 8212.24 | 8212.24 | 242422.24 | 244672.74 | 258367.74 | 258367.74 | 259767.2 | 259767.2 | 393634.8 | 406413.9 | 591176.7 | 1009256.45 | 1009256.45 | 2081147.91 | 2092488.94 | 2279856.94 | 2283756.94 | 2283756.94 | 2310179.81 | 2401654.375 | 2401654.375 | 2401654.375 | 2427154.375 | 2442374.375 | 2442374.375 | 2442374.375 | 2442374.375 | 2472087.835 | 2472087.835 | 2472087.835 | 2497587.835 | 2497647.335 | 2589121.9 | 2757753.1 | 2757753.1 | 2757753.1 | 2757907.8 | 2757907.8 | 2763443 | 2874712.8 | 2921643.81 | 2921643.81 | 2921643.81 | 2970321.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406 | 3017163.406
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8212.24 | -8212.24 | -8212.24 | 770629.2966 | 770629.2966 | 536419.2966 | 534168.7966 | 1104604.9491 | 1104604.9491 | 1103205.4891 | 1882047.0257 | 1748179.4257 | 1735400.3257 | 1550637.5257 | 1132557.7757 | 1132557.7757 | 60666.3157 | 49325.2857 | -138042.7143 | -141942.7143 | -141942.7143 | -168365.5843 | -259840.1493 | -259840.1493 | -259840.1493 | -285340.1493 | -300560.1493 | -300560.1493 | -300560.1493 | -300560.1493 | -330273.6093 | -330273.6093 | -330273.6093 | -355773.6093 | -355833.1093 | 1110375.3989 | 941744.1989 | 941744.1989 | 1136454.5831 | 1136299.8831 | 1136299.8831 | 1130764.6831 | 1019494.8831 | 972563.8731 | 972563.8731 | 972563.8731 | 923886.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771 | 877044.2771
|  | CHECK | CHECK
| Revenue Recognition | -0.00010599 | 3894207.6832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80429.5869 | 0 | 0 | 0 | 2150183.3435 | 0 | 0 | 0 | 0 | 398402.1033 | 0 | 0 | 0 | 394348.2848 | 0 | 0 | 0 | 184172.5022 | 0 | 0 | 0 | 0 | 252203.7704 | 0 | 0 | 0 | 2998.1162 | 0 | 0 | 0 | 163776.4294 | 0 | 0 | 0 | 0 | 27116.5053 | 0 | 0 | 0 | 42045.4462 | 0 | 0 | 0 | 198531.5951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 3894207.6832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80429.5869 | 80429.5869 | 80429.5869 | 80429.5869 | 2230612.9303 | 2230612.9303 | 2230612.9303 | 2230612.9303 | 2230612.9303 | 2629015.0336 | 2629015.0336 | 2629015.0336 | 2629015.0336 | 3023363.3184 | 3023363.3184 | 3023363.3184 | 3023363.3184 | 3207535.8206 | 3207535.8206 | 3207535.8206 | 3207535.8206 | 3207535.8206 | 3459739.591 | 3459739.591 | 3459739.591 | 3459739.591 | 3462737.7072 | 3462737.7072 | 3462737.7072 | 3462737.7072 | 3626514.1366 | 3626514.1366 | 3626514.1366 | 3626514.1366 | 3626514.1366 | 3653630.6419 | 3653630.6419 | 3653630.6419 | 3653630.6419 | 3695676.0881 | 3695676.0881 | 3695676.0881 | 3695676.0881 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832 | 3894207.6832

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | Grand Total
(blank)
1. Panels |  |  | 1388645.8634 | [5 empty] | 0 |  | 0 |  |  | 1388645.8634
2. Inverters |  |  | 244186.0465 | [7 empty] | 0 |  |  | 244186.0465
3. Mounting Structures | 0 |  | 143056.8331 |  |  | 64293.75 |  |  |  |  | 0 |  |  | 207350.5831
4. DC Equipment |  |  | 201020.233 |  | 84875.2463 | 41290.6604 |  |  | 34408.8836 |  | 0 | 11469.6279 |  | 373064.6512
5. Monitoring |  | 19558.7545 | 15805.2422 | 21612.7457 | [6 empty] | 0 |  |  | 56976.7424
6. AC Equipment |  |  | 52063.8216 | 344664.9002 | 75030.3502 | 36898.3071 |  |  | 30748.5893 |  | 0 | 10249.5298 |  | 549655.4983
8. Product Add On
9. AC & DC installation |  |  | 94268.3824 |  | 139517.2059 | 30165.8824 |  |  | 94268.3824 |  | 0 | 18853.6765 |  | 377073.5294
10. Site Logistics | 0 |  | 9317.7674 | 29860.3931 | 42976.9919 | 11442.3544 | 2203.7704 | 1384.28 | 3673.6965 |  | 0 | 1230.3922 |  | 102089.6459
11. Due Dilligence | 0 | 60870.8323 |  |  | 50818.1553 |  |  |  |  | 26915.1281 |  |  |  | 138604.1158
13. Engineering | [10 empty] | 0 |  | 198531.5951 | 198531.5951
14. General Expenses |  | 0 | 1819.1539 | 2264.0643 | 1130.3353 | 81.5479 | 0 | 1613.8362 | 676.8776 | 201.3772 | 0 | 242.2199 |  | 8029.4122
15. Service Add On | [6 empty] | 250000 | [6 empty] | 250000
12. BDP Commission
7.BESS
Grand Total | 0 | 80429.5869 | 2150183.3435 | 398402.1033 | 394348.2848 | 184172.5022 | 252203.7704 | 2998.1162 | 163776.4294 | 27116.5053 | 0 | 42045.4462 | 198531.5951 | 3894207.6832

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | Grand Total
(blank)
1. Panels |  |  | 840217.8 | [5 empty] | 5535.2 |  |  |  | 845753
2. Inverters |  |  | 275481.4 | [9 empty] | 275481.4
3. Mounting Structures |  |  | 78183.6 | [9 empty] | 78183.6
4. DC Equipment |  |  | 187487.4274 |  | 79161.3926 | 38510.9477 |  |  | 32092.4565 |  | 10697.4855 |  | 347949.7097
5. Monitoring |  | 13695 | 10848.85 | 11383.29 | [8 empty] | 35927.14
6. AC Equipment |  |  | 26705.8175 | 179609.37 | 39524.6099 | 19228.1886 |  |  | 16023.4905 |  | 5341.1635 |  | 286432.6399
8. Product Add On |  |  |  | 59880 |  | 3900 | 15220 | [5 empty] | 79000
9. AC & DC installation |  |  | 139641.6055 |  | 206669.5762 | 44685.3138 |  |  | 139641.6055 |  | 27928.3211 |  | 558566.4221
10. Site Logistics |  |  | 14375.1496 | 51000 | 47625.2214 | 36700.1077 | 25500 | 26350 | 34125.0897 |  | 2875.0299 |  | 238550.5983
11. Due Dilligence |  | 13312.24 |  |  | 11585.8 |  |  |  |  | 6000 |  |  | 30898.04
13. Engineering | [11 empty] | 48677.596 | 48677.596
14. General Expenses |  | 0 | 1399.46 | 1610.1 | 2045.03 | 72.87 | 0 | 3363.46 | 59.5 | 154.7 | 89.01 |  | 8794.13
15. Service Add On | [6 empty] | 182949.13 | [5 empty] | 182949.13
12. BDP Commission
7.BESS
Grand Total |  | 27007.24 | 1574341.11 | 303482.76 | 386611.63 | 143097.4278 | 223669.13 | 29713.46 | 227477.3422 | 6154.7 | 46931.01 | 48677.596 | 3017163.406

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate | [5 empty] | FINANCIAL CLOSE CERTIFICATE
Project Name: | Dobsonpoint
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion: |  |  |  | 1. Financial Close | 1. Financial Close
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 0.65851 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.33687 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.2279 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 0.5454 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
Dobsonpoint |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Dobsonpoint | 0 | 0 | 0