## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application | Declined
PTI
Commissioning Approval | Abandoned

## Project Plan
[9 empty] | 2026-02-11 | 2026-02-11
| PROJECT PLAN | Milkwood Square | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 375
| PROJECT DEVELOPER | Peet Verenney
| PROJECT MANAGERS | Lloyd Brown
| CONTRACT VALUE | 3199251.4666
| Phase: | Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Expected Status | Comment
|  |  | 44 |  |  | 49 |  | 97.5% | 100%
1 | Project Initiation | 2025-04-09 | 147 | 2025-09-03 | 2025-04-09 | 146 | 2025-09-02 | 100% | 100%
1.1 | BD Handover | 2025-04-09 | 1 | 2025-04-10 | 2025-04-09 | 1 | 2025-04-10 | 100% | 100%
1.2 | Project Introduction | 2025-08-20 | 1 | 2025-08-21 | 2025-08-19 | 1 | 2025-08-20 | 100% | 100%
1.3 | HSE | 2025-08-20 | 10 | 2025-09-03 | 2025-08-19 | 10 | 2025-09-02 | 100% | 100%
1.4 | Installer Kick Off | 2025-08-20 | 1 | 2025-08-21 | 2025-08-19 | 1 | 2025-08-20 | 100% | 100%
1.5 | Project Review | 2025-08-26 | 1 | 2025-08-27 | 2025-08-27 | 1 | 2025-08-28 | 100% | 100%
2 | Site Establishment | 2025-05-12 | 115 | 2025-09-04 | 2025-05-12 | 114 | 2025-09-03 | 100% | 100%
2.1 | Solar Contractor Establishment | 2025-09-03 | 1 | 2025-09-04 | 2025-09-02 | 1 | 2025-09-03 | 100% | 100% |  | 35 | Net Work Days
2.2 | Roof Construction | 2025-05-12 | 80 | 2025-09-02 | 2025-05-12 | 80 | 2025-09-02 | 100% | 100%
3 | AC Installation | 2025-08-13 | 57 | 2025-10-09 | 2025-08-11 | 67 | 2025-10-17 | 100% | 100% |  | 7 | Total Weeks
3.1 | Inverters delivered | 2025-08-28 | 1 | 2025-08-29 | 2025-09-04 | 0 | 2025-09-04 | 100% | 100% |  | 53.5714 | kW/Week Installation Rate
3.2 | Inverters Mounted | 2025-09-04 | 5 | 2025-09-11 | 2025-10-01 | 2 | 2025-10-03 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-08-13 | 25 | 2025-09-17 | 2025-08-11 | 25 | 2025-09-15 | 100% | 100%
3.4 | AC Works | 2025-09-17 | 15 | 2025-10-09 | 2025-10-03 | 10 | 2025-10-17 | 100% | 100%
3.5 | AC Tie-In | 2025-09-17 | 3 | 2025-09-22 | 2025-10-03 | 3 | 2025-10-08 | 100% | 100%
4 | DC Works | 2025-09-04 | 27 | 2025-10-01 | 2025-09-04 | 18 | 2025-09-22 | 100% | 100%
4.1 | Lifeline Installation (If Applicable) | [6 empty] | 100% | 100%
4.1 | Mounting Structure delivered | 2025-09-04 | 1 | 2025-09-05 | 2025-09-04 | 0 | 2025-09-04 | 100% | 100%
4.2 | Mounting Structure installation | 2025-09-04 | 10 | 2025-09-18 | 2025-09-05 | 9 | 2025-09-18 | 100% | 100%
4.3 | DC Cable delivered | 2025-09-04 | 1 | 2025-09-05 | 2025-09-15 | 1 | 2025-09-16 | 100% | 100%
4.3 | DC Stringing | 2025-09-28 | 3 | 2025-10-01 | 2025-09-17 | 3 | 2025-09-22 | 100% | 100%
5 | Module installation | 2025-08-28 | 34 | 2025-10-01 | 2025-09-04 | 14 | 2025-09-18 | 100% | 100%
5.1 | Module delivery | 2025-08-28 | 1 | 2025-08-29 | 2025-09-04 | 0 | 2025-09-04 | 100% | 100%
5.2 | Module mounting | 2025-09-18 | 8 | 2025-10-01 | 2025-09-06 | 9 | 2025-09-18 | 100% | 100%
6 | Commissioning | 2025-10-09 | 8 | 2025-10-17 | 2025-10-17 | 4 | 2025-10-21 | 100% | 100%
6.1 | Commissioning | 2025-10-09 | 1 | 2025-10-10 | 2025-10-17 | 1 | 2025-10-20 | 100% | 100%
6.2 | Practical Completion | 2025-10-10 | 5 | 2025-10-17 | 2025-10-20 | 1 | 2025-10-21 | 100% | 100%
7 | QA Inspections | 2025-10-17 | 3 | 2025-10-20 | 2025-10-21 | 1 | 2025-10-22 | 100% | 100%
7.1 | Red-Team Inspection | 2025-10-17 | 1 | 2025-10-20 | 2025-10-21 | 1 | 2025-10-22 | 100% | 100%
8 | Project Closure | 2025-10-20 | 24 | 2025-11-13 | 2025-11-10 | 24 | 2025-12-04 | 80% | 100%
8.1 | Equipment serial numbers | 2025-10-20 | 2 | 2025-10-22 | 2025-11-17 | 2 | 2025-11-19 | 100% | 100%
8.2 | Snags completion | 2025-10-20 | 2 | 2025-10-22 | 2025-11-10 | 2 | 2025-11-12 | 100% | 100%
8.3 | System Performance Monitoring | 2025-10-22 | 5 | 2025-10-29 | 2025-11-12 | 5 | 2025-11-19 | 100% | 100%
8.4 | Handover documentation | 2025-10-29 | 10 | 2025-11-12 | 2025-11-19 | 10 | 2025-12-03 | 100% | 100%
8.5 | Handover to Client | 2025-11-12 | 1 | 2025-11-13 | 2025-12-03 | 1 | 2025-12-04 | 100% | 100% | check with Dorpstraat
8.6 | Handover to Matriarch | 2025-10-24 | 5 | 2025-10-31 | 2025-11-24 | 5 | 2025-12-01 | 0% | 100% | has this been done?
plus one day as rain delay 11 September
plus one day as rain delay 16 September
Formulas:
Planned Start = MIN([Planned Start, row below]:E16)
Planned Start = [Planned Start, row above]
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = [Actual Start, row above]
Actual End = MAX([Actual End, row below]:K16)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C14)
Expected Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  | FINANCIAL REVIEW | TIMELINE REVIEW |  | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 3199251.4666 |  | 3137319.4266 |  | 3199251.4666 | Start Date |  | 2283369.5185 | 1581620.6775 | 915881.9462 | 693300.8 | 915881.9462 | 693300.8
2 | Planned Expenditure | 2724095.5806 |  | 2274921.4775 |  | 2384966.2233 | 2025-09-03
3 | Planned Profit | 475155.886 |  | 862397.9491 |  | 814285.2433 | End Date - PC
4 | Planned Margin | 14.85% |  | 27.49% |  | 25.45% | 2025-10-17
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE |  | MILESTONE NOTES & COMMENTS
1 | Deposit |  | 50% | 1218506.09 | 2025-07-11 | 004790 + CN 004857 + 004857 | 2025-04-24 | 2025-04-25
1 | Deposit |  |  | 182776.07 | 2025-07-11 | 004790 + CN 004857 + 004857 | 2025-04-24 | 2025-07-18
1 | Deposit |  |  | 198343.5733 | 2025-07-11 | 004790 + CN 004857 + 004857 | 2025-04-24 | 2026-01-16
2 | Delivery of Panels |  | 25% | 799812.8667 | 2025-09-11 | 004790 + CN 004857 + 004857 | 2025-04-24 | 2025-09-18
3 | Delivery of Inverters |  | 10% | 319925.1467 | 2025-09-11 | 004790 + CN 004857 + 004857 | 2025-04-24 | 2025-09-18
4 | Installation Complete |  | 10% | 319925.1467 | 2025-10-23 | 004790 + CN 004857 + 004857 | 2025-04-24 | 2025-10-24
5 | Commissioning Complete |  | 5% | 159962.5733 | 2025-10-31 | 004790 + CN 004857 + 004857 | 2025-04-24 | 2026-01-02
6 | Reduction in Size |  | 0% | -61932.04 |  | 004790 + CN 004857 + 004857 | 21/10/2025 | 2025-10-24
7 | - |  | 0% | 0
|  |  | 100% | 3137319.4266
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
3607917.3406
-3379822.48
228094.8606
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 1098061.7993
2 | Delivery of Panels |  | 30% | 941195.828
3 | Delivery of Inverters |  | 20% | 627463.8853
4 | Practical Completion |  | 10% | 313731.9427
5 | Handover |  | 5% | 156865.9713
| Total |  | 100% | 3137319.4266
|  |  | 100% | 3137319.4266

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abandoned
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 2724095.5806 |  | 2274921.4775 | 449174.1031
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 1036485.45 |  | 756608.4 | 279877.05
2 | 2. Inverters | 236694 |  | 206611.05 | 30082.95
3 | 3. Mounting Structures | 154440 |  | 96112.72 | 58327.28
4 | 4. DC Equipment | 184231 |  | 310459.2475 | -126228.2475
5 | 5. Monitoring | 174000 |  | 128277.96 | 45722.04
6 | 6. AC Equipment | 314004.9 |  | 185011.8 | 128993.1
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 0 |  | 18600 | -18600
9 | 9. AC & DC installation | 315975 |  | 462250 | -146275
10 | 10. Site Logistics | 52509.7667 |  | 16050 | 36459.7667
11 | 11. Due Dilligence | 110305 |  | 26180 | 84125
12 | 12. BDP Commission | 0 |  | 23757.79 | -23757.79
13 | 13. Engineering | 138800.464 |  | 39216.49 | 99583.974
14 | 14. General Expenses | 6650 |  | 5786.02 | 863.98
15 | 15. Service Add On | 0 |  | 0 | 0
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 2724095.5806 | 3199251.4666 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 2274921.4775
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | ERROR on REV |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 1036485.45 | 2025-10-23 | 1036485.45 | 1219394.6471 |  | 1 | 1. Panels | Jinko 620W - Mono - 66HL4M-(V) Mono-Facial module (N-Type) | 662 | 1227.6 | 812671.2 |  | Menlo INV0003178 | 2025-08-31 | 1282693.481 | 0 | 2025-10-24 | 756608.4
1 |  | Delivery Budget |  |  |  | 2025-10-24 |  |  |  | 1 | 1. Panels |  |  | 1.98 |  |  |  |  | 0
1 | [5 empty] | 2025-10-25 |  |  |  | 1 | 1. Panels | Futile trip delivery cost |  |  | 9000 |  | Menlo INV0003178 | 2025-08-31 | 14205.3039 |  | 2025-10-24
1 | [5 empty] | 2025-08-31 |  |  |  | 1 | 1. Panels | Credit Note 40 modules - we only require 622 modules |  |  | -49104 |  | Menlo CRN0000244 | 2025-08-31 | -77504.1378 |  | 2025-08-31
1 | [5 empty] | 2025-09-01 |  |  |  | 1 | 1. Panels | Jinko 620W - Mono - 66HL4M-(V) returned to stock | -13 | 1227.6 | -15958.8 |  | Allocated to Cpt Storeoom | 2025-10-31 |  |  | 2025-10-31
1 | [5 empty] | 2025-09-02 |  |  |  | 1 | 1. Panels | 4 broken panels (17 panels returned in total |  | 385640 |  |  |  |  | 0 |  |  |  | BUDGET | Installer Allocation
[6 empty] | 2025-09-03 | [16 empty] | AC Equipment | 314004.9
2 | Inverters | Inverter Budget |  |  | 236694 | 2025-09-04 | 236694 | 278463.5294 |  | 2 | 2. Inverters | Huawei 100KTL | 3 | 68870.35 | 206611.05 |  | Menlo - INV0003178 | 2025-08-31 | 278463.5294 | 0 | 2025-10-24 | 206611.05 | DC Equipment | 114091
2 | [5 empty] | 2025-09-05 |  |  |  | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | AC Labour | 96525
2 | [5 empty] | 2025-09-06 |  |  |  | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 219450
2 | [5 empty] | 2025-09-07 |  |  |  | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [5 empty] | 2025-09-08 |  |  |  | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 39323.1
2 | [5 empty] | 2025-09-09 |  |  |  | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 0
2 | [5 empty] | 2025-09-10 |  |  |  | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
2025-09-11
3 | Mounting Structures | Structure Budget |  |  | 154440 | 2025-09-12 | 154440 | 181694.1176 |  | 3 | 3. Mounting Structures | Schletter Structure |  |  | 96112.72 | PO4291-MLKW-20250901 - RV Approved | Schletter - INV2155 | 2025-09-30 | 181694.1176 | 0 | 2025-10-30 | 96112.72 | Other | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Total | 791894
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Less 15% | 673109.9
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | R/Wp | 1.795
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL - Cosmic Sun | Installer Price
[23 empty] | AC Equipment | 93700
4 | DC Equipment | DC Cable Budget |  |  | 70140 | 2025-09-04 | 184231 | 216742.3529 |  | 4 | 4. DC Equipment | DC Cable | 8000 | 13.5 | 108000 |  | Menlo - INV0003178 | 2025-08-31 | 102014.5162 | 0 | 2025-10-24 | 310459.2475 | DC Equipment | 121459.25
4 |  | DC Equipment Budget |  |  | 114091 | 2025-09-05 |  |  |  | 4 | 4. DC Equipment | DC Cable - moved from Blackheath | 6000 | 13.5 | 81000 |  | Allocated from Spear - Blackheath | 2025-09-30 | 0 |  | 2025-09-30 |  | AC Labour | 147050 | 0.43765
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | DC Labour | 315200 | 0.9381
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Offloading | 4950
4 | [5 empty] | 2025-09-01 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 121459.25 | 10% | 12145.93 | PO4241-MLKW-20250819 - RV Approved | CS_MWS_001 | 2025-08-31 | 11472.7886 |  | 2025-09-01 |  | Container | 6600
4 | [5 empty] | 2025-09-11 |  |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 18218.88 |  | CS_MWS_001 | 2025-08-31 | 17209.1688 |  | 2025-09-11 |  | HSE | 4500
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 24291.85 |  | CS_MWS_002 | 2025-08-31 | 22945.5678 |  | 2025-10-30 |  | Telehandler | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 30364.8125 |  | CS_MWS_002 | 2025-08-31 | 28681.9598 |  | 2025-10-09 |  | HSE | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 12145.925 |  | CS_MWS_002 | 2025-08-31 | 11472.7839 |  | 2025-10-30 |  | Other | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 12145.925 |  | CS_MWS_002 | 2025-08-31 | 11472.7839 |  | 2025-10-30 |  | Other | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 6072.9625 |  | CS_MWS_002 | 2025-08-31 | 5736.392 |  | 2025-11-19 |  | Total | 693459.25
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 6072.9625 |  | CS_MWS_002 | 2025-08-31 | 5736.392 |  | 2025-11-19 |  | R/Wp | 1.8492
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 159000 | 2025-09-04 | 174000 | 204705.8824 |  | 5 | 5. Monitoring | Smartlogger |  |  | 8598.34 |  | Menlo - INV0003178 | 2025-08-31 | 12898.4893 | -0.0011388 | 2025-10-24 | 128277.96
5 |  | Revenue Metering |  |  | 15000 | 2025-08-29 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 21048 | PO4072-MLW-20250630 - RV Approved | Accuenergy Inv: ASAI 005873 | 2025-07-31 | 28715.1406 |  | 2025-08-29
5 | [5 empty] | 2025-09-30 |  |  |  | 5 | 5. Monitoring | Techsitter |  |  | 11169 |  | Matriarch - INV-5207 | 2025-10-31 | 17959.9909 |  | 2025-11-13
[10 empty] | 5 | 5. Monitoring | Courier of Techsitter Meter |  |  | 297.62 |  | DSV Inv:180147748 | 2025-09-30 | 478.5793 |  | 2025-10-30
5 | [5 empty] | 1900-01-30 |  |  |  | 5 | 5. Monitoring | APEX |  |  | 85000 | PO4318-MLKW-20250916 - RV Approved | Rubicon - INVWCRE-0070809 | 2025-09-30 | 142740.1379 |  | 2025-10-30
5 | [5 empty] | 2025-09-11 |  |  |  | 5 | 5. Monitoring | Powersupply |  |  | 1190 |  | Mantech QUO124941 | 2025-09-30 | 1913.5455 |  | 2025-09-11
5 | [9 empty] | 5 | 5. Monitoring | Lithium Battery |  |  | 975 |  | Allocated from Steelpark | 2026-01-31 | 0 |  | 2026-01-31
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 314004.9 | 2025-09-30 | 314004.9 | 369417.5294 |  | 6 | 6. AC Equipment | PVDB/Comms DB & Tie In Breaker |  |  | 91311.8 | PO4162-MLW-20250725 - RV Approved | Switchboard 2-SOI002244 | 2025-08-31 | 182324.4764 | 0 | 2025-09-30 | 185011.8
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [5 empty] | 2025-09-01 |  |  |  | 6 | 6. AC Equipment | Project Kick Off | 93700 | 10% | 9370 | PO4241-MLKW-20250819 - RV Approved | CS_MWS_001 | 2025-08-31 | 18709.3053 |  | 2025-09-01
6 | [5 empty] | 2025-09-11 |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 14055 |  | CS_MWS_001 | 2025-08-31 | 28063.958 |  | 2025-09-11
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 18740 |  | CS_MWS_002 | 2025-08-31 | 37418.6106 |  | 2025-10-30
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 23425 |  | CS_MWS_002 | 2025-08-31 | 46773.2633 |  | 2025-10-09
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 9370 |  | CS_MWS_002 | 2025-08-31 | 18709.3053 |  | 2025-10-30
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 9370 |  | CS_MWS_002 | 2025-08-31 | 18709.3053 |  | 2025-10-30
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 4685 |  | CS_MWS_002 | 2025-08-31 | 9354.6527 |  | 2025-11-19
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 4685 |  | CS_MWS_002 | 2025-08-31 | 9354.6527 |  | 2025-11-19
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 0 | 0 |  | 8 | 8. Product Add On | [8 empty] | 0 |  | 18600
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On | Material Transport |  |  | 18600 | PO4384-MLKW-20251020 - RV Approved | ABL Transport - 0196 | 2025-10-31 |  |  | 2025-10-24
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 96525 | 2025-08-31 | 315975 | 371735.2941 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0 |  | 462250
9 |  | DC Installation Budget |  |  | 219450 | 2025-09-01 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 462250 | 10% | 46225 | PO4241-MLKW-20250819 - RV Approved | CS_MWS_001 | 2025-08-31 | 37173.5294 |  | 2025-09-01
9 | [5 empty] | 2025-09-11 |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 69337.5 |  | CS_MWS_001 | 2025-08-31 | 55760.2941 |  | 2025-09-11
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 92450 |  | CS_MWS_004 | 2025-10-31 | 74347.0588 |  | 2025-10-30
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 115562.5 |  | CS_MWS_003 | 2025-10-31 | 92933.8235 |  | 2025-10-09
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 46225 |  | CS_MWS_005 | 2025-10-31 | 37173.5294 |  | 2025-10-30
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 46225 |  | CS_MWS_006 | 2025-10-31 | 37173.5294 |  | 2025-10-30
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 23112.5 |  | CS_MWS_007 | 2025-10-31 | 18586.7647 |  | 2025-11-19
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 23112.5 |  | CS_MWS_008 | 2025-11-30 | 18586.7647 |  | 2025-11-19
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-08-31 | 52509.7667 | 61776.1961 |  | 10 | 10. Site Logistics | [7 empty] | 0 | 0 |  | 16050
10 |  | Scaffolding |  |  | 39323.1 | 2025-08-31 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Security |  |  | 0 | 2025-08-31 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 4686.6667 | 2025-08-31 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [5 empty] | 2025-09-01 |  |  |  | 10 | 10. Site Logistics | Project Kick Off | 16050 | 10% | 1605 | PO4241-MLKW-20250819 - RV Approved | CS_MWS_001 | 2025-08-31 | 6177.6196 |  | 2025-09-01
10 | [5 empty] | 2025-09-11 |  |  |  | 10 | 10. Site Logistics | Site Establishment |  | 15% | 2407.5 |  | CS_MWS_001 | 2025-08-31 | 9266.4294 |  | 2025-09-11
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 3210 |  | CS_MWS_002 | 2025-08-31 | 12355.2392 |  | 2025-10-30
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 4012.5 |  | CS_MWS_002 | 2025-08-31 | 15444.049 |  | 2025-10-09
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 1605 |  | CS_MWS_002 | 2025-08-31 | 6177.6196 |  | 2025-10-30
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 1605 |  | CS_MWS_002 | 2025-08-31 | 6177.6196 |  | 2025-10-30
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 802.5 |  | CS_MWS_002 | 2025-08-31 | 3088.8098 |  | 2025-11-19
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 802.5 |  | CS_MWS_002 | 2025-08-31 | 3088.8098 |  | 2025-11-19
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2025-07-29 | 110305 | 129770.5882 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 20180 |  | SunSpot E031 | 2026-01-31 | 83969.1997 | 0.0044124 | 2026-02-05 | 26180
11 |  | Structural Sign Off |  |  | 19305 | 2025-07-29 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 0 |  |  |  | 0
11 |  | Grid Study - Outside of CoCT |  |  | 80000 | 2025-07-29 |  |  |  | 11 | 11. Due Dilligence | Grid Study - Outside of CoCT |  |  | 0 |  |  |  | 0
11 | [5 empty] | 2025-07-29 |  |  |  | 11 | 11. Due Dilligence | Red Team |  |  | 6000 |  | Matriarch - INV-5370 | 2025-10-31 | 45801.3841 |  | 2025-11-30
11 | [5 empty] | 2025-07-29 |  |  |  | 11 | 11. Due Dilligence | [7 empty] | 0
2025-07-29
12 | BDP Commission |  |  |  |  | 2025-07-29 | 0 | 0 |  | 12 | 12. BDP Commission |  |  |  | 11878.895 |  | Auxilio Dei - INV 032 | 2025-07-31 |  |  | 2025-07-29 | 23757.79
12 | BDP Commission |  |  |  |  | 2025-07-29 |  |  |  | 12 | 12. BDP Commission |  |  |  | 11878.895 |  | Auxilio Dei - INV 032 | 2025-07-31 |  |  | 2025-10-30
2025-07-29
13 | Engineering | Matriarch Defects Period |  |  | 32233.064 | 2025-07-29 | 138800.464 | 157727.8 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 39216.49 |  | Matriarch - INV-5369 | 2025-10-31 | 157727.8 | 0 | 2025-11-30 | 39216.49
13 |  | Management |  |  | 15200 | 2025-07-29 |  |  |  | 13 | 13. Engineering | Management |  |  | 0 |  |  |  | 0
13 |  | Project manager |  |  | 51680 | 2025-07-29 |  |  |  | 13 | 13. Engineering | Project manager |  |  | 0 |  |  |  | 0
13 |  | Planner time |  |  | 19760 | 2025-07-29 |  |  |  | 13 | 13. Engineering | Planner time |  |  | 0 |  |  |  | 0
13 |  | De Snagging |  |  | 19927.4 | 2025-07-29 |  |  |  | 13 | 13. Engineering | De Snagging |  |  | 0 |  |  |  | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 6650 | 2025-04-30 | 6650 | 7823.5294 |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  | 2025-04-30 | 0 | -0.001358 | 2025-04-30 | 5786.02
14 | [5 empty] | 2025-05-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-05-31 | 0 |  | 2025-05-31
14 | [5 empty] | 2025-06-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-06-30 | 0 |  | 2025-06-30
14 | [5 empty] | 2025-07-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 2954.75 |  | Expense Claim | 2025-07-31 | 3027.8101 |  | 2025-07-30
14 | [5 empty] | 2025-08-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-08-31 | 0 |  | 2025-08-31
14 | [5 empty] | 2025-09-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 2831.27 |  | Expense Claim | 2025-09-30 | 2054.9406 |  | 2025-10-10
14 | [5 empty] | 2025-10-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-10-31 | 0 |  | 2025-10-30
14 | [5 empty] | 2025-11-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-11-30 | 0 |  | 2025-11-30
14 | [5 empty] | 2025-12-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-12-31 | 2740.78 |  | 2026-01-08
14 | [5 empty] | 2026-01-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  |  | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | [8 empty] | 0 |  | 0
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
| Panel Procurement Budget | 1219394.6471
| Inverter Procurement Budget | 278463.5294
| Mounting Structure Budget | 181694.1176
| DC Equipment Budget | 216742.3529
| AC Equipment Budget | 369417.5294
| Monitoring Budget | 204705.8824
| Optional Extras Budget | 0
| MV Metering Budget | 0
| ADD ON | 0
| Battery System | 0
| Generator | 0
Services
| AC Installer Budget | 113558.8235
| DC Installer Budget | 258176.4706
| In-House Expense Budget | 157727.8
| Compliance Budget | 129770.5882
| Offloading Budget | 10000
| Roof Access Budget for Equipment | 0
| Site storage | 5513.7255
| On Site Security | 0
| Roof Access Budget for Installers | 46262.4706
| EPC Management Fee | 0
| ADD ON | 0
Expenses
| Total EE Expense Budget | 7823.5294

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 3199251.4666 | 3199251.4666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1599625.7333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1119738.0133 | 0 | 0 | 0 | 0 | 0 | 319925.1467 | 159962.5733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1599625.7333 | 1599625.7333 | 1599625.7333 | 1599625.7333 | 1599625.7333 | 1599625.7333 | 1599625.7333 | 1599625.7333 | 1599625.7333 | 2719363.7466 | 2719363.7466 | 2719363.7466 | 2719363.7466 | 2719363.7466 | 2719363.7466 | 3039288.8933 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666 | 3199251.4666
| Planned Expenditure | 2724095.5806 | 2724095.5806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249105.464 | 0 | 0 | 0 | 164034.7667 | 799375 | 154440 | 0 | 0 | 314004.9 | 0 | 0 | 1036485.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6650 | 6650 | 6650 | 6650 | 6650 | 6650 | 6650 | 6650 | 6650 | 6650 | 6650 | 6650 | 6650 | 255755.464 | 255755.464 | 255755.464 | 255755.464 | 419790.2306 | 1219165.2306 | 1373605.2306 | 1373605.2306 | 1373605.2306 | 1687610.1306 | 1687610.1306 | 1687610.1306 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806 | 2724095.5806
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6650 | -6650 | -6650 | -6650 | -6650 | -6650 | -6650 | -6650 | -6650 | -6650 | 1592975.7333 | 1592975.7333 | 1592975.7333 | 1343870.2694 | 1343870.2694 | 1343870.2694 | 1343870.2694 | 1179835.5027 | 380460.5027 | 1345758.516 | 1345758.516 | 1345758.516 | 1031753.616 | 1031753.616 | 1031753.616 | 315193.3127 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886 | 475155.886
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 3137319.4266 | 3137319.4266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1218506.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 182776.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1119738.0133 | 0 | 0 | 0 | 0 | 257993.1067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159962.5733 | 0 | 198343.5733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1218506.09 | 1218506.09 | 1218506.09 | 1218506.09 | 1218506.09 | 1218506.09 | 1218506.09 | 1218506.09 | 1218506.09 | 1218506.09 | 1218506.09 | 1218506.09 | 1401282.16 | 1401282.16 | 1401282.16 | 1401282.16 | 1401282.16 | 1401282.16 | 1401282.16 | 1401282.16 | 1401282.16 | 2521020.1733 | 2521020.1733 | 2521020.1733 | 2521020.1733 | 2521020.1733 | 2779013.28 | 2779013.28 | 2779013.28 | 2779013.28 | 2779013.28 | 2779013.28 | 2779013.28 | 2779013.28 | 2779013.28 | 2779013.28 | 2938975.8533 | 2938975.8533 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266 | 3137319.4266
| Actual + Planned Expenditure | 2274921.4775 | 2274921.4775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14833.645 | 0 | 0 | 0 | -28056 | 69345.93 | 105208.88 | 0 | 0 | 172311.8 | 176196.0825 | 0 | 1163480.59 | 454714.135 | 0 | 11169 | 69345.925 | 45216.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 975 | 20180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14833.645 | 14833.645 | 14833.645 | 14833.645 | -13222.355 | 56123.575 | 161332.455 | 161332.455 | 161332.455 | 333644.255 | 509840.3375 | 509840.3375 | 1673320.9275 | 2128035.0625 | 2128035.0625 | 2139204.0625 | 2208549.9875 | 2253766.4775 | 2253766.4775 | 2253766.4775 | 2253766.4775 | 2253766.4775 | 2253766.4775 | 2253766.4775 | 2253766.4775 | 2253766.4775 | 2254741.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775 | 2274921.4775
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1218506.09 | 1218506.09 | 1218506.09 | 1218506.09 | 1218506.09 | 1218506.09 | 1218506.09 | 1218506.09 | 1218506.09 | 1218506.09 | 1218506.09 | 1218506.09 | 1401282.16 | 1401282.16 | 1386448.515 | 1386448.515 | 1386448.515 | 1386448.515 | 1414504.515 | 1345158.585 | 1239949.705 | 2359687.7183 | 2359687.7183 | 2187375.9183 | 2011179.8358 | 2011179.8358 | 1105692.3525 | 650978.2175 | 650978.2175 | 639809.2175 | 570463.2925 | 525246.8025 | 525246.8025 | 525246.8025 | 525246.8025 | 525246.8025 | 685209.3758 | 685209.3758 | 883552.9491 | 883552.9491 | 882577.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491 | 862397.9491
|  | CHECK | CHECK
| Revenue Recognition | 0.0019156 | 3199251.4647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31742.9507 | 0 | 0 | 0 | 2251626.5678 | 0 | 0 | 0 | 0 | 328881.321 | 0 | 0 | 0 | 481703.8808 | 0 | 0 | 0 | 18586.7647 | 0 | 0 | 0 | 0 | 2740.78 | 0 | 0 | 0 | 83969.1997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 3199251.4647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31742.9507 | 31742.9507 | 31742.9507 | 31742.9507 | 2283369.5185 | 2283369.5185 | 2283369.5185 | 2283369.5185 | 2283369.5185 | 2612250.8395 | 2612250.8395 | 2612250.8395 | 2612250.8395 | 3093954.7203 | 3093954.7203 | 3093954.7203 | 3093954.7203 | 3112541.485 | 3112541.485 | 3112541.485 | 3112541.485 | 3112541.485 | 3115282.265 | 3115282.265 | 3115282.265 | 3115282.265 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647 | 3199251.4647

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | Grand Total
(blank)
1. Panels | [5 empty] | 1219394.6471 |  |  |  |  | 0 |  | 1219394.6471
2. Inverters | [5 empty] | 278463.5294 |  |  |  |  | 0 |  | 278463.5294
3. Mounting Structures | [6 empty] | 181694.1176 |  |  |  | 0 |  | 181694.1176
4. DC Equipment | [5 empty] | 216742.3529 | 0 |  |  |  | 0 |  | 216742.3529
5. Monitoring |  |  |  |  | 28715.1406 | 12898.4893 | 145132.2627 | 17959.9909 |  |  | 0 | 0 | 204705.8835
6. AC Equipment | [5 empty] | 369417.5294 |  |  |  |  | 0 |  | 369417.5294
8. Product Add On
9. AC & DC installation | [5 empty] | 92933.8235 |  | 260214.7059 | 18586.7647 |  | 0 |  | 371735.2941
10. Site Logistics | [5 empty] | 61776.1961 |  |  |  |  | 0 |  | 61776.1961
11. Due Dilligence | 0 | [6 empty] | 45801.3841 |  |  | 0 | 83969.1997 | 129770.5838
13. Engineering | 0 | [6 empty] | 157727.8 |  |  | 0 |  | 157727.8
14. General Expenses | 0 | 0 | 0 | 0 | 3027.8101 | 0 | 2054.9406 | 0 | 0 | 2740.78 | 0 |  | 7823.5308
15. Service Add On
12. BDP Commission
7.BESS
Grand Total | 0 | 0 | 0 | 0 | 31742.9507 | 2251626.5678 | 328881.321 | 481703.8808 | 18586.7647 | 2740.78 | 0 | 83969.1997 | 3199251.4647

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | Grand Total
(blank)
1. Panels | [5 empty] | 772567.2 |  | -15958.8 |  |  |  |  | 756608.4
2. Inverters | [5 empty] | 206611.05 | [6 empty] | 206611.05
3. Mounting Structures | [6 empty] | 96112.72 | [5 empty] | 96112.72
4. DC Equipment | [5 empty] | 229459.2475 | 81000 | [5 empty] | 310459.2475
5. Monitoring |  |  |  |  | 21048 | 8598.34 | 86487.62 | 11169 |  |  |  | 975 | 128277.96
6. AC Equipment | [5 empty] | 185011.8 | [6 empty] | 185011.8
8. Product Add On | [7 empty] | 18600 |  |  |  |  | 18600
9. AC & DC installation | [5 empty] | 115562.5 |  | 323575 | 23112.5 |  |  |  | 462250
10. Site Logistics | [5 empty] | 16050 | [6 empty] | 16050
11. Due Dilligence | 0 | [6 empty] | 6000 |  |  | 0 | 20180 | 26180
13. Engineering | 0 | [6 empty] | 39216.49 |  |  |  |  | 39216.49
14. General Expenses | 0 | 0 | 0 | 0 | 2954.75 | 0 | 2831.27 | 0 | 0 | 0 |  |  | 5786.02
15. Service Add On
12. BDP Commission |  |  |  |  | 23757.79 | [7 empty] | 23757.79
7.BESS
Grand Total | 0 | 0 | 0 | 0 | 47760.54 | 1533860.1375 | 266431.61 | 382601.69 | 23112.5 | 0 | 0 | 21155 | 2274921.4775

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate | [5 empty] | FINANCIAL CLOSE CERTIFICATE
Project Name: | Milkwood Square
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion: |  |  |  | 1. Financial Close | 1. Financial Close
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 0.74105 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.37909 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.25646 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 0.61376 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
Milkwood Square |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Milkwood Square | 0 | 0 | 0