## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[9 empty] | 2026-02-02 | 2026-02-02
| PROJECT PLAN | Pimville | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 362
| PROJECT DEVELOPER | Natasha Watkins-Baker
| PROJECT MANAGERS | JT Moorosi
| CONTRACT VALUE | 3400106
| Phase: | Construction
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Status | Comment
|  |  | 44 |  |  | 184 |  | 81% | 84.08%
1 | Project Initiation | 2025-04-22 | 42 | 2025-06-03 | 2025-04-29 | 17 | 2025-05-16 | 100% | 100%
1.1 | BD Handover | 2025-04-22 | 1 | 2025-04-23 | 2025-05-13 | 1 | 2025-05-14 | 100% | 100%
1.2 | Project Introduction | 2025-06-02 | 1 | 2025-06-03 | 2025-05-15 | 1 | 2025-05-16 | 100% | 100%
1.3 | HSE | 2025-04-22 | 10 | 2025-05-07 | 2025-04-29 | 10 | 2025-05-14 | 100% | 100%
1.4 | Installer Kick Off | 2025-05-26 | 1 | 2025-05-27 | 2025-05-14 | 1 | 2025-05-15 | 100% | 100%
1.5 | Project Review | 2025-05-26 | 1 | 2025-05-27 | 2025-05-08 | 1 | 2025-05-09 | 100% | 100%
2 | Site Establishment | 2025-06-09 | 1 | 2025-06-10 | 2025-06-10 | 1 | 2025-06-11 | 100% | 100%
2.1 | Solar Contractor Establishment | 2025-06-09 | 1 | 2025-06-10 | 2025-06-10 | 1 | 2025-06-11 | 100% | 100% |  | 131 | Net Work Days
3 | AC Installation | 2025-05-19 | 60 | 2025-07-18 | 2025-05-20 | 142 | 2025-10-09 | 100% | 100% |  | 26.2 | Total Weeks
3.1 | Inverters delivered | 2025-06-10 | 1 | 2025-06-11 | 2025-05-20 | 1 | 2025-05-21 | 100% | 100% |  | 13.8168 | kW/Week Installation Rate
3.2 | Inverters Mounted | 2025-06-11 | 5 | 2025-06-19 | 2025-07-24 | 1 | 2025-07-25 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-05-19 | 25 | 2025-06-24 | 2025-05-20 | 28 | 2025-06-30 | 100% | 100%
3.4 | AC Works | 2025-06-24 | 18 | 2025-07-18 | 2025-07-24 | 10 | 2025-08-07 | 100% | 100%
3.5 | AC Tie-In | 2025-06-24 | 3 | 2025-06-27 | 2025-10-08 | 1 | 2025-10-09 | 100% | 100%
4 | DC Works | 2025-06-09 | 39 | 2025-07-18 | 2025-05-20 | 185 | 2025-11-21 | 90.91% | 75.05%
4.1 | Lifeline Installation (If Applicable) | [6 empty] | 0% | 0%
4.1 | Mounting Structure delivered | 2025-06-09 | 1 | 2025-06-10 | 2025-05-26 | 1 | 2025-05-27 | 100% | 100%
4.2 | Mounting Structure installation | 2025-06-10 | 15 | 2025-07-02 | 2025-11-11 | 4 | 2025-11-17 | 100% | 100%
4.3 | DC Cable delivered | 2025-06-09 | 1 | 2025-06-10 | 2025-05-20 | 1 | 2025-05-21 | 100% | 100%
4.3 | DC Stringing | 2025-07-11 | 5 | 2025-07-18 | 2025-11-14 | 5 | 2025-11-21 | 100% | 100%
5 | Module installation | 2025-06-25 | 19 | 2025-07-14 | 2025-06-10 | 181 | 2025-12-08 | 50% | 66.64%
5.1 | Module delivery | 2025-06-25 | 1 | 2025-06-26 | 2025-06-10 | 1 | 2025-06-11 | 100% | 100%
5.2 | Module removal |  |  |  | 2025-09-10 | 55 | 2025-11-04 | 100% | 100%
5.3 | Module mounting | 2025-06-26 | 12 | 2025-07-14 | 2025-11-17 | 15 | 2025-12-08 | 100% | 100%
6 | Commissioning | 2025-07-18 | 5 | 2025-07-23 | 2025-12-08 | 3 | 2025-12-11 | 100% | 100%
6.1 | Commissioning | 2025-07-18 | 1 | 2025-07-21 | 2025-12-08 | 1 | 2025-12-09 | 100% | 100%
6.2 | Practical Completion | 2025-07-21 | 2 | 2025-07-23 | 2025-12-09 | 2 | 2025-12-11 | 100% | 100%
7 | QA Inspections | 2025-07-23 | 1 | 2025-07-24 | 2025-12-11 | 1 | 2025-12-12 | 100% | 100%
7.1 | Red-Team Inspection | 2025-07-23 | 1 | 2025-07-24 | 2025-12-11 | 1 | 2025-12-12 | 100% | 100%
8 | Project Closure | 2025-07-24 | 15 | 2025-08-08 | 2025-12-12 | 63 | 2026-02-13 | 7.097% | 30.94%
8.1 | Equipment serial numbers | 2025-07-24 | 2 | 2025-07-28 | 2025-12-12 | 2 | 2025-12-17 | 100% | 100%
8.2 | Snags completion | 2025-07-24 | 5 | 2025-07-31 | 2026-01-15 | 15 | 2026-02-05 | 0% | 85.71% | Client QC scheduled for Monday 26 Jan
8.3 | System Performance Monitoring | 2025-07-31 | 5 | 2025-08-07 | 2026-02-05 | 5 | 2026-02-12 | 0% | 0%
8.4 | Handover documentation | 2025-07-24 | 9 | 2025-08-06 | 2026-02-05 | 2 | 2026-02-09 | 10% | 0%
8.5 | Handover to Client | 2025-08-06 | 1 | 2025-08-07 | 2026-02-09 | 2 | 2026-02-11 | 0% | 0% | Portfolio Handover
8.6 | Handover to Matriarch | 2025-08-02 | 5 | 2025-08-08 | 2026-02-07 | 5 | 2026-02-13 | 0% | 0%
Formulas:
Planned Start = MIN([Planned Start, row below]:E16)
Planned Start = WORKDAY.INTL([Planned End, row above],0,1,Data!$C3:C14)
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = WORKDAY.INTL([Actual End, row above],0,1,Data!$C3:C14)
Actual End = MAX([Actual End, row below]:K16)
Actual End = MAX([Actual End, row below])
Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 3400106 |  | 3400106 |  |  |  | Start Date | 3156976.8545 | 2847842.0277 | 207797.7917 | 89555.745 | 29102.4772 | 47054.42
2 | Planned Expenditure | 3100368.1219 |  | 2937397.7727 | VO PM Limit | Current VO Total
3 | Planned Profit | 299737.8781 |  | 462708.2273 | 14986.8939 | 107847.455 |  | End Date - PC
4 | Planned Margin | 8.816% |  | 13.61%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE |  | MILESTONE NOTES & COMMENTS
1 | Deposit |  | 20% | 680021.2 |  | 2025-04-30 | 004735 | 2025-05-01 | 2025-04-30
2 | Delivery of Panels |  | 20% | 680021.2 |  | 2025-07-02 | 004735 | 2025-05-01 | 2025-06-20
3 | Delivery of Inverters |  | 15% | 510015.9 |  | 2025-06-17 | 004735 | 2025-05-01 | 2025-05-30
4 | Commissioning Complete |  | 15% | 510015.9 |  | 2025-07-30 | 004735 | 2025-05-01 | 2026-01-02
5 | Final Completion Issued |  | 25% | 850026.5 |  | 2025-07-31 | 004735 | 2025-05-01 | 2026-01-02
6 | Handover |  | 5% | 170005.3 |  | 2026-02-18 | 004735 | 2025-05-01 | 2026-02-18 |  | Portfolio handover
7 | - |  | 0% | 0
|  |  | 100% | 3400106
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 3100368.1219 |  | 2937397.7727 | 162970.3492
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 760057.76 |  | 724840.6 | 35217.16
2 | 2. Inverters | 210000 |  | 206611.05 | 3388.95
3 | 3. Mounting Structures | 162792 |  | 79861 | 82931
4 | 4. DC Equipment | 289337.8 |  | 318357.0328 | -29019.2328
5 | 5. Monitoring | 49000 |  | 35927.13 | 13072.87
6 | 6. AC Equipment | 409690.7261 |  | 209378.6183 | 200312.1078
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 0 |  | 33530 | -33530
9 | 9. AC & DC installation | 292600 |  | 481307.7492 | -188707.7492
10 | 10. Site Logistics | 81453.8 |  | 59547.3374 | 21906.4626
11 | 11. Due Dilligence | 116088 |  | 42864.76 | 73223.24
12 | 12. BDP Commission | 65796.159 |  | 0 | 65796.159
13 | 13. Engineering | 157251.8768 |  | 42501.325 | 114750.5518
14 | 14. General Expenses | 6300 |  | 5250.26 | 1049.74
15 | 15. Service Add On | 500000 |  | 697420.91 | -197420.91
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 3100368.1219 | 3400106.1797 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 2937397.7727
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 760057.76 | 2025-07-24 | 760057.76 | 863702 |  | 1 | 1. Panels | Jinko 620W - Menlo | 584 | 1233.8 | 425271.2 | PO3905-DIP-PH2-PIM-20250514 | Menlo INV0002940 | 2025-05-31 | 863702 | 0 | 2025-07-24 | 724840.6
1 |  | Delivery Budget |  |  |  | 2025-07-28 |  |  |  | 1 | 1. Panels |  |  |  | 295268 |  | Menlo INV0002940 | 2025-05-31 | 0 |  | 2025-07-28
1 | [9 empty] | 1 | 1. Panels | Jinko 620W - Menlo | 3 |  | 3701.4 |  | MSA Energy INV0003446 | 2025-11-30 | 0 |  | 2026-01-23
1 | [9 empty] | 1 | 1. Panels | Transport |  |  | 600 |  | MSA Energy INV0003446 | 2025-11-30 | 0 |  | 2026-01-23
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 409690.7261
2 | Inverters | Inverter Budget |  |  | 210000 | 2025-07-17 | 210000 | 238636.3636 |  | 2 | 2. Inverters | Huawei 100KTL - Menlo | 3 | 68870.35 | 206611.05 | PO3905-DIP-PH2-PIM-20250514 | Menlo: INV0002911 | 2025-05-31 | 238636.3636 | 0 | 2025-07-17 | 206611.05 | DC Equipment | 170757.8
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | AC Labour | 90440
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 202160
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 25313.8
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 4440
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 162792 | 2025-06-27 | 162792 | 184990.9091 |  | 3 | 3. Mounting Structures | Schletter Structure |  |  | 79861 | PO3943-DPS-20250521 - RV Approved | Schletter INV1793 | 2025-05-31 | 178441.8663 | 0.0028368 | 2025-06-27 | 79861 | Other | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [6 empty] | 2025-06-30 | 6549.04 |  |  |  | Total | 911302.3261
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Less 15% | 774606.9772
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | R/Wp | 2.1398
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL - Thula Moya | Installer Price
[23 empty] | AC Equipment | 92047.8981
4 | DC Equipment | DC Cable Budget | 9740.5 |  | 118580 | 2025-07-17 | 289337.8 | 328792.9545 |  | 4 | 4. DC Equipment | DC Cable - Menlo | 10000 | 13.4 | 134000 | PO3905-DIP-PH2-PIM-20250514 | Menlo: INV0002911 | 2025-05-31 | 138392.595 | 0 | 2025-07-17 | 318357.0328 | DC Equipment | 184357.0328
4 |  | DC Equipment Budget |  |  | 170757.8 |  |  |  |  | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | AC Labour | 148767.8425
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | DC Labour | 332539.8833
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Offloading | 9056.4839
4 | [5 empty] | 2025-05-15 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 184357.0328 | 10% | 18435.7033 | PO3876-DRS-20250513 - RV Approved | Thula Moya Inv: IN04719 | 2025-05-31 | 19040.036 |  | 2025-05-15 |  | Scaffolding | 33030.524
4 | [5 empty] | 2025-05-15 |  |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 27653.5549 |  | Thula Moya Inv: IN04719 | 2025-05-31 | 28560.0539 |  | 2025-05-15 |  | Storage | 5453.4239
4 | [5 empty] | 2025-07-11 |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 6.4% | 11798.8501 |  | Thula Moya IN04778 | 2025-07-31 | 12185.623 |  | 2025-07-11 |  | Telehandler | 0
[6 empty] | 2025-08-14 |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 13.6% | 25072.5565 |  | Thula Moya IN04799 | 2025-07-31 | 25894.4489 |  | 2025-08-14
4 | [5 empty] | 2025-07-11 |  |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 19.75% | 36410.514 |  | Thula Moya IN04778 | 2025-07-31 | 37604.071 |  | 2025-07-11 |  | HSE | 2006.9113
[6 empty] | 2025-10-16 |  |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 5.25% | 9678.7442 |  | Thula Moya IN04846 | 2025-08-31 | 9996.0189 |  | 2025-12-12
4 | [5 empty] | 2025-10-30 |  |  |  | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 18435.7033 |  | Thula Moya IN04847 | 2025-08-31 | 19040.036 |  | 2025-12-18 |  | Other | 0
4 | [5 empty] | 2025-10-30 |  |  |  | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 18435.7033 |  | Thula Moya IN04848 | 2025-08-31 | 19040.036 |  | 2025-12-18 |  | Other | 0
4 | [5 empty] | 2025-11-07 |  |  |  | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 9217.8516 |  | Thula Moya IN04849 | 2025-08-31 | 9520.018 |  | 2026-02-18 |  | Total | 807260
4 | [5 empty] | 2025-12-07 |  |  |  | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 9217.8516 |  | Thula Moya IN04850 | 2025-08-31 | 9520.018 |  | 2026-03-20 |  | R/Wp | 2.23
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 34000 | 2025-07-17 | 49000 | 55681.8182 |  | 5 | 5. Monitoring | Smartlogger - Menlo |  |  | 8598.35 | PO3905-DIP-PH2-PIM-20250514 | Menlo: INV0002911 | 2025-05-31 | 12277.0934 | -0.0044773 | 2025-07-17 | 35927.13
5 |  | Revenue Metering |  |  | 15000 | 2025-05-29 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 13695 | PO3837-DIP-Ph2-Pimville-20250429 - RV Approved | Accuenergy Inv: ASAI005363 | 2025-04-30 | 19114.2374 |  | 2025-05-29
[6 empty] | 2025-07-29 |  |  |  | 5 | 5. Monitoring |  |  |  | 214.28 |  | Accuenergy - Inv ASAI-005800 | 2025-06-30 | 4039.4628 |  | 2025-07-29
5 | [5 empty] | 2025-06-30 |  |  |  | 5 | 5. Monitoring | Techsitter |  |  | 11169 |  | Matriarch Inv: 4451 | 2025-06-30 | 17082.0931 |  | 2025-06-30
5 | [5 empty] | 2025-05-22 |  |  |  | 5 | 5. Monitoring | UPS |  |  | 2250.5 | PO3863-DIP Ph2-20250509 - RV Approved | Frontline INV725690 | 2025-05-31 | 3168.936 |  | 2025-05-22
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 409690.7261 | 2025-07-28 | 409690.7261 | 465557.6433 |  | 6 | 6. AC Equipment | [7 empty] | 0 | -0.0029508 |  | 209378.6183
6 | [5 empty] | 2025-07-29 |  |  |  | 6 | 6. AC Equipment | PVDB |  |  | 117330.71 | PO3881-DIP-Ph2-Pimville-20250513 - RV Approved | Switchboard Inv: 2-SOI002097 | 2025-06-30 | 260887.2352 |  | 2025-07-29
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [5 empty] | 2025-05-15 |  |  |  | 6 | 6. AC Equipment | Project Kick Off | 92047.8981 | 10% | 9204.8 | PO3876-DRS-20250513 - RV Approved | Thula Moya Inv: IN04719 | 2025-05-31 | 20757.8666 |  | 2025-05-15
6 | [5 empty] | 2025-05-15 |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 13807.1847 |  | Thula Moya Inv: IN04719 | 2025-05-31 | 31136.7654 |  | 2025-05-15
6 | [5 empty] | 2025-07-11 |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 6.4% | 5891.0655 |  | Thula Moya IN04778 | 2025-07-31 | 13098.9047 |  | 2025-07-11
[6 empty] | 2025-08-14 |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 13.6% | 12518.5141 |  | Thula Moya IN04799 | 2025-07-31 | 27108.1624 |  | 2025-08-14
6 | [5 empty] | 2025-07-11 |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 19.75% | 18179.4599 |  | Thula Moya IN04778 | 2025-07-31 | 40422.4011 |  | 2025-07-11
[6 empty] | 2025-10-16 |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 5.25% | 4832.5147 |  | Thula Moya IN04846 | 2025-08-31 | 10745.1952 |  | 2025-12-12
6 | [5 empty] | 2025-10-30 |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 9204.7898 |  | Thula Moya IN04847 | 2025-08-31 | 20467.0385 |  | 2025-12-18
6 | [5 empty] | 2025-10-30 |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 9204.7898 |  | Thula Moya IN04848 | 2025-08-31 | 20467.0385 |  | 2025-12-18
6 | [5 empty] | 2025-11-07 |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 4602.3949 |  | Thula Moya IN04849 | 2025-08-31 | 10233.5193 |  | 2026-02-18
6 | [5 empty] | 2025-12-07 |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 4602.3949 |  | Thula Moya IN04850 | 2025-08-31 | 10233.5193 |  | 2026-03-20
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 0 | 0 |  | 8 | 8. Product Add On | [8 empty] | 0 |  | 33530
8 | [5 empty] | 2025-06-26 |  |  |  | 8 | 8. Product Add On | Delay on site - VO |  | 17600 | 17600 |  | Thula Moya IN04759 | 2025-06-30 |  |  | 2025-06-26
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On | Waterpoint |  |  | 15930 | PO4353-DPS-20251006 - RV Approved | Lutendo Construction Inv: INV00825 | 2025-09-30 |  |  | 2025-10-09
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 90440 | 2025-05-14 | 292600 | 344235.2941 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | -0.006866 |  | 481307.7492
9 |  | DC Installation Budget |  |  | 202160 | 2025-05-15 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 481307.7259 | 10% | 48130.78 | PO3876-DRS-20250513 - RV Approved | Thula Moya Inv: IN04719 | 2025-05-31 | 34423.5341 |  | 2025-05-15
9 | [5 empty] | 2025-05-15 |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 72196.16 |  | Thula Moya Inv: IN04719 | 2025-05-31 | 51635.294 |  | 2025-05-15
9 | [5 empty] | 2025-07-11 |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 6.4% | 30803.6945 |  | Thula Moya IN04778 | 2025-07-31 | 22031.0584 |  | 2025-07-11
[6 empty] | 2025-08-14 |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 13.6% | 65457.8507 |  | Thula Moya IN04799 | 2025-07-31 | 46815.9992 |  | 2025-08-14
9 | [5 empty] | 2025-07-11 |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 19.75% | 95058.2759 |  | Thula Moya IN04778 | 2025-07-31 | 67986.4694 |  | 2025-07-11
[6 empty] | 2025-10-16 |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 5.25% | 25268.6556 |  | Thula Moya IN04846 | 2025-08-31 | 18072.3521 |  | 2025-12-12
9 | [5 empty] | 2025-10-30 |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 48130.78 |  | Thula Moya IN04847 | 2025-08-31 | 34423.533 |  | 2025-12-18
9 | [5 empty] | 2025-10-30 |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 48130.78 |  | Thula Moya IN04848 | 2025-08-31 | 34423.533 |  | 2025-12-18
9 | [5 empty] | 2025-11-07 |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 24065.3863 |  | Thula Moya IN04849 | 2025-08-31 | 17211.7639 |  | 2026-02-18
9 | [5 empty] | 2025-12-07 |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 24065.3863 |  | Thula Moya IN04850 | 2025-08-31 | 17211.7639 |  | 2026-03-20
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-06-17 | 81453.8 | 95828 |  | 10 | 10. Site Logistics |  |  |  | 0 |  |  |  | 0 | 0.0046652 |  | 59547.3374
10 |  | Scaffolding |  |  | 25313.8 | 2025-06-18 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
[6 empty] | 2025-06-19 |  |  |  | 10 | 10. Site Logistics | Security - June |  |  | 10000 | PO3977-DPS-20250603 - RV Approved | Mehlo Security - Inv 06/2025 | 2025-06-30 | 9626.375 |  | 2025-06-19
[6 empty] | 2025-06-20 |  |  |  | 10 | 10. Site Logistics | Security - August | [5 empty] | 2025-08-31 | 27211.7
[6 empty] | 2025-06-21 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
[6 empty] | 2025-06-22 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Security |  |  | 43200 | 2025-06-23 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 4440 | 2025-06-24 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [5 empty] | 2025-05-15 |  |  |  | 10 | 10. Site Logistics | Project Kick Off | 49547.3432 | 10% | 4954.73 | PO3876-DRS-20250513 - RV Approved | Thula Moya Inv: IN04719 | 2025-05-31 | 4769.6089 |  | 2025-05-15
10 | [5 empty] | 2025-05-15 |  |  |  | 10 | 10. Site Logistics | Site Establishment |  | 15% | 7432.1 |  | Thula Moya Inv: IN04719 | 2025-05-31 | 7154.4182 |  | 2025-05-15
10 | [5 empty] | 2025-07-11 |  |  |  | 10 | 10. Site Logistics | AC Installation Complete |  | 6.4% | 3171.03 |  | Thula Moya IN04778 | 2025-07-31 | 3052.5524 |  | 2025-07-11
[6 empty] | 2025-08-14 |  |  |  | 10 | 10. Site Logistics | AC Installation Complete |  | 13.6% | 6738.4387 |  | Thula Moya IN04799 | 2025-07-31 | 6486.6738 |  | 2025-08-14
10 | [5 empty] | 2025-07-11 |  |  |  | 10 | 10. Site Logistics | DC Installation Complete |  | 19.75% | 9785.6003 |  | Thula Moya IN04778 | 2025-07-31 | 9419.9858 |  | 2025-07-11
[6 empty] | 2025-10-16 |  |  |  | 10 | 10. Site Logistics | DC Installation Complete |  | 5.25% | 2601.2355 |  | Thula Moya IN04846 | 2025-08-31 | 4186.1015 |  | 2025-12-12
10 | [5 empty] | 2025-10-30 |  |  |  | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 4954.7343 |  | Thula Moya IN04847 | 2025-08-31 | 7973.5266 |  | 2025-12-18
10 | [5 empty] | 2025-10-30 |  |  |  | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 4954.7343 |  | Thula Moya IN04848 | 2025-08-31 | 7973.5266 |  | 2025-12-18
10 | [5 empty] | 2025-11-07 |  |  |  | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 2477.3672 |  | Thula Moya IN04849 | 2025-08-31 | 3986.7633 |  | 2026-02-18
10 | [5 empty] | 2025-12-07 |  |  |  | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 2477.3672 |  | Thula Moya IN04850 | 2025-08-31 | 3986.7633 |  | 2026-03-20
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2025-09-11 | 116088 | 136574.1176 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 9941.1 |  | Sunspot E027 | 2025-07-31 | 48582.7905 | 0.0023467 | 2025-11-27 | 42864.76
11 |  | Structural Sign Off |  |  | 18088 | 2025-09-12 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 8212.24 | PO3745-DIP-Ph2-20250313 - RV Approved | L&B Consulting - Invoice 1934 | 2025-04-30 | 37133.6275 |  | 2025-04-10
11 |  | Grid Study |  |  | 80000 | 2025-09-13 |  |  |  | 11 | 11. Due Dilligence | Eskom Connection Fee |  |  | 13611.42 |  | Eskom Inv: SDI965705783 | 2026-01-31 | 0 |  | 2026-01-29
11 |  | Lightning risk Assessment |  |  | 7000 | 2025-09-14 |  |  |  | 11 | 11. Due Dilligence | Lightning Risk Assessment |  |  | 5100 | PO3844-Dipula Ph2-20250430 - RV Approved | LPS Inv: IN306837 | 2025-04-30 | 23060.8823 |  | 2025-06-26
11 | [5 empty] | 2025-09-15 |  |  |  | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 |  | Matriarch - INV-5975 | 2025-12-31 | 27796.815 |  | 2026-01-29
2025-09-16
12 | BDP Commission | Referral Fee |  |  | 54830.1325 | 2025-09-17 | 65796.159 | 0 |  | 12 | 12. BDP Commission | Referral Fee | [9 empty] | 0
12 | BDP Commission | PD Fee |  |  | 10966.0265 | 2025-09-18 |  |  |  | 12 | 12. BDP Commission | PD Fee
2025-09-19
13 | Engineering | Matriarch Defects Period |  |  | 29637.7511 | 2025-09-20 | 157251.8768 | 178695.3145 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 42501.325 |  |  | 2026-02-28 | 178695.3145 | 0 | 2026-02-27 | 42501.325
13 |  | Management |  |  | 20571.4286 | 2025-09-21 |  |  |  | 13 | 13. Engineering | Management |  |  | 0 |  |  |  | 0
13 |  | Project manager |  |  | 61200 | 2025-09-22 |  |  |  | 13 | 13. Engineering | Project manager |  |  | 0 |  |  |  | 0
13 |  | Planner time |  |  | 26742.8571 | 2025-09-23 |  |  |  | 13 | 13. Engineering | Planner time |  |  | 0 |  |  |  | 0
13 |  | De Snagging |  |  | 19099.84 | 2025-09-24 |  |  |  | 13 | 13. Engineering | De Snagging |  |  | 0 |  |  |  | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 6300 | 2025-04-30 | 6300 | 7411.7647 |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  | 2025-04-30 | 0 | 1570.795 | 2025-04-30 | 5250.26
14 | [5 empty] | 2025-06-09 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 1399.46 |  | Expense Claim | 2025-05-31 | 1610.7668 |  | 2025-06-09
14 | [5 empty] | 2025-07-04 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 1531.08 |  | Expense Claim | 2025-06-30 | 1904.2759 |  | 2025-07-04
14 | [5 empty] | 2025-08-07 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 1925.06 |  | Expense Claim | 2025-07-31 | 918.7756 |  | 2025-08-07
14 | [5 empty] | 2025-09-05 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 109.06 |  | Expense Claim | 2025-08-31 | 101.4892 |  | 2025-09-05
14 | [5 empty] | 2025-09-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-09-30 | 0 |  | 2025-09-30
14 | [5 empty] | 2025-10-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 113.76 |  | Expense Claim | 2025-10-31 | 612.5183 |  | 2025-11-06
14 | [5 empty] | 2025-11-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 83.78 |  | Expense Claim | 2025-11-30 | 76.8662 |  | 2025-12-05
14 | [5 empty] | 2025-12-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 88.06 |  | Expense Claim | 2025-12-31 | 616.2776 |  | 2026-01-08
14 | [5 empty] | 2026-01-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  |  | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | Welcome Bonus |  |  | 500000 | 2025-06-19 | 500000 | 500000 |  | 15 | 15. Service Add On | Welcome Bonus - Site establishment |  |  | 255000 |  | Luxanio Trading - 23401/202506/274898/I | 2025-06-30 | 238317.757 | 0.0029907 | 2025-06-19 | 697420.91
15 | [9 empty] | 15 | 15. Service Add On | Welcome Bonus - Commissioning |  |  | 255000 |  | Luxanio Trading - 23401/202506/274898/I | 2025-06-30 | 250000 |  | 2026-01-15
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | Community Engagement |  |  | 0 |  |  |  | 0
15 | [5 empty] | 2025-09-11 |  |  |  | 15 | 15. Service Add On | VO - Installation of DC | 50% | 180494.91 | 90247.455 |  | Thula Moya IN04885 | 2025-08-31 | 11682.24 |  | 2025-09-11
15 | [5 empty] | 2025-10-15 |  |  |  | 15 | 15. Service Add On |  |  |  | 90247.455 |  | Thula Moya IN04885 | 2025-08-31 | 0 |  | 2025-12-12
15 | [9 empty] | 15 | 15. Service Add On | Container Shift - ThulaMoya |  |  | 6926 | PO4389-DPS-20251021 - RV Approved | Thula Moya - IN04930 | 2025-10-31 | 0 |  | 2025-11-19
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
| Panel Procurement Budget | 760057.76 |  | 863702
| Inverter Procurement Budget | 210000 |  | 238636.3636
| Mounting Structure Budget | 162792 |  | 184990.9091
| DC Equipment Budget | 289337.8 |  | 328792.9545
| AC Equipment Budget | 409690.7261 |  | 465557.6433
| Monitoring Budget | 49000 |  | 55681.8182
| Optional Extras Budget | 0 |  | 0
| MV Metering Budget | 0 |  | 0
| ADD ON | 0 |  | 0
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 90440 |  | 106400
| DC Installer Budget | 202160 |  | 237835.2941
| In-House Expense Budget | 157251.8768 |  | 178695.3145
| Compliance Budget | 116088 |  | 136574.1176
| Offloading Budget | 8500 |  | 10000
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 4440 |  | 5223.5294
| On Site Security | 43200 |  | 50823.5294
| Roof Access Budget for Installers | 25313.8 |  | 29780.9412
| EPC Management Fee | 0 |  | 0
| ADD ON | 500000 |  | 500000
Expenses
| Total EE Expense Budget | 6300 |  | 7411.7647
Note on W37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date
Note on W131: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date
Note on W165: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date
Note on W166: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Mizelda Isaacs please update the payment date

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 3400106 | 3400106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 680021.2 | 0 | 0 | 0 | 0 | 0 | 0 | 510015.9 | 0 | 680021.2 | 0 | 0 | 0 | 1360042.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170005.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 680021.2 | 680021.2 | 680021.2 | 680021.2 | 680021.2 | 680021.2 | 680021.2 | 1190037.1 | 1190037.1 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106
| Planned Expenditure | 3100368.1219 | 2929610.3219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6300 | 0 | 292600 | 0 | 15000 | 0 | 0 | 533813.8 | 210432 | 0 | 0 | 362580 | 760057.76 | 409690.7261 | 0 | 0 | 0 | 0 | 0 | 116088 | 116005.3387 | 107042.6971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6300 | 6300 | 298900 | 298900 | 313900 | 313900 | 313900 | 847713.8 | 1058145.8 | 1058145.8 | 1058145.8 | 1420725.8 | 2180783.56 | 2590474.2861 | 2590474.2861 | 2590474.2861 | 2590474.2861 | 2590474.2861 | 2590474.2861 | 2706562.2861 | 2822567.6248 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219 | 2929610.3219
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 673721.2 | 673721.2 | 381121.2 | 381121.2 | 366121.2 | 366121.2 | 366121.2 | 342323.3 | 131891.3 | 811912.5 | 811912.5 | 449332.5 | -310725.26 | 639626.4139 | 639626.4139 | 639626.4139 | 639626.4139 | 639626.4139 | 639626.4139 | 523538.4139 | 407533.0752 | 300490.3781 | 300490.3781 | 300490.3781 | 300490.3781 | 300490.3781 | 300490.3781 | 300490.3781 | 300490.3781 | 300490.3781 | 300490.3781 | 300490.3781 | 300490.3781 | 300490.3781 | 300490.3781 | 300490.3781 | 300490.3781 | 300490.3781 | 300490.3781 | 300490.3781 | 300490.3781 | 300490.3781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781 | 470495.6781
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 3400106 | 3400106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 680021.2 | 0 | 0 | 0 | 510015.9 | 0 | 0 | 680021.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1360042.4 | 0 | 0 | 0 | 0 | 0 | 0 | 170005.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 680021.2 | 680021.2 | 680021.2 | 680021.2 | 1190037.1 | 1190037.1 | 1190037.1 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 1870058.3 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3230100.7 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106 | 3400106
| Actual + Planned Expenditure | 2937397.7727 | 2937397.7727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8212.24 | 0 | 0 | 0 | 0 | 201815.0129 | 2250.5 | 13695 | 0 | 1399.46 | 265000 | 102561 | 12700.08 | 211098.49 | 349209.4 | 425271.2 | 412812.99 | 1925.06 | 109787.36 | 0 | 0 | 109.06 | 90247.455 | 0 | 0 | 0 | 15930 | 0 | 0 | 0 | 113.76 | 0 | 6926 | 9941.1 | 83.78 | 132628.605 | 161452.0148 | 0 | 0 | 88.06 | 255000 | 4301.4 | 19611.42 | 0 | 0 | 40363 | 42501.325 | 0 | 0 | 40363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8212.24 | 8212.24 | 8212.24 | 8212.24 | 8212.24 | 210027.2529 | 212277.7529 | 225972.7529 | 225972.7529 | 227372.2129 | 492372.2129 | 594933.2129 | 607633.2929 | 818731.7829 | 1167941.1829 | 1593212.3829 | 2006025.3729 | 2007950.4329 | 2117737.7929 | 2117737.7929 | 2117737.7929 | 2117846.8529 | 2208094.3079 | 2208094.3079 | 2208094.3079 | 2208094.3079 | 2224024.3079 | 2224024.3079 | 2224024.3079 | 2224024.3079 | 2224138.0679 | 2224138.0679 | 2231064.0679 | 2241005.1679 | 2241088.9479 | 2373717.5529 | 2535169.5677 | 2535169.5677 | 2535169.5677 | 2535257.6277 | 2790257.6277 | 2794559.0277 | 2814170.4477 | 2814170.4477 | 2814170.4477 | 2854533.4477 | 2897034.7727 | 2897034.7727 | 2897034.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727 | 2937397.7727
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8212.24 | -8212.24 | -8212.24 | 671808.96 | 671808.96 | 469993.9471 | 467743.4471 | 964064.3471 | 964064.3471 | 962664.8871 | 1377686.0871 | 1275125.0871 | 1262425.0071 | 1051326.5171 | 702117.1171 | 276845.9171 | -135967.0729 | -137892.1329 | -247679.4929 | -247679.4929 | -247679.4929 | -247788.5529 | -338036.0079 | -338036.0079 | -338036.0079 | -338036.0079 | -353966.0079 | -353966.0079 | -353966.0079 | -353966.0079 | -354079.7679 | -354079.7679 | -361005.7679 | -370946.8679 | -371030.6479 | -503659.2529 | -665111.2677 | -665111.2677 | 694931.1323 | 694843.0723 | 439843.0723 | 435541.6723 | 415930.2523 | 415930.2523 | 415930.2523 | 545572.5523 | 503071.2273 | 503071.2273 | 503071.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273 | 462708.2273
|  | CHECK | CHECK
| Revenue Recognition | 1570.6138 | 3398535.3862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79308.7472 | 0 | 0 | 0 | 1633707.1981 | 0 | 0 | 0 | 0 | 788406.2389 | 0 | 0 | 0 | 361607.9161 | 0 | 0 | 0 | 327707.4941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612.5183 | 0 | 0 | 0 | 76.8662 | 0 | 0 | 0 | 0 | 28413.0926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178695.3145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 3398535.3862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79308.7472 | 79308.7472 | 79308.7472 | 79308.7472 | 1713015.9454 | 1713015.9454 | 1713015.9454 | 1713015.9454 | 1713015.9454 | 2501422.1843 | 2501422.1843 | 2501422.1843 | 2501422.1843 | 2863030.1004 | 2863030.1004 | 2863030.1004 | 2863030.1004 | 3190737.5945 | 3190737.5945 | 3190737.5945 | 3190737.5945 | 3190737.5945 | 3190737.5945 | 3190737.5945 | 3190737.5945 | 3190737.5945 | 3191350.1128 | 3191350.1128 | 3191350.1128 | 3191350.1128 | 3191426.979 | 3191426.979 | 3191426.979 | 3191426.979 | 3191426.979 | 3219840.0716 | 3219840.0716 | 3219840.0716 | 3219840.0716 | 3219840.0716 | 3219840.0716 | 3219840.0716 | 3219840.0716 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862 | 3398535.3862
0

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | Grand Total
(blank)
1. Panels |  |  | 863702 | [5 empty] | 0 |  | 0 |  | 863702
2. Inverters |  |  | 238636.3636 | [7 empty] | 0 |  | 238636.3636
3. Mounting Structures | 0 |  | 178441.8663 | 6549.04 | [6 empty] | 0 |  | 184990.9063
4. DC Equipment |  |  | 185992.6849 |  | 75684.1429 | 67116.1267 |  |  |  |  | 0 |  | 328792.9545
5. Monitoring |  | 19114.2374 | 15446.0294 | 21121.5559 | [6 empty] | 0 |  | 55681.8227
6. AC Equipment |  |  | 51894.632 | 260887.2352 | 80629.4682 | 72146.3109 |  |  |  |  | 0 |  | 465557.6462
8. Product Add On
9. AC & DC installation |  |  | 86058.8281 |  | 136833.527 | 121342.9459 |  |  |  |  | 0 |  | 344235.301
10. Site Logistics | 0 |  | 11924.0271 | 9626.375 | 18959.2119 | 55318.3814 |  |  |  |  | 0 |  | 95827.9953
11. Due Dilligence | 0 | 60194.5099 |  |  | 48582.7905 |  |  |  |  | 27796.815 |  |  | 136574.1153
13. Engineering | 0 | [9 empty] | 0 | 178695.3145 | 178695.3145
14. General Expenses | 0 | 0 | 1610.7668 | 1904.2759 | 918.7756 | 101.4892 | 0 | 612.5183 | 76.8662 | 616.2776 | 0 |  | 5840.9697
15. Service Add On |  |  |  | 488317.757 |  | 11682.24 |  | 0 |  |  | 0 |  | 499999.997
12. BDP Commission
7.BESS
Grand Total | 0 | 79308.7472 | 1633707.1981 | 788406.2389 | 361607.9161 | 327707.4941 | 0 | 612.5183 | 76.8662 | 28413.0926 | 0 | 178695.3145 | 3398535.3862
|  | 79093.55 | 1633707.2 | 776724 | 361607.92 | 339604.93 | [6 empty] | 3190737.6
|  | 215.1972 | -0.0018751 | 11682.2389 | -0.0039039 | -11897.4359 | [6 empty] | -0.0055284
3400106
3190737.6
209368.4

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | Grand Total
(blank)
1. Panels |  |  | 720539.2 | [5 empty] | 4301.4 |  |  |  | 724840.6
2. Inverters |  |  | 206611.05 | [9 empty] | 206611.05
3. Mounting Structures |  |  | 79861 | [9 empty] | 79861
4. DC Equipment |  |  | 180089.2582 |  | 73281.9205 | 64985.8541 | [6 empty] | 318357.0328
5. Monitoring |  | 13695 | 10848.85 | 11383.28 | [8 empty] | 35927.13
6. AC Equipment |  |  | 23011.9847 | 117330.71 | 36589.0395 | 32446.8841 | [6 empty] | 209378.6183
8. Product Add On |  |  |  | 17600 |  |  | 15930 | [5 empty] | 33530
9. AC & DC installation |  |  | 120326.94 |  | 191319.821 | 169660.9882 | [6 empty] | 481307.7492
10. Site Logistics |  |  | 12386.83 | 10000 | 19695.0689 | 17465.4385 |  |  |  |  | 0 |  | 59547.3374
11. Due Dilligence |  | 13312.24 |  |  | 9941.1 |  |  |  |  | 6000 |  |  | 29253.34
13. Engineering | 0 | [10 empty] | 42501.325 | 42501.325
14. General Expenses | 0 | 0 | 1399.46 | 1531.08 | 1925.06 | 109.06 | 0 | 113.76 | 83.78 | 88.06 |  |  | 5250.26
15. Service Add On |  |  |  | 510000 |  | 180494.91 |  | 6926 |  |  | 0 |  | 697420.91
12. BDP Commission
7.BESS
Grand Total | 0 | 27007.24 | 1355074.5729 | 667845.07 | 332752.01 | 465163.1348 | 15930 | 7039.76 | 4385.18 | 6088.06 | 0 | 42501.325 | 2923786.3527

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate | [5 empty] | FINANCIAL CLOSE CERTIFICATE
Project Name: | Pimville
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion: |  |  |  | 1. Financial Close | 1. Financial Close
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 0.76766 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.3927 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.26567 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 0.6358 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
Pimville |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Pimville | 0 | 0 | 0