## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate |  |  |  | FINANCIAL CLOSE CERTIFICATE
Project Name: | Seshego Circle
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Product Agreement
EPC Agreement
O&M Agreeement
Cost Proposal
Deposit Received
Risks / Notes
Acknowledgement and Acceptance:
Role | Name | Signature | Date

## Certificate - Planning
Emergent Energy – Planning Phase Completion Certificate |  |  |  | PLANNING CERTIFICATE
Project Name: | Seshego Circle
Client Representative:
Programme Manager: | Roedolph Venter
Project Manager: | Eon Van Rensburg
Project Engineer:
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Project Introduction Presentation
Project Brief
Engineering Pack
BOQ
PO – Material & Equipment
PO - Contractors
HSE – NOC
HSE – EE File
HSE – Contractor File
SSEG Application
Risks / Notes
Acknowledgement and Acceptance:
Role | Name | Signature | Date

## Change Register
Change Register
ID | Description | Supporting Image (If Applicable) | Impact | Proposed Date | Proposed By | Status | Approved By | Approved Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
DEC011
DEC012
DEC013
DEC014
DEC015
DEC016
DEC017
DEC018
DEC019
DEC020
DEC021
DEC022
DEC023
DEC024
DEC025
DEC026
DEC027
DEC028
DEC029
DEC030

## BOQ
Item | Supplier | Description | Quantity | Comments
PV Module
DC Cable Red & Black
Inverters
Mounting Structure
Current Transformers (Production)
Current Transformers (Consumption)
Solar Production Meter (Techistter)
Grid Consumption Meter
Wi-Fi Router & Sim
Switch
Back Up Battery
PVDB
Supplier List
Accuenergy
Krannich
Menlo
Red Pole
Schletter
Switchboard
Techsitter

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[9 empty] | 2026-02-02 | 2026-02-02
| PROJECT PLAN | Seshego Circle | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 1360
| PROJECT DEVELOPER | Dayne Sage |  |  |  | Target Month | 2025-10-31
| PROJECT MANAGERS | Eon Van Rensburg
| CONTRACT VALUE | 10428344.3462
| Phase: | Construction
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Status | Comment
|  |  | 60 |  |  | 123 |  | 55.78% | 53.06%
1 | Project Initiation | 2025-07-07 | 94 | 2025-10-09 | 2025-07-07 | 94 | 2025-10-09 | 100% | 100%
1.1 | BD Handover | 2025-07-07 | 5 | 2025-07-14 | 2025-07-07 | 5 | 2025-07-14 | 100% | 100%
1.2 | Project Introduction | 2025-09-29 | 1 | 2025-09-30 | 2025-09-29 | 1 | 2025-09-30 | 100% | 100%
1.3 | HSE | 2025-09-29 | 8 | 2025-10-09 | 2025-09-29 | 8 | 2025-10-09 | 100% | 100%
1.4 | Installer Kick Off | 2025-09-29 | 1 | 2025-09-30 | 2025-09-29 | 1 | 2025-09-30 | 100% | 100%
1.5 | Project Review | 2025-09-29 | 1 | 2025-09-30 | 2025-09-29 | 1 | 2025-09-30 | 100% | 100%
2 | Site Establishment | 2025-10-13 | 1 | 2025-10-14 | 2025-10-13 | 1 | 2025-10-14 | 100% | 100%
2.1 | Solar Contractor Establishment | 2025-10-13 | 1 | 2025-10-14 | 2025-10-13 | 1 | 2025-10-14 | 100% | 100% |  | 66 | Net Work Days
2.2 | Civil Works |  |  |  | 2025-10-27 | 36 | 2025-12-02 | 100% | 100% | Inverter stands
2.2 | Roof Remedial Work |  |  |  | 2025-10-20 | 10 | 2025-10-30 | 100% | 100%
3 | AC Installation | 2025-09-29 | 52 | 2025-11-20 | 2025-09-29 | 133 | 2026-02-09 | 83.61% | 57.11% |  | 13.2 | Total Weeks
3.1 | Inverters delivered | 2025-10-13 | 1 | 2025-10-14 | 2025-10-13 | 1 | 2025-10-14 | 100% | 100% |  | 103.0303 | kW/Week Installation Rate
3.2 | Inverters Mounted | 2025-11-04 | 1 | 2025-11-05 | 2025-12-02 | 1 | 2025-12-03 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-09-29 | 30 | 2025-11-10 | 2025-09-29 | 34 | 2025-11-14 | 100% | 100%
3.4 | AC Works - Tie In 1 | 2025-11-10 | 8 | 2025-11-20 | 2025-12-02 | 15 | 2026-01-26 | 100% | 100%
3.5 | AC Works - Tie In 2 |  |  |  | 2026-01-12 | 8 | 2026-01-28 | 100% | 100%
3.6 | AC Tie In 1 |  |  |  | 2026-02-06 | 1 | 2026-02-09 | 0% | 0%
3.7 | AC Tie-In 2 | 2025-11-10 | 2 | 2025-11-12 | 2026-02-06 | 1 | 2026-02-09 | 0% | 0%
4 | DC Works | 2025-10-13 | 53 | 2025-12-05 | 2025-10-13 | 100 | 2026-01-21 | 62.61% | 67.39%
4.1 | Lifeline Installation (If Applicable) | [6 empty] | 0% | 0%
4.1 | Mounting Structure delivered | 2025-10-13 | 1 | 2025-10-14 | 2025-10-13 | 1 | 2025-10-14 | 100% | 100%
4.2 | Mounting Structure installation -Tie In 1 | 2025-10-14 | 10 | 2025-10-28 | 2025-10-27 | 8 | 2025-11-06 | 100% | 100%
4.3 | Mounting Structure installation -Tie In 2 |  |  |  | 2025-11-13 | 8 | 2025-11-25 | 100% | 100%
4.4 | DC Cable delivered | 2025-10-13 | 1 | 2025-10-14 | 2025-10-13 | 1 | 2025-10-14 | 100% | 100%
4.5 | DC Stringing Tie In 1 |  |  |  | 2025-11-15 | 6 | 2025-11-24 | 100% | 100%
4.6 | DC Stringing Tie In 2 | 2025-11-15 | 15 | 2025-12-05 | 2025-11-18 | 22 | 2026-01-21 | 90% | 100%
5 | Module installation | 2025-10-13 | 36 | 2025-11-18 | 2025-10-13 | 38 | 2025-11-20 | 100% | 100%
5.1 | Module delivery | 2025-10-13 | 1 | 2025-10-14 | 2025-10-13 | 1 | 2025-10-14 | 100% | 100%
5.2 | Module mounting - Tie In 1 | 2025-10-21 | 20 | 2025-11-18 | 2025-11-04 | 12 | 2025-11-20 | 100% | 100%
5.2 | Module mounting - Tie In 2 | 2025-10-21 | 20 | 2025-11-18 | 2025-11-18 | 10 | 2025-12-02 | 100% | 100%
6 | Commissioning | 2025-12-05 | 7 | 2025-12-12 | 2026-02-09 | 4 | 2026-02-13 | 0% | 0%
6.1 | Commissioning - Tie In 1 | 2025-12-05 | 2 | 2025-12-09 | 2026-02-09 | 1 | 2026-02-10 | 0% | 0%
6.2 | Commissioning - Tie In 2 |  |  |  | 2026-02-09 | 1 | 2026-02-10 | 0% | 0%
6.3 | Practical Completion | 2025-12-09 | 3 | 2025-12-12 | 2026-02-10 | 3 | 2026-02-13 | 0% | 0%
7 | QA Inspections | 2025-12-05 | 3 | 2025-12-08 | 2026-02-13 | 5 | 2026-02-18 | 0% | 0%
7.1 | Red-Team Inspection | 2025-12-05 | 1 | 2025-12-08 | 2026-02-13 | 3 | 2026-02-18 | 0% | 0%
8 | Project Closure | 2025-12-05 | 48 | 2026-01-22 | 2026-02-13 | 20 | 2026-03-05 | 0% | 0%
8.1 | Equipment serial numbers | 2025-12-05 | 1 | 2025-12-08 | 2026-02-13 | 1 | 2026-02-16 | 0% | 0%
8.2 | Snags completion | 2025-12-08 | 5 | 2025-12-15 | 2026-02-18 | 5 | 2026-02-25 | 0% | 0%
8.3 | System Performance Monitoring | 2025-12-12 | 5 | 2026-01-22 | 2026-02-13 | 5 | 2026-02-20 | 0% | 0%
8.4 | Handover documentation | 2025-12-15 | 1 | 2026-01-19 | 2026-02-25 | 1 | 2026-02-26 | 0% | 0%
8.5 | Handover to Client | 2026-01-19 | 1 | 2026-01-20 | 2026-02-26 | 1 | 2026-02-27 | 0% | 0%
8.6 | Handover to Matriarch | 2026-01-19 | 1 | 2026-01-20 | 2026-02-26 | 5 | 2026-03-05 | 0% | 0%
Formulas:
Dayne Sage = MIN([Dayne Sage, row below]:E16)
Dayne Sage = [Dayne Sage, row above]
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Dayne Sage],[Duration (days)],1,Data!$C3:C45)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = [Actual Start, row above]
Actual End = MAX([Actual End, row below]:K16)
Actual End = WORKDAY.INTL([Actual Start],[Target Month],1,Data!$C3:C45)
Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  | FINANCIAL REVIEW | TIMELINE REVIEW
1 | Planned Revenue | 10428344.3462 |  | 10428344.35 |  |  | Start Date
2 | Planned Expenditure | 9590676.1311 |  | 7349211.2423
3 | Planned Profit | 837668.2151 |  | 3079133.1077 |  |  | End Date - PC
4 | Planned Margin | 8.033% |  | 29.53%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Claim 1 |  | 28.83% | 3006602.38 | 2025-11-25 | 004866 | 2025-10-28 | 2025-12-08
1 | Claim 1 |  | 29% | 3006602.38 | 2025-11-25 | 004866 | 2025-10-28 | 2025-12-03
2 | Claim 2 |  | 21.34% | 2225569 | 2025-12-25 | 004903 | 2025-12-17 | 2026-01-12
3 | Claim 3 |  | 0% | 0
4 | Claim 4 |  | 21% | 2189570.59 | 2026-02-25 |  |  | 2026-02-25
5 |  |  | 0% | 0
6 |  |  | 0% | 0
7 | - |  | 0% | 0
|  |  | 100.2% | 10428344.35
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 3649920.5225
2 | Delivery of Panels |  | 30% | 3128503.305
3 | Delivery of Inverters |  | 20% | 2085668.87
4 | Practical Completion |  | 10% | 1042834.435
5 | Handover |  | 5% | 521417.2175
| Total |  | 100% | 10428344.35
|  |  | 100% | 10428344.35

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-17 | Builders Holiday
2025-12-18 | Builders Holiday
2025-12-19 | Builders Holiday
2025-12-20 | Builders Holiday
2025-12-21 | Builders Holiday
2025-12-22 | Builders Holiday
2025-12-23 | Builders Holiday
2025-12-24 | Builders Holiday
2025-12-25 | Builders Holiday
2025-12-26 | Builders Holiday
2025-12-27 | Builders Holiday
2025-12-28 | Builders Holiday
2025-12-29 | Builders Holiday
2025-12-30 | Builders Holiday
2025-12-31 | Builders Holiday
2026-01-01 | Builders Holiday
2026-01-02 | Builders Holiday
2026-01-03 | Builders Holiday
2026-01-04 | Builders Holiday
2026-01-05 | Builders Holiday
2026-01-06 | Builders Holiday
2026-01-07 | Builders Holiday
2026-01-08 | Builders Holiday
2026-01-09 | Builders Holiday
2026-01-10 | Builders Holiday
2026-01-11 | Builders Holiday
2026-01-12 | Builders Holiday
2026-01-13 | Builders Holiday
2026-01-14 | Builders Holiday
2026-01-15 | Builders Holiday
2026-01-16 | Builders Holiday
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 9590676.1311 | 12428344.3462 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 7349211.2423
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 2857717.17 | 2025-12-31 | 2857717.17 | 3072814.1613 |  | 1 | 1. Panels | Jinko 590 | 1298 | 1150.5 | 1493349 |  | Menlo - INV0003320 | 2025-10-31 | 1729623.9295 | 0 | 2025-12-12 | 2657189.4
1 |  | Delivery Budget | [7 empty] | 1 | 1. Panels | Jinko 590 balance | 1008 | 1150.5 | 1159704 |  | Menlo - INV0003319 | 2025-10-31 | 1343190.2318 |  | 2025-12-18
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | Replacement Panels - Damaged due to weather | 2 |  | 4136.4 | PO4556-DSHC-20260119 - RV Approved | MSA Energy - INV0003547 | 2026-01-31 | 0 |  | 2026-04-01
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 1511034.3
2 | Inverters | Inverter Budget | 11 |  | 770000 | 2025-12-31 | 770000 | 827956.9892 |  | 2 | 2. Inverters | Huawei 100KTL | 11 | 68870.358 | 757573.938 |  | Menlo - INV0003320 | 2025-10-31 | 827956.9892 | 0 | 2025-12-12 | 757573.938 | DC Equipment | 675888.1
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | AC Labour | 340042.5
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 720090
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 70393.8
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 33546.6667
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 1105818.21 | 1900-01-29 | 1105818.21 | 1189051.8387 |  | 3 | 3. Mounting Structures | K2 Structure |  |  | 40621.45 | PO4364-DSHC-20251009 - RV Approved | Krannich - 15-10014095 | 2025-10-31 | 142264.2188 | 0 | 2025-12-12 | 363159.38 | Other | 0
3 | [9 empty] | 3 | 3. Mounting Structures |  |  |  | 45778.95 |  | krannich - 15-10014122 | 2025-10-31 | 160326.787 |  | 2025-12-18 |  | Total | 3359495.3667
3 | [9 empty] | 3 | 3. Mounting Structures |  |  |  | 50931.2 |  | krannich - 15-10014093 | 2025-10-31 | 178370.9686 |  | 2025-12-12 |  | Less 15% | 2855571.0617
3 | [9 empty] | 3 | 3. Mounting Structures |  |  |  | 202184.62 |  | Krannich - 15-10014094 | 2025-10-31 | 708089.8644 |  | 2025-12-12 |  | R/Wp | 2.0997
3 | [9 empty] | 3 | 3. Mounting Structures | Earthing plates |  |  | 71394.92 | PO4490-DSHC-20251125 - RV Approved | K2 Systems - Inv139402 | 2025-11-30 | 0 |  | 2025-11-28
[10 empty] | 3 | 3. Mounting Structures |  |  |  | -67046.2 |  | K2 Systems - Credit SACN42026 | 2026-01-31 | 0 |  | 2026-02-06
[10 empty] | 3 | 3. Mounting Structures | Terragriff (254 clamps short returned) to be deducted from subbie |  |  | 3737.49 |  |  | 2026-02-28 |  |  | 2026-02-28
3 | [9 empty] | 3 | 3. Mounting Structures | Universal KL-Clamp |  |  | 15556.95 | PO4553-DSHC-20260116 - RV Approved | K2 Systems - InvSAI672026 | 2026-01-31 | 0 |  | 2026-01-23 |  | ACTUAL - JA Electrical | Installer Price
[23 empty] | AC Equipment | 231508.8
4 | DC Equipment | DC Cable Budget | 36274.45 |  | 441602 | 2025-12-31 | 1117490.1 | 1201602.2581 |  | 4 | 4. DC Equipment | DC Cable - old price | 14000 | 13.5 | 189000 |  | Menlo - INV0003320 | 2025-10-31 | 318264.9978 | 0 | 2025-12-12 | 713565.2 | DC Equipment | 169665.2
4 |  | DC Equipment Budget |  |  | 675888.1 | 2025-12-31 |  |  |  | 4 | 4. DC Equipment |  | 26000 | 13.65 | 354900 |  | Menlo - INV0003320 | 2025-10-31 | 597630.9402 |  | 2025-12-18 |  | AC Labour | 142795.4
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | DC Labour | 962496.8
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Offloading | 55490
4 | [5 empty] | 2025-08-31 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 169665.2 | 10% | 16966.52 |  | JA Electrical - Inv 1104 | 2025-10-31 | 28570.632 |  | 2025-11-06 |  | Scaffolding | 75760
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 25449.78 |  | JA Electrical - Inv 1105 | 2025-10-31 | 42855.948 |  | 2025-11-06 |  | Storage | 11407
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 10% | 16966.52 |  | JA ElectricalInv 1142 | 2025-12-31 | 28570.632 |  | 2025-12-12 |  | Site Ablutions | 17072
[10 empty] | 4 | 4. DC Equipment | AC Installation Complete |  | 10% | 16966.52 |  |  | 2026-01-31 | 28570.632 |  | 2026-02-14
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 20% | 33933.04 |  | JA ElectricalInv 1142 | 2025-12-31 | 57141.264 |  | 2025-12-12 |  | Return of excess material | 14195
[10 empty] | 4 | 4. DC Equipment | DC Installation Complete |  | 5% | 8483.26 |  |  | 2026-01-31 | 14285.316 |  | 2026-02-14
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 16966.52 |  |  | 2026-02-28 | 28570.632 |  | 2026-02-20 |  | Waste Skip | 22620
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 16966.52 |  |  | 2026-03-31 | 28570.632 |  | 2026-03-04 |  | Other | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 8483.26 |  |  | 2026-03-31 | 14285.316 |  | 2026-03-04 |  | Total | 1703010.2
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 8483.26 |  |  | 2026-02-28 | 14285.316 |  | 2026-03-27 |  | R/Wp | 1.2522
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 34000 | 2025-08-31 | 49000 | 52688.172 |  | 5 | 5. Monitoring | Smartlogger |  |  | 8598.34 |  | Menlo - INV0003320 | 2025-10-31 | 5015.4617 | 0.0040394 | 2025-12-12 | 91265.29
5 |  | Revenue Metering |  |  | 15000 | 2025-08-31 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 27301 | PO4416-DSHC-20251028 - RV Approved | Accuenergy Inv :ASAI-006727 | 2025-10-31 | 9478.94 |  | 2025-11-28
5 | [5 empty] | 2025-08-31 |  |  |  | 5 | 5. Monitoring | Techsitter |  |  | 11169 |  | Matriarch - INV-4742 | 2025-09-30 | 7261.7211 |  | 2025-08-31
[10 empty] | 5 | 5. Monitoring | DElivery of Techsitter |  |  | 335.86 |  | DSV Inv:180156930 | 2025-11-30 | 0 |  | 2025-12-31
5 | [5 empty] | 2025-08-31 |  |  |  | 5 | 5. Monitoring | Apex Device and Licenses |  |  | 44000 | PO4077-DSHC-20250630 - RV Approved | Rubicon INVWCRE-0069079 | 2025-09-30 | 28607.3712 |  | 2025-08-31
[10 empty] | 5 | 5. Monitoring | Above Apex allocated to Corporate Park |  |  | -44000 |  | Allocated to Corporate Park | 2025-10-31 | 0 |  | 2025-10-31
[10 empty] | 5 | 5. Monitoring | New Apex device |  |  | 40000 | PO4420-DSHC-20251029 - RV Approved | Rubicon - INVWCRE-0072121 | 2025-11-30 | 0 |  | 2025-12-30
[10 empty] | 5 | 5. Monitoring | Delivery of Apex |  |  | 285.59 |  | DSV Inv:180155155 | 2025-11-30 | 0 |  | 2025-12-30
5 | [5 empty] | 2025-08-07 |  |  |  | 5 | 5. Monitoring | UPS |  |  | 3575.5 | PO4070-DSHC-20250630 - RV Approved | Frontiline QTE107313 | 2025-09-30 | 2324.674 |  | 2025-08-07
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 1511034.3 | 2025-08-31 | 1511034.3 | 1624768.0645 |  | 6 | 6. AC Equipment | [7 empty] | 0 | 5.3091e-05 |  | 586437.82
6 | [5 empty] | 1900-01-29 |  |  |  | 6 | 6. AC Equipment | PVDB |  |  | 354929.22 | PO4330-DSHC-20250925 - MI Approved | Switchboard - 2-SOI002604 | 2025-11-30 | 983356.5392 |  | 2025-12-30
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [5 empty] | 2025-08-31 |  |  |  | 6 | 6. AC Equipment | Project Kick Off | 231508.8 | 10% | 23150.88 |  | JA Electrical - Inv 1104 | 2025-10-31 | 64141.1525 |  | 2025-11-06
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 34726.32 |  | JA Electrical - Inv 1105 | 2025-10-31 | 96211.7288 |  | 2025-11-06
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 10% | 23150.78 |  | JA ElectricalInv 1142 | 2025-12-31 | 64141.2873 |  | 2025-12-12
[10 empty] | 6. | 6. AC Equipment | AC Installation Complete |  | 10% | 23150.88 |  |  | 2026-01-31 | 64141.1744 |  | 2026-02-14
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 20% | 46301.66 |  | JA ElectricalInv 1142 | 2025-12-31 | 128282.0717 |  | 2025-12-12
[10 empty] | 6 | 6. AC Equipment | DC Installation Complete |  | 5% | 11575.44 |  |  | 2026-01-31 | 32070.5872 |  | 2026-02-14
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 23150.88 |  |  | 2026-02-28 | 64141.1744 |  | 2026-02-20
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 23150.88 |  |  | 2026-03-31 | 64141.1744 |  | 2026-03-04
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 11575.44 |  |  | 2026-03-31 | 32070.5872 |  | 2026-03-04
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 11575.44 |  |  | 2026-02-28 | 32070.5872 |  | 2026-03-27
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 300000 | 322580.6452 |  | 8 | 8. Product Add On | [7 empty] | 0 | 9818.0735 |  | 341826
8 |  | Transformer |  |  | 300000 | 2025-08-31 |  |  |  | 8 | 8. Product Add On | Tie In Kiosk | 2 | 25000 | 50000 |  |  | 2026-02-28 | 0 |  | 2026-02-14
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [5 empty] | 1900-01-29 |  |  |  | 8 | 8. Product Add On | Brick Face Inverter Rooms | 232956 | 75% | 174717 | PO4365-DSHC-20251013 - RV Approved | Van Staden Three : Inv 3021 | 2025-10-31 | 200089.1896 |  | 2025-10-16
8 | [9 empty] | 8 | 8. Product Add On |  |  | 25% | 58239 |  | Van Staden Three : Inv 3037 | 2025-10-31 | 66696.3965 |  | 2025-12-18
8 | [9 empty] | 8 | 8. Product Add On | Inverter stand |  |  | 48720 | PO4450-DSHC-20251107 - RV Approved |  | 2026-01-31 | 45976.9855 |  | 2026-01-31
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | Grounding Washers |  |  | 10150 | PO4571-DSHC-20260123 - RV Approved |  | 2026-02-28 | 0 |  | 2026-02-28
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 340042.5 | 2025-08-31 | 1060132.5 | 1204696.0227 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0 |  | 1105292.2
9 |  | DC Installation Budget |  |  | 720090 | 2025-08-31 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 1105292.2 | 10% | 110529.22 |  | JA Electrical - Inv 1104 | 2025-10-31 | 120469.6023 |  | 2025-11-06
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 165793.83 |  | JA Electrical - Inv 1105 | 2025-10-31 | 180704.4034 |  | 2025-11-06
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 10% | 110529.22 |  | JA ElectricalInv 1142 | 2025-12-31 | 120469.6023 |  | 2025-12-12
[10 empty] | 9 | 9. AC & DC installation | AC Installation Complete |  | 10% | 110529.22 |  |  | 2026-01-31 | 120469.6023 |  | 2026-02-14
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 20% | 221058.44 |  | JA ElectricalInv 1142 | 2025-12-31 | 240939.2045 |  | 2025-12-12
[10 empty] | 9 | 9. AC & DC installation | DC Installation Complete |  | 5% | 55264.61 |  |  | 2026-01-31 | 60234.8011 |  | 2026-02-14
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 110529.22 |  |  | 2026-02-28 | 120469.6023 |  | 2026-02-20
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 110529.22 |  |  | 2026-03-31 | 120469.6023 |  | 2026-03-04
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 55264.61 |  |  | 2026-03-31 | 60234.8011 |  | 2026-03-04
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 55264.61 |  |  | 2026-02-28 | 60234.8011 |  | 2026-03-27
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-08-31 | 184440.4667 | 209591.4394 |  | 10 | 10. Site Logistics | [7 empty] | 0 | 0.0018946 |  | 302543.9
10 |  | Scaffolding |  |  | 70393.8 | 2025-08-31 |  |  |  | 10 | 10. Site Logistics | Security - Oct - Deposit |  |  | 18000 | PO4363-DSHC-20251009 - RV Approved | Cycad Security - INV0002672 | 2025-10-31 | 12469.7429 |  | 2025-10-16
[6 empty] | 1900-01-29 |  |  |  | 11 | 10. Site Logistics | Security - Oct - Balance |  |  | 18000 |  | Cycad Security - INV0002672 | 2025-10-31 | 12469.7429 |  | 2025-10-31
[6 empty] | 1900-01-29 |  |  |  | 12 | 10. Site Logistics | Security - Nov |  |  | 60000 |  | Cycad Security - INV0002699 | 2025-11-30 | 38348.8212 |  | 2025-11-28
[10 empty] | 12 | 10. Site Logistics | Security - Dec 02-11/12 |  |  | 10000 | PO4524-DSHC-20251208-MI - Approved | Cycad Security - INV0002713 | 2025-12-31 | 6927.6373 |  | 2025-12-12
[10 empty] | 13 | 10. Site Logistics | [7 empty] | 0
10 |  | Security |  |  | 72000 | 2025-08-31 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 33546.6667 | 2025-08-31 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [5 empty] | 2025-08-31 |  |  |  | 10 | 10. Site Logistics | Project Kick Off | 196544 | 10% | 19654.4 |  | JA Electrical - Inv 1104 | 2025-10-31 | 13615.8509 |  | 2025-11-06
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Site Establishment |  | 15% | 29481.6 |  | JA Electrical - Inv 1105 | 2025-10-31 | 20423.7763 |  | 2025-11-06
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | AC Installation Complete |  | 10% | 19654.4 |  | JA ElectricalInv 1142 | 2025-12-31 | 16832.8754 |  | 2025-12-12
[10 empty] | 10 | 10. Site Logistics | AC Installation Complete |  | 10% | 19654.4 |  |  | 2026-01-31 | 13615.8554 |  | 2026-02-14
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | DC Installation Complete |  | 20% | 39308.7 |  | JA ElectricalInv 1142 | 2025-12-31 | 27231.6415 |  | 2025-12-12
[10 empty] | 10 | 10. Site Logistics | DC Installation Complete |  | 5% | 9827.2 |  |  | 2026-01-31 | 6807.9277 |  | 2026-02-14
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 19654.4 |  |  | 2026-02-28 | 13615.8554 |  | 2026-02-20
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 19654.4 |  |  | 2026-03-31 | 13615.8554 |  | 2026-03-04
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 9827.2 |  |  | 2026-03-31 | 6807.9277 |  | 2026-03-04
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 9827.2 |  |  | 2026-02-28 | 6807.9277 |  | 2026-03-27
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 34004.25 | 2025-08-31 | 182012.75 | 206832.6705 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 34004.25 |  |  | 2026-02-28 | 39765.3909 | 0.00021007 | 2026-02-13 | 142343.85
11 |  | Structural sign off |  |  | 68008.5 | 2025-08-31 |  |  |  | 11 | 11. Due Dilligence | Structural sign off |  |  | 9019.6 |  | L & B consulting Inv: 1934 | 2025-09-30 | 14096.2195 |  | 2025-04-10
11 | [5 empty] | 2025-08-31 |  |  |  | 11 | 11. Due Dilligence | Site Inspection |  |  | 9620 |  | Ace Properties: Inv 3031 | 2025-09-30 | 15034.5505 |  | 2025-03-07
11 |  | Grid Study - Outside of CoCT |  |  | 80000 | 2025-08-31 |  |  |  | 11 | 11. Due Dilligence | Grid Study - Outside of CoCT |  |  | 79700 | PO4167-DSHC-20250728 - RV Approved | Okusha Engineering EE20 | 2025-09-30 | 123406.0137 |  | 2025-02-28
11 | [9 empty] | 11 | 11. Due Dilligence | Red Team |  |  | 10000 |  |  | 2026-02-28 | 14530.4957 |  | 2026-02-28
12 | BDP Commission | [5 empty] | 0 | 0 |  | 12 | 12. BDP Commission | [10 empty] | 0
12 | BDP Commission | [8 empty] | 12 | 12. BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 110470.5687 | 2025-08-31 | 429230.6344 | 487762.0846 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 130354.3043 |  |  | 2026-02-28 | 487762.0846 | 0 | 2026-02-28 | 130354.3043
13 |  | Management |  |  | 77714.2857 | 2025-08-31 |  |  |  | 13 | 13. Engineering | Management | [6 empty] | 0
13 |  | Project manager |  |  | 136000 | 2025-08-31 |  |  |  | 13 | 13. Engineering | Project manager | [6 empty] | 0
13 |  | Planner time |  |  | 52000 | 2025-08-31 |  |  |  | 13 | 13. Engineering | Planner time | [6 empty] | 0
13 |  | De Snagging |  |  | 53045.78 | 2025-08-31 |  |  |  | 13 | 13. Engineering | De Snagging | [6 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 23800 | 2025-09-05 | 23800 | 28000 |  | 14 | 14. General Expenses | Travel |  |  | 13986.75 |  | Expense Claim | 2025-09-30 | 16326.8878 | 0 | 2025-09-05 | 47089.8
14 | [5 empty] | 2025-07-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 10587.7 |  | Expense Claim | 2025-10-31 | 3732.1067 |  | 2025-11-06
14 | [5 empty] | 2025-08-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 5515.35 |  | Expense Claim | 2025-11-30 | 3279.4745 |  | 2025-12-05
14 | [5 empty] | 2025-09-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-12-31 | 0 |  | 2025-12-31
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 8500 |  |  | 2026-01-31 | 2330.7655 |  | 2026-02-07
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 8500 |  |  | 2026-02-28 | 2330.7655 |  | 2026-03-12
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | [5 empty] | 0 | 2000000 |  | 15 | 15. Service Add On | [8 empty] | 0 |  | 110570.16
15 | [9 empty] | 15 | 15. Service Add On
15 | [5 empty] | 2025-11-30 |  |  |  | 15 | 15. Service Add On | Relocation of panels - JA Electrical |  |  | 56132.72 | PO4507-DSHC-20251201 - RV Approved | JA Electrical - Inv 1143 | 2025-12-31 |  |  | 2026-02-05
15 | [9 empty] | 15 | 15. Service Add On | Trenching |  |  | 5717.44 | PO4518-DSHC-20251203 - RV Approved |  | 2026-01-31 |  |  | 2026-01-31
15 | [9 empty] | 15 | 15. Service Add On |  |  |  | 48720 |  | JA Electrical - Inv 1144 | 2025-12-31 |  |  | 2026-01-31
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
| Panel Procurement Budget | 2857717.17 |  | 3072814.1613
| Inverter Procurement Budget | 770000 |  | 827956.9892
| Mounting Structure Budget | 1105818.21 |  | 1189051.8387
| DC Equipment Budget | 1117490.1 |  | 1201602.2581
| AC Equipment Budget | 1511034.3 |  | 1624768.0645
| Monitoring Budget | 49000 |  | 52688.172
| Optional Extras Budget | 0 |  | 0
| MV Metering Budget | 300000 |  | 322580.6452
| ADD ON | 0 |  | 0
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 340042.5 |  | 386411.9318
| DC Installer Budget | 720090 |  | 818284.0909
| In-House Expense Budget | 429230.6344 |  | 487762.0846
| Compliance Budget | 182012.75 |  | 206832.6705
| Offloading Budget | 8500 |  | 9659.0909
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 33546.6667 |  | 38121.2121
| On Site Security | 72000 |  | 81818.1818
| Roof Access Budget for Installers | 70393.8 |  | 79992.9545
| EPC Management Fee | 0 |  | 0
| ADD ON | 2000000 |  | 2000000
Expenses
| Total EE Expense Budget | 23800 |  | 28000
Note on U118: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Roedolph Venter can I please get assist with this

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 9590676.1311 |  | 7349211.2423 | 2241464.8888
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 2857717.17 |  | 2657189.4 | 200527.77
2 | 2. Inverters | 770000 |  | 757573.938 | 12426.062
3 | 3. Mounting Structures | 1105818.21 |  | 363159.38 | 742658.83
4 | 4. DC Equipment | 1117490.1 |  | 713565.2 | 403924.9
5 | 5. Monitoring | 49000 |  | 91265.29 | -42265.29
6 | 6. AC Equipment | 1511034.3 |  | 586437.82 | 924596.48
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 300000 |  | 341826 | -41826
9 | 9. AC & DC installation | 1060132.5 |  | 1105292.2 | -45159.7
10 | 10. Site Logistics | 184440.4667 |  | 302543.9 | -118103.4333
11 | 11. Due Dilligence | 182012.75 |  | 142343.85 | 39668.9
12 | 12. BDP Commission | 0 |  | 0 | 0
13 | 13. Engineering | 429230.6344 |  | 130354.3043 | 298876.3301
14 | 14. General Expenses | 23800 |  | 47089.8 | -23289.8
15 | 15. Service Add On | 0 |  | 110570.16 | -110570.16
| check: | 0 | #REF! | 0

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 10428344.3462 | 10428344.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6013204.76 | 0 | 0 | 0 | 2225569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2189570.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6013204.76 | 6013204.76 | 6013204.76 | 6013204.76 | 8238773.76 | 8238773.76 | 8238773.76 | 8238773.76 | 8238773.76 | 8238773.76 | 8238773.76 | 8238773.76 | 8238773.76 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35
| Planned Expenditure | 9590676.1311 | 8484857.9211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3715850.6511 | 23800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4745207.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3715850.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3715850.6511 | -3739650.6511 | -3739650.6511 | -3739650.6511 | -3739650.6511 | -3739650.6511 | -3739650.6511 | -3739650.6511 | -3739650.6511 | -3739650.6511 | -3739650.6511 | -3739650.6511 | -3739650.6511 | 2273554.1089 | 2273554.1089 | 2273554.1089 | 2273554.1089 | 4499123.1089 | -246084.1611 | -246084.1611 | -246084.1611 | -246084.1611 | -246084.1611 | -246084.1611 | -246084.1611 | -246084.1611 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 10428344.35 | 10428344.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006602.38 | 3006602.38 | 0 | 0 | 0 | 0 | 2225569 | 0 | 0 | 0 | 0 | 0 | 2189570.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006602.38 | 6013204.76 | 6013204.76 | 6013204.76 | 6013204.76 | 6013204.76 | 8238773.76 | 8238773.76 | 8238773.76 | 8238773.76 | 8238773.76 | 8238773.76 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35
| Actual + Planned Expenditure | 7349211.2423 | 7349211.2423 | 0 | 0 | 0 | 0 | 0 | 79700 | 9620 | 0 | 0 | 0 | 0 | 9019.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3575.5 | 0 | 0 | 55169 | 13986.75 | 0 | 0 | 0 | 0 | 0 | 192717 | 0 | -26000 | 436340.25 | 0 | 0 | 158695.92 | 5515.35 | 3263161.308 | 1618621.95 | 0 | 395550.67 | 0 | 0 | 15556.95 | 103157.44 | -2413.48 | 339455.78 | 170301.02 | 154241.7943 | 255451.53 | 8500 | 0 | 85150.51 | 4136.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 79700 | 89320 | 89320 | 89320 | 89320 | 89320 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 101915.1 | 101915.1 | 101915.1 | 157084.1 | 171070.85 | 171070.85 | 171070.85 | 171070.85 | 171070.85 | 171070.85 | 363787.85 | 363787.85 | 337787.85 | 774128.1 | 774128.1 | 774128.1 | 932824.02 | 938339.37 | 4201500.678 | 5820122.628 | 5820122.628 | 6215673.298 | 6215673.298 | 6215673.298 | 6231230.248 | 6334387.688 | 6331974.208 | 6671429.988 | 6841731.008 | 6995972.8023 | 7251424.3323 | 7259924.3323 | 7259924.3323 | 7345074.8423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423 | 7349211.2423
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | -79700 | -89320 | -89320 | -89320 | -89320 | -89320 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -101915.1 | -101915.1 | -101915.1 | -157084.1 | -171070.85 | -171070.85 | -171070.85 | -171070.85 | -171070.85 | -171070.85 | -363787.85 | -363787.85 | -337787.85 | -774128.1 | -774128.1 | -774128.1 | -932824.02 | 2068263.01 | 1811704.082 | 193082.132 | 193082.132 | -202468.538 | -202468.538 | 2023100.462 | 2007543.512 | 1904386.072 | 1906799.552 | 1567343.772 | 1397042.752 | 3432371.5477 | 3176920.0177 | 3168420.0177 | 3168420.0177 | 3083269.5077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077 | 3079133.1077
|  | CHECK | CHECK
| Revenue Recognition | 9818.0797 | 10418526.2665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207057.4377 | 0 | 0 | 0 | 6882663.6019 | 0 | 0 | 0 | 1024984.8349 | 0 | 0 | 0 | 0 | 690536.216 | 0 | 0 | 0 | 388503.647 | 0 | 0 | 0 | 884584.6328 | 0 | 0 | 0 | 0 | 340195.8961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 10418526.2665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207057.4377 | 207057.4377 | 207057.4377 | 207057.4377 | 7089721.0396 | 7089721.0396 | 7089721.0396 | 7089721.0396 | 8114705.8745 | 8114705.8745 | 8114705.8745 | 8114705.8745 | 8114705.8745 | 8805242.0905 | 8805242.0905 | 8805242.0905 | 8805242.0905 | 9193745.7376 | 9193745.7376 | 9193745.7376 | 9193745.7376 | 10078330.3704 | 10078330.3704 | 10078330.3704 | 10078330.3704 | 10078330.3704 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665 | 10418526.2665

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | Grand Total
(blank)
1. Panels |  |  | 3072814.1613 |  |  | 0 | 0 |  | 3072814.1613
2. Inverters |  |  | 827956.9892 |  |  | 0 |  |  | 827956.9892
3. Mounting Structures |  |  | 1189051.8387 | 0 |  |  | 0 |  | 1189051.8387
4. DC Equipment |  |  | 987322.518 |  | 85711.896 | 0 | 42855.948 | 85711.896 | 1201602.2581
5. Monitoring |  | 38193.7663 | 14494.4017 | 0 |  | 0 |  |  | 52688.168
6. AC Equipment |  |  | 160352.8813 | 983356.5392 | 192423.3591 | 0 | 96211.7616 | 192423.5232 | 1624768.0645
8. Product Add On | 0 |  | 266785.5862 |  |  | 0 | 55795.059 |  | 322580.6452
9. AC & DC installation |  |  | 301174.0057 |  | 361408.8068 | 0 | 180704.4034 | 361408.8068 | 1204696.0227
10. Site Logistics | 0 |  | 58979.1131 | 38348.8212 | 50992.1541 | 0 | 20423.7831 | 40847.5661 | 209591.4375
11. Due Dilligence |  | 152536.7836 | [5 empty] | 54295.8867 | 206832.6702
13. Engineering | 0 |  |  |  |  | 0 |  | 487762.0846 | 487762.0846
14. General Expenses |  | 16326.8878 | 3732.1067 | 3279.4745 | 0 | 0 | 2330.7655 | 2330.7655 | 28000
15. Service Add On
12. BDP Commission
7.BESS
Grand Total | 0 | 207057.4377 | 6882663.6019 | 1024984.8349 | 690536.216 | 0 | 398321.7206 | 1224780.5289 | 10428344.34

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | Grand Total
(blank)
1. Panels |  |  | 2653053 |  |  | 4136.4 |  | 2657189.4
2. Inverters |  |  | 757573.938 |  |  |  |  | 757573.938
3. Mounting Structures |  |  | 339516.22 | 71394.92 |  | 15556.95 |  | 426468.09
4. DC Equipment |  |  | 586316.3 |  | 50899.56 | 25449.78 | 50899.56 | 713565.2
5. Monitoring |  | 58744.5 | -8100.66 | 40621.45 |  |  |  | 91265.29
6. AC Equipment |  |  | 57877.2 | 354929.22 | 69452.44 | 34726.32 | 69452.64 | 586437.82
8. Product Add On |  |  | 232956 |  |  | 48720 |  | 281676
9. AC & DC installation |  |  | 276323.05 |  | 331587.66 | 165793.83 | 331587.66 | 1105292.2
10. Site Logistics |  |  | 85136 | 60000 | 68963.1 | 29481.6 | 58963.2 | 302543.9
11. Due Dilligence |  | 98339.6 |  |  |  |  | 44004.25 | 142343.85
13. Engineering | [6 empty] | 130354.3043 | 130354.3043
14. General Expenses |  | 13986.75 | 10587.7 | 5515.35 | 0 | 8500 | 8500 | 47089.8
15. Service Add On |  |  |  |  | 104852.72 | 5717.44 |  | 110570.16
12. BDP Commission
7.BESS
Grand Total |  | 171070.85 | 4991238.748 | 532460.94 | 625755.48 | 338082.32 | 693761.6143 | 7352369.9523

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 0.20433 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.10453 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.070716 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 0.16924 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
Seshego Circle |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Seshego Circle | 0 | 0 | 0