## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[10 empty] | 2026-02-02 | 2026-02-02
| PROJECT PLAN | Tskana Corner | [7 empty] | 0 | 1
| PROJECT SIZE (kWp) | 308
| PROJECT DEVELOPER | Natasha Watkins-Baker
| PROJECT MANAGERS | JT Moorosi
| CONTRACT VALUE | 2696545
| Phase: | Construction
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Expected Status |  | Comment
|  |  | 39 |  |  | 252 |  | 67.67% | 63.54%
1 | Project Initiation | 2025-04-22 | 42 | 2025-06-03 | 2025-04-29 | 17 | 2025-05-16 | 100% | 100% | 17
1.1 | BD Handover | 2025-04-22 | 1 | 2025-04-23 | 2025-05-13 | 1 | 2025-05-14 | 100% | 100%
1.2 | Project Introduction | 2025-06-02 | 1 | 2025-06-03 | 2025-05-15 | 1 | 2025-05-16 | 100% | 100%
1.3 | HSE | 2025-04-22 | 10 | 2025-05-07 | 2025-04-29 | 10 | 2025-05-14 | 100% | 100%
1.4 | Installer Kick Off | 2025-05-26 | 1 | 2025-05-27 | 2025-05-14 | 1 | 2025-05-15 | 100% | 100%
1.5 | Project Review | 2025-05-26 | 1 | 2025-05-27 | 2025-05-08 | 1 | 2025-05-09 | 100% | 100%
2 | Site Establishment | 2025-06-09 | 1 | 2025-06-10 | 2025-06-10 | 1 | 2025-06-11 | 100% | 100% | 1
2.1 | Solar Contractor Establishment | 2025-06-09 | 1 | 2025-06-10 | 2025-06-10 | 1 | 2025-06-11 | 100% | 100% | 1 |  | 176 | Net Work Days
3 | AC Installation | 2025-05-19 | 57 | 2025-07-15 | 2025-05-20 | 241 | 2026-01-16 | 91.02% | 100% | 219.3508 |  | 35.2 | Total Weeks
3.1 | Inverters delivered | 2025-06-10 | 1 | 2025-06-11 | 2025-06-11 | 1 | 2025-06-12 | 100% | 100% |  |  | 8.75 | kW/Week Installation Rate
3.2 | Inverters Mounted | 2025-06-11 | 5 | 2025-06-19 | 2025-08-20 | 1 | 2025-08-21 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-05-19 | 25 | 2025-06-24 | 2025-05-20 | 25 | 2025-06-25 | 100% | 100%
3.4 | AC Works | 2025-06-24 | 15 | 2025-07-15 | 2025-08-20 | 149 | 2026-01-16 | 90% | 100% |  | Tech-sitter wired; inverter & tie-in cables prepared; pre-tie-in checks progressing.
3.5 | AC Tie-In | 2025-06-24 | 3 | 2025-06-27 | 2026-01-12 | 1 | 2026-01-13 | 0% | 100% |  | Need approval for the new Tie-In plan ¦ Submitting today 23 Jan
4 | DC Works | 2025-06-09 | 28 | 2025-07-07 | 2025-06-10 | 143 | 2025-10-31 | 95.45% | 75.02% | 136.5
4.1 | Lifeline Installation (If Applicable) | [6 empty] | 0% | 0%
4.1 | Mounting Structure delivered | 2025-06-09 | 1 | 2025-06-10 | 2025-06-11 | 1 | 2025-06-12 | 100% | 100%
4.2 | Mounting Structure installation | 2025-06-10 | 10 | 2025-06-25 | 2025-06-10 | 6 | 2025-06-19 | 100% | 100%
4.3 | DC Cable delivered | 2025-06-09 | 1 | 2025-06-10 | 2025-06-11 | 1 | 2025-06-12 | 100% | 100%
4.3 | DC Stringing | 2025-06-30 | 5 | 2025-07-07 | 2025-10-13 | 14 | 2025-10-31 | 100% | 100% |  | DC ~85%. Comms cables pulled; tech-sitter connected at PVDB. Finish comms; ready for shutdown.
5 | Module installation | 2025-06-18 | 15 | 2025-07-03 | 2025-06-11 | 51 | 2025-08-01 | 100% | 100% | 1900-02-19
5.1 | Module delivery | 2025-06-18 | 1 | 2025-06-19 | 2025-06-11 | 1 | 2025-06-12 | 100% | 100%
5.2 | Module mounting | 2025-06-19 | 10 | 2025-07-03 | 2025-06-12 | 35 | 2025-08-01 | 100% | 100%
6 | Commissioning | 2025-07-15 | 3 | 2025-07-18 | 2025-10-13 | 127 | 2026-02-17 | 54.88% | 33.32% | 69.6951
6.1 | Remove and Refit of Modules | 2025-07-15 | 1 | 2025-07-16 | 2025-10-13 | 45 | 2025-12-15 | 100% | 100% |  | Factoring in a 45 day roof delay
6.2 | Work because of Roof remidial |  |  |  | 2025-10-13 | 35 | 2025-11-17 | 100% | 100%
6.3 | Practical Completion | 2025-07-16 | 2 | 2025-07-18 | 2026-02-15 | 2 | 2026-02-17 | 0% | 0% |  | linked to AC tie complexity
7 | QA Inspections | 2025-07-18 | 3 | 2025-07-21 | 2026-02-17 | 1 | 2026-02-18 | 0% | 0% | 0
7.1 | Red-Team Inspection | 2025-07-18 | 1 | 2025-07-21 | 2026-02-17 | 1 | 2026-02-18 | 0% | 0%
8 | Project Closure | 2025-07-21 | 14 | 2025-08-04 | 2026-02-18 | 14 | 2026-03-04 | 0% | 0% | 0
8.1 | Equipment serial numbers | 2025-07-21 | 2 | 2025-07-23 | 2026-02-18 | 2 | 2026-02-20 | 0% | 0%
8.2 | Snags completion | 2025-07-21 | 5 | 2025-07-28 | 2026-02-18 | 5 | 2026-02-25 | 0% | 0%
8.3 | System Performance Monitoring | 2025-07-28 | 5 | 2025-08-04 | 2026-02-25 | 5 | 2026-03-04 | 0% | 0%
8.4 | Handover documentation | 2025-07-21 | 5 | 2025-07-28 | 2026-02-18 | 5 | 2026-02-25 | 0% | 0%
8.5 | Handover to Client | 2025-07-28 | 1 | 2025-07-29 | 2026-02-25 | 1 | 2026-02-26 | 0% | 0%
8.6 | Handover to Matriarch | 2025-07-23 | 5 | 2025-07-30 | 2026-02-20 | 5 | 2026-02-27 | 0% | 0%
Formulas:
Planned Start = MIN([Planned Start, row below]:E16)
Planned Start = WORKDAY.INTL([Planned End, row above],0,1,Data!$C3:C14)
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = [Actual End, row above]
Actual End = MAX([Actual End, row below]:K16)
Actual End = MAX([Actual End, row below])
Expected Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 2696545 |  | 2696545 |  |  |  | Start Date | 2012394.0351 | 1641057.17 | 604580.4893 | 822739.1125 | 470784.3993 | 781632.3
2 | Planned Expenditure | 2451177.9109 |  | 2463796.2825 | VO PM LIMIT | CURRENT VO Total
3 | Planned Profit | 245367.0891 |  | 232748.7175 | 12268.3545 | 242242 |  | End Date - PC
4 | Planned Margin | 9.099% |  | 8.631%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE |  | MILESTONE NOTES & COMMENTS
1 | Deposit |  | 20% | 539309 |  | 2025-04-30 | 004739 | 2025-05-01 | 2025-04-30
2 | Delivery of Panels |  | 20% | 539309 |  | 2025-06-25 | 004739 | 2025-05-01 | 2025-06-20
3 | Delivery of Inverters |  | 15% | 404481.75 |  | 2025-06-17 | 004739 | 2025-05-01 | 2025-06-20
4 | Commissioning Complete |  | 15% | 404481.75 |  | 2025-07-25 | 004739 | 2025-05-01 | 2026-02-24
5 | Final Completion Issued |  | 25% | 674136.25 |  | 2025-07-28 | 004739 | 2025-05-01 | 2026-02-25
6 | Handover |  | 5% | 134827.25 |  | 2026-03-05 | 004739 | 2025-05-01 | 2026-03-05
7 | - |  | 0% | 0
|  |  | 100% | 2696545
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 943790.75
2 | Delivery of Panels |  | 30% | 808963.5
3 | Delivery of Inverters |  | 20% | 539309
4 | Practical Completion |  | 10% | 269654.5
5 | Handover |  | 5% | 134827.25
| Total |  | 100% | 2696545
|  |  | 100% | 2696545

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 2451177.9109 |  | 2463796.2825 | -12618.3716
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 647549.21 |  | 620962.18 | 26587.03
2 | 2. Inverters | 210000 |  | 206611.05 | 3388.95
3 | 3. Mounting Structures | 138694.5 |  | 71480.8 | 67213.7
4 | 4. DC Equipment | 255176.3 |  | 214275.25 | 40901.05
5 | 5. Monitoring | 49000 |  | 35927.13 | 13072.87
6 | 6. AC Equipment | 373625.7261 |  | 201092.11 | 172533.6161
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 0 |  | 308513 | -308513
9 | 9. AC & DC installation | 249287.5 |  | 308000 | -58712.5
10 | 10. Site Logistics | 46350 |  | 29143.22 | 17206.78
11 | 11. Due Dilligence | 29000 |  | 22670.42 | 6329.58
12 | 12. BDP Commission | 53861.1344 |  | 0 | 53861.1344
13 | 13. Engineering | 93383.5405 |  | 33706.8125 | 59676.728
14 | 14. General Expenses | 5250 |  | 7414.31 | -2164.31
15 | 15. Service Add On | 300000 |  | 404000 | -104000
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 2451177.9109 | 2696545.3009 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 2463796.2825
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 647549.21 | 2025-07-29 | 647549.21 | 735851.375 |  | 1 | 1. Panels | Longi 620W - Menlo | 194 | 1175.96 | 228137 | PO3932-DIP-Ph2-Tsakane-20250519 - RV Approved | Krannich - INV 15-10012800 | 2025-05-31 | 270346.4567 | 0 | 2025-07-29 | 620962.18
[6 empty] | 2025-07-29 | [6 empty] | 315 | 1175.96 | 370428.63 |  | Krannich - INV 15-10012799 | 2025-05-31 | 438964.6028 |  | 2025-07-29
1 |  | Delivery Budget |  |  |  | 2025-07-29 |  |  |  | 1 | 1. Panels | ChemiTek Solar Wash |  |  | 1842 |  | Krannich - INV 15-10012799 | 2025-05-31 | 2182.8032 |  | 2025-07-29
1 | [5 empty] | 2025-07-29 |  |  |  | 1 | 1. Panels | EPR Fees |  |  | 6284.25 |  | Krannich - INV 15-10012799 | 2025-05-31 | 7446.9495 |  | 2025-07-29
1 | [5 empty] | 2025-07-29 |  |  |  | 1 | 1. Panels |  |  |  | 10400 |  | Krannich - INV 15-10012799 | 2025-05-31 | 12324.1874 |  | 2025-07-29
1 | [5 empty] | 2025-07-29 |  |  |  | 1 | 1. Panels |  |  |  | 3870.3 |  | Krannich - INV 15-10012800 | 2025-05-31 | 4586.3753 |  | 2025-07-29
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 373625.7261
2 | Inverters | Inverter Budget |  |  | 210000 | 2025-07-24 | 210000 | 238636.3636 |  | 2 | 2. Inverters | Huawei 100KTL - Menlo | 3 | 68870.35 | 206611.05 | PO3908-DIP-PH2-TSK-20250514 | Menlo INV0002938 | 2025-05-31 | 238636.3636 | 0 | 2025-07-24 | 206611.05 | DC Equipment | 153914.3
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | AC Labour | 77052.5
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 172235
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 0
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 1850
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 138694.5 | 2025-06-27 | 138694.5 | 157607.3864 |  | 3 | 3. Mounting Structures | Schletter Structure |  |  | 60238.8 | PO3942-DTC-20250521 - RV Approved | Schletter - INV1790 | 2025-05-31 | 107042.4866 | -0.0026062 | 2025-06-27 | 71480.8 | Other | 0
3 | [5 empty] | 2025-07-29 |  |  |  | 3 | 3. Mounting Structures | Schletter - Mid and End Clamps top up/replacement - VO |  |  | 11242 | PO3999-DTC-20250617 - RV Approved | Schletter - INV1869 | 2025-06-30 | 5688.1206 |  | 2025-07-29 |  | Total | 787177.5261
3 | [9 empty] | 3 | 3. Mounting Structures | Available Budget |  |  | 0 |  |  | 2025-08-31 | 44876.7818 |  |  |  | Less 15% | 669100.8972
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | R/Wp | 2.1724
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL - Cosmic Sun | Installer Price
[23 empty] | AC Equipment | 83761.4
4 | DC Equipment | DC Cable Budget | 8317.95 |  | 101262 | 2025-05-05 | 255176.3 | 289973.0682 |  | 4 | 4. DC Equipment | DC Cable - Krannich | 8000 | 13.89 | 111120 | PO3932-DIP-Ph2-Tsakane-20250519 - RV Approved | Krannich - INV 15-10012816 | 2025-05-31 | 150375.7776 | 0 | 2025-05-05 | 214275.25 | DC Equipment | 103155.25
4 |  | DC Equipment Budget |  |  | 153914.3 | 2025-05-05 |  |  |  | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | AC Labour | 92400
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | DC Labour | 215600
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Offloading | 4950
4 | [5 empty] | 2025-05-15 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 103155.25 | 10% | 10315.525 | PO3875-DTC-20250513 - RV Approved | Cosmic Sun CS_TSK_001 | 2025-05-31 | 13959.7291 |  | 2025-05-15 |  | Scaffolding | 13093.23
4 | [5 empty] | 2025-06-19 |  |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 15473.2875 |  | Cosmic Sun CS_TSK_002 | 2025-06-30 | 20939.5936 |  | 2025-06-19 |  | Storage | 6600
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 20631.05 |  | Cosmic Sun CS_TSK_004 | 2025-06-30 | 27919.4581 |  | 2026-01-29 |  | Telehandler | 0
4 | [5 empty] | 2025-07-03 |  |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 25788.8125 |  | Cosmic Sun CS_TSK_003 | 2025-06-30 | 34899.3226 |  | 2025-07-03 |  | HSE | 4500
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 10315.525 |  | Cosmic Sun CS_TSK_005 | 2025-06-30 | 13959.7291 |  | 2026-02-24 |  | Other | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 10315.525 |  | Cosmic Sun CS_TSK_006 | 2025-06-30 | 13959.7291 |  | 2026-03-04 |  | Other | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 5157.7625 |  | Cosmic Sun CS_TSK_007 | 2025-06-30 | 6979.8645 |  | 2026-03-04 |  | Total | 524059.88
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 5157.7625 |  | Cosmic Sun CS_TSK_008 | 2025-06-30 | 6979.8645 |  | 2026-03-27 |  | R/Wp | 1.7015
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 34000 | 2025-07-17 | 49000 | 55681.8182 |  | 5 | 5. Monitoring | Smartlogger - Menlo |  |  | 8598.35 | PO3908-DIP-PH2-TSK-20250514 | Menlo INV0002935 | 2025-05-31 | 12277.0934 | -0.0044773 | 2025-07-17 | 35927.13
5 |  | Revenue Metering |  |  | 15000 | 2025-05-31 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 13695 | PO3838-DIP-Ph2-Tsakane-20250429 - RV Approved | Accuenergy Inv: ASAI005364 | 2025-04-30 | 19114.2374 |  | 2025-05-31
[6 empty] | 2025-07-29 |  |  |  | 5 | 5. Monitoring |  |  |  | 214.28 |  | Accuenergy - Inv ASAI-005800 | 2025-06-30 | 332.1028 |  | 2025-07-29
5 | [5 empty] | 2025-06-30 |  |  |  | 5 | 5. Monitoring | Techsitter |  |  | 11169 |  | Matriarch Inv: 4451 | 2025-06-30 | 20789.4531 |  | 2025-06-30
5 | [5 empty] | 2025-05-22 |  |  |  | 5 | 5. Monitoring | UPS |  |  | 2250.5 | PO3863-DIP Ph2-20250509 - RV Approved | Frontline INV725690 | 2025-05-31 | 3168.936 |  | 2025-05-22
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 373625.7261 | 2025-07-28 | 373625.7261 | 424574.6887 |  | 6 | 6. AC Equipment | [7 empty] | 0 | -0.0030876 |  | 201092.11
6 | [5 empty] | 2025-07-29 |  |  |  | 6 | 6. AC Equipment | PVDB |  |  | 117330.71 | PO3874-DIP-Ph2-Tsakane-20250513 - RV Approved | Switchboard Inv: 2-SOI002098 | 2025-06-30 | 247725.5307 |  | 2025-07-29
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [5 empty] | 2025-05-15 |  |  |  | 6 | 6. AC Equipment | Project Kick Off | 83761.4 | 10% | 8376.14 | PO3875-DTC-20250513 - RV Approved | Cosmic Sun CS_TSK_001 | 2025-05-31 | 17946.6989 |  | 2025-05-15
6 | [5 empty] | 2025-06-19 |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 12564.21 |  | Cosmic Sun CS_TSK_002 | 2025-06-30 | 26265.5937 |  | 2025-06-19
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 16752.28 |  | Cosmic Sun CS_TSK_004 | 2025-06-30 | 35369.8316 |  | 2026-01-29
6 | [5 empty] | 2025-07-03 |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 20940.35 |  | Cosmic Sun CS_TSK_003 | 2025-06-30 | 44212.2895 |  | 2025-07-03
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 8376.14 |  | Cosmic Sun CS_TSK_005 | 2025-06-30 | 17684.9158 |  | 2026-02-24
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 8376.14 |  | Cosmic Sun CS_TSK_006 | 2025-06-30 | 17684.9158 |  | 2026-03-04
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 4188.07 |  | Cosmic Sun CS_TSK_007 | 2025-06-30 | 8842.4579 |  | 2026-03-04
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 4188.07 |  | Cosmic Sun CS_TSK_008 | 2025-06-30 | 8842.4579 |  | 2026-03-27
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 0 | 0 |  | 8 | 8. Product Add On | Inverter Cage - Deposit | 30% | 21138 | 6341.4 | PO4481-DTC-20251124 - RV Approved | JRL Engineering INV00425 | 2025-11-30 |  | 0 | 2025-11-27 | 308513
8 | [9 empty] | 8 | 8. Product Add On | Inverter Cage - Balance | 70% |  | 14796.6 |  | JRL Engineering INV00425 | 2025-11-30 |  |  | 2025-12-30
8 | [5 empty] | 1900-01-29 |  |  |  | 8 | 8. Product Add On | DB cage with Roof - Deposit | 30% | 22900 | 6870 | PO4481-DTC-20251124 - RV Approved | JRL Engineering INV00426 | 2025-11-30 |  |  | 2025-11-27
8 | [9 empty] | 8 | 8. Product Add On | DB cage with Roof - Balance | 70% |  | 16030 |  | JRL Engineering INV00426 | 2025-11-30 |  |  | 2025-12-30
8 | [5 empty] | 1900-01-29 |  |  |  | 8 | 8. Product Add On | Waterpoints - Plumbryt - Deposit |  |  | 16160 | PO4549-DTC-20260108 - RV Approved | Plumryt INV 024 | 2026-01-31 |  |  | 2026-01-29
[10 empty] | 8 | 8. Product Add On | Waterpoints - Plumbryt - Balance |  |  | 4040 |  | Plumryt INV 024 | 2026-01-31 |  |  | 2026-02-12
8 | [5 empty] | 2025-10-09 |  |  |  | 8 | 8. Product Add On | CS - Waterproofing removing and reinstall panels - VO |  |  | 115500 | PO4357-DTC-20251006 - RV Approved | Cosmic Sun - CS_TSK_010 | 2025-10-31 |  |  | 2025-10-09
[6 empty] | 1900-01-06 |  |  |  | 8 | 8. Product Add On | CS - Waterproofing removing and reinstall panels - VO |  |  | 115500 |  | Cosmic Sun - CS_TSK_012 | 2025-11-30 |  |  | 2025-12-18
8 | [5 empty] | 2025-10-02 |  |  |  | 8 | 8. Product Add On | CS - DB Stand |  |  | 7275 | PO4343-DTC-20250930 - RV Approved | Cosmic Sun: CS_TSK_009 | 2025-09-30 |  |  | 2025-10-02
8 | [9 empty] | 8 | 8. Product Add On | E Stop |  |  | 6000 |  | Cosmic Sun - CS_TSK_011 | 2025-11-30 |  |  | 2025-11-20
8 | [9 empty] | 8 | 8. Product Add On
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 77052.5 | 2025-05-14 | 249287.5 | 293279.4118 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0 |  | 308000
9 |  | DC Installation Budget |  |  | 172235 | 2025-05-15 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 308000 | 10% | 30800 | PO3875-DTC-20250513 - RV Approved | Cosmic Sun CS_TSK_001 | 2025-05-31 | 29327.9412 |  | 2025-05-15
9 | [5 empty] | 2025-06-19 |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 46200 |  | Cosmic Sun CS_TSK_002 | 2025-06-30 | 43991.9118 |  | 2025-06-19
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 61600 |  | Cosmic Sun CS_TSK_004 | 2025-06-30 | 58655.8824 |  | 2026-01-29
9 | [5 empty] | 2025-07-03 |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 77000 |  | Cosmic Sun CS_TSK_003 | 2025-06-30 | 73319.8529 |  | 2025-07-03
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 30800 |  | Cosmic Sun CS_TSK_005 | 2025-06-30 | 29327.9412 |  | 2026-02-24
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 30800 |  | Cosmic Sun CS_TSK_006 | 2025-06-30 | 29327.9412 |  | 2026-03-04
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 15400 |  | Cosmic Sun CS_TSK_007 | 2025-06-30 | 14663.9706 |  | 2026-03-04
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 15400 |  | Cosmic Sun CS_TSK_008 | 2025-06-30 | 14663.9706 |  | 2026-03-27
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-05-15 | 46350 | 54529.4118 |  | 10 | 10. Site Logistics | [7 empty] | 0 | -0.004435 |  | 29143.22
[6 empty] | 2025-05-15 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
[6 empty] | 2025-05-15 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
[6 empty] | 2025-05-15 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
[6 empty] | 2025-05-15 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Scaffolding |  |  | 0 | 2025-05-15 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Security |  |  | 36000 | 2025-05-15 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 1850 | 2025-05-15 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [5 empty] | 2025-05-15 |  |  |  | 10 | 10. Site Logistics | Project Kick Off | 29143.23 | 10% | 2914.323 | PO3875-DTC-20250513 - RV Approved | Cosmic Sun CS_TSK_001 | 2025-05-31 | 1525.94 |  | 2025-05-15
10 | [5 empty] | 2025-06-19 |  |  |  | 10 | 10. Site Logistics | Site Establishment |  | 15% | 4371.4845 |  | Cosmic Sun CS_TSK_002 | 2025-06-30 | 3493.9577 |  | 2025-06-19
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 5828.646 |  | Cosmic Sun CS_TSK_004 | 2025-06-30 | 4015.9169 |  | 2026-01-29
[6 empty] | 2025-08-31 |  |  |  | 10 | 10. Site Logistics |  |  |  | -0.01 |  | Cosmic Sun CS_TSK_004 | 2025-08-31 | 0 |  | 2025-08-31
10 | [5 empty] | 2025-07-03 |  |  |  | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 7285.8075 |  | Cosmic Sun CS_TSK_003 | 2025-06-30 | 5019.8962 |  | 2025-07-03
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 2914.323 |  | Cosmic Sun CS_TSK_005 | 2025-06-30 | 2007.9585 |  | 2026-02-24
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 2914.323 |  | Cosmic Sun CS_TSK_006 | 2025-06-30 | 2007.9585 |  | 2026-03-04
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 1457.1615 |  | Cosmic Sun CS_TSK_007 | 2025-06-30 | 1003.9792 |  | 2026-03-04
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 1457.1615 |  | Cosmic Sun CS_TSK_008 | 2025-06-30 | 1003.9792 |  | 2026-03-27
10 | [9 empty] | 10 | 10. Site Logistics | [6 empty] | 2025-07-31 | 34449.83
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2025-04-09 | 29000 | 34117.6471 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 8458.18 |  | Sunspot E027 | 2025-07-31 | 13975.0528 | -0.00016566 | 2026-03-03 | 22670.42
11 |  | Structural Sign Off |  |  | 18000 | 2025-04-10 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 8212.24 | PO3745-DIP-Ph2-20250313 - RV Approved | L&B Consulting - Invoice 1934 | 2025-04-30 | 11112.9478 |  | 2025-04-10
11 | [5 empty] | 2025-04-11 |  |  |  | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 |  |  | 2026-02-28 | 9029.6467 |  | 2026-03-30
11 | [5 empty] | 2025-04-12 |  |  |  | 11 | 11. Due Dilligence | [7 empty] | 0
11 | [5 empty] | 2025-04-13 |  |  |  | 11 | 11. Due Dilligence | [7 empty] | 0
2025-04-14
12 | BDP Commission | Referral Fee |  |  | 44884.2787 | 2025-04-15 | 53861.1344 | 0 |  | 12 | 12. BDP Commission | Referral Fee | [9 empty] | 0
12 | BDP Commission | PD Fee |  |  | 8976.8557 | 2025-04-16 |  |  |  | 12 | 12. BDP Commission | PD Fee
2025-04-17
13 | Engineering | Matriarch Defects Period |  |  | 24983.5405 | 2025-04-18 | 93383.5405 | 106117.6596 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 33706.8125 |  |  | 2026-02-28 | 106117.6596 | 0 | 2026-03-30 | 33706.8125
13 |  | Management |  |  | 12000 | 2025-04-19 |  |  |  | 13 | 13. Engineering | Management |  |  | 0 |  |  | 2025-11-30 | 0 |  | 2026-03-30
13 |  | Project manager |  |  | 27200 | 2025-04-20 |  |  |  | 13 | 13. Engineering | Project manager |  |  | 0 |  |  | 2025-11-30 | 0 |  | 2026-03-30
13 |  | Planner time |  |  | 15600 | 2025-04-21 |  |  |  | 13 | 13. Engineering | Planner time |  |  | 0 |  |  | 2025-11-30 | 0 |  | 2026-03-30
13 |  | De Snagging |  |  | 13600 | 2025-04-22 |  |  |  | 13 | 13. Engineering | De Snagging |  |  | 0 |  |  | 2025-11-30 | 0 |  | 2026-03-30
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 5250 | 2025-05-08 | 5250 | 6176.4706 |  | 14 | 14. General Expenses | Travel |  |  | 2352.17 |  | Site Visit | 2025-04-30 | 2052.8133 | 244.1795 | 2025-05-08 | 7414.31
14 | [5 empty] | 2025-05-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-05-31 | 0 |  | 2025-05-31
14 | [5 empty] | 2025-07-04 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 2345.52 |  | Expense Claim | 2025-06-30 | 1348.757 |  | 2025-07-04
14 | [5 empty] | 2025-08-07 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 685.44 |  | Expense Claim | 2025-07-31 | 716.5719 |  | 2025-08-07
14 | [5 empty] | 2025-08-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-08-31 | 0 |  | 2025-08-31
14 | [5 empty] | 2025-09-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-09-30 | 0 |  | 2025-09-30
14 | [5 empty] | 2025-10-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 631.18 |  | Expense Claim | 2025-10-31 | 647.8828 |  | 2025-11-06
14 | [5 empty] | 2025-11-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-11-30 | 0 |  | 2025-11-30
14 | [5 empty] | 2025-12-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-12-31 | 0 |  | 2025-12-30
14 | [5 empty] | 2026-01-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 700 |  |  | 2026-01-31 | 583.1331 |  | 2026-01-31
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 700 |  |  | 2026-02-28 | 583.1331 |  | 2026-03-07
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | Welcome Bonus |  |  | 300000 | 2025-06-19 | 300000 | 300000 |  | 15 | 15. Service Add On | Welcome Bonus - Site Establishment |  |  | 202000 |  | Luxanio Trading - 23404-202506-274901-I | 2025-06-30 | 141258.7413 | 0 | 2025-06-19 | 404000
15 | [5 empty] | #REF! |  |  |  | 15 | 15. Service Add On | Welcome Bonus - Commissioning |  |  | 202000 |  | Luxanio Trading - 23404-202506-274901-I | 2025-06-30 | 141258.7413 |  | 2026-02-24
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [5 empty] | 2025-08-31 |  |  |  | 15 | 15. Service Add On | Community Engagement |  |  | 0 |  |  | 2025-09-30 | 17482.5175 |  | 2025-09-30
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
| Panel Procurement Budget | 647549.21 |  | 735851.375
| Inverter Procurement Budget | 210000 |  | 238636.3636
| Mounting Structure Budget | 138694.5 |  | 157607.3864
| DC Equipment Budget | 255176.3 |  | 289973.0682
| AC Equipment Budget | 373625.7261 |  | 424574.6887
| Monitoring Budget | 49000 |  | 55681.8182
| Optional Extras Budget | 0 |  | 0
| MV Metering Budget | 0 |  | 0
| ADD ON | 0 |  | 0
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 77052.5 |  | 90650
| DC Installer Budget | 172235 |  | 202629.4118
| In-House Expense Budget | 93383.5405 |  | 106117.6596
| Compliance Budget | 29000 |  | 34117.6471
| Offloading Budget | 8500 |  | 10000
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 1850 |  | 2176.4706
| On Site Security | 36000 |  | 42352.9412
| Roof Access Budget for Installers | 0 |  | 0
| EPC Management Fee | 0 |  | 0
| ADD ON | 300000 |  | 300000
Expenses
| Total EE Expense Budget | 5250 |  | 6176.4706
Note on W84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date
Note on W89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 2696545 | 2696545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 539309 | 0 | 0 | 0 | 0 | 0 | 0 | 404481.75 | 539309 | 0 | 0 | 0 | 404481.75 | 674136.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134827.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 539309 | 539309 | 539309 | 539309 | 539309 | 539309 | 539309 | 943790.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1887581.5 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2561717.75 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545
| Planned Expenditure | 2451177.9109 | 2451177.9109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000 | 118044.6748 | 29200 | 0 | 260426.3 | 295637.5 | 0 | 15000 | 0 | 0 | 300000 | 138694.5 | 0 | 0 | 34000 | 210000 | 1021174.9361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000 | 147044.6748 | 176244.6748 | 176244.6748 | 436670.9748 | 732308.4748 | 732308.4748 | 747308.4748 | 747308.4748 | 747308.4748 | 1047308.4748 | 1186002.9748 | 1186002.9748 | 1186002.9748 | 1220002.9748 | 1430002.9748 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109 | 2451177.9109
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -29000 | -147044.6748 | -176244.6748 | 363064.3252 | 102638.0252 | -192999.4748 | -192999.4748 | -207999.4748 | -207999.4748 | -207999.4748 | -103517.7248 | 297096.7752 | 297096.7752 | 297096.7752 | 263096.7752 | 457578.5252 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 110539.8391 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891 | 245367.0891
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 2696545 | 2696545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 539309 | 0 | 0 | 0 | 0 | 0 | 0 | 943790.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1078618 | 134827.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 539309 | 539309 | 539309 | 539309 | 539309 | 539309 | 539309 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 1483099.75 | 2561717.75 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545 | 2696545
| Actual + Planned Expenditure | 2463796.2825 | 2463796.2825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8212.24 | 0 | 0 | 0 | 113472.17 | 52405.988 | 2250.5 | 13695 | 0 | 0 | 280608.982 | 60238.8 | 144529.49 | 0 | 8598.35 | 206611.05 | 749749.17 | 685.44 | 0 | 0 | -0.01 | 0 | 0 | 0 | 0 | 7275 | 115500 | 0 | 0 | 0 | 631.18 | 0 | 6000 | 13211.4 | 0 | 0 | 115500 | 0 | 30826.6 | 0 | 0 | 0 | 121671.976 | 0 | 4040 | 0 | 254405.988 | 87767.162 | 0 | 0 | 26202.994 | 39706.8125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8212.24 | 8212.24 | 8212.24 | 8212.24 | 121684.41 | 174090.398 | 176340.898 | 190035.898 | 190035.898 | 190035.898 | 470644.88 | 530883.68 | 675413.17 | 675413.17 | 684011.52 | 890622.57 | 1640371.74 | 1641057.18 | 1641057.18 | 1641057.18 | 1641057.17 | 1641057.17 | 1641057.17 | 1641057.17 | 1641057.17 | 1648332.17 | 1763832.17 | 1763832.17 | 1763832.17 | 1763832.17 | 1764463.35 | 1764463.35 | 1770463.35 | 1783674.75 | 1783674.75 | 1783674.75 | 1899174.75 | 1899174.75 | 1930001.35 | 1930001.35 | 1930001.35 | 1930001.35 | 2051673.326 | 2051673.326 | 2055713.326 | 2055713.326 | 2310119.314 | 2397886.476 | 2397886.476 | 2397886.476 | 2424089.47 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825 | 2463796.2825
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8212.24 | -8212.24 | -8212.24 | 531096.76 | 417624.59 | 365218.602 | 362968.102 | 349273.102 | 349273.102 | 349273.102 | 1012454.87 | 952216.07 | 807686.58 | 807686.58 | 799088.23 | 592477.18 | -157271.99 | -157957.43 | -157957.43 | -157957.43 | -157957.42 | -157957.42 | -157957.42 | -157957.42 | -157957.42 | -165232.42 | -280732.42 | -280732.42 | -280732.42 | -280732.42 | -281363.6 | -281363.6 | -287363.6 | -300575 | -300575 | -300575 | -416075 | -416075 | -446901.6 | -446901.6 | -446901.6 | -446901.6 | -568573.576 | -568573.576 | -572613.576 | -572613.576 | 251598.436 | 298658.524 | 298658.524 | 298658.524 | 272455.53 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175 | 232748.7175
|  | CHECK | CHECK
| Revenue Recognition | 243.8638 | 2696301.1362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32279.9984 | 0 | 0 | 0 | 1310112.3413 | 0 | 0 | 0 | 0 | 1125446.5872 | 0 | 0 | 0 | 49141.4547 | 0 | 0 | 0 | 44876.7818 | 0 | 0 | 0 | 0 | 17482.5175 | 0 | 0 | 0 | 647.8828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583.1331 | 0 | 0 | 0 | 115730.4393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 2696301.1362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32279.9984 | 32279.9984 | 32279.9984 | 32279.9984 | 1342392.3398 | 1342392.3398 | 1342392.3398 | 1342392.3398 | 1342392.3398 | 2467838.927 | 2467838.927 | 2467838.927 | 2467838.927 | 2516980.3817 | 2516980.3817 | 2516980.3817 | 2516980.3817 | 2561857.1635 | 2561857.1635 | 2561857.1635 | 2561857.1635 | 2561857.1635 | 2579339.681 | 2579339.681 | 2579339.681 | 2579339.681 | 2579987.5638 | 2579987.5638 | 2579987.5638 | 2579987.5638 | 2579987.5638 | 2579987.5638 | 2579987.5638 | 2579987.5638 | 2579987.5638 | 2579987.5638 | 2579987.5638 | 2579987.5638 | 2579987.5638 | 2580570.6968 | 2580570.6968 | 2580570.6968 | 2580570.6968 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362 | 2696301.1362

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | Grand Total
(blank) |  |  | 438964.6028 | [10 empty] | 438964.6028
1. Panels |  |  | 296886.7722 | [7 empty] | 0 |  |  | 296886.7722
2. Inverters |  |  | 238636.3636 | [7 empty] | 0 |  |  | 238636.3636
3. Mounting Structures |  |  | 107042.4866 | 5688.1206 |  | 44876.7818 |  |  |  |  | 0 |  |  | 157607.389
4. DC Equipment |  |  | 164335.5066 | 125637.5615 | [6 empty] | 0 |  |  | 289973.0682
5. Monitoring |  | 19114.2374 | 15446.0294 | 21121.5559 | [6 empty] | 0 |  |  | 55681.8227
6. AC Equipment |  |  | 17946.6989 | 406627.9929 | [6 empty] | 0 |  |  | 424574.6918
8. Product Add On
9. AC & DC installation |  |  | 29327.9412 | 263951.4706 | [6 empty] | 0 |  |  | 293279.4118
10. Site Logistics | 0 |  | 1525.94 | 18553.6462 | 34449.83 | 0 |  |  |  |  | 0 |  |  | 54529.4162
11. Due Dilligence |  | 11112.9478 |  |  | 13975.0528 | [5 empty] | 0 |  | 9029.6467 | 34117.6472
13. Engineering | [8 empty] | 0 |  | 0 |  | 106117.6596 | 106117.6596
14. General Expenses |  | 2052.8133 | 0 | 1348.757 | 716.5719 | 0 | 0 | 647.8828 | 0 | 0 | 0 | 583.1331 | 583.1331 | 5932.2911
15. Service Add On |  |  |  | 282517.4825 |  |  | 17482.5175 |  |  |  | 0 |  |  | 300000
12. BDP Commission
7.BESS
Grand Total | 0 | 32279.9984 | 1310112.3413 | 1125446.5872 | 49141.4547 | 44876.7818 | 17482.5175 | 647.8828 | 0 | 0 | 0 | 583.1331 | 115730.4393 | 2696301.1362
|  | 32280 | 1310112.34 | 1125446.59 | 49141.45 | 44876.78
|  | -0.0015557 | 0.0013378 | -0.0027758 | 0.0047154 | 0.0017979

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | Grand Total
(blank) |  |  | 370428.63 | [9 empty] | 370428.63
1. Panels |  |  | 250533.55 | [9 empty] | 250533.55
2. Inverters |  |  | 206611.05 | [9 empty] | 206611.05
3. Mounting Structures |  |  | 60238.8 | 11242 |  | 0 | [6 empty] | 71480.8
4. DC Equipment |  |  | 121435.525 | 92839.725 | [8 empty] | 214275.25
5. Monitoring |  | 13695 | 10848.85 | 11383.28 | [8 empty] | 35927.13
6. AC Equipment |  |  | 8376.14 | 192715.97 | [8 empty] | 201092.11
8. Product Add On | [6 empty] | 7275 | 115500 | 165538 |  | 20200 |  | 308513
9. AC & DC installation |  |  | 30800 | 277200 | [8 empty] | 308000
10. Site Logistics |  |  | 2914.323 | 26228.907 |  | -0.01 | [6 empty] | 29143.22
11. Due Dilligence |  | 8212.24 |  |  | 8458.18 | [6 empty] | 6000 | 22670.42
13. Engineering | [8 empty] | 0 |  |  | 33706.8125 | 33706.8125
14. General Expenses |  | 2352.17 | 0 | 2345.52 | 685.44 | 0 | 0 | 631.18 | 0 | 0 | 700 | 700 | 7414.31
15. Service Add On |  |  |  | 404000 |  |  | 0 | [5 empty] | 404000
12. BDP Commission
7.BESS
Grand Total |  | 24259.41 | 1062186.868 | 1017955.402 | 9143.62 | -0.01 | 7275 | 116131.18 | 165538 | 0 | 20900 | 40406.8125 | 2463796.2825

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate | [5 empty] | FINANCIAL CLOSE CERTIFICATE
Project Name: | Tskana Corner
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion: |  |  |  | 1. Financial Close | 1. Financial Close
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 0.90225 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.46155 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.31225 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 0.74727 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
Tskana Corner |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Tskana Corner | 0 | 0 | 0