## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate |  |  |  | FINANCIAL CLOSE CERTIFICATE
Project Name: | Sibasa
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[9 empty] | 2026-02-11 | 2026-02-11
| PROJECT PLAN | Sibasa | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 467
| PROJECT DEVELOPER | Natasha Watkins-Baker
| PROJECT MANAGERS | Eon Van Rensburg
| CONTRACT VALUE | 4662650
| Phase: | Construction
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Expected Status | Comment
|  |  | 61 |  |  | 266 |  | 74.78% | 75%
1 | Project Initiation | 2025-04-22 | 23 | 2025-05-15 | 2025-04-29 | 17 | 2025-05-16 | 100% | 100%
1.1 | BD Handover | 2025-04-22 | 1 | 2025-04-23 | 2025-05-13 | 1 | 2025-05-14 | 100% | 100%
1.2 | Project Introduction | 2025-05-14 | 1 | 2025-05-15 | 2025-05-15 | 1 | 2025-05-16 | 100% | 100%
1.3 | HSE | 2025-04-22 | 10 | 2025-05-07 | 2025-04-29 | 10 | 2025-05-14 | 100% | 100%
1.4 | Installer Kick Off | 2025-05-07 | 1 | 2025-05-08 | 2025-05-14 | 1 | 2025-05-15 | 100% | 100%
1.5 | Project Review | 2025-05-07 | 1 | 2025-05-08 | 2025-05-08 | 1 | 2025-05-09 | 100% | 100%
2 | Site Establishment | 2025-05-21 | 1 | 2025-05-22 | 2025-05-21 | 1 | 2025-05-22 | 100% | 100%
2.1 | Solar Contractor Establishment | 2025-05-21 | 1 | 2025-05-22 | 2025-05-21 | 1 | 2025-05-22 | 100% | 100% |  | 166 | Net Work Days
3 | AC Installation | 2025-04-23 | 72 | 2025-07-04 | 2025-04-23 | 112 | 2025-08-13 | 100% | 100% |  | 33.2 | Total Weeks
3.1 | Inverters delivered | 2025-05-22 | 1 | 2025-05-23 | 2025-05-22 | 1 | 2025-05-23 | 100% | 100% |  | 14.0663 | kW/Week Installation Rate
3.2 | Inverters Mounted | 2025-05-23 | 5 | 2025-05-30 | 2025-07-23 | 12 | 2025-08-08 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-04-23 | 25 | 2025-05-29 | 2025-04-23 | 45 | 2025-06-27 | 100% | 100%
3.4 | AC Works | 2025-05-29 | 25 | 2025-07-04 | 2025-07-23 | 15 | 2025-08-13 | 100% | 100%
3.5 | AC Tie-In | 2025-05-29 | 3 | 2025-06-03 | 2025-08-06 | 1 | 2025-08-07 | 100% | 100%
4 | DC Works | 2025-05-21 | 51 | 2025-07-11 | 2025-05-21 | 89 | 2025-08-18 | 100% | 100%
4.1 | Lifeline Installation (If Applicable) | [6 empty] | 0% | 0%
4.1 | Mounting Structure delivered | 2025-05-21 | 1 | 2025-05-22 | 2025-05-21 | 1 | 2025-05-22 | 100% | 100%
4.2 | Mounting Structure installation | 2025-05-22 | 10 | 2025-06-05 | 2025-05-22 | 10 | 2025-06-05 | 100% | 100%
4.3 | DC Cable delivered | 2025-05-21 | 1 | 2025-05-22 | 2025-05-29 | 1 | 2025-05-30 | 100% | 100%
4.3 | DC Stringing | 2025-06-27 | 10 | 2025-07-11 | 2025-06-16 | 45 | 2025-08-18 | 100% | 100%
5 | Module installation | 2025-05-29 | 32 | 2025-06-30 | 2025-05-29 | 25 | 2025-06-23 | 100% | 100%
5.1 | Module delivery | 2025-05-29 | 1 | 2025-05-30 | 2025-05-29 | 1 | 2025-05-30 | 100% | 100%
5.2 | Module mounting | 2025-05-30 | 20 | 2025-06-30 | 2025-05-30 | 15 | 2025-06-23 | 100% | 100%
6 | Commissioning | 2025-07-11 | 10 | 2025-07-21 | 2025-10-20 | 114 | 2026-02-11 | 98.21% | 100%
6.1 | Roof Work Removal and Refit | 2025-07-11 | 1 | 2025-07-14 | 2025-10-20 | 55 | 2026-02-05 | 100% | 100%
6.2 | Practical Completion | 2025-07-14 | 5 | 2025-07-21 | 2026-02-10 | 1 | 2026-02-11 | 0% | 100%
7 | QA Inspections | 2025-07-21 | 1 | 2025-07-22 | 2026-02-11 | 1 | 2026-02-12 | 0% | 0%
7.1 | Red-Team Inspection | 2025-07-21 | 1 | 2025-07-22 | 2026-02-11 | 1 | 2026-02-12 | 0% | 0% | Anderson Colsulting booked for 11 Feb
8 | Project Closure | 2025-07-22 | 14 | 2025-08-05 | 2026-02-12 | 11 | 2026-02-23 | 0% | 0%
8.1 | Equipment serial numbers | 2025-07-22 | 2 | 2025-07-24 | 2026-02-12 | 2 | 2026-02-16 | 0% | 0%
8.2 | Snags completion | 2025-07-22 | 5 | 2025-07-29 | 2026-02-12 | 1 | 2026-02-13 | 0% | 0%
8.3 | System Performance Monitoring | 2025-07-29 | 5 | 2025-08-05 | 2026-02-13 | 5 | 2026-02-20 | 0% | 0%
8.4 | Handover documentation | 2025-07-22 | 6 | 2025-07-30 | 2026-02-12 | 6 | 2026-02-20 | 0% | 0%
8.5 | Handover to Client | 2025-07-30 | 1 | 2025-07-31 | 2026-02-20 | 1 | 2026-02-23 | 0% | 0%
8.6 | Handover to Matriarch | 2025-07-24 | 5 | 2025-07-31 | 2026-02-14 | 5 | 2026-02-20 | 0% | 0%
Formulas:
Planned Start = MIN([Planned Start, row below]:E16)
Planned Start = WORKDAY.INTL([Planned End, row above],0,1,Data!$C3:C44)
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C44)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = WORKDAY.INTL([Actual End, row above],0,1,Data!$C3:C44)
Actual End = MAX([Actual End, row below]:K16)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C44)
Expected Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 4662650 |  | 4662650 |  |  |  | Start Date | 4538499.1143 | 3579234.0275 | 0 | 592893.72 | 0 | 589893.72
2 | Planned Expenditure | 4250720.1452 |  | 4172127.7475 | VO PM LIMIT | CURRENT VO Total
3 | Planned Profit | 411929.8548 |  | 490522.2525 | 20596.4927 | 553310 |  | End Date - PC
4 | Planned Margin | 8.835% |  | 10.52%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE |  | MILESTONE NOTES & COMMENTS
1 | Deposit |  | 20% | 932530 |  | 2025-05-30 | 004738 | 2025-05-01 | 2025-04-30
2 | Delivery of Panels |  | 20% | 827620.8696 |  | 2025-06-05 | 004738 | 2025-05-01 | 2025-06-06
|  |  |  | 104909.1304 |  | 2025-06-06 | 004738 | 2025-05-01 | 2025-07-04
3 | Delivery of Inverters |  | 15% | 699397.5 |  | 2025-05-29 | 004738 | 2025-05-01 | 2025-05-30
4 | Commissioning Complete |  | 15% | 699397.5 |  | 2025-07-28 | 004738 | 2025-05-01 | 2026-02-18
5 | Final Completion Issued |  | 25% | 1165662.5 |  | 2025-07-29 | 004738 | 2025-05-01 | 2026-02-19
6 | Handover |  | 5% | 233132.5 |  | 2026-03-02 | 004738 | 2025-05-01 | 2026-03-02
7 | - |  | 0% | 0
|  |  | 100% | 4662650
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 1631927.5
2 | Delivery of Panels |  | 30% | 1398795
3 | Delivery of Inverters |  | 20% | 932530
4 | Practical Completion |  | 10% | 466265
5 | Handover |  | 5% | 233132.5
| Total |  | 100% | 4662650
|  |  | 100% | 4662650

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-17 | Builders Holiday
2025-12-18 | Builders Holiday
2025-12-19 | Builders Holiday
2025-12-20 | Builders Holiday
2025-12-21 | Builders Holiday
2025-12-22 | Builders Holiday
2025-12-23 | Builders Holiday
2025-12-24 | Builders Holiday
2025-12-25 | Builders Holiday
2025-12-26 | Builders Holiday
2025-12-27 | Builders Holiday
2025-12-28 | Builders Holiday
2025-12-29 | Builders Holiday
2025-12-30 | Builders Holiday
2025-12-31 | Builders Holiday
2026-01-01 | Builders Holiday
2026-01-02 | Builders Holiday
2026-01-03 | Builders Holiday
2026-01-04 | Builders Holiday
2026-01-05 | Builders Holiday
2026-01-06 | Builders Holiday
2026-01-07 | Builders Holiday
2026-01-08 | Builders Holiday
2026-01-09 | Builders Holiday
2026-01-10 | Builders Holiday
2026-01-11 | Builders Holiday
2026-01-12 | Builders Holiday
2026-01-13 | Builders Holiday
2026-01-14 | Builders Holiday
2026-01-15 | Builders Holiday
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 4250720.1452 |  | 4172127.7475 | 78592.3977
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 1020809.83 |  | 933252.8 | 87557.03
2 | 2. Inverters | 320000 |  | 275481.4 | 44518.6
3 | 3. Mounting Structures | 379532.79 |  | 154149.2 | 225383.59
4 | 4. DC Equipment | 363479.3 |  | 383972.2525 | -20492.9525
5 | 5. Monitoring | 49000 |  | 35927.14 | 13072.86
6 | 6. AC Equipment | 628218.8087 |  | 280470.48 | 347748.3287
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 0 |  | 629215 | -629215
9 | 9. AC & DC installation | 368077.5 |  | 560350 | -192272.5
10 | 10. Site Logistics | 99195.1333 |  | 86215.75 | 12979.3833
11 | 11. Due Dilligence | 115012.25 |  | 36674.97 | 78337.28
12 | 12. BDP Commission | 90423.6002 |  | 0 | 90423.6002
13 | 13. Engineering | 158920.933 |  | 58283.125 | 100637.808
14 | 14. General Expenses | 8050 |  | 39135.63 | -31085.63
15 | 15. Service Add On | 650000 |  | 699000 | -49000
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 4250720.1452 | 4662649.8794 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 4172127.7475
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | ERROR on REV |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 1020809.83 | 2025-07-29 | 1020809.83 | 1160011.1705 |  | 1 | 1. Panels | Jinko 620W - MENLO | 753 | 1233.8 | 929051.4 | PO3901-DIP-PH2-SIBA-20250514 | Menlo INV0002964 | 2025-05-31 | 1160011.1705 | 0 | 2025-07-29 | 933252.8
1 |  | Delivery Budget | [7 empty] | 1 | 1. Panels | Replacement panels | 3 | 1233.8 | 3701.4 |  | MSA Energy INV0003591 | 2026-02-28 | 0 |  | 2026-04-06
1 | [9 empty] | 1 | 1. Panels | Transport |  |  | 500 |  | MSA Energy INV0003591 | 2026-02-28 | 0 |  | 2026-04-06
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 628218.8087
2 | Inverters | Inverter Budget |  |  | 320000 | 2025-07-17 | 320000 | 363636.3636 |  | 2 | 2. Inverters | Huawei 100KTL - MENLO | 4 | 68870.35 | 275481.4 | PO3901-DIP-PH2-SIBA-20250514 | Menlo INV0002927 | 2025-05-31 | 363636.3636 | 0 | 2025-07-17 | 275481.4 | DC Equipment | 208317.3
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | AC Labour | 116707.5
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 251370
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 29821.8
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 5673.3333
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 379532.79 | 2025-06-27 | 379532.79 | 431287.2614 |  | 3 | 3. Mounting Structures | Schletter Structure |  | 155161.68 | 134923.2 | PO3898-DSS-20250514 - RV Approved | Schletter - INV1781 | 2025-05-31 | 377495.6823 | 0 | 2025-06-27 | 154149.2 | Other | 0
3 | [5 empty] | 2025-05-29 |  |  |  | 3 | 3. Mounting Structures | KlipLok Structure |  |  | 19226 | PO3954-DSS-20250526 - RV Approved | Schletter - INV1800 | 2025-05-31 | 53791.5791 |  | 2025-05-29 |  | Total | 1248608.742
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Less 15% | 1061317.4307
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | R/Wp | 2.2726
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL - Cosmic Sun | Installer Price
[23 empty] | AC Equipment | 98446.4
4 | DC Equipment | DC Cable Budget | 12745.45 |  | 155162 | 2025-05-05 | 363479.3 | 413044.6591 |  | 4 | 4. DC Equipment | DC Cable | 8000 | 13.89 | 111120 | PO3933-DIP-Ph2-Siba--20250519 - RV Approved | Krannich - INV 15-10012803 | 2025-05-31 | 156288.2503 | -0.002601 | 2025-05-05 | 383972.2525 | DC Equipment | 147452.25
4 |  | DC Equipment Budget |  |  | 208317.3 | 2025-05-05 |  |  |  | 4 | 4. DC Equipment | Freight |  |  | 35100 |  | Krannich - INV 15-10012803 | 2025-05-31 | 49367.5089 |  | 2025-05-05 |  | AC Labour | 184110
4 | [5 empty] | 2025-07-29 |  |  |  | 4 | 4. DC Equipment | Additional DC Cable - VO | 6000 | 13.89 | 90300 | PO3997-DSS-20250612 - RV Approved | Krannich - INV 15-10012950 | 2025-06-30 | 36579.2422 |  | 2025-07-29 |  | DC Labour | 376240
4 | [9 empty] | 4 | 4. DC Equipment | Freight | [6 empty] | 0 |  |  |  | Offloading | 8800
4 | [5 empty] | 2025-05-15 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 147452.25 | 10% | 14745.225 | PO3888-DSS-20250513 - RV Approved | Cosmic Sun: CS_SRS_001 | 2025-05-31 | 20738.8896 |  | 2025-05-15 |  | Scaffolding | 19852.4
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 22117.84 |  | Cosmic Sun : CS_SRS_002 | 2025-05-31 | 31108.338 |  | 2025-05-29 |  | Storage | 0
4 | [5 empty] | 2025-08-21 |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 29490.45 |  | Cosmic Sun: CS_SRS_004 | 2025-06-30 | 31723.3154 |  | 2025-08-21 |  | Telehandler | 0
4 | [5 empty] | 2025-06-26 |  |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 36863.0625 |  | Cosmic Sun : CS_SRS_003 | 2025-06-30 | 39654.1442 |  | 2025-06-26 |  | HSE | 4500
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 14745.225 |  | Cosmic Sun : CS_SRS_005 | 2025-06-30 | 15861.6577 |  | 2026-02-13 |  | Other | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 14745.225 |  | Cosmic Sun : CS_SRS_006 | 2025-06-30 | 15861.6577 |  | 2026-02-20 |  | Other | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 7372.6125 |  | Cosmic Sun : CS_SRS_007 | 2025-06-30 | 7930.8288 |  | 2026-02-28 |  | Total | 839401.05
4 | [5 empty] | 2025-10-31 |  |  |  | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 7372.6125 |  | Cosmic Sun : CS_SRS_008 | 2025-06-30 | 7930.8288 |  | 2026-03-30 |  | R/Wp | 1.7974
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 34000 | 2025-07-17 | 49000 | 55681.8182 |  | 5 | 5. Monitoring | Smartlogger - MENLO |  |  | 8598.36 | PO3901-DIP-PH2-SIBA-20250514 | Menlo INV0002927 | 2025-05-31 | 12277.1044 | 0.00021546 | 2025-07-17 | 35927.14
5 |  | Revenue Metering |  |  | 15000 | 2025-05-29 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 13695 | PO3833-DIP-Ph2-Sibasa-20250429 - RV Approved | ACCUENERGY - INV ASAI-005359 | 2025-04-30 | 19114.2374 |  | 2025-05-29
[6 empty] | 2025-07-29 |  |  |  | 5 | 5. Monitoring |  |  |  | 214.28 |  | Accuenergy - Inv ASAI-005800 | 2025-06-30 | 332.1027 |  | 2025-07-29
5 | [5 empty] | 2025-06-30 |  |  |  | 5 | 5. Monitoring | Techsitter |  |  | 11169 |  | Matriarch Inv: 4451 | 2025-06-30 | 20789.4383 |  | 2025-06-30
5 | [5 empty] | 2025-05-22 |  |  |  | 5 | 5. Monitoring | UPS |  |  | 2250.5 | PO3863-DIP Ph2-20250509 - RV Approved | Frontline INV725690 | 2025-05-31 | 3168.9352 |  | 2025-05-22
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 628218.8087 | 2025-07-29 | 628218.8087 | 713885.0099 |  | 6 | 6. AC Equipment | [7 empty] | 0 | 0.002285 |  | 280470.48
6 | [5 empty] | 2025-07-29 |  |  |  | 6 | 6. AC Equipment | PVDB |  |  | 182024.08 | PO3887-DIP-Ph2-Sibasa-20250513 - RV Approved | Switchboard - Inv 2-SOI002092 | 2025-06-30 | 462275.0005 |  | 2025-07-29
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [5 empty] | 2025-05-15 |  |  |  | 6 | 6. AC Equipment | Project Kick Off | 98446.4 | 10% | 9844.64 | PO3888-DSS-20250513 - RV Approved | Cosmic Sun: CS_SRS_001 | 2025-05-31 | 25470.948 |  | 2025-05-15
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 14766.96 |  | Cosmic Sun : CS_SRS_002 | 2025-05-31 | 38206.422 |  | 2025-05-29
6 | [5 empty] | 2025-08-21 |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 19689.28 |  | Cosmic Sun: CS_SRS_004 | 2025-06-30 | 50115.3699 |  | 2025-08-21
6 | [5 empty] | 2025-06-26 |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 24611.6 |  | Cosmic Sun : CS_SRS_003 | 2025-06-30 | 62644.2124 |  | 2025-06-26
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 9844.64 |  | Cosmic Sun : CS_SRS_005 | 2025-06-30 | 25057.6849 |  | 2026-02-13
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 9844.64 |  | Cosmic Sun : CS_SRS_006 | 2025-06-30 | 25057.6849 |  | 2026-02-20
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 4922.32 |  | Cosmic Sun : CS_SRS_007 | 2025-06-30 | 12528.8425 |  | 2026-02-28
6 | [5 empty] | 2025-10-31 |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 4922.32 |  | Cosmic Sun : CS_SRS_008 | 2025-06-30 | 12528.8425 |  | 2026-03-30
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 0 | 0 |  | 8 | 8. Product Add On | [8 empty] | 0 |  | 629215
8 | [9 empty] | 8 | 8. Product Add On
8 | [5 empty] | 2025-07-31 |  |  |  | 8 | 8. Product Add On | Inverter Cage with roof |  |  | 97734 |  | The Engineering Hub INV/2025/06/0575 | 2025-06-30 |  |  | 2025-07-31
8 | [9 empty] | 8 | 8. Product Add On | E-stop |  |  | 12300 |  | Cosmic Sun - CS_SRS_010 | 2025-11-30 |  |  | 2025-12-04
8 | [5 empty] | 0 |  |  |  | 8 | 8. Product Add On | Waterpoints |  |  | 24295 | PO4341-DSS-20250929 - RV Approved | Shanduka Projects - QT2365 | 2025-09-30 |  |  | 2025-09-30
8 | [5 empty] | 0 |  |  |  | 8 | 8. Product Add On | CS - Re-establishment Cost - VO |  |  | 14690 |  | Cosmic Sun - CS_SRS_012 | 2026-01-31 |  |  | 2026-02-12
8 | [5 empty] | 0 |  |  |  | 8 | 8. Product Add On | CS - Waterproofing removing and reinstall panels - Deposit - VO | 448320 | 50% | 224160 | PO4376-DSS-20251017 - RV Approved | Cosmic Sun - CS_SRS_009 | 2025-10-31 |  |  | 2025-10-24
[10 empty] | 8 | 8. Product Add On | CS - Waterproofing removing and reinstall panels - All material on roof - VO |  | 25% | 112080 |  | Cosmic Sun -CS_SRS_011 | 2025-12-31 |  |  | 2025-12-12
[10 empty] | 8 | 8. Product Add On | CS - Waterproofing removing and reinstall panels - Snag Completion - VO |  | 25% | 112080 |  | Cosmic Sun - CS_SRS_013 | 2026-02-28 |  |  | 2026-02-12
[10 empty] | 8 | 8. Product Add On
[10 empty] | 8 | 8. Product Add On | Amendment to inverter cage (updated design) |  |  | 31876 | PO4582-DSS-20260127 - RV Approved | Engineering Hub INV/2026/01/0246 | 2026-01-31 |  |  | 2026-02-28
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 116707.5 | 2025-05-14 | 368077.5 | 433032.3529 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0 |  | 560350
9 |  | DC Installation Budget |  |  | 251370 | 2025-05-15 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 560350 | 10% | 56035 | PO3888-DSS-20250513 - RV Approved | Cosmic Sun: CS_SRS_001 | 2025-05-31 | 43303.2353 |  | 2025-05-15
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 84052.5 |  | Cosmic Sun : CS_SRS_002 | 2025-05-31 | 64954.8529 |  | 2025-05-29
9 | [5 empty] | 2025-08-21 |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 112070 |  | Cosmic Sun: CS_SRS_004 | 2025-06-30 | 86606.4706 |  | 2025-08-21
9 | [5 empty] | 2025-06-26 |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 140087.5 |  | Cosmic Sun : CS_SRS_003 | 2025-06-30 | 108258.0882 |  | 2025-06-26
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 56035 |  | Cosmic Sun : CS_SRS_005 | 2025-06-30 | 43303.2353 |  | 2026-02-13
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 56035 |  | Cosmic Sun : CS_SRS_006 | 2025-06-30 | 43303.2353 |  | 2026-02-20
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 28017.5 |  | Cosmic Sun : CS_SRS_007 | 2025-06-30 | 21651.6176 |  | 2026-02-28
9 | [5 empty] | 2025-10-31 |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 28017.5 |  | Cosmic Sun : CS_SRS_008 | 2025-06-30 | 21651.6176 |  | 2026-03-30
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-05-28 | 99195.1333 | 116700.1569 |  | 10 | 10. Site Logistics | [7 empty] | 0 | -0.0045931 |  | 86215.75
10 |  | Scaffolding |  |  | 29821.8 | 2025-05-29 |  |  |  | 10 | 10. Site Logistics | Security - May |  |  | 2825 | PO3955-DSS-20250526 - RV Approved | Bright Integrated Solutions: Inv 05/27 | 2025-05-31 | 4422.2947 |  | 2025-05-29
[6 empty] | 2025-06-12 |  |  |  | 10 | 10. Site Logistics | Security - June |  |  | 1905 | PO3975-DSS-20250602 - RV Approved | Bright Integrated Solutions: Inv 05/30 | 2025-06-30 | 2982.1138 |  | 2025-06-12
[6 empty] | 2025-06-13 |  |  |  | 10 | 10. Site Logistics | Security - November |  |  | 29000 | PO4377-DSS-20251017 - RV Approved | Bright Integrated Solutions: Inv10/25 | 2025-11-30 |  |  | 2025-11-28
[6 empty] | 2025-06-14 |  |  |  | 10 | 10. Site Logistics | Security - December - Service complete |  |  | 19333.35 |  | Bright Integrated Solutions: Inv12/25 | 2025-12-31 |  |  | 2026-01-09
[6 empty] | 2025-06-15 |  |  |  | 10 | 10. Site Logistics
[6 empty] | 2025-06-16 |  |  |  | 10 | 10. Site Logistics
10 |  | Security |  |  | 55200 | 2025-06-17 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 5673.3333 | 2025-06-18 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [5 empty] | 2025-05-15 |  |  |  | 10 | 10. Site Logistics | Project Kick Off | 33152.4 | 10% | 3315.24 | PO3888-DSS-20250513 - RV Approved | Cosmic Sun: CS_SRS_001 | 2025-05-31 | 5189.7233 |  | 2025-05-15
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Site Establishment |  | 15% | 4972.86 |  | Cosmic Sun : CS_SRS_002 | 2025-05-31 | 7784.5849 |  | 2025-05-29
10 | [5 empty] | 2025-08-21 |  |  |  | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 6630.48 |  | Cosmic Sun: CS_SRS_004 | 2025-06-30 | 10379.4466 |  | 2025-08-21
10 | [5 empty] | 2025-06-26 |  |  |  | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 8288.1 |  | Cosmic Sun : CS_SRS_003 | 2025-06-30 | 12974.3082 |  | 2025-06-26
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 3315.24 |  | Cosmic Sun : CS_SRS_005 | 2025-06-30 | 5189.7233 |  | 2026-02-13
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 3315.24 |  | Cosmic Sun : CS_SRS_006 | 2025-06-30 | 5189.7233 |  | 2026-02-20
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 1657.62 |  | Cosmic Sun : CS_SRS_007 | 2025-06-30 | 2594.8616 |  | 2026-02-28
10 | [5 empty] | 2025-10-31 |  |  |  | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 1657.62 |  | Cosmic Sun : CS_SRS_008 | 2025-06-30 | 2594.8616 |  | 2026-03-30
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | Contingency | [5 empty] | 2025-08-31 | 57398.52
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11670.75 | 2025-07-31 | 115012.25 | 135308.5294 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 12824.57 |  | Sunspot E027 | 2025-07-31 | 35947.2719 | 0.0015216 | 2025-07-31 | 36674.97
11 |  | Structural Sign Off |  |  | 23341.5 | 2025-04-10 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 9019.6 | PO3745-DIP-Ph2-20250313 - RV Approved | L&B Consulting - Invoice 1934 | 2025-04-30 | 45725.4705 |  | 2025-04-10
11 |  | Grid Study |  |  | 80000 | 2025-07-24 |  |  |  | 11 | 11. Due Dilligence | 2nd Structural Assessment |  |  | 8830.8 |  | L&B Consulting - Invoice 1986 | 2025-06-30 | 33638.6227 |  | 2025-07-24
11 | [5 empty] | 2025-07-31 |  |  |  | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 |  | Matriarch - IN-4753 | 2025-07-31 | 19997.1628 |  | 2025-07-31
11 | [5 empty] | 2025-08-01 |  |  |  | 11 | 11. Due Dilligence | [7 empty] | 0
2025-08-02
12 | BDP Commission | Referral Fee |  |  | 75353.0002 | 2025-08-03 | 90423.6002 | 0 |  | 12 | 12. BDP Commission | Referral Fee | [9 empty] | 0
12 | BDP Commission | PD Fee |  |  | 15070.6 | 2025-08-04 |  |  |  | 12 | 12. BDP Commission | PD Fee
13 | Engineering | Matriarch Defects Period |  |  | 41791.5702 | 2025-07-31 | 158920.933 | 180591.9693 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 58283.125 |  | Matriarch - INV-4752 | 2025-07-31 | 180591.9693 | 0 | 2025-07-31 | 58283.125
13 |  | Management |  |  | 26285.7143 | 2025-07-31 |  |  |  | 13 | 13. Engineering | Management |  |  | 0 |  |  | 2025-07-31 | 0 |  | 2025-07-31
13 |  | Project manager |  |  | 34000 | 2025-07-31 |  |  |  | 13 | 13. Engineering | Project manager |  |  | 0 |  |  | 2025-07-31 | 0 |  | 2025-07-31
13 |  | Planner time |  |  | 34171.4286 | 2025-07-31 |  |  |  | 13 | 13. Engineering | Planner time |  |  | 0 |  |  | 2025-07-31 | 0 |  | 2025-07-31
13 |  | De Snagging |  |  | 22672.22 | 2025-07-31 |  |  |  | 13 | 13. Engineering | De Snagging |  |  | 0 |  |  | 2025-07-31 | 0 |  | 2025-07-31
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 8050 | 2025-04-30 | 8050 | 9470.5882 |  | 14 | 14. General Expenses | Travel |  |  | 10950 |  | Site Visit | 2025-04-30 | 5699.53 | 0.0017739 | 2025-04-30 | 39135.63
14 | [5 empty] | 2025-06-06 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 7624.05 |  | Expense Claim | 2025-05-31 | 2681.3708 |  | 2025-06-06
14 | [5 empty] | 2025-07-04 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 10878.61 |  | Expense Claim | 2025-06-30 | 598.8222 |  | 2025-07-04
14 | [5 empty] | 2025-08-07 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-07-31 | 0 |  | 2025-08-07
14 | [5 empty] | 2025-09-05 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 805 |  | Expense Claim | 2025-08-31 | 490.8634 |  | 2025-09-05
14 | [5 empty] | 2025-09-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-09-30 | 0 |  | 2025-09-30
14 | [5 empty] | 2025-10-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 1247.83 |  | Expense Claim | 2025-10-31 | 0 |  | 2025-11-07
14 | [5 empty] | 2025-11-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 4630.14 |  | Expense Claim | 2025-11-30 | 0 |  | 2025-12-05
14 | [5 empty] | 2025-12-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2026-01-31 | 0 |  | 2026-02-05
14 | [5 empty] | 2026-01-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 1500 |  |  | 2026-02-28 | 0 |  | 2026-03-05
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 1500 |  |  | 2026-03-31 | 0 |  | 2026-04-09
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | Welcome Bonus |  |  | 650000 | 2025-07-11 | 650000 | 650000 |  | 15 | 15. Service Add On | Welcome Bonus - Site Establishment |  |  | 349500 |  | Lizinex - 23408/202506/274905/I | 2025-06-30 | 291623.8768 | 15368.8473 | 2025-07-11 | 699000
15 | [5 empty] | #REF! |  |  |  | 15 | 15. Service Add On | Welcome Bonus - Commissioning |  |  | 349500 |  | Lizinex - 23408/202506/274905/I | 2025-06-30 | 291623.8768 |  | 2026-02-18
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [5 empty] | 2025-08-31 |  |  |  | 15 | 15. Service Add On | Community Engagement |  |  | 0 |  |  | 2025-08-31 | 51383.3992
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [9 empty] | 2026-02-28
15 | [9 empty] | 15 | 15. Service Add On |  |  |  | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
| Panel Procurement Budget | 1020809.83 |  | 1160011.1705
| Inverter Procurement Budget | 320000 |  | 363636.3636
| Mounting Structure Budget | 379532.79 |  | 431287.2614
| DC Equipment Budget | 363479.3 |  | 413044.6591
| AC Equipment Budget | 628218.8087 |  | 713885.0099
| Monitoring Budget | 49000 |  | 55681.8182
| Optional Extras Budget | 0 |  | 0
| MV Metering Budget | 0 |  | 0
| ADD ON | 0 |  | 0
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 116707.5 |  | 137302.9412
| DC Installer Budget | 251370 |  | 295729.4118
| In-House Expense Budget | 158920.933 |  | 180591.9693
| Compliance Budget | 115012.25 |  | 135308.5294
| Offloading Budget | 8500 |  | 10000
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 5673.3333 |  | 6674.5098
| On Site Security | 55200 |  | 64941.1765
| Roof Access Budget for Installers | 29821.8 |  | 35084.4706
| EPC Management Fee | 0 |  | 0
| ADD ON | 650000 |  | 650000
Expenses
| Total EE Expense Budget | 8050 |  | 9470.5882
Note on W36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date
Note on W37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date
Note on W38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 4662650 | 4662650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1631927.5 | 932530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1865060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233132.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1631927.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4429517.5 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650
| Planned Expenditure | 4250720.1452 | 4250720.1452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23341.5 | 0 | 0 | 8050 | 363479.3 | 368077.5 | 0 | 53321.8 | 0 | 0 | 60873.3333 | 379532.79 | 0 | 650000 | 354000 | 80000 | 1894973.3219 | 15070.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23341.5 | 23341.5 | 23341.5 | 31391.5 | 394870.8 | 762948.3 | 762948.3 | 816270.1 | 816270.1 | 816270.1 | 877143.4333 | 1256676.2233 | 1256676.2233 | 1906676.2233 | 2260676.2233 | 2340676.2233 | 4235649.5452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452 | 4250720.1452
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -23341.5 | -23341.5 | -23341.5 | -31391.5 | -394870.8 | -762948.3 | -762948.3 | 815657.4 | 1748187.4 | 1748187.4 | 1687314.0667 | 1307781.2767 | 1307781.2767 | 657781.2767 | 303781.2767 | 223781.2767 | 193867.9548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 178797.3548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548 | 411929.8548
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 4662650 | 4662650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932530 | 0 | 0 | 0 | 699397.5 | 827620.8696 | 0 | 0 | 0 | 104909.1304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1865060 | 0 | 233132.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932530 | 932530 | 932530 | 932530 | 1631927.5 | 2459548.3696 | 2459548.3696 | 2459548.3696 | 2459548.3696 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 2564457.5 | 4429517.5 | 4429517.5 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650 | 4662650
| Actual + Planned Expenditure | 4172127.7475 | 4172127.7475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9019.6 | 0 | 0 | 10950 | 146220 | 83940.105 | 2250.5 | 161656.16 | 7624.05 | 1905 | 0 | 344773.4625 | 22047.61 | 349500 | 284079.76 | 8830.8 | 1376431.455 | 0 | 0 | 167880.21 | 0 | 805 | 0 | 0 | 0 | 24295 | 0 | 0 | 224160 | 0 | 1247.83 | 0 | 0 | 29000 | 16930.14 | 112080 | 0 | 0 | 0 | 19333.35 | 0 | 0 | 0 | 0 | 210710.105 | 433440.105 | 73846.0525 | 1500 | 0 | 0 | 0 | 41970.0525 | 5701.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9019.6 | 9019.6 | 9019.6 | 19969.6 | 166189.6 | 250129.705 | 252380.205 | 414036.365 | 421660.415 | 423565.415 | 423565.415 | 768338.8775 | 790386.4875 | 1139886.4875 | 1423966.2475 | 1432797.0475 | 2809228.5025 | 2809228.5025 | 2809228.5025 | 2977108.7125 | 2977108.7125 | 2977913.7125 | 2977913.7125 | 2977913.7125 | 2977913.7125 | 3002208.7125 | 3002208.7125 | 3002208.7125 | 3226368.7125 | 3226368.7125 | 3227616.5425 | 3227616.5425 | 3227616.5425 | 3256616.5425 | 3273546.6825 | 3385626.6825 | 3385626.6825 | 3385626.6825 | 3385626.6825 | 3404960.0325 | 3404960.0325 | 3404960.0325 | 3404960.0325 | 3404960.0325 | 3615670.1375 | 4049110.2425 | 4122956.295 | 4124456.295 | 4124456.295 | 4124456.295 | 4124456.295 | 4166426.3475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475 | 4172127.7475
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9019.6 | -9019.6 | -9019.6 | 912560.4 | 766340.4 | 682400.295 | 680149.795 | 1217891.135 | 2037887.9546 | 2035982.9546 | 2035982.9546 | 1691209.4921 | 1774071.0125 | 1424571.0125 | 1140491.2525 | 1131660.4525 | -244771.0025 | -244771.0025 | -244771.0025 | -412651.2125 | -412651.2125 | -413456.2125 | -413456.2125 | -413456.2125 | -413456.2125 | -437751.2125 | -437751.2125 | -437751.2125 | -661911.2125 | -661911.2125 | -663159.0425 | -663159.0425 | -663159.0425 | -692159.0425 | -709089.1825 | -821169.1825 | -821169.1825 | -821169.1825 | -821169.1825 | -840502.5325 | -840502.5325 | -840502.5325 | -840502.5325 | -840502.5325 | -1051212.6375 | 380407.2575 | 306561.205 | 538193.705 | 538193.705 | 538193.705 | 538193.705 | 496223.6525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525 | 490522.2525
|  | CHECK | CHECK
| Revenue Recognition | 15368.9665 | 4647281.0335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70539.2379 | 0 | 0 | 0 | 2419897.254 | 0 | 0 | 0 | 0 | 1811035.355 | 0 | 0 | 0 | 236536.404 | 0 | 0 | 0 | 109272.7826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 4647281.0335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70539.2379 | 70539.2379 | 70539.2379 | 70539.2379 | 2490436.4919 | 2490436.4919 | 2490436.4919 | 2490436.4919 | 2490436.4919 | 4301471.8469 | 4301471.8469 | 4301471.8469 | 4301471.8469 | 4538008.2509 | 4538008.2509 | 4538008.2509 | 4538008.2509 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335 | 4647281.0335

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | 2026-03-31 | Grand Total
(blank)
1. Panels |  |  | 1160011.1705 | [7 empty] | 0 |  | 0 |  | 1160011.1705
2. Inverters |  |  | 363636.3636 | [7 empty] | 0 |  |  |  | 363636.3636
3. Mounting Structures | 0 |  | 431287.2614 | [7 empty] | 0 |  |  |  | 431287.2614
4. DC Equipment |  |  | 257502.9868 | 155541.6749 | [6 empty] | 0 |  |  |  | 413044.6617
5. Monitoring |  | 19114.2374 | 15446.0396 | 21121.5409 | [6 empty] | 0 |  |  |  | 55681.818
6. AC Equipment |  |  | 63677.3701 | 650207.6375 | [6 empty] | 0 |  |  |  | 713885.0076
8. Product Add On
9. AC & DC installation |  |  | 108258.0882 | 324774.2647 | [6 empty] | 0 |  |  |  | 433032.3529
10. Site Logistics |  |  | 17396.603 | 41905.0385 |  | 57398.52 |  |  |  |  | 0 |  |  |  | 116700.1615
11. Due Dilligence |  | 45725.4705 |  | 33638.6227 | 55944.4347 | [5 empty] | 0 |  |  |  | 135308.5279
13. Engineering |  |  |  |  | 180591.9693 | [5 empty] | 0 |  |  |  | 180591.9693
14. General Expenses |  | 5699.53 | 2681.3708 | 598.8222 | 0 | 490.8634 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 9470.5865
15. Service Add On |  |  |  | 583247.7535 |  | 51383.3992 |  |  |  |  | 0 |  |  |  | 634631.1527
12. BDP Commission
7.BESS
Grand Total | 0 | 70539.2379 | 2419897.254 | 1811035.355 | 236536.404 | 109272.7826 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 4647281.0335
4662650
4647281.0335
4662650
-4662650

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | Grand Total
(blank)
1. Panels |  |  | 929051.4 | [8 empty] | 4201.4 |  | 933252.8
2. Inverters |  |  | 275481.4 | [10 empty] | 275481.4
3. Mounting Structures |  |  | 154149.2 | [10 empty] | 154149.2
4. DC Equipment |  |  | 183083.065 | 200889.1875 | [9 empty] | 383972.2525
5. Monitoring |  | 13695 | 10848.86 | 11383.28 | [9 empty] | 35927.14
6. AC Equipment |  |  | 24611.6 | 255858.88 | [9 empty] | 280470.48
8. Product Add On |  |  |  | 97734 |  |  | 24295 | 224160 | 12300 | 112080 | 46566 | 112080 |  | 629215
9. AC & DC installation |  |  | 140087.5 | 420262.5 | [9 empty] | 560350
10. Site Logistics |  |  | 11113.1 | 26769.3 |  |  |  |  | 29000 | 19333.35 |  |  |  | 86215.75
11. Due Dilligence |  | 9019.6 |  | 8830.8 | 18824.57 | [8 empty] | 36674.97
13. Engineering |  |  |  |  | 58283.125 | [8 empty] | 58283.125
14. General Expenses |  | 10950 | 7624.05 | 10878.61 | 0 | 805 | 0 | 1247.83 | 4630.14 |  | 0 | 1500 | 1500 | 39135.63
15. Service Add On | 0 |  |  | 699000 |  | 0 | [7 empty] | 699000
12. BDP Commission
7.BESS
Grand Total | 0 | 33664.6 | 1736050.175 | 1731606.5575 | 77107.695 | 805 | 24295 | 225407.83 | 45930.14 | 131413.35 | 46566 | 117781.4 | 1500 | 4172127.7475

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 0.59506 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.30441 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.20594 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 0.49285 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
Sibasa |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Sibasa | 0 | 0 | 0