## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate |  |  |  | FINANCIAL CLOSE CERTIFICATE
Project Name: | Riverside Mall
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Product Agreement
EPC Agreement
O&M Agreeement
Cost Proposal
Deposit Received
Risks / Notes
Acknowledgement and Acceptance:
Role | Name | Signature | Date

## Certificate - Planning
Emergent Energy – Planning Phase Completion Certificate |  |  |  | PLANNING CERTIFICATE
Project Name: | Riverside Mall
Client Representative:
Programme Manager: | Roedolph Venter
Project Manager: | Justin Franke
Project Engineer:
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Project Introduction Presentation
Project Brief
Engineering Pack
BOQ
PO – Material & Equipment
PO - Contractors
HSE – NOC
HSE – EE File
HSE – Contractor File
SSEG Application
Risks / Notes
Acknowledgement and Acceptance:
Role | Name | Signature | Date

## Change Register
Change Register
ID | Description | Supporting Image (If Applicable) | Impact | Proposed Date | Proposed By | Status | Approved By | Approved Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
DEC011
DEC012
DEC013
DEC014
DEC015
DEC016
DEC017
DEC018
DEC019
DEC020
DEC021
DEC022
DEC023
DEC024
DEC025
DEC026
DEC027
DEC028
DEC029
DEC030

## BOQ
Item | Supplier | Description | Quantity | Comments
PV Module | Menlo | Jinko 610W - JKM610N-72HL4M-BDV | 302
DC Cable Red & Black | Menlo | Enco cable | 4000
Inverters | Menlo | 1 x Huawei 100KTL, 1 x Huawei 50KTL | 2
Mounting Structure | Schletter | Kliplok Brown built Seam Clamp | 187kWp
Current Transformers (Production) | Accuenergy | 400A/5A CL 0.5 C.T. Split Core | 3
Current Transformers (Consumption) | Accuenergy
Solar Production Meter (Techistter) | Techsitter | Revenue Grade Meter | 1
Grid Consumption Meter | Accuenergy | Acurev 1313 Grid Meter | 1
Wi-Fi Router & Sim | Accuenergy | Teltonika RUT241 | 1
Switch | Accuenergy | TWS200 | 1 | Stock received from 1 Bolt (Refer to PO4360_RR_20251014_Red Rocket
Back Up Battery | Red Pole | 12v LifePo Battery | 1
PVDB | Switchboard |  | 1
UPS Battery Power Supply | Mantech/Current Automation | 12V 150W Meanwell MW-AD155-A | 1
Supplier List
Accuenergy
Krannich
Menlo
Red Pole
Schletter
Switchboard
Techsitter
Mantech/Current Automation

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC | Pending |  |  | In progress
7.1 Agreement | Pending |  |  | In progress
13.2 Agreement | Pending |  |  | In progress
EE File | Pending |  |  | In progress
Subbie File |  |  |  | No contractor appointed
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[9 empty] | 2026-02-24 | 2026-02-24
| PROJECT PLAN | Riverside Mall |  |  | Net Work Days |  | 36 |  | 0 | 1
| PROJECT SIZE (kWp) | 184 |  |  | Total Weeks |  | 7.2
| PROJECT DEVELOPER | Cole Bisset |  |  | kW/Week Installation Rate |  | 25.5556
| PROJECT MANAGERS | Justin Franke |  |  | Proposed Contractor |  | Leading Edge Power
| CONTRACT VALUE | 1862957.151
| Phase: | Construction
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration | Planned End | Actual Start | Duration | Actual End | Status | Expected Status | Comment
|  |  | 35 |  |  | 49 |  | 53.85% | 56.39% |  | 2026-02-24 | 2026-02-24
[11 empty] | 1 | 0
1 | Project Initiation | 2025-11-12 | 77 | 2026-01-28 | 2025-11-12 | 83 | 2026-02-03 | 100% | 100%
1.1 | Project Charter Handover | 2025-11-12 | 1 | 2025-11-13 | 2025-11-12 | 1 | 2025-11-13 | 100% | 100% |  | Milestone | Start Date | Duration | End Date | Progress
1.2 | HSE Readiness and Signoff | 2026-01-07 | 12 | 2026-01-26 | 2026-01-07 | 12 | 2026-01-26 | 100% | 100% |  | Project Initiation | 2025-11-12 | 83 | 2026-02-03 | 100%
1.3 | Project Introduction | 2026-01-12 | 1 | 2026-01-13 | 2026-01-12 | 1 | 2026-01-13 | 100% | 100% |  | Site Establishment | 2026-02-03 | 1 | 2026-02-04 | 100%
1.4 | Installer Kick Off | 2026-01-27 | 1 | 2026-01-28 | 2026-01-27 | 1 | 2026-01-28 | 100% | 100% |  | AC Installation | 2025-12-29 | 70 | 2026-03-09 | 74.58%
1.5 | Project Review | 2026-01-23 | 3 | 2026-01-28 | 2026-02-03 |  | 2026-02-03 | 100% | 100% |  | DC Works | 2026-02-03 | 28 | 2026-03-03 | 56.25%
[11 empty] | Module installation | 2026-02-03 | 17 | 2026-02-20 | 100%
2 | Site Establishment | 2026-01-29 | 1 | 2026-01-30 | 2026-02-03 | 1 | 2026-02-04 | 100% | 100% |  | Commissioning | 2026-03-13 | 11 | 2026-03-24 | 0%
2.1 | Solar Contractor Establishment | 2026-01-29 | 1 | 2026-01-30 | 2026-02-03 | 1 | 2026-02-04 | 100% | 100% |  | QA Inspections | 2026-03-17 | 3 | 2026-03-20 | 0%
[11 empty] | Project Closure | 2026-03-18 | 20 | 2026-04-07 | 0%
3 | AC Installation | 2025-12-29 | 52 | 2026-02-19 | 2025-12-29 | 70 | 2026-03-09 | 74.58% | 78.96%
3.1 | Inverters delivered | 2026-01-29 | 1 | 2026-01-30 | 2026-02-03 | 1 | 2026-02-04 | 100% | 100%
3.2 | Inverters Mounted | 2026-01-30 | 2 | 2026-02-03 | 2026-02-04 | 2 | 2026-02-06 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-12-29 | 25 | 2026-02-12 | 2025-12-29 | 30 | 2026-02-19 | 100% | 100%
3.4 | AC Works | 2026-02-12 | 5 | 2026-02-19 | 2026-02-17 | 14 | 2026-03-09 | 20% | 35%
3.5 | AC Tie-In | 2026-02-12 | 1 | 2026-02-13 | 2026-02-25 | 1 | 2026-02-26 | 0% | 0% | Confirmed
4 | DC Works | 2026-01-29 | 26 | 2026-02-24 | 2026-02-03 | 28 | 2026-03-03 | 56.25% | 72.16%
4.1 | Mounting Structure delivered | 2026-01-29 | 1 | 2026-01-30 | 2026-02-03 | 1 | 2026-02-04 | 100% | 100%
4.2 | Mounting Structure installation | 2026-01-30 | 3 | 2026-02-04 | 2026-02-04 | 7 | 2026-02-13 | 100% | 100%
4.3 | DC Cable delivered | 2026-01-29 | 1 | 2026-01-30 | 2026-02-04 | 1 | 2026-02-05 | 100% | 100%
4.4 | DC Stringing | 2026-02-14 | 7 | 2026-02-24 | 2026-02-20 | 7 | 2026-03-03 | 0% | 36.36%
5 | Module installation | 2026-01-29 | 19 | 2026-02-17 | 2026-02-03 | 17 | 2026-02-20 | 100% | 100%
5.1 | Module delivery | 2026-01-29 | 1 | 2026-01-30 | 2026-02-03 | 1 | 2026-02-04 | 100% | 100%
5.2 | Module mounting | 2026-02-04 | 9 | 2026-02-17 | 2026-02-16 | 4 | 2026-02-20 | 100% | 100%
6 | Commissioning | 2026-02-24 | 9 | 2026-03-05 | 2026-03-13 | 11 | 2026-03-24 | 0% | 0%
6.1 | Commissioning | 2026-02-24 | 1 | 2026-02-25 | 2026-03-13 | 1 | 2026-03-16 | 0% | 0%
6.2 | Practical Completion | 2026-02-25 | 1 | 2026-02-26 | 2026-03-16 | 1 | 2026-03-17 | 0% | 0%
6.3 | System Performance Monitoring | 2026-02-26 | 5 | 2026-03-05 | 2026-03-17 | 5 | 2026-03-24 | 0% | 0%
7 | QA Inspections | 2026-02-26 | 14 | 2026-03-12 | 2026-03-17 | 3 | 2026-03-20 | 0% | 0%
7.1 | Red-Team Inspection | 2026-02-26 | 3 | 2026-03-03 | 2026-03-17 | 1 | 2026-03-18 | 0% | 0%
7.2 | Snags completion | 2026-03-03 | 7 | 2026-03-12 | 2026-03-18 | 2 | 2026-03-20 | 0% | 0%
8 | Project Closure | 2026-03-03 | 16 | 2026-03-19 | 2026-03-18 | 20 | 2026-04-07 | 0% | 0%
8.1 | Handover documentation | 2026-03-03 | 7 | 2026-03-12 | 2026-03-18 | 7 | 2026-03-27 | 0% | 0%
8.2 | Handover to Client | 2026-03-12 | 1 | 2026-03-13 | 2026-03-27 | 1 | 2026-03-30 | 0% | 0%
8.3 | Handover to Matriarch | 2026-03-12 | 5 | 2026-03-19 | 2026-03-27 | 5 | 2026-04-07 | 0% | 0%
Formulas:
Justin Franke = MIN([Justin Franke, row below]:E17)
Justin Franke = WORKDAY.INTL([Planned End, row above],0,1,Data!$C3:C60)+14
Planned End = MAX([Planned End, row below]:G17)
Planned End = WORKDAY.INTL([Justin Franke],[Duration],1,Data!$C3:C60)
Proposed Contractor = MIN([Proposed Contractor, row below]:I17)
Proposed Contractor = WORKDAY.INTL([Leading Edge Power, row above],0,1,Data!$C3:C60)+14
Leading Edge Power = MAX([Leading Edge Power, row below]:K17)
Leading Edge Power = WORKDAY.INTL([Proposed Contractor],[Duration],1,Data!$C3:C60)
Expected Status = LET( _xlpm.s,VALUE([Proposed Contractor]), _xlpm.e,VALUE([Leading Edge Power]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW
1 | Planned Revenue | 1862957.151 |  | 1862957.151 | VO PM LIMIT | CURRENT VO Total |  | Start Date |  |  | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
2 | Planned Expenditure | 1520558.8732 |  | 1301173.9944 | 17119.9139 | 0 |  |  |  |  | 1973058.1214 | 1301173.9944 | 1404767.085 | 921330.228
3 | Planned Profit | 342398.2777 |  | 561783.1566 |  |  |  | End Date - PC
4 | Planned Margin | 18.38% |  | 30.16%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Acceptance and Initial Deposit |  | 25% | 465739.2877 |  | 2025-11-14 | 004879 | 2025-11-13 | 2025-11-14 | [5 empty] | 1900-01-06
2 | Delivery of Panels |  | 50% | 931478.5755 |  | 2026-02-05 | 004936 | 2026-02-05 | 2026-02-06
3 | Delivery of Inverters |  | 10% | 186295.7151 |  | 2026-02-05 | 004936 | 2026-02-05 | 2026-02-06
4 | Practical Completion |  | 10% | 186295.7151 |  | 2026-03-12 |  |  | 2026-03-31
5 | Handover |  | 5% | 93147.8575 |  | 2026-03-19 |  |  | 2026-04-03
6 | - |  | 0% | 0
7 | - |  | 0% | 0
|  |  | 100% | 1862957.151
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 652035.0028
2 | Delivery of Panels |  | 30% | 558887.1453
3 | Delivery of Inverters |  | 20% | 372591.4302
4 | Practical Completion |  | 10% | 186295.7151
5 | Handover |  | 5% | 93147.8575
| Total |  | 100% | 1862957.151
|  |  | 100% | 1862957.151
Note on R14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Thami Cambalele please invoice these for us

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from Costed
EXPENDITURE |  | 1520558.8732 |  | 1301173.9944 | 219384.8788
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 408885.35 |  | 368440 | 40445.35
2 | 2. Inverters | 113600 |  | 112476.43 | 1123.57
3 | 3. Mounting Structures | 84258 |  | 51620.6 | 32637.4
4 | 4. DC Equipment | 155045.7 |  | 155527.8 | -482.1
5 | 5. Monitoring | 34000 |  | 37782.84 | -3782.84
6 | 6. AC Equipment | 249598.8174 |  | 157338.18 | 92260.6374
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 187500 |  | 79978.17 | 107521.83
9 | 9. AC & DC installation | 147225 |  | 194250.01 | -47025.01
10 | 10. Site Logistics | 34366.2667 |  | 44166.2 | -9799.9333
11 | 11. Due Dilligence | 89000 |  | 75572.5 | 13427.5
12 | 12. BDP Commission | 0 |  | 0 | 0
13 | 13. Engineering | 16449.7392 |  | 23286.9644 | -6837.2252
14 | 14. General Expenses | 630 |  | 734.3 | -104.3
15 | 15. Service Add On | 0 |  | 0 | 0
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 1520558.8732 | 1862957.151 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 1301173.9944
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FORECASTED PAYMENT DATE | Total COS | ERROR on REV |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 408885.35 | 2026-03-30 | 408885.35 | 511106.6875 |  | 1 | 1. Panels | Jinko Tiger Neo N-type66HL4M-BDV - 610W | 302 | 1220 | 368440 |  | MSA Energy - INV0003559 | 2026-01-31 | 511106.6875 | 0 | 2026-03-28 | 368440
1 |  | Delivery Budget | [7 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 249598.8174
2 | Inverters | Inverter Budget |  |  | 113600 | 2026-03-30 | 113600 | 143797.4684 |  | 2 | 2. Inverters | Huawei 100KTL - Menlo | 1 | 68870.35 | 68870.35 |  | MSA Energy - INV0003559 | 2026-01-31 | 88048.5091 | 0 | 2026-03-28 | 112476.43 | DC Equipment | 100795.7
2 | [9 empty] | 2 | 2. Inverters | Huawei 50KTL | 1 | 43606.08 | 43606.08 |  | MSA Energy - INV0003559 | 2026-01-31 | 55748.9592 |  | 2026-03-28 |  | AC Labour | 46810
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 100415
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 11466.2667
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 0
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 84258 | 2026-02-28 | 84258 | 105322.5 |  | 3 | 3. Mounting Structures | Schletter Structure |  |  | 51620.6 | PO4563-RSM-20260121 - RV Approved | Schletter - INV002599 | 2026-01-31 | 105322.5 | 0 | 2026-03-02 | 51620.6 | Other | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Total | 517585.7841
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Less 15% | 439947.9164
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | R/Wp | 2.391
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL | Installer Price LEP
[23 empty] | AC Equipment | 68823.16
4 | DC Equipment | DC Cable Budget | 3875 |  | 54250 | 2026-03-30 | 155045.7 | 193807.125 |  | 4 | 4. DC Equipment | DC Cable - Menlo | 4000 | 13.99 | 55960 |  | MSA Energy - INV0003559 | 2026-01-31 | 69733.1713 | 0 | 2026-03-28 | 155527.8 | DC Equipment | 99567.8
4 |  | DC Equipment Budget |  |  | 100795.7 | 2026-02-24 |  |  |  | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | AC Labour | 61665.63
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | DC Labour | 132584.38
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Offloading | 12000
4 | [9 empty] | 4 | 4. DC Equipment | Project Kick Off | 99567.8 | 20% | 19913.56 |  | Leading Edge Power INV-0182 | 2026-01-31 | 24814.7907 |  | 2026-01-29 |  | Forklift | 0
4 | [9 empty] | 4 | 4. DC Equipment | Site Establishment |  | 20% | 19913.56 |  | Leading Edge Power INV-0183 | 2026-01-31 | 24814.7907 |  | 2026-02-05 |  | Geda | 6198.5
4 | [9 empty] | 4 | 4. DC Equipment | AC Installation Complete |  | 15% | 14935.17 |  |  | 2026-02-28 | 18611.0931 |  | 2026-03-16 |  | Logistics | 14717.7
4 | [9 empty] | 4 | 4. DC Equipment | DC Installation Complete |  | 15% | 14935.17 |  |  | 2026-02-28 | 18611.0931 |  | 2026-03-10 |  | COC | 4500
4 | [9 empty] | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 9956.78 |  |  | 2026-03-31 | 12407.3954 |  | 2026-03-31 |  | HSE | 6750
4 | [9 empty] | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 9956.78 |  |  | 2026-03-31 | 12407.3954 |  | 2026-03-27 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 4978.39 |  |  | 2026-03-31 | 6203.6977 |  | 2026-03-27 |  | Total | 406807.17
4 | [9 empty] | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 4978.39 |  |  | 2026-03-31 | 6203.6977 |  | 2026-04-19 |  | R/Wp | 2.2109
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 19000 | 2026-03-30 | 34000 | 42500 |  | 5 | 5. Monitoring | Smartlogger |  |  | 8598.34 |  | MSA Energy - INV0003570 | 2026-01-31 | 9671.8365 | 0 | 2026-03-30 | 37782.84
5 |  | Revenue Metering |  |  | 15000 | 2026-03-30 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 12417 | PO4577-RSM-20260126 - RV Approved | Accuenergy Inv: ASAI-007302 | 2026-01-31 | 13967.2534 |  | 2026-02-27
[10 empty] | 5 | 5. Monitoring | 8 Port Switch |  |  | 1767.5 |  | Allocated from Red Rocket | 2026-01-31 | 1988.1711 |  | 2026-01-31
5 | [9 empty] | 5 | 5. Monitoring | Techsitter |  |  | 15000 |  |  | 2026-02-28 | 16872.7391 |  | 2026-03-30
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 249598.8174 | 2026-03-14 | 249598.8174 | 311998.5217 |  | 6 | 6. AC Equipment | [7 empty] | 0 | -2802.5686 |  | 157338.18
6 | [9 empty] | 6 | 6. AC Equipment | PVDB |  |  | 88515.02 |  | Switchboard Inv: 2-SOI002863 | 2026-02-28 | 175523.5467 |  | 2026-03-30
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | Project Kick Off | 68823.16 | 20% | 13764.632 |  | Leading Edge Power INV-0182 | 2026-01-31 | 28696.2793 |  | 2026-01-29
6 | [9 empty] | 6 | 6. AC Equipment | Site Establishment |  | 20% | 13764.632 |  | Leading Edge Power INV-0183 | 2026-01-31 | 28696.2793 |  | 2026-02-05
6 | [9 empty] | 6 | 6. AC Equipment | AC Installation Complete |  | 15% | 10323.474 |  |  | 2026-02-28 | 20471.2462 |  | 2026-03-16
6 | [9 empty] | 6 | 6. AC Equipment | DC Installation Complete |  | 15% | 10323.474 |  |  | 2026-02-28 | 20471.2462 |  | 2026-03-10
6 | [9 empty] | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 6882.316 |  |  | 2026-03-31 | 13647.4975 |  | 2026-03-31
6 | [9 empty] | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 6882.316 |  |  | 2026-03-31 | 13647.4975 |  | 2026-03-27
6 | [9 empty] | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 3441.158 |  |  | 2026-03-31 | 6823.7487 |  | 2026-03-27
6 | [9 empty] | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 3441.158 |  |  | 2026-03-31 | 6823.7487 |  | 2026-04-19
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | Inverter Room Prep |  |  | 100000 | 2026-02-26 | 187500 | 234375 |  | 8 | 8. Product Add On | [7 empty] | 0 | -107298.4 |  | 79978.17
8 |  | Permanent Anchor Points |  |  | 87500 | 2026-02-26 |  |  |  | 8 | 8. Product Add On | Inverter Room Prep |  |  | 80000 |  |  | 2026-03-31 | 234438.9725 |  | 2026-03-31
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | Anchor Points - Deposit (move deposit payment to 7th Avenue | 67474.56 | 50% | -33737.28 | PO4565-RSM-20260121 - RV Approved | Hisafe - 00360 | 2026-01-31 | 53617.2137 |  | 2026-01-29
8 | [9 empty] | 8 | 8. Product Add On | Anchor Points - Ascend Deposit |  |  | 33715.45 |  | Ascend Inv-4989 | 2026-02-28 | 53617.2137 |  | 2026-02-13
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
[10 empty] | 8 | 8. Product Add On
[10 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 46810 | 2026-02-26 | 147225 | 163583.3333 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0 |  | 194250.01
9 |  | DC Installation Budget |  |  | 100415 | 2026-03-03 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 194250.01 | 20% | 38850.002 |  | Leading Edge Power INV-0182 | 2026-01-31 | 32716.6667 |  | 2026-01-29
9 | [9 empty] | 9 | 9. AC & DC installation | Site Establishment |  | 20% | 38850.002 |  | Leading Edge Power INV-0183 | 2026-01-31 | 32716.6667 |  | 2026-02-05
9 | [9 empty] | 9 | 9. AC & DC installation | AC Installation Complete |  | 15% | 29137.5015 |  |  | 2026-02-28 | 24537.5 |  | 2026-03-16
9 | [9 empty] | 9 | 9. AC & DC installation | DC Installation Complete |  | 15% | 29137.5015 |  |  | 2026-02-28 | 24537.5 |  | 2026-03-10
9 | [9 empty] | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 19425.001 |  |  | 2026-03-31 | 16358.3333 |  | 2026-03-31
9 | [9 empty] | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 19425.001 |  |  | 2026-03-31 | 16358.3333 |  | 2026-03-27
9 | [9 empty] | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 9712.5005 |  |  | 2026-03-31 | 8179.1667 |  | 2026-03-27
9 | [9 empty] | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 9712.5005 |  |  | 2026-04-30 | 8179.1667 |  | 2026-04-19
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2026-02-26 | 34366.2667 | 38184.7407 |  | 10 | 10. Site Logistics | [7 empty] | 0 | 0 |  | 44166.2
10 |  | Scaffolding |  |  | 11466.2667 | 2026-02-26 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Security |  |  | 14400 | 2026-02-26 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 0 | 2026-02-26 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | Project Kick Off | 44166.2 | 20% | 8833.24 |  | Leading Edge Power INV-0182 | 2026-01-31 | 7636.9481 |  | 2026-01-29
10 | [9 empty] | 10 | 10. Site Logistics | Site Establishment |  | 20% | 8833.24 |  | Leading Edge Power INV-0183 | 2026-01-31 | 7636.9481 |  | 2026-02-05
10 | [9 empty] | 10 | 10. Site Logistics | AC Installation Complete |  | 15% | 6624.93 |  |  | 2026-02-28 | 5727.7111 |  | 2026-03-16
10 | [9 empty] | 10 | 10. Site Logistics | DC Installation Complete |  | 15% | 6624.93 |  |  | 2026-02-28 | 5727.7111 |  | 2026-03-10
10 | [9 empty] | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 4416.62 |  |  | 2026-03-31 | 3818.4741 |  | 2026-03-31
10 | [9 empty] | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 4416.62 |  |  | 2026-03-31 | 3818.4741 |  | 2026-03-27
10 | [9 empty] | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 2208.31 |  |  | 2026-03-31 | 1909.237 |  | 2026-03-27
10 | [9 empty] | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 2208.31 |  |  | 2026-04-30 | 1909.237 |  | 2026-04-19
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2026-03-05 | 89000 | 98888.8889 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 11000 |  |  | 2026-03-31 | 12594.6283 | -0.001858 | 2026-04-07 | 75572.5
11 |  | Structural sign off |  |  | 18000 | 2026-03-05 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 8572.5 |  | L&B Invoice: | 2025-11-30 | 10023.6483 |  | 2025-11-13
11 |  | Scada for CoCT |  |  | 60000 | 2026-03-05 |  |  |  | 11 | 11. Due Dilligence | Scada for CoCT |  |  | 50000 | PO4608-RSM020260204 - RV Approved | Rubicon - INVRED-0139197 | 2026-02-28 | 68419.4336 |  | 2026-03-30
11 | [9 empty] | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 |  |  | 2026-03-31 | 7851.1804 |  | 2026-03-31
11 | [9 empty] | 11 | 11. Due Dilligence | [7 empty] | 0
12 | BDP Commission | PD Fee |  |  | 0 |  | 0 | 0 |  | 12 | 12. BDP Commission | PD Fee |  |  | 0 | [6 empty] | 0
12 | BDP Commission | [8 empty] | 12 | 12. BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 16449.7392 | 2026-03-19 | 16449.7392 | 18692.8854 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 23286.9644 |  |  | 2026-03-31 | 18692.8854 | 0 | 2026-03-24 | 23286.9644
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 630 | 2026-03-19 | 630 | 700 |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-12-31 | 0 | 0 | 2026-01-07 | 734.3
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 261.8 |  | Expense Claim | 2026-01-31 | 249.571 |  | 2026-02-05
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 157.5 |  |  | 2026-02-28 | 150.143 |  | 2026-03-07
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 157.5 |  |  | 2026-03-31 | 150.143 |  | 2026-04-07
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 157.5 |  |  | 2026-04-30 | 150.143 |  | 2026-05-07
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | [8 empty] | 0 |  | 0
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
| Panel Procurement Budget | 408885.35 |  | 511106.6875
| Inverter Procurement Budget | 113600 |  | 143797.4684
| Mounting Structure Budget | 84258 |  | 105322.5
| DC Equipment Budget | 155045.7 |  | 193807.125
| AC Equipment Budget | 249598.8174 |  | 311998.5217
| Monitoring Budget | 34000 |  | 42500
| Optional Extras Budget | 0 |  | 0
| MV Equipment Budget | 0 |  | 0
| ADD ON | 187500 |  | 234375
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 46810 |  | 52011.1111
| DC Installer Budget | 100415 |  | 111572.2222
| In-House Expense Budget | 16449.7392 |  | 18692.8854
| Compliance Budget | 89000 |  | 98888.8889
| Offloading Budget | 8500 |  | 9444.4444
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 0 |  | 0
| On Site Security | 14400 |  | 16000
| Roof Access Budget for Installers | 11466.2667 |  | 12740.2963
| EPC Management Fee | 0 |  | 0
| ADD ON | 0 |  | 0
Expenses
| Total EE Expense Budget | 630 |  | 700

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-11-10 to 2031-05-05
PLANNED |  | CHECK | CHECK
| Planned Revenue | 1862957.151 | 1862957.151 | 465739.2877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1117774.2906 | 0 | 0 | 0 | 0 | 186295.7151 | 93147.8575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 1583513.5783 | 1583513.5783 | 1583513.5783 | 1583513.5783 | 1583513.5783 | 1769809.2934 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151
| Planned Expenditure | 1520558.8732 | 1520558.8732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 453729.9667 | 189415 | 249598.8174 | 17079.7392 | 0 | 610735.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 453729.9667 | 643144.9667 | 892743.7841 | 909823.5232 | 909823.5232 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732 | 1520558.8732
| PLANNED CashFlow |  |  | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 1583513.5783 | 1583513.5783 | 1583513.5783 | 1129783.6117 | 940368.6117 | 877065.5094 | 953133.6277 | 953133.6277 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777 | 342398.2777
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 1862957.151 | 1862957.151 | 465739.2877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1117774.2906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279443.5726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 465739.2877 | 1583513.5783 | 1583513.5783 | 1583513.5783 | 1583513.5783 | 1583513.5783 | 1583513.5783 | 1583513.5783 | 1583513.5783 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151 | 1862957.151
| Actual + Planned Expenditure | 1301173.9944 | 1301173.9944 | 8572.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49391.654 | 81623.234 | 33715.45 | 0 | 12417 | 51778.1 | 61021.0755 | 61021.0755 | 621184.4699 | 288794.077 | 11157.5 | 20340.3585 | 0 | 0 | 157.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 8572.5 | 8572.5 | 8572.5 | 8572.5 | 8572.5 | 8572.5 | 8572.5 | 8572.5 | 8572.5 | 8572.5 | 8572.5 | 57964.154 | 139587.388 | 173302.838 | 173302.838 | 185719.838 | 237497.938 | 298519.0135 | 359540.089 | 980724.5589 | 1269518.6359 | 1280676.1359 | 1301016.4944 | 1301016.4944 | 1301016.4944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944 | 1301173.9944
| ACTUAL CashFlow |  |  | 457166.7877 | 457166.7877 | 457166.7877 | 457166.7877 | 457166.7877 | 457166.7877 | 457166.7877 | 457166.7877 | 457166.7877 | 457166.7877 | 457166.7877 | 407775.1337 | 1443926.1903 | 1410210.7403 | 1410210.7403 | 1397793.7403 | 1346015.6403 | 1284994.5648 | 1223973.4893 | 602789.0194 | 593438.5151 | 582281.0151 | 561940.6566 | 561940.6566 | 561940.6566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566 | 561783.1566
|  | CHECK | CHECK
| Revenue Recognition | -110100.9704 | 1973058.1214 | 0 | 0 | 10023.6483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1097183.2425 | 0 | 0 | 0 | 453278.177 | 0 | 0 | 0 | 0 | 402334.5069 | 0 | 0 | 0 | 10238.5467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 1973058.1214 | 0 | 0 | 10023.6483 | 10023.6483 | 10023.6483 | 10023.6483 | 10023.6483 | 10023.6483 | 10023.6483 | 10023.6483 | 10023.6483 | 1107206.8909 | 1107206.8909 | 1107206.8909 | 1107206.8909 | 1560485.0678 | 1560485.0678 | 1560485.0678 | 1560485.0678 | 1560485.0678 | 1962819.5747 | 1962819.5747 | 1962819.5747 | 1962819.5747 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214 | 1973058.1214

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-03-30 | Grand Total
(blank)
1. Panels | 0 |  |  | 0 | 511106.6875 |  |  |  |  | 511106.6875
2. Inverters |  |  |  | 0 | 143797.4684 |  |  |  |  | 143797.4684
3. Mounting Structures |  |  |  | 0 | 105322.5 |  |  |  |  | 105322.5
4. DC Equipment |  |  |  | 0 | 119362.7528 |  | 68240.6746 | 6203.6977 |  | 193807.125
5. Monitoring |  |  |  | 0 | 25627.2609 | 16872.7391 |  |  |  | 42500
6. AC Equipment |  |  |  | 0 | 57392.5586 |  | 78914.7681 | 7174.0698 | 168517.1252 | 311998.5217
8. Product Add On | 0 |  |  | 0 | 107234.4274 | 127140.5726 |  |  |  | 234375
9. AC & DC installation |  |  |  | 0 | 65433.3333 |  | 89970.8333 | 8179.1667 |  | 163583.3333
10. Site Logistics |  |  |  | 0 | 15273.8963 |  | 21001.6074 | 1909.237 |  | 38184.7407
11. Due Dilligence |  | 10023.6483 |  | 0 |  | 68419.4336 | 20445.8088 |  |  | 98888.8907
13. Engineering |  |  |  | 0 |  |  | 18692.8854 |  |  | 18692.8854
14. General Expenses |  |  | 0 | 0 | 249.571 | 150.143 | 150.143 | 150.143 |  | 700
15. Service Add On
12. BDP Commission
7.BESS
Grand Total | 0 | 10023.6483 | 0 | 0 | 1150800.4562 | 212582.8882 | 297416.7206 | 23616.3142 | 168517.1252 | 1862957.1528

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-03-30 | Grand Total
(blank)
1. Panels |  |  |  |  | 368440 |  |  |  |  | 368440
2. Inverters |  |  |  |  | 112476.43 |  |  |  |  | 112476.43
3. Mounting Structures |  |  |  |  | 51620.6 |  |  |  |  | 51620.6
4. DC Equipment |  |  |  |  | 95787.12 |  | 54762.29 | 4978.39 |  | 155527.8
5. Monitoring |  |  |  |  | 22782.84 | 15000 |  |  |  | 37782.84
6. AC Equipment |  |  |  |  | 27529.264 |  | 37852.738 | 3441.158 | 80831.95 | 149655.11
8. Product Add On |  |  |  |  | 67474.56 | 80000 |  |  |  | 147474.56
9. AC & DC installation |  |  |  |  | 77700.004 |  | 106837.5055 | 9712.5005 |  | 194250.01
10. Site Logistics |  |  |  |  | 17666.48 |  | 24291.41 | 2208.31 |  | 44166.2
11. Due Dilligence |  | 8572.5 |  |  |  | 50000 | 17000 |  |  | 75572.5
13. Engineering | [6 empty] | 23286.9644 |  |  | 23286.9644
14. General Expenses |  |  | 0 |  | 261.8 | 157.5 | 157.5 | 157.5 |  | 734.3
15. Service Add On
12. BDP Commission |  |  |  | 0 | [5 empty] | 0
7.BESS
Grand Total |  | 8572.5 | 0 | 0 | 841739.098 | 145157.5 | 264188.4079 | 20497.8585 | 80831.95 | 1360987.3144

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill
2025-12-15 | Builders Break
2025-12-16 | Builders Break
2025-12-17 | Builders Break
2025-12-18 | Builders Break
2025-12-19 | Builders Break
2025-12-20 | Builders Break
2025-12-21 | Builders Break
2025-12-22 | Builders Break
2025-12-23 | Builders Break
2025-12-24 | Builders Break
2025-12-25 | Builders Break
2025-12-26 | Builders Break
2025-12-27 | Builders Break
2025-12-28 | Builders Break
2025-12-29 | Builders Break
2025-12-30 | Builders Break
2025-12-31 | Builders Break
2026-01-01 | Builders Break
2026-01-02 | Builders Break
2026-01-03 | Builders Break
2026-01-04 | Builders Break
2026-01-05 | Builders Break
2026-01-06 | Builders Break
2026-01-07 | Builders Break
2026-01-08 | Builders Break
Builders Break
Builders Break
Builders Break
Builders Break
Builders Break
Builders Break
Builders Break
Builders Break
2026-03-21 | Human Rights day
2026-04-03 | Good Friday
2026-04-06 | Family Day
2026-04-27 | Freedom Day
2026-05-01 | Workers day
2026-06-16 | Youth Day Holiday
2026-08-09 | Womens Day
2026-08-10 | Womens Day Observerd
2026-09-24 | Heritage Day
2026-12-16 | Day of Reconciliation
2026-12-25 | Christmas Day
2026-12-26 | Day of Goodwill