## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[10 empty] | 2026-03-06 | 2026-03-06
| PROJECT PLAN | [8 empty] | 0 | 1
PROJECT SIZE (kWp)
PROJECT DEVELOPER
PROJECT MANAGERS
CONTRACT VALUE
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Expected Status |  | Comment
1 | Project Activities - Magic Co | 2026-01-15 | 5 | 2026-01-20 | 2026-01-15 | 5 | 2026-01-20 |  |  | 0
1.1 | Installation | 2026-01-15 | 1 | 2026-01-16 | 2026-01-15 | 1 | 2026-01-16 | 100% | 100%
1.2 | Commission | 2026-01-16 | 2 | 2026-01-20 | 2026-01-16 | 2 | 2026-01-20 | 100% | 100%
1 | Project Activities - Dipula - Blackheath | 2026-03-06 | 5 | 2026-03-11 | 2026-03-06 | 5 | 2026-03-11
1.1 | Relocation of Inverters | 2026-03-06 | 1 | 2026-03-09 | 2026-03-06 | 1 | 2026-03-09 | 0% | 0%
1.2 | Recommission | 2026-03-09 | 2 | 2026-03-11 | 2026-03-09 | 2 | 2026-03-11 | 0% | 0%
1 | Project Activities - Busamed Harrismith | 2026-01-15 | 14 | 2026-01-29 | 2026-01-15 | 14 | 2026-01-29
1.1 | Execution | 2026-01-15 | 10 | 2026-01-29 | 2026-01-15 | 10 | 2026-01-29 | 100% | 100%
1 | Project Activities - Dipula - Kopanong Kudube | 2026-03-06 | 5 | 2026-03-11 | 2026-03-06 | 5 | 2026-03-11
1.1 | Execution | 2026-03-06 | 1 | 2026-03-09 | 2026-03-06 | 1 | 2026-03-09 | 0% | 0%
1.2 | Validation | 2026-03-09 | 2 | 2026-03-11 | 2026-03-09 | 2 | 2026-03-11 | 0% | 0%
1 | Project Activities - Dipula - Sam Sekhoti | 2026-03-06 | 5 | 2026-03-11 | 2026-03-06 | 5 | 2026-03-11
1.1 | Execution | 2026-03-06 | 1 | 2026-03-09 | 2026-03-06 | 1 | 2026-03-09 | 0% | 0%
1.2 | Validation | 2026-03-09 | 2 | 2026-03-11 | 2026-03-09 | 2 | 2026-03-11 | 0% | 0%
1 | Project Activities - Project Name 6 | 2026-03-06 | 5 | 2026-03-11 | 2026-03-06 | 5 | 2026-03-11
1.1 | PrEng Sign off | 2026-03-06 | 1 | 2026-03-09 | 2026-03-06 | 1 | 2026-03-09 | 0% | 0%
1.2 | Handover Documentation | 2026-03-09 | 2 | 2026-03-11 | 2026-03-09 | 2 | 2026-03-11 | 0% | 0%
1.3 | O&M Handover | 2026-03-06 | 1 | 2026-03-09 | 2026-03-06 | 1 | 2026-03-09 | 0% | 0%
1.4 | Client Handover | 2026-03-09 | 1 | 2026-03-10 | 2026-03-09 | 1 | 2026-03-10 | 0% | 0%
1 | Project Activities - Project Name 7 | 2026-03-06 | 5 | 2026-03-11 | 2026-03-06 | 5 | 2026-03-11
1.1 | PrEng Sign off | 2026-03-06 | 1 | 2026-03-09 | 2026-03-06 | 1 | 2026-03-09 | 0% | 0%
1.2 | Handover Documentation | 2026-03-09 | 2 | 2026-03-11 | 2026-03-09 | 2 | 2026-03-11 | 0% | 0%
1.3 | O&M Handover | 2026-03-06 | 1 | 2026-03-09 | 2026-03-06 | 1 | 2026-03-09 | 0% | 0%
1.4 | Client Handover | 2026-03-09 | 1 | 2026-03-10 | 2026-03-09 | 1 | 2026-03-10 | 0% | 0%
1 | Project Activities - Project Name 8 | 2026-03-06 | 5 | 2026-03-11 | 2026-03-06 | 5 | 2026-03-11
1.1 | PrEng Sign off | 2026-03-06 | 1 | 2026-03-09 | 2026-03-06 | 1 | 2026-03-09 | 0% | 0%
1.2 | Handover Documentation | 2026-03-09 | 2 | 2026-03-11 | 2026-03-09 | 2 | 2026-03-11 | 0% | 0%
1.3 | O&M Handover | 2026-03-06 | 1 | 2026-03-09 | 2026-03-06 | 1 | 2026-03-09 | 0% | 0%
1.4 | Client Handover | 2026-03-09 | 1 | 2026-03-10 | 2026-03-09 | 1 | 2026-03-10 | 0% | 0%
1 | Project Activities - Project Name 9 | 2026-03-06 | 5 | 2026-03-11 | 2026-03-06 | 5 | 2026-03-11
1.1 | PrEng Sign off | 2026-03-06 | 1 | 2026-03-09 | 2026-03-06 | 1 | 2026-03-09 | 0% | 0%
1.2 | Handover Documentation | 2026-03-09 | 2 | 2026-03-11 | 2026-03-09 | 2 | 2026-03-11 | 0% | 0%
1.3 | O&M Handover | 2026-03-06 | 1 | 2026-03-09 | 2026-03-06 | 1 | 2026-03-09 | 0% | 0%
1.4 | Client Handover | 2026-03-09 | 1 | 2026-03-10 | 2026-03-09 | 1 | 2026-03-10 | 0% | 0%
1 | Project Activities - Project Name 10 | 2026-03-06 | 5 | 2026-03-11 | 2026-03-06 | 5 | 2026-03-11
1.1 | PrEng Sign off | 2026-03-06 | 1 | 2026-03-09 | 2026-03-06 | 1 | 2026-03-09 | 0% | 0%
1.2 | Handover Documentation | 2026-03-09 | 2 | 2026-03-11 | 2026-03-09 | 2 | 2026-03-11 | 0% | 0%
1.3 | O&M Handover | 2026-03-06 | 1 | 2026-03-09 | 2026-03-06 | 1 | 2026-03-09 | 0% | 0%
1.4 | Client Handover | 2026-03-09 | 1 | 2026-03-10 | 2026-03-09 | 1 | 2026-03-10 | 0% | 0%
Formulas:
Planned Start = MIN([Planned Start, row below]:E13)
Planned Start = WORKDAY.INTL([Planned End, row above],0,1,Data!$C3:C14)
Planned End = MAX([Planned End, row below]:G13)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I13)
Actual Start = WORKDAY.INTL([Actual End, row above],0,1,Data!$C3:C14)
Actual End = MAX([Actual End, row below]:K13)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C14)
Expected Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  | FINANCIAL REVIEW | TIMELINE REVIEW
1 | Revenue | 12510 |  | 12510 |  |  | Start Date
2 | Expenditure | 10008 |  | 155792
3 | Profit | 2502 |  | -143282 |  |  | End Date - PC
4 | Margin | 20% |  | -1145%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Magic Company - Deposit |  |  | 6255 | 2025-12-31 | 004909 | 2025-12-12 | 2025-12-15
2 | Magic Company - Balance |  |  | 6255 | 2026-01-31 | 004912 | 2026-01-12 | 2026-01-23
1 | Dipula Blackheath - No Revenue |  |  | 0
1 | Busamed Harrismith - No Revenue |  |  | 0
1 | Dipula - Kopnaong Kudube |  |  | 0
1 | Dipula - Sam Sekhoti |  |  | 0
1 | Project Name 6 - Milestone 1
2 | Project Name 6 - Milestone 2
1 | Project Name 7 - Milestone 1
2 | Project Name 7 - Milestone 2
1 | Project Name 8 - Milestone 1
2 | Project Name 8 - Milestone 2
1 | Project Name 9 - Milestone 1
2 | Project Name 9 - Milestone 2
1 | Project Name 10 - Milestone 1
2 | Project Name 10 - Milestone 2
|  |  | 0% | 12510
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 4378.5
2 | Delivery of Panels |  | 30% | 3753
3 | Delivery of Inverters |  | 20% | 2502
4 | Practical Completion |  | 10% | 1251
5 | Handover |  | 5% | 625.5
| Total |  | 100% | 12510
|  |  | 100% | 12510

## Expenditure Tracking (hidden)
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 10008 |  | 2790 | 7218
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Products - Magic Co | 2840 |  | 2790 | 50
2 | 2. Services - Magic Co | 7168 |  | 0 | 7168
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
| check: | 0 | #REF! | 153002

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 10008 | 12510 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 155792
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | 1. Products - Magic Co |  |  |  | 2840 | 2026-01-07 | 2840 | 3550 |  | 1 | 1. Products - Magic Co | Router - Used from BMG Fluid tech |  |  | 2790 |  | Allocated from BMG Fluid Tech | 2026-02-28 | 3550 |  | 2026-02-28 | 2790
1 | 1. Products - Magic Co | [8 empty] | 1 | 1. Products - Magic Co | [7 empty] | 0
1 | 1. Products - Dipula Blackheath | [5 empty] | 0 | 0 |  | 1 | 1. Products - Dipula Blackheath | [7 empty] | 0 |  |  | 0
1 | 1. Products - Dipula Blackheath | [8 empty] | 1 | 1. Products - Dipula Blackheath
1 | 1. Products - Busamed Harrismith | [5 empty] | 0 | 0 |  | 1 | 1. Products - Busamed Harrismith | Meter & CTs |  |  | 7694 | PO4596-BHM-20260203 | Accuenergy Inv: ASAI-007319 | 2026-03-31 | 0 |  | 2026-03-31 | 7694
1 | 1. Products - Busamed Harrismith | [8 empty] | 1 | 1. Products - Busamed Harrismith
1 | 1. Products - Busamed Harrismith | [8 empty] | 1 | 1. Products - Busamed Harrismith
1 | 1. Products - Busamed Harrismith | [8 empty] | 1 | 1. Products - Busamed Harrismith
1 | 1. Products - Dipula - Kopnaong Kudube | [5 empty] | 0 | 0 |  | 1 | 1. Products - Dipula - Kopnaong Kudube | [10 empty] | 0
1 | 1. Products - Dipula - Kopnaong Kudube | [8 empty] | 1 | 1. Products - Dipula - Kopnaong Kudube
1 | 1. Products - Dipula - Kopnaong Kudube | [8 empty] | 1 | 1. Products - Dipula - Kopnaong Kudube
1 | 1. Products - Dipula - Kopnaong Kudube | [8 empty] | 1 | 1. Products - Dipula - Kopnaong Kudube
1 | 1. Products - Dipula - Sam Sekhoti | [5 empty] | 0 | 0 |  | 1 | 1. Products - Dipula - Sam Sekhoti | [10 empty] | 0
1 | 1. Products - Dipula - Sam Sekhoti | [8 empty] | 1 | 1. Products - Dipula - Sam Sekhoti
1 | 1. Products - Dipula - Sam Sekhoti | [8 empty] | 1 | 1. Products - Dipula - Sam Sekhoti
1 | 1. Products - Dipula - Sam Sekhoti | [8 empty] | 1 | 1. Products - Dipula - Sam Sekhoti
1 | 1. Products - Project Name 6 | [5 empty] | 0 | 0 |  | 1 | 1. Products - Project Name 6 | [10 empty] | 0
1 | 1. Products - Project Name 6 | [8 empty] | 1 | 1. Products - Project Name 6
1 | 1. Products - Project Name 6 | [8 empty] | 1 | 1. Products - Project Name 6
1 | 1. Products - Project Name 6 | [8 empty] | 1 | 1. Products - Project Name 6
1 | 1. Products - Project Name 7 | [5 empty] | 0 | 0 |  | 1 | 1. Products - Project Name 7 | [10 empty] | 0
1 | 1. Products - Project Name 7 | [8 empty] | 1 | 1. Products - Project Name 7
1 | 1. Products - Project Name 7 | [8 empty] | 1 | 1. Products - Project Name 7
1 | 1. Products - Project Name 7 | [8 empty] | 1 | 1. Products - Project Name 7
1 | 1. Products - Project Name 8 | [5 empty] | 0 | 0 |  | 1 | 1. Products - Project Name 8 | [10 empty] | 0
1 | 1. Products - Project Name 8 | [8 empty] | 1 | 1. Products - Project Name 8
1 | 1. Products - Project Name 8 | [8 empty] | 1 | 1. Products - Project Name 8
1 | 1. Products - Project Name 8 | [8 empty] | 1 | 1. Products - Project Name 8
1 | 1. Products - Project Name 9 | [5 empty] | 0 | 0 |  | 1 | 1. Products - Project Name 9 | [10 empty] | 0
1 | 1. Products - Project Name 9 | [8 empty] | 1 | 1. Products - Project Name 9
1 | 1. Products - Project Name 9 | [8 empty] | 1 | 1. Products - Project Name 9
1 | 1. Products - Project Name 9 | [8 empty] | 1 | 1. Products - Project Name 9
1 | 1. Products - Project Name 10 | [5 empty] | 0 | 0 |  | 1 | 1. Products - Project Name 10 | [10 empty] | 0
1 | 1. Products - Project Name 10 | [8 empty] | 1 | 1. Products - Project Name 10
1 | 1. Products - Project Name 10 | [8 empty] | 1 | 1. Products - Project Name 10
1 | 1. Products - Project Name 10 | [8 empty] | 1 | 1. Products - Project Name 10
2 | 2. Services - Magic Co |  |  |  | 7168 | 2026-01-07 | 7168 | 8960 |  | 2 | 2. Services - Magic Co | Travel |  |  | 0 |  |  | 2026-02-28 | 8960 |  | 2026-01-17 | 0
2 | 2. Services - Magic Co | [8 empty] | 2 | 2. Services - Magic Co | [7 empty] | 0
2 | 2. Services - Dipula Blackheath | [5 empty] | 0 | 0 |  | 2 | 2. Services - Dipula Blackheath | Labour & Material to relocate two inverters |  |  | 36540 | PO4637-DBH-20260220 - RV Apporved | Cosmic Sun Inv: CS_BLA_999 | 2026-02-28 | 0 |  | 2026-02-26 | 36540
2 | 2. Services - Dipula Blackheath | [8 empty] | 2 | 2. Services - Dipula Blackheath
2 | 2. Services - Busamed Harrismith | [5 empty] | 0 | 0 |  | 2 | 2. Services - Busamed Harrismith | AC Works - Matthews Group |  |  | 25749 | PO4598-BHM-20260203 | Matthews roup Inv: 1596 | 2026-02-28 | 0 |  | 2026-02-06 | 51498
2 | 2. Services - Busamed Harrismith | [8 empty] | 2 | 2. Services - Busamed Harrismith |  |  |  | 25749 |  |  | 2026-03-31 |  |  | 2026-03-31
2 | 2. Services - Busamed Harrismith | [8 empty] | 2 | 2. Services - Busamed Harrismith
2 | 2. Services - Busamed Harrismith | [8 empty] | 2 | 2. Services - Busamed Harrismith
2 | 2. Services - Dipula - Kopnaong Kudube | [5 empty] | 0 | 0 |  | 2 | 2. Services - Dipula - Kopnaong Kudube | AC & DC Snag Resolution - Cosmic Sun |  |  | 30195 | PO4635-DIP_KK-20260219 | Cosmic Sun Inv: CS_KPG_001 | 2026-02-28 | 0 |  | 2026-03-19 | 30195
2 | 2. Services - Dipula - Kopnaong Kudube | [8 empty] | 2 | 2. Services - Dipula - Kopnaong Kudube
2 | 2. Services - Dipula - Kopnaong Kudube | [8 empty] | 2 | 2. Services - Dipula - Kopnaong Kudube
2 | 2. Services - Dipula - Kopnaong Kudube | [8 empty] | 2 | 2. Services - Dipula - Kopnaong Kudube
2 | 2. Services - Dipula - Sam Sekhoti | [5 empty] | 0 | 0 |  | 2 | 2. Services - Dipula - Sam Sekhoti | AC & DC Snag Resolution - Cosmic Sun |  |  | 27075 | PO4634-DSS-20260219 | CS_SSK_001 | 2026-02-28 | 0 |  | 2026-03-19 | 27075
2 | 2. Services - Dipula - Sam Sekhoti | [8 empty] | 2 | 2. Services - Dipula - Sam Sekhoti
2 | 2. Services - Dipula - Sam Sekhoti | [8 empty] | 2 | 2. Services - Dipula - Sam Sekhoti
2 | 2. Services - Dipula - Sam Sekhoti | [8 empty] | 2 | 2. Services - Dipula - Sam Sekhoti
2 | 2. Services - Project Name 6 | [5 empty] | 0 | 0 |  | 2 | 2. Services - Project Name 6 | [10 empty] | 0
2 | 2. Services - Project Name 6 | [8 empty] | 2 | 2. Services - Project Name 6
2 | 2. Services - Project Name 6 | [8 empty] | 2 | 2. Services - Project Name 6
2 | 2. Services - Project Name 6 | [8 empty] | 2 | 2. Services - Project Name 6
2 | 2. Services - Project Name 7 | [5 empty] | 0 | 0 |  | 2 | 2. Services - Project Name 7 | [10 empty] | 0
2 | 2. Services - Project Name 7 | [8 empty] | 2 | 2. Services - Project Name 7
2 | 2. Services - Project Name 7 | [8 empty] | 2 | 2. Services - Project Name 7
2 | 2. Services - Project Name 7 | [8 empty] | 2 | 2. Services - Project Name 7
2 | 2. Services - Project Name 8 | [5 empty] | 0 | 0 |  | 2 | 2. Services - Project Name 8 | [10 empty] | 0
2 | 2. Services - Project Name 8 | [8 empty] | 2 | 2. Services - Project Name 8
2 | 2. Services - Project Name 8 | [8 empty] | 2 | 2. Services - Project Name 8
2 | 2. Services - Project Name 8 | [8 empty] | 2 | 2. Services - Project Name 8
2 | 2. Services - Project Name 9 | [5 empty] | 0 | 0 |  | 2 | 2. Services - Project Name 9 | [10 empty] | 0
2 | 2. Services - Project Name 9 | [8 empty] | 2 | 2. Services - Project Name 9
2 | 2. Services - Project Name 9 | [8 empty] | 2 | 2. Services - Project Name 9
2 | 2. Services - Project Name 9 | [8 empty] | 2 | 2. Services - Project Name 9
2 | 2. Services - Project Name 10 | [5 empty] | 0 | 0 |  | 2 | 2. Services - Project Name 10 | [10 empty] | 0
2 | 2. Services - Project Name 10 | [8 empty] | 2 | 2. Services - Project Name 10
2 | 2. Services - Project Name 10 | [8 empty] | 2 | 2. Services - Project Name 10
2 | 2. Services - Project Name 10 | [8 empty] | 2 | 2. Services - Project Name 10
Only services to be capture below, products above
| Project Name | Magic Co
| Project Value | 12510
|  | COS | REV
| Products | 2840 | 3550
| Services | 7168 | 8960
| Project Name | Dipula - BlackHeath
| Project Value | 0
|  | COS | REV
| Products | 0 | 0
| Services | 0 | 0
| Project Name | Busamed Harrismith
| Project Value | 0
|  | COS | REV
| Products | 0 | 0
| Services | 0 | 0
| Project Name | Dipula - Kopanong Kudube
| Project Value | 0
|  | COS | REV
| Products | 0 | 0
| Services | 0 | 0
| Project Name | Dipula - Sam Sekhoti
| Project Value | 0
|  | COS | REV
| Products | 0 | 0
| Services | 0 | 0
| Project Name | Project Name 6
| Project Value | 300000
|  | COS | REV
Products
Services
| Project Name | Project Name 7
| Project Value | 300000
|  | COS | REV
Products
Services
| Project Name | Project Name 8
| Project Value | 300000
|  | COS | REV
Products
Services
| Project Name | Project Name 9
| Project Value | 300000
|  | COS | REV
Products
Services
| Project Name | Project Name 10
| Project Value | 300000
|  | COS | REV
Products
Services

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 12510 | 12510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6255 | 0 | 0 | 0 | 6255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6255 | 6255 | 6255 | 6255 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510
| Planned Expenditure | 10008 | 10008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008 | 10008
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6255 | -3753 | -3753 | -3753 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502 | 2502
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 12510 | 12510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6255 | 0 | 0 | 0 | 0 | 6255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6255 | 6255 | 6255 | 6255 | 6255 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510
| Actual + Planned Expenditure | 155792 | 155792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25749 | 0 | 0 | 39330 | 0 | 0 | 57270 | 0 | 33443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25749 | 25749 | 25749 | 65079 | 65079 | 65079 | 122349 | 122349 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792 | 155792
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6255 | 6255 | 6255 | 6255 | 6255 | 12510 | 12510 | -13239 | -13239 | -13239 | -52569 | -52569 | -52569 | -109839 | -109839 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282 | -143282
|  | CHECK | CHECK
| Revenue Recognition | 0 | 12510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 12510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510 | 12510

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2026-02-28 | 2026-03-31 | Grand Total
(blank)
1. Products - Magic Co | 0 | 3550 |  | 3550
2. Services - Magic Co | 0 | 3550 |  | 3550
1. Products - Dipula Blackheath | 0 |  |  | 0
1. Products - Busamed Harrismith |  | 0 |  | 0
1. Products - Project Name 4
1. Products - Project Name 5
1. Products - Project Name 6
1. Products - Project Name 7
1. Products - Project Name 8
1. Products - Project Name 9
1. Products - Project Name 10
2. Services - Dipula Blackheath |  |  | 0 | 0
2. Services - Busamed Harrismith |  |  | 0 | 0
2. Services - Project Name 4
2. Services - Project Name 5
2. Services - Project Name 6
2. Services - Project Name 7
2. Services - Project Name 8
2. Services - Project Name 9
2. Services - Project Name 10
Grand Total | 0 | 7100 | 0 | 7100

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2026-02-28 | 2026-03-31 | Grand Total
(blank)
1. Products - Magic Co |  | 2500 |  | 2500
2. Services - Magic Co |  | 2500 |  | 2500
1. Products - Dipula Blackheath
1. Products - Busamed Harrismith |  | 7694 |  | 7694
1. Products - Project Name 4
1. Products - Project Name 5
1. Products - Project Name 6 |  |  |  |  | 0
1. Products - Project Name 7
1. Products - Project Name 8
1. Products - Project Name 9
1. Products - Project Name 10
2. Services - Dipula Blackheath |  |  | 36540 | 36540
2. Services - Busamed Harrismith |  |  | 51498 | 51498
2. Services - Project Name 4
2. Services - Project Name 5
2. Services - Project Name 6
2. Services - Project Name 7
2. Services - Project Name 8
2. Services - Project Name 9
2. Services - Project Name 10
Grand Total |  | 12694 | 88038 | 100732

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | #DIV/0! | #REF! |  | #DIV/0! | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | #DIV/0! | #REF! |  | #DIV/0! | #REF!
AC Labour | #REF! | #REF! | 96174 | #DIV/0! | #REF! |  | #DIV/0! | #REF!
DC Labour | #REF! | #REF! | 230160 | #DIV/0! | #REF! |  | #DIV/0! | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | #DIV/0! | #REF! |  | #DIV/0! | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | #DIV/0! | #REF!
DC installation | #REF! | #REF! |  | #DIV/0! | #REF! |  | #DIV/0! | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
0 |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | 0 | 0 | 0 | 0