## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW
1 | Planned Revenue | 3786732 |  | 3786732 |  |  |  | Start Date
2 | Planned Expenditure | 3478221.256 |  | 2789768.8875 | VO PM Limit | Current VO Total
3 | Planned Profit | 308510.744 |  | 996963.1125 | 15425.5372 | 81762.5 |  | End Date - PC
4 | Planned Margin | 8.147% |  | 26.33%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Deposit |  | 20% | 757346.4 |  | 2025-04-30 | 004733 | 2025-05-01 | 2025-04-29
2 | Delivery of Panels |  | 20% | 757346.4 |  | 2025-06-18 | 004733 | 2025-05-01 | 2025-06-20
3 | Delivery of Inverters |  | 15% | 568009.8 |  | 2025-06-10 | 004733 | 2025-05-01 | 2025-06-06
4 | Commissioning Complete |  | 15% | 568009.8 |  | 2025-07-31 | 004733 | 2025-05-01 | 2025-08-27
5 | Final Completion Issued |  | 25% | 946683 |  | 2025-07-31 | 004733 | 2025-05-01 | 2025-08-27
6 | Handover |  | 5% | 189336.6 |  | 2025-09-29 | 004733 | 2025-05-01 | 2025-09-18
7 | - |  | 0% | 0
|  |  | 100% | 3786732
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 1325356.2
2 | Delivery of Panels |  | 30% | 1136019.6
3 | Delivery of Inverters |  | 20% | 757346.4
4 | Practical Completion |  | 10% | 378673.2
5 | Handover |  | 5% | 189336.6
| Total |  | 100% | 3786732
|  |  | 100% | 3786732

## Project Plan
[9 empty] | 2026-03-06 | 2026-03-06
| PROJECT PLAN | Kroonstad | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 391
| PROJECT DEVELOPER | Natasha Watkins-Baker
| PROJECT MANAGERS | JT Moorosi
| CONTRACT VALUE | 3786732
| Phase: | Compliance Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Expected Status | Comment
|  |  | 52 |  |  | 91 |  | 100% | 100%
1 | Project Initiation | 2025-04-22 | 35 | 2025-05-27 | 2025-04-29 | 17 | 2025-05-16 | 100% | 100%
1.1 | BD Handover | 2025-04-22 | 1 | 2025-04-23 | 2025-05-13 | 1 | 2025-05-14 | 100% | 100%
1.2 | Project Introduction | 2025-05-26 | 1 | 2025-05-27 | 2025-05-15 | 1 | 2025-05-16 | 100% | 100%
1.3 | HSE | 2025-04-22 | 10 | 2025-05-07 | 2025-04-29 | 10 | 2025-05-14 | 100% | 100%
1.4 | Installer Kick Off | 2025-05-19 | 1 | 2025-05-20 | 2025-05-14 | 1 | 2025-05-15 | 100% | 100%
1.5 | Project Review | 2025-05-19 | 1 | 2025-05-20 | 2025-05-08 | 1 | 2025-05-09 | 100% | 100%
2 | Site Establishment | 2025-06-02 | 1 | 2025-06-03 | 2025-06-02 | 1 | 2025-06-03 | 100% | 100%
2.1 | Solar Contractor Establishment | 2025-06-02 | 1 | 2025-06-03 | 2025-06-02 | 1 | 2025-06-03 | 100% | 100% |  | 65 | Net Work Days
3 | AC Installation | 2025-05-05 | 50 | 2025-06-24 | 2025-05-05 | 91 | 2025-08-04 | 100% | 100% |  | 13 | Total Weeks
3.1 | Inverters delivered | 2025-06-03 | 1 | 2025-06-04 | 2025-05-29 | 1 | 2025-05-30 | 100% | 100% |  | 30.0769 | kW/Week Installation Rate
3.2 | Inverters Mounted | 2025-06-04 | 5 | 2025-06-11 | 2025-07-22 | 5 | 2025-07-29 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-05-05 | 25 | 2025-06-09 | 2025-05-05 | 37 | 2025-06-26 | 100% | 100%
3.4 | AC Works | 2025-06-09 | 10 | 2025-06-24 | 2025-07-22 | 6 | 2025-07-30 | 100% | 100%
3.5 | AC Tie-In | 2025-06-09 | 3 | 2025-06-12 | 2025-07-30 | 3 | 2025-08-04 | 100% | 100%
4 | DC Works | 2025-06-02 | 39 | 2025-07-11 | 2025-05-22 | 62 | 2025-07-23 | 100% | 100%
4.1 | Lifeline Installation (If Applicable) | [6 empty] | 0% | 0%
4.1 | Mounting Structure delivered | 2025-06-02 | 1 | 2025-06-03 | 2025-05-22 | 1 | 2025-05-23 | 100% | 100%
4.2 | Mounting Structure installation | 2025-06-03 | 10 | 2025-06-18 | 2025-05-26 | 10 | 2025-06-09 | 100% | 100%
4.3 | DC Cable delivered | 2025-06-02 | 1 | 2025-06-03 | 2025-07-22 | 1 | 2025-07-23 | 100% | 100%
4.3 | DC Stringing | 2025-06-28 | 10 | 2025-07-11 | 2025-06-23 | 15 | 2025-07-14 | 100% | 100%
5 | Module installation | 2025-06-11 | 20 | 2025-07-01 | 2025-06-03 | 20 | 2025-06-23 | 100% | 100%
5.1 | Module delivery | 2025-06-11 | 1 | 2025-06-12 | 2025-06-03 | 1 | 2025-06-04 | 100% | 100%
5.2 | Module mounting | 2025-06-12 | 12 | 2025-07-01 | 2025-06-04 | 12 | 2025-06-23 | 100% | 100%
6 | Commissioning | 2025-07-11 | 13 | 2025-07-24 | 2025-08-04 | 28 | 2025-09-01 | 100% | 100% | 12-Aug: IV curves captured; Techsitter rewired; comms restored; AC/DC snags fixed. Site not yet stable for PC – further investigation underway. Risk to 15-Aug PC if root cause not resolved by 13-Aug.
6.1 | Commissioning | 2025-07-11 | 4 | 2025-07-17 | 2025-08-04 | 7 | 2025-08-13 | 100% | 100% | Functional tests ongoing; logs being pulled and OEM consult planned.
6.2 | Practical Completion | 2025-07-17 | 5 | 2025-07-24 | 2025-08-13 | 13 | 2025-09-01 | 100% | 100%
7 | QA Inspections | 2025-07-24 | 1 | 2025-07-25 | 2025-09-01 | 1 | 2025-09-02 | 100% | 100%
7.1 | Red-Team Inspection | 2025-07-24 | 1 | 2025-07-25 | 2025-09-01 | 1 | 2025-09-02 | 100% | 100%
8 | Project Closure | 2025-07-24 | 14 | 2025-08-07 | 2025-09-02 | 24 | 2025-09-26 | 100% | 100%
8.1 | Equipment serial numbers | 2025-07-25 | 2 | 2025-07-29 | 2025-09-02 | 2 | 2025-09-04 | 100% | 100%
8.2 | Snags completion | 2025-07-25 | 4 | 2025-07-31 | 2025-09-02 | 4 | 2025-09-08 | 100% | 100%
8.3 | System Performance Monitoring | 2025-07-31 | 5 | 2025-08-07 | 2025-09-08 | 5 | 2025-09-15 | 100% | 100%
8.4 | Handover documentation | 2025-07-24 | 6 | 2025-08-01 | 2025-09-15 | 4 | 2025-09-19 | 100% | 100%
8.5 | Handover to Client | 2025-08-01 | 1 | 2025-08-04 | 2025-09-19 | 1 | 2025-09-22 | 100% | 100% | Align with Roedolph on client over
8.6 | Handover to Matriarch | 2025-07-27 | 5 | 2025-08-01 | 2025-09-22 | 3 | 2025-09-26 | 100% | 100%
Formulas:
Planned Start = MIN([Planned Start, row below]:E16)
Planned Start = WORKDAY.INTL([Planned End, row above],0,1,Data!$C3:C14)
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = WORKDAY.INTL([Actual End, row above],0,1,Data!$C3:C14)
Actual End = MAX([Actual End, row below]:K16)
Actual End = MAX([Actual End, row below])

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 3478221.256 |  | 2789768.8875 | 688452.3685
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 822562.51 |  | 778527.8 | 44034.71
2 | 2. Inverters | 210000 |  | 206611.05 | 3388.95
3 | 3. Mounting Structures | 176179.5 |  | 67072.02 | 109107.48
4 | 4. DC Equipment | 317797.8 |  | 228221.7675 | 89576.0325
5 | 5. Monitoring | 49000 |  | 35927.14 | 13072.86
6 | 6. AC Equipment | 398615.7261 |  | 200393.09 | 198222.6361
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 0 |  | 68584.8 | -68584.8
9 | 9. AC & DC installation | 316662.5 |  | 470550 | -153887.5
10 | 10. Site Logistics | 63976.2 |  | 46421.6 | 17554.6
11 | 11. Due Dilligence | 117575.5 |  | 33449.73 | 84125.77
12 | 12. BDP Commission | 67721.8982 |  | 0 | 67721.8982
13 | 13. Engineering | 131304.6217 |  | 47334.15 | 83970.4717
14 | 14. General Expenses | 6825 |  | 10913.24 | -4088.24
15 | 15. Service Add On | 800000 |  | 595762.5 | 204237.5
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 3478221.256 | 3786732.1258 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 2789768.8875
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 822562.51 | 2025-07-29 | 822562.51 | 934730.125 |  | 1 | 1. Panels | Jinko 620W - MENLO | 631 | 1233.8 | 778527.8 | PO3904-DIP-PH2-PNP-20250514 | Menlo INV0002963 | 2025-05-31 | 934730.125 | 0 | 2025-07-29 | 778527.8
1 |  | Delivery Budget | [7 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 398615.7261
2 | Inverters | Inverter Budget |  |  | 210000 | 2025-07-29 | 210000 | 238636.3636 |  | 2 | 2. Inverters | Huawei 100KTL - MENLO | 3 | 68870.35 | 206611.05 | PO3904-DIP-PH2-PNP-20250514 | Menlo INV0002963 | 2025-05-31 | 238636.3636 | 0 | 2025-07-29 | 206611.05 | DC Equipment | 189585.8
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | AC Labour | 97877.5
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 218785
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 26666.2
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 4810
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 176179.5 | 2025-06-27 | 176179.5 | 200203.9773 |  | 3 | 3. Mounting Structures | Schletter Structure |  |  | 62801.6 | PO3946-DPK-20250521 - RV Approved | Schletter - INV1786 | 2025-05-31 | 146262.4841 | 0.0043917 | 2025-06-27 | 67072.02 | Other | 0
3 | [5 empty] | 2025-06-30 |  |  |  | 3 | 3. Mounting Structures | Schletter PRO 551 clamps ( stock from PE store) | 300 | 24.88 | 7464 |  | Allocated from PE Stockroom | 2025-06-30 | 15404.4463 |  | 2025-06-30 |  | Total | 944840.2261
[6 empty] | 2025-07-31 |  |  |  | 3 | 3. Mounting Structures | Schletter PRO 551 clamps ( stock from PE store) | -300 | 24.88 | -7464 |  | Allocated to PE Stockroom | 2025-07-31 | 0 |  | 2025-07-31
[10 empty] | 3 | 3. Mounting Structures | End Clamps | 300 | 11.48 | 3444 |  | Allocated to PE Stockroom | 2025-07-31 | 36831.45
[6 empty] | 2025-07-29 |  |  |  | 3 | 3. Mounting Structures | Delivery Fee |  |  | 826.42 |  | DSV Invoice: 180135241 | 2025-06-30 | 1705.5925 |  | 2025-07-29
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Less 15% | 803114.1922
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | R/Wp | 2.054
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL - Cosmic Sun | Installer Price
[23 empty] | AC Equipment | 106054
4 | DC Equipment | DC Cable Budget | 10531.7 |  | 128212 | 2025-07-29 | 317797.8 | 361133.8636 |  | 4 | 4. DC Equipment | DC Cable = Menlo | 600 | 13.4 | 8040 | PO3904-DIP-PH2-PNP-20250514 | Menlo INV0002963 | 2025-05-31 | 16665.636 | -0.01053 | 2025-07-29 | 228221.7675 | DC Equipment | 93821.75
4 |  | DC Equipment Budget |  |  | 189585.8 | 2025-07-29 |  |  |  | 4 | 4. DC Equipment | DC Cable = Menlo | 5400 | 13.4 | 72360 |  | Menlo INV0002963 | 2025-05-31 | 149990.7237 |  | 2025-07-29 |  | AC Labour | 149030
4 | [5 empty] | 2025-08-21 |  |  |  | 4 | 4. DC Equipment | DC Cable = Menlo _Top Up - VO | 4000 | 13.5 | 54000 | PO4017-DPK-20250520 - RV Approved | Menlo INV0003033 | 2025-06-30 | 34511.7717 |  | 2025-08-21 |  | DC Labour | 321520
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Offloading | 4950
4 | [5 empty] | 2025-05-15 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 93821.75 | 10% | 9382.175 | PO3879-DPK-20250513 - RV Approved | Cosmic Sun: CS_KRN_001 | 2025-05-31 | 19447.7504 |  | 2025-05-15 |  | Scaffolding | 16621.6
4 | [5 empty] | 2025-06-05 |  |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 14073.2625 |  | Cosmic Sun: CS_KRN_002 | 2025-05-31 | 29171.6256 |  | 2025-06-05 |  | Storage | 6600
4 | [5 empty] | 2025-08-07 |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 18764.35 |  | Cosmic Sun: CS_KRN_004 | 2025-06-30 | 29692.3571 |  | 2025-08-07 |  | Telehandler | 0
4 | [5 empty] | 2025-07-11 |  |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 23455.44 |  | Cosmic Sun: CS_KRN_003 | 2025-06-30 | 37115.4503 |  | 2025-07-11 |  | HSE | 4500
4 | [5 empty] | 2025-09-04 |  |  |  | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 9382.18 |  | Cosmic Sun: CS_KRN_005 | 2025-06-30 | 14846.1865 |  | 2025-09-04 |  | Other | 0
4 | [5 empty] | 2025-09-04 |  |  |  | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 9382.18 |  | Cosmic Sun: CS_KRN_006 | 2025-06-30 | 14846.1865 |  | 2025-09-04 |  | Other | 0
4 | [5 empty] | 2025-09-25 |  |  |  | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 4691.09 |  | Cosmic Sun: CS_KRN_007 | 2025-06-30 | 7423.0932 |  | 2025-09-25 |  | Total | 703097.35
4 | [5 empty] | 2025-09-26 |  |  |  | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 4691.09 |  | Cosmic Sun: CS_KRN_008 | 2025-06-30 | 7423.0932 |  | 2025-10-24 |  | R/Wp | 1.7982
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 34000 | 2025-07-17 | 49000 | 55681.8182 |  | 5 | 5. Monitoring | Smartlogger - Menlo - faulty awaiting RMA |  |  | 8598.35 | PO3904-DIP-PH2-PNP-20250514 | Menlo INV0002933 | 2025-05-31 | 12277.0934 | 0.0049348 | 2025-07-17 | 35927.14
[6 empty] | 2025-10-16 |  |  |  | 5 | 5. Monitoring |  |  |  | 8598.35 |  | Menlo INV0003159 | 2025-08-31 | 0 |  | 2025-10-16
[10 empty] | 5 | 5. Monitoring | Smartlogger - Moveto BMG Fluid Tech |  |  | -8598.35 |  | Allocated to BMG Fluid Tech | 2025-11-30 | 0 |  | 2025-11-30
5 |  | Revenue Metering |  |  | 15000 | 2025-05-29 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 13695 | PO3835-DIP-Ph2-PnP-20250429 - RV Approved | Accuenergy - INV ASAI-005361 | 2025-04-30 | 19114.2374 |  | 2025-05-29
[6 empty] | 2025-07-29 |  |  |  | 5 | 5. Monitoring |  |  |  | 214.29 |  | Accuenergy - Inv ASAI-005800 | 2025-06-30 | 4143.3482 |  | 2025-07-29
5 | [5 empty] | 2025-06-30 |  |  |  | 5 | 5. Monitoring | Techsitter |  |  | 11169 |  | Matriarch Inv: 4451 | 2025-06-30 | 16978.1983 |  | 2025-06-30
5 | [5 empty] | 2025-05-22 |  |  |  | 5 | 5. Monitoring | UPS |  |  | 2250.5 | PO3863-DIP Ph2-20250509 - RV Approved | Frontline INV725690 | 2025-05-31 | 3168.936 |  | 2025-05-22
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 398615.7261 | 2025-07-28 | 398615.7261 | 452972.416 |  | 6 | 6. AC Equipment | [7 empty] | 0 | -0.0017343 |  | 200393.09
6 | [5 empty] | 2025-07-29 |  |  |  | 6 | 6. AC Equipment | PVDB |  |  | 94339.09 | PO3884-DIP-Ph2-Kroon-20250513 - RV Approved | Switchboard - Inv 2-SOI002093 | 2025-06-30 | 213245.9034 |  | 2025-07-29
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [5 empty] | 2025-05-15 |  |  |  | 6 | 6. AC Equipment | Project Kick Off | 106054 | 10% | 10605.4 | PO3879-DPK-20250513 - RV Approved | Cosmic Sun: CS_KRN_001 | 2025-05-31 | 24258.1519 |  | 2025-05-15
6 | [5 empty] | 2025-06-05 |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 15908.1 |  | Cosmic Sun: CS_KRN_002 | 2025-05-31 | 36387.2279 |  | 2025-06-05
6 | [5 empty] | 2025-08-07 |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 21210.8 |  | Cosmic Sun: CS_KRN_004 | 2025-06-30 | 47231.5525 |  | 2025-08-07
6 | [5 empty] | 2025-07-11 |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 26513.5 |  | Cosmic Sun: CS_KRN_003 | 2025-06-30 | 59931.6281 |  | 2025-07-11
6 | [5 empty] | 2025-09-04 |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 10605.4 |  | Cosmic Sun: CS_KRN_005 | 2025-06-30 | 23972.6513 |  | 2025-09-04
6 | [5 empty] | 2025-09-04 |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 10605.4 |  | Cosmic Sun: CS_KRN_006 | 2025-06-30 | 23972.6513 |  | 2025-09-04
6 | [5 empty] | 2025-09-25 |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 5302.7 |  | Cosmic Sun: CS_KRN_007 | 2025-06-30 | 11986.3256 |  | 2025-09-25
6 | [5 empty] | 2025-09-26 |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 5302.7 |  | Cosmic Sun: CS_KRN_008 | 2025-06-30 | 11986.3256 |  | 2025-10-24
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 0 | 0 |  | 8 | 8. Product Add On | [8 empty] | 0 |  | 68584.8
8 | [9 empty] | 8 | 8. Product Add On
8 | [5 empty] | 2025-10-31 |  |  |  | 8 | 8. Product Add On | Aircons Supply and Install - Rubycon |  |  | 36794.4 | PO4534-DPK-20251210 - RV Approved | Rubycon - RD0710251 | 2025-12-31 |  |  | 2025-12-18
8 | [5 empty] | 2025-10-31 |  |  |  | 8 | 8. Product Add On | Burglar Door Added Security |  |  | 5770 | PO4355-DPK-20251006 - RV Approved | Rubycon - RD1112253 | 2025-10-31 |  |  | 2025-10-09
8 | [5 empty] | 2025-10-31 |  |  |  | 8 | 8. Product Add On | Waterpoints |  |  | 24908.5 | PO4387-DPK-202510210 - RVApproved | Rubycon - RD2310251 | 2025-10-31 |  |  | 2025-11-13
8 | [5 empty] | 2025-10-02 |  |  |  | 8 | 8. Product Add On | Delivery of Clamps for Waterpoints |  |  | 261.4 |  | DSV Inv: 180158820 | 2025-12-31 |  |  | 2026-01-29
8 | [5 empty] | 0 |  |  |  | 8 | 8. Product Add On | Clamps | 30 | 28.35 | 850.5 |  | Allocated from Joburg Storeroom | 31/01/2025 |  |  | 2026-01-31
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 97877.5 | 2025-05-14 | 316662.5 | 372544.1176 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0 |  | 470550
9 |  | DC Installation Budget |  |  | 218785 | 2025-05-15 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 470550 | 10% | 47055 | PO3879-DPK-20250513 - RV Approved | Cosmic Sun: CS_KRN_001 | 2025-05-31 | 37254.4118 |  | 2025-05-15
9 | [5 empty] | 2025-06-05 |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 70582.5 |  | Cosmic Sun: CS_KRN_002 | 2025-05-31 | 55881.6176 |  | 2025-06-05
9 | [5 empty] | 2025-08-07 |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 94110 |  | Cosmic Sun: CS_KRN_004 | 2025-06-30 | 74508.8235 |  | 2025-08-07
9 | [5 empty] | 2025-07-11 |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 117637.5 |  | Cosmic Sun: CS_KRN_003 | 2025-06-30 | 93136.0294 |  | 2025-07-11
9 | [5 empty] | 2025-09-04 |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 47055 |  | Cosmic Sun: CS_KRN_005 | 2025-06-30 | 37254.4118 |  | 2025-09-04
9 | [5 empty] | 2025-09-04 |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 47055 |  | Cosmic Sun: CS_KRN_006 | 2025-06-30 | 37254.4118 |  | 2025-09-04
9 | [5 empty] | 2025-09-25 |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 23527.5 |  | Cosmic Sun: CS_KRN_007 | 2025-06-30 | 18627.2059 |  | 2025-09-25
9 | [5 empty] | 2025-09-26 |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 23527.5 |  | Cosmic Sun: CS_KRN_008 | 2025-06-30 | 18627.2059 |  | 2025-10-24
9 | [5 empty] | 2025-09-27 |  |  |  | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [5 empty] | 2025-09-28 |  |  |  | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [5 empty] | 2025-09-29 |  |  |  | 9 | 9. AC & DC installation | [7 empty] | 0
2025-09-30
10 | Site Logistics | Offloading |  |  | 8500 | 2025-10-01 | 63976.2 | 75266.1176 |  | 10 | 10. Site Logistics | [7 empty] | 0 | -0.0035881 |  | 46421.6
10 |  | Scaffolding |  |  | 26666.2 | 2025-10-02 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
[6 empty] | 2025-10-03 |  |  |  | 10 | 10. Site Logistics | Security - June: Monika Security Services |  |  | 13750 | PO3984-DPK-20250606 - RV Approved | Monika Security - INV0002664 | 2025-06-30 | 16579.343 |  | 2025-06-19
[6 empty] | 2025-10-04 |  |  |  | 10 | 10. Site Logistics | [6 empty] | 2025-08-31 | 19292.33
[6 empty] | 2025-10-05 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
[6 empty] | 2025-10-06 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
[6 empty] | 2025-10-07 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Security |  |  | 24000 | 2025-10-08 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 4810 | 2025-10-09 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [5 empty] | 2025-05-15 |  |  |  | 10 | 10. Site Logistics | Project Kick Off | 32671.6 | 10% | 3267.16 | PO3879-DPK-20250513 - RV Approved | Cosmic Sun: CS_KRN_001 | 2025-05-31 | 3939.4448 |  | 2025-05-15
10 | [5 empty] | 2025-06-05 |  |  |  | 10 | 10. Site Logistics | Site Establishment |  | 15% | 4900.74 |  | Cosmic Sun: CS_KRN_002 | 2025-05-31 | 5909.1672 |  | 2025-06-05
10 | [5 empty] | 2025-08-07 |  |  |  | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 6534.32 |  | Cosmic Sun: CS_KRN_004 | 2025-06-30 | 7878.8896 |  | 2025-08-07
10 | [5 empty] | 2025-07-11 |  |  |  | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 8167.9 |  | Cosmic Sun: CS_KRN_003 | 2025-06-30 | 9848.6121 |  | 2025-07-11
10 | [5 empty] | 2025-09-04 |  |  |  | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 3267.16 |  | Cosmic Sun: CS_KRN_005 | 2025-06-30 | 3939.4448 |  | 2025-09-04
10 | [5 empty] | 2025-09-04 |  |  |  | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 3267.16 |  | Cosmic Sun: CS_KRN_006 | 2025-06-30 | 3939.4448 |  | 2025-09-04
10 | [5 empty] | 2025-09-25 |  |  |  | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 1633.58 |  | Cosmic Sun: CS_KRN_007 | 2025-06-30 | 1969.7224 |  | 2025-09-25
10 | [5 empty] | 2025-09-26 |  |  |  | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 1633.58 |  | Cosmic Sun: CS_KRN_008 | 2025-06-30 | 1969.7224 |  | 2025-10-24
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2025-09-11 | 117575.5 | 138324.1176 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 10737.49 |  | Sunspot E027 | 2025-07-31 | 44940.7056 | 0.0036224 | 2025-09-11 | 33449.73
11 |  | Structural Sign Off |  |  | 19575.5 | 2025-04-10 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 8212.24 | PO3745-DIP-Ph2-20250313 - RV Approved | L&B Consulting - Invoice 1934 | 2025-04-30 | 33695.502 |  | 2025-04-10
11 |  | Grid Study |  |  | 80000 | 2025-04-11 |  |  |  | 11 | 11. Due Dilligence | [7 empty] | 0
11 |  | Lightning Risk Assessment |  |  | 7000 | 2025-06-26 |  |  |  | 11 | 11. Due Dilligence | Lightning Risk Assessment |  |  | 8500 | PO3844-Dipula Ph2-20250430 - RV Approved | LPS Inv: IN306837 | 2025-04-30 | 34876.2052 |  | 2025-06-26
11 | [5 empty] | 2025-07-31 |  |  |  | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 |  | Matriarch - IN-4753 | 2025-07-31 | 24811.7012 |  | 2025-07-31
2025-08-01
12 | BDP Commission | Referral Fee |  |  | 56434.9152 | 2025-08-02 | 67721.8982 | 0 |  | 12 | 12. BDP Commission | Referral Fee | [9 empty] | 0
12 | BDP Commission | PD Fee |  |  | 11286.983 | 2025-08-03 |  |  |  | 12 | 12. BDP Commission | PD Fee
13 | Engineering | Matriarch Defects Period |  |  | 30904.6217 | 2025-07-31 | 131304.6217 | 149209.7974 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 47334.15 |  | Matriarch - INV-4752 | 2025-07-31 | 149209.7974 | 0 | 2025-07-31 | 47334.15
13 |  | Management |  |  | 20000 | 2025-07-31 |  |  |  | 13 | 13. Engineering | Management |  |  | 0 |  |  | 2025-07-31 | 0 |  | 2025-07-31
13 |  | Project manager |  |  | 40800 | 2025-07-31 |  |  |  | 13 | 13. Engineering | Project manager |  |  | 0 |  |  | 2025-07-31 | 0 |  | 2025-07-31
13 |  | Planner time |  |  | 26000 | 2025-07-31 |  |  |  | 13 | 13. Engineering | Planner time |  |  | 0 |  |  | 2025-07-31 | 0 |  | 2025-07-31
13 |  | De Snagging |  |  | 13600 | 2025-07-31 |  |  |  | 13 | 13. Engineering | De Snagging |  |  | 0 |  |  | 2025-07-31 | 0 |  | 2025-07-31
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 6825 | 2025-05-08 | 6825 | 8029.4118 |  | 14 | 14. General Expenses | Travel |  |  | 4000 |  | Site Visit | 2025-04-30 | 3395.1001 | 0.00070657 | 2025-05-08 | 10913.24
14 | [5 empty] | 2025-04-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  | 2025-04-30 | 0 |  | 2025-04-30
14 | [5 empty] | 2025-06-07 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 2980.88 |  | Expense Claim | 2025-05-31 | 2813.3629 |  | 2025-06-07
14 | [5 empty] | 2025-07-04 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 88.06 |  | Expense Claim | 2025-06-30 | 83.8363 |  | 2025-07-04
14 | [5 empty] | 2025-08-07 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 3573.38 |  | Expense Claim | 2025-07-31 | 1034.4225 |  | 2025-08-07
14 | [5 empty] | 2025-08-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 270.92 |  | Expense Claim | 2025-08-31 | 702.6893 |  | 2025-08-31
14 | [5 empty] | 2025-09-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-09-30 | 0 |  | 2025-09-30
14 | [5 empty] | 2025-10-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-10-31 | 0 |  | 2025-10-31
14 | [5 empty] | 2025-11-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  | 2025-11-30 | 0 |  | 2025-11-30
14 | [5 empty] | 2025-12-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  | 2025-12-31 | 0 |  | 2025-12-31
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | Welcome Bonus |  |  | 800000 | 2025-06-26 | 800000 | 800000 |  | 15 | 15. Service Add On | Welcome Bonus - Site Establishment |  |  | 284000 |  | Luxanio Trading - 23398/202506/274844/I | 2025-06-30 | 400000 | 0 | 2025-06-26 | 595762.5
15 | [5 empty] | 2025-09-18 |  |  |  | 15 | 15. Service Add On | Welcome Bonus - Commissioning |  |  | 284000 |  | Luxanio Trading - 23398/202506/274844/I | 2025-06-30 | 400000 |  | 2025-09-18
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | Community Engagement |  |  | 0 |  |  |  | 0
15 | [9 empty] | 15 | 15. Service Add On | CS - Establishment and re-establishment - VO |  |  | 16006.25 | PO4342-DPK-20250930 - RV Approved | Cosmic Sun: CS_KRN_009 | 2025-09-30 | 0 |  | 2025-10-02
15 | [9 empty] | 15 | 15. Service Add On | Matriarch - Labour & Call Out - VO |  |  | 5756.25 | PO4345-DPK-20251003 - RV Approved | Matriarch - INV-5208 | 2025-10-31 | 0 |  | 2025-11-30
15 | [9 empty] | 15 | 15. Service Add On | CS - Installation of E Stop - VO |  |  | 6000 |  | Cosmic Sun - CS_KRN_010 | 2025-11-30 | 0 |  | 2025-11-19
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
| Panel Procurement Budget | 822562.51 |  | 934730.125
| Inverter Procurement Budget | 210000 |  | 238636.3636
| Mounting Structure Budget | 176179.5 |  | 200203.9773
| DC Equipment Budget | 317797.8 |  | 361133.8636
| AC Equipment Budget | 398615.7261 |  | 452972.416
| Monitoring Budget | 49000 |  | 55681.8182
| Optional Extras Budget | 0 |  | 0
| MV Metering Budget | 0 |  | 0
| ADD ON | 0 |  | 0
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 97877.5 |  | 115150
| DC Installer Budget | 218785 |  | 257394.1176
| In-House Expense Budget | 131304.6217 |  | 149209.7974
| Compliance Budget | 117575.5 |  | 138324.1176
| Offloading Budget | 8500 |  | 10000
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 4810 |  | 5658.8235
| On Site Security | 24000 |  | 28235.2941
| Roof Access Budget for Installers | 26666.2 |  | 31372
| EPC Management Fee | 0 |  | 0
| ADD ON | 800000 |  | 800000
Expenses
| Total EE Expense Budget | 6825 |  | 8029.4118
Note on Q90: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Peet Verreynne where did the clamps come from Reply: Unfortunately i do not have context of this. @JT Moorosi please indicate where these clamp came from. Reply: Hi @Tasneema van Harte @Peet Verreynne clamps where from the JHB warehouse.

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 3786732 | 3786732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 757346.4 | 0 | 0 | 0 | 0 | 0 | 568009.8 | 757346.4 | 0 | 0 | 0 | 0 | 0 | 1514692.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189336.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 757346.4 | 757346.4 | 757346.4 | 757346.4 | 757346.4 | 757346.4 | 1325356.2 | 2082702.6 | 2082702.6 | 2082702.6 | 2082702.6 | 2082702.6 | 2082702.6 | 3597395.4 | 3597395.4 | 3597395.4 | 3597395.4 | 3597395.4 | 3597395.4 | 3597395.4 | 3597395.4 | 3597395.4 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732
| Planned Expenditure | 3478221.256 | 3478221.256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99575.5 | 0 | 0 | 0 | 6825 | 316662.5 | 0 | 15000 | 0 | 0 | 0 | 983179.5 | 0 | 0 | 34000 | 0 | 1948002.556 | 0 | 0 | 0 | 0 | 0 | 11000 | 0 | 0 | 35166.2 | 28810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8212.24 | 8212.24 | 8212.24 | 8212.24 | 12212.24 | 82521.975 | 84772.475 | 98467.475 | 206912.9575 | 206912.9575 | 220662.9575 | 575964.5575 | 594685.6175 | 770459.9575 | 779058.3075 | 779058.3075 | 1985847.1075 | 2130039.9575 | 2130039.9575 | 2184039.9575 | 2184310.8775 | 2324930.3575 | 2335667.8475 | 2619667.8475 | 2654822.7175 | 2670828.9675 | 2676598.9675 | 2685197.3175 | 2720352.1875 | 2720352.1875 | 2720352.1875 | 2745260.6875 | 2751260.6875 | 2748418.5875 | 2748418.5875 | 2748418.5875 | 2785212.9875 | 2785212.9875 | 2785212.9875 | 2785212.9875 | 2785212.9875 | 2785212.9875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8212.24 | -8212.24 | -8212.24 | 749134.16 | 745134.16 | 674824.425 | 672573.925 | 658878.925 | 550433.4425 | 1118443.2425 | 1862039.6425 | 1506738.0425 | 1488016.9825 | 1312242.6425 | 1303644.2925 | 1303644.2925 | 1611548.2925 | 1467355.4425 | 1467355.4425 | 1413355.4425 | 1413084.5225 | 1272465.0425 | 1261727.5525 | 977727.5525 | 942572.6825 | 1115903.0325 | 1110133.0325 | 1101534.6825 | 1066379.8125 | 1066379.8125 | 1066379.8125 | 1041471.3125 | 1035471.3125 | 1038313.4125 | 1038313.4125 | 1038313.4125 | 1001519.0125 | 1001519.0125 | 1001519.0125 | 1001519.0125 | 1001519.0125 | 1001519.0125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 3786732 | 3786732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 757346.4 | 0 | 0 | 0 | 0 | 568009.8 | 0 | 757346.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1514692.8 | 0 | 0 | 189336.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 757346.4 | 757346.4 | 757346.4 | 757346.4 | 757346.4 | 1325356.2 | 1325356.2 | 2082702.6 | 2082702.6 | 2082702.6 | 2082702.6 | 2082702.6 | 2082702.6 | 2082702.6 | 2082702.6 | 2082702.6 | 2082702.6 | 3597395.4 | 3597395.4 | 3597395.4 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732 | 3786732
| Actual + Planned Expenditure | 2789768.8875 | 2786324.8875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8212.24 | 0 | 0 | 0 | 4000 | 70309.735 | 2250.5 | 13695 | 108445.4825 | 0 | 13750 | 355301.6 | 18721.06 | 175774.34 | 8598.35 | 0 | 1206788.8 | 144192.85 | 0 | 54000 | 270.92 | 140619.48 | 10737.49 | 284000 | 35154.87 | 16006.25 | 5770 | 8598.35 | 35154.87 | 0 | 0 | 24908.5 | 6000 | -2842.1 | 0 | 0 | 36794.4 | 0 | 0 | 0 | 0 | 0 | 1111.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8212.24 | 8212.24 | 8212.24 | 8212.24 | 12212.24 | 82521.975 | 84772.475 | 98467.475 | 206912.9575 | 206912.9575 | 220662.9575 | 575964.5575 | 594685.6175 | 770459.9575 | 779058.3075 | 779058.3075 | 1985847.1075 | 2130039.9575 | 2130039.9575 | 2184039.9575 | 2184310.8775 | 2324930.3575 | 2335667.8475 | 2619667.8475 | 2654822.7175 | 2670828.9675 | 2676598.9675 | 2685197.3175 | 2720352.1875 | 2720352.1875 | 2720352.1875 | 2745260.6875 | 2751260.6875 | 2748418.5875 | 2748418.5875 | 2748418.5875 | 2785212.9875 | 2785212.9875 | 2785212.9875 | 2785212.9875 | 2785212.9875 | 2785212.9875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875 | 2786324.8875
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8212.24 | -8212.24 | -8212.24 | 749134.16 | 745134.16 | 674824.425 | 672573.925 | 658878.925 | 1118443.2425 | 1118443.2425 | 1862039.6425 | 1506738.0425 | 1488016.9825 | 1312242.6425 | 1303644.2925 | 1303644.2925 | 96855.4925 | -47337.3575 | -47337.3575 | -101337.3575 | 1413084.5225 | 1272465.0425 | 1261727.5525 | 1167064.1525 | 1131909.2825 | 1115903.0325 | 1110133.0325 | 1101534.6825 | 1066379.8125 | 1066379.8125 | 1066379.8125 | 1041471.3125 | 1035471.3125 | 1038313.4125 | 1038313.4125 | 1038313.4125 | 1001519.0125 | 1001519.0125 | 1001519.0125 | 1001519.0125 | 1001519.0125 | 1001519.0125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125 | 1000407.1125
|  | CHECK | CHECK
| Revenue Recognition | -0.12803 | 3786732.128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91081.0447 | 0 | 0 | 0 | 1716794.122 | 0 | 0 | 0 | 0 | 1702033.8653 | 0 | 0 | 0 | 256828.0767 | 0 | 0 | 0 | 19995.0193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 3786732.128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91081.0447 | 91081.0447 | 91081.0447 | 91081.0447 | 1807875.1668 | 1807875.1668 | 1807875.1668 | 1807875.1668 | 1807875.1668 | 3509909.0321 | 3509909.0321 | 3509909.0321 | 3509909.0321 | 3766737.1087 | 3766737.1087 | 3766737.1087 | 3766737.1087 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128 | 3786732.128

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 31/01/2025 | Grand Total
(blank)
1. Panels |  |  | 934730.125 | [7 empty] | 0 |  | 934730.125
2. Inverters |  |  | 238636.3636 | [7 empty] | 0 |  | 238636.3636
3. Mounting Structures | 0 |  | 146262.4841 | 17110.0388 | 36831.45 | [5 empty] | 0 |  | 200203.9729
4. DC Equipment |  |  | 215275.7357 | 145858.1385 | [6 empty] | 0 |  | 361133.8742
5. Monitoring |  | 19114.2374 | 15446.0294 | 21121.5464 |  | 0 |  |  | 0 |  | 0 |  | 55681.8132
6. AC Equipment |  |  | 60645.3799 | 392327.0379 | [6 empty] | 0 |  | 452972.4177
8. Product Add On
9. AC & DC installation |  |  | 93136.0294 | 279408.0882 | [6 empty] | 0 |  | 372544.1176
10. Site Logistics |  |  | 9848.6121 | 46125.1792 |  | 19292.33 |  |  |  |  | 0 |  | 75266.1212
11. Due Dilligence |  | 68571.7072 |  |  | 69752.4068 | [5 empty] | 0 |  | 138324.114
13. Engineering |  |  |  |  | 149209.7974 | [5 empty] | 0 |  | 149209.7974
14. General Expenses |  | 3395.1001 | 2813.3629 | 83.8363 | 1034.4225 | 702.6893 | 0 | 0 | 0 | 0 | 0 |  | 8029.4111
15. Service Add On |  |  |  | 800000 |  |  | 0 | 0 | 0 |  | 0 |  | 800000
12. BDP Commission
7.BESS
Grand Total | 0 | 91081.0447 | 1716794.122 | 1702033.8653 | 256828.0767 | 19995.0193 | 0 | 0 | 0 | 0 | 0 |  | 3786732.128

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 31/01/2025 | Grand Total
(blank)
1. Panels |  |  | 778527.8 | [9 empty] | 778527.8
2. Inverters |  |  | 206611.05 | [9 empty] | 206611.05
3. Mounting Structures |  |  | 62801.6 | 8290.42 | -4020 | [7 empty] | 67072.02
4. DC Equipment |  |  | 103855.4375 | 124366.33 | [8 empty] | 228221.7675
5. Monitoring |  | 13695 | 10848.85 | 11383.29 |  | 8598.35 |  |  | -8598.35 |  |  |  | 35927.14
6. AC Equipment |  |  | 26513.5 | 173879.59 | [8 empty] | 200393.09
8. Product Add On | [7 empty] | 30678.5 |  | 37055.8 |  | 850.5 | 68584.8
9. AC & DC installation |  |  | 117637.5 | 352912.5 | [8 empty] | 470550
10. Site Logistics |  |  | 8167.9 | 38253.7 | [8 empty] | 46421.6
11. Due Dilligence |  | 16712.24 |  |  | 16737.49 | [7 empty] | 33449.73
13. Engineering |  |  |  |  | 47334.15 | [7 empty] | 47334.15
14. General Expenses |  | 4000 | 2980.88 | 88.06 | 3573.38 | 270.92 | 0 | 0 | 0 | 0 |  |  | 10913.24
15. Service Add On |  |  |  | 568000 |  |  | 16006.25 | 5756.25 | 6000 |  | 0 |  | 595762.5
12. BDP Commission
7.BESS
Grand Total |  | 34407.24 | 1317944.5175 | 1277173.89 | 63625.02 | 8869.27 | 16006.25 | 36434.75 | -2598.35 | 37055.8 | 0 | 850.5 | 2789768.8875

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate | [5 empty] | FINANCIAL CLOSE CERTIFICATE
Project Name: | Kroonstad
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion: |  |  |  | 1. Financial Close | 1. Financial Close
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 0.71072 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.36358 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.24597 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 0.58864 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
Kroonstad |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Kroonstad | 0 | 0 | 0