## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Certificate - Financial Close (hidden)
Emergent Energy – Financial Close Completion Certificate |  |  |  | FINANCIAL CLOSE CERTIFICATE
Project Name: | Seshego Circle
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Product Agreement
EPC Agreement
O&M Agreeement
Cost Proposal
Deposit Received
Risks / Notes
Acknowledgement and Acceptance:
Role | Name | Signature | Date

## Certificate - Planning (hidden)
Emergent Energy – Planning Phase Completion Certificate |  |  |  | PLANNING CERTIFICATE
Project Name: | Seshego Circle
Client Representative:
Programme Manager: | Roedolph Venter
Project Manager: | Eon Van Rensburg
Project Engineer:
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Project Introduction Presentation
Project Brief
Engineering Pack
BOQ
PO – Material & Equipment
PO - Contractors
HSE – NOC
HSE – EE File
HSE – Contractor File
SSEG Application
Risks / Notes
Acknowledgement and Acceptance:
Role | Name | Signature | Date

## Change Register
Change Register
ID | Description | Supporting Image (If Applicable) | Impact | Proposed Date | Proposed By | Status | Approved By | Approved Date | Results / Comments
DEC001 | We need to manufacture Tie-In Kiosks because of space contraints in the Mini-subs |  | AC tie-in delay | 2026-02-03 | Peet | In Progress
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
DEC011
DEC012
DEC013
DEC014
DEC015
DEC016
DEC017
DEC018
DEC019
DEC020
DEC021
DEC022
DEC023
DEC024
DEC025
DEC026
DEC027
DEC028
DEC029
DEC030

## BOQ (hidden)
Item | Supplier | Description | Quantity | Comments
PV Module
DC Cable Red & Black
Inverters
Mounting Structure
Current Transformers (Production)
Current Transformers (Consumption)
Solar Production Meter (Techistter)
Grid Consumption Meter
Wi-Fi Router & Sim
Switch
Back Up Battery
PVDB
Supplier List
Accuenergy
Krannich
Menlo
Red Pole
Schletter
Switchboard
Techsitter

## Compliance (hidden)
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[9 empty] | 2026-02-24 | 2026-02-24
| PROJECT PLAN | Seshego Circle | [6 empty] | 0 | Kios
| PROJECT SIZE (kWp) | 1360 | [7 empty] | AC kiosk delay TBC AC Tie in delay. **RISK** No Kiosk
| PROJECT DEVELOPER | Dayne Sage |  |  |  | Target Month | 2025-10-31
| PROJECT MANAGERS | Eon Van Rensburg
| CONTRACT VALUE | 10428344.3462
| Phase: | Construction
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Status | Comment
|  |  | 60 |  |  | 141 |  | 63.96% | 63.96%
1 | Project Initiation | 2025-07-07 | 94 | 2025-10-09 | 2025-07-07 | 94 | 2025-10-09 | 100% | 100%
1.1 | BD Handover | 2025-07-07 | 5 | 2025-07-14 | 2025-07-07 | 5 | 2025-07-14 | 100% | 100%
1.2 | Project Introduction | 2025-09-29 | 1 | 2025-09-30 | 2025-09-29 | 1 | 2025-09-30 | 100% | 100%
1.3 | HSE | 2025-09-29 | 8 | 2025-10-09 | 2025-09-29 | 8 | 2025-10-09 | 100% | 100%
1.4 | Installer Kick Off | 2025-09-29 | 1 | 2025-09-30 | 2025-09-29 | 1 | 2025-09-30 | 100% | 100%
1.5 | Project Review | 2025-09-29 | 1 | 2025-09-30 | 2025-09-29 | 1 | 2025-09-30 | 100% | 100%
2 | Site Establishment | 2025-10-13 | 1 | 2025-10-14 | 2025-10-13 | 1 | 2025-10-14 | 100% | 100%
2.1 | Solar Contractor Establishment | 2025-10-13 | 1 | 2025-10-14 | 2025-10-13 | 1 | 2025-10-14 | 100% | 100% |  | 78 | Net Work Days
2.2 | Civil Works |  |  |  | 2025-10-27 | 36 | 2025-12-02 | 100% | 100%
2.2 | Roof Remedial Work |  |  |  | 2025-10-20 | 10 | 2025-10-30 | 100% | 100%
3 | AC Installation | 2025-09-29 | 52 | 2025-11-20 | 2025-09-29 | 154 | 2026-03-02 | 97.37% | 97.37% |  | 15.6 | Total Weeks
3.1 | Inverters delivered | 2025-10-13 | 1 | 2025-10-14 | 2025-10-13 | 1 | 2025-10-14 | 100% | 100% |  | 87.1795 | kW/Week Installation Rate
3.2 | Inverters Mounted | 2025-11-04 | 1 | 2025-11-05 | 2025-12-02 | 1 | 2025-12-03 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-09-29 | 30 | 2025-11-10 | 2025-09-29 | 34 | 2025-11-14 | 100% | 100%
3.4 | AC Works - Tie In 1 | 2025-11-10 | 8 | 2025-11-20 | 2025-12-02 | 15 | 2026-01-26 | 100% | 100%
3.5 | AC Works - Tie In 2 |  |  |  | 2026-01-12 | 8 | 2026-01-28 | 100% | 100%
3.6 | Tie in Kiosk |  |  |  | 2026-02-03 | 15 | 2026-02-24 | 100% | 100%
3.7 | AC Tie In 1 |  |  |  | 2026-02-27 | 1 | 2026-03-02 | 0% | 0% | Scheduled
3.8 | AC Tie-In 2 | 2025-11-10 | 2 | 2025-11-12 | 2026-02-27 | 1 | 2026-03-02 | 0% | 0% | Scheduled
4 | DC Works | 2025-10-13 | 53 | 2025-12-05 | 2025-10-13 | 100 | 2026-01-21 | 100% | 100%
4.1 | Lifeline Installation (If Applicable) | [6 empty] | 0% | 0%
4.1 | Mounting Structure delivered | 2025-10-13 | 1 | 2025-10-14 | 2025-10-13 | 1 | 2025-10-14 | 100% | 100%
4.2 | Mounting Structure installation -Tie In 1 | 2025-10-14 | 10 | 2025-10-28 | 2025-10-27 | 8 | 2025-11-06 | 100% | 100%
4.3 | Mounting Structure installation -Tie In 2 |  |  |  | 2025-11-13 | 8 | 2025-11-25 | 100% | 100%
4.4 | DC Cable delivered | 2025-10-13 | 1 | 2025-10-14 | 2025-10-13 | 1 | 2025-10-14 | 100% | 100%
4.5 | DC Stringing Tie In 1 |  |  |  | 2025-11-15 | 6 | 2025-11-24 | 100% | 100%
4.6 | DC Stringing Tie In 2 | 2025-11-15 | 15 | 2025-12-05 | 2025-11-18 | 22 | 2026-01-21 | 100% | 100%
5 | Module installation | 2025-10-13 | 36 | 2025-11-18 | 2025-10-13 | 38 | 2025-11-20 | 100% | 100%
5.1 | Module delivery | 2025-10-13 | 1 | 2025-10-14 | 2025-10-13 | 1 | 2025-10-14 | 100% | 100%
5.2 | Module mounting - Tie In 1 | 2025-10-21 | 20 | 2025-11-18 | 2025-11-04 | 12 | 2025-11-20 | 100% | 100%
5.2 | Module mounting - Tie In 2 | 2025-10-21 | 20 | 2025-11-18 | 2025-11-18 | 10 | 2025-12-02 | 100% | 100%
6 | Commissioning | 2025-12-05 | 7 | 2025-12-12 | 2026-02-27 | 4 | 2026-03-03 | 14.29% | 14.29%
6.1 | Fibre cable install |  |  |  | 2026-02-17 | 1 | 2026-02-18 | 100% | 100%
6.2 | Commissioning - Tie In 1 | 2025-12-05 | 2 | 2025-12-09 | 2026-02-27 | 2 | 2026-03-03 | 0% | 0%
6.3 | Commissioning - Tie In 2 |  |  |  | 2026-02-27 | 2 | 2026-03-03 | 0% | 0%
6.4 | Practical Completion | 2025-12-09 | 3 | 2025-12-12 | 2026-02-28 | 2 | 2026-03-03 | 0% | 0%
7 | QA Inspections | 2025-12-05 | 3 | 2025-12-08 | 2026-03-01 | 1 | 2026-03-02 | 0% | 0%
7.1 | Red-Team Inspection | 2025-12-05 | 1 | 2025-12-08 | 2026-03-01 | 1 | 2026-03-02 | 0% | 0%
8 | Project Closure | 2025-12-05 | 48 | 2026-01-22 | 2026-03-01 | 16 | 2026-03-17 | 0% | 0%
8.1 | Equipment serial numbers | 2025-12-05 | 1 | 2025-12-08 | 2026-03-01 | 1 | 2026-03-02 | 0% | 0%
8.2 | Snags completion | 2025-12-08 | 5 | 2025-12-15 | 2026-03-02 | 5 | 2026-03-09 | 0% | 0%
8.3 | System Performance Monitoring | 2025-12-12 | 5 | 2026-01-22 | 2026-03-03 | 5 | 2026-03-10 | 0% | 0%
8.4 | Handover documentation | 2025-12-15 | 1 | 2026-01-19 | 2026-03-09 | 1 | 2026-03-10 | 0% | 0%
8.5 | Handover to Client | 2026-01-19 | 1 | 2026-01-20 | 2026-03-10 | 1 | 2026-03-11 | 0% | 0%
8.6 | Handover to Matriarch | 2026-01-19 | 1 | 2026-01-20 | 2026-03-10 | 5 | 2026-03-17 | 0% | 0%
Formulas:
Seshego Circle = MIN([Seshego Circle, row below]:E16)
Seshego Circle = [Seshego Circle, row above]
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Seshego Circle],[Duration (days)],1,Data!$C3:C45)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = [Actual Start, row above]
Actual End = MAX([Actual End, row below]:K16)
Actual End = WORKDAY.INTL([Actual Start],[Target Month],1,Data!$C3:C45)
Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  | FINANCIAL REVIEW | TIMELINE REVIEW
1 | Planned Revenue | 10428344.3462 |  | 10428344.35 |  |  | Start Date
2 | Planned Expenditure | 9590676.1311 |  | 7658861.9823
3 | Planned Profit | 837668.2151 |  | 2769482.3677 |  |  | End Date - PC
4 | Planned Margin | 8.033% |  | 26.56%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Claim 1 |  | 28.83% | 3006602.38 | 2025-11-25 | 004866 | 2025-10-28 | 2025-12-08
1 | Claim 1 |  | 29% | 3006602.38 | 2025-11-25 | 004866 | 2025-10-28 | 2025-12-03
2 | Claim 2 |  | 21.34% | 2225569 | 2025-12-25 | 004903 | 2025-12-17 | 2026-01-12
3 | Claim 3 |  | 0% | 0
4 | Claim 4 |  | 21% | 2189570.59 | 2026-02-25 |  |  | 2026-03-25
5 |  |  | 0% | 0
6 |  |  | 0% | 0
7 | - |  | 0% | 0
|  |  | 100.2% | 10428344.35
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 3649920.5225
2 | Delivery of Panels |  | 30% | 3128503.305
3 | Delivery of Inverters |  | 20% | 2085668.87
4 | Practical Completion |  | 10% | 1042834.435
5 | Handover |  | 5% | 521417.2175
| Total |  | 100% | 10428344.35
|  |  | 100% | 10428344.35

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-17 | Builders Holiday
2025-12-18 | Builders Holiday
2025-12-19 | Builders Holiday
2025-12-20 | Builders Holiday
2025-12-21 | Builders Holiday
2025-12-22 | Builders Holiday
2025-12-23 | Builders Holiday
2025-12-24 | Builders Holiday
2025-12-25 | Builders Holiday
2025-12-26 | Builders Holiday
2025-12-27 | Builders Holiday
2025-12-28 | Builders Holiday
2025-12-29 | Builders Holiday
2025-12-30 | Builders Holiday
2025-12-31 | Builders Holiday
2026-01-01 | Builders Holiday
2026-01-02 | Builders Holiday
2026-01-03 | Builders Holiday
2026-01-04 | Builders Holiday
2026-01-05 | Builders Holiday
2026-01-06 | Builders Holiday
2026-01-07 | Builders Holiday
2026-01-08 | Builders Holiday
2026-01-09 | Builders Holiday
2026-01-10 | Builders Holiday
2026-01-11 | Builders Holiday
2026-01-12 | Builders Holiday
2026-01-13 | Builders Holiday
2026-01-14 | Builders Holiday
2026-01-15 | Builders Holiday
2026-01-16 | Builders Holiday
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 9590676.1311 |  | 7658861.9823 | 1931814.1488
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 2857717.17 |  | 2667866.8 | 189850.37
2 | 2. Inverters | 770000 |  | 757573.938 | 12426.062
3 | 3. Mounting Structures | 1105818.21 |  | 365443.08 | 740375.13
4 | 4. DC Equipment | 1117490.1 |  | 713565.2 | 403924.9
5 | 5. Monitoring | 49000 |  | 91265.29 | -42265.29
6 | 6. AC Equipment | 1511034.3 |  | 586437.82 | 924596.48
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 300000 |  | 291826 | 8174
9 | 9. AC & DC installation | 1060132.5 |  | 1105292.21 | -45159.71
10 | 10. Site Logistics | 184440.4667 |  | 302543.9 | -118103.4333
11 | 11. Due Dilligence | 182012.75 |  | 142343.85 | 39668.9
12 | 12. BDP Commission | 0 |  | 0 | 0
13 | 13. Engineering | 429230.6344 |  | 130354.3043 | 298876.3301
14 | 14. General Expenses | 23800 |  | 38589.8 | -14789.8
15 | 15. Service Add On | 0 |  | 465759.79 | -465759.79
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 9590676.1311 | 12428344.3462 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 7658861.9823
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 2857717.17 | 2025-12-31 | 2857717.17 | 3072814.1613 |  | 1 | 1. Panels | Jinko 590 | 1298 | 1150.5 | 1493349 |  | Menlo - INV0003320 | 2025-10-31 | 1729623.9295 | 0 | 2025-12-12 | 2667866.8
1 |  | Delivery Budget | [7 empty] | 1 | 1. Panels | Jinko 590 balance | 1008 | 1150.5 | 1159704 |  | Menlo - INV0003319 | 2025-10-31 | 1343190.2318 |  | 2025-12-18
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | Replacement Panels - Damaged due to weather | 2 |  | 4136.4 | PO4556-DSHC-20260119 - RV Approved | MSA Energy - INV0003547 | 2026-01-31 | 0 |  | 2026-04-01
1 | [9 empty] | 1 | 1. Panels | Panels and Delivery | 7 |  | 10677.4 |  | MSA Energy - INV0003541 | 2026-01-31 | 0 |  | 2026-03-16
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 1511034.3
2 | Inverters | Inverter Budget | 11 |  | 770000 | 2025-12-31 | 770000 | 827956.9892 |  | 2 | 2. Inverters | Huawei 100KTL | 11 | 68870.358 | 757573.938 |  | Menlo - INV0003320 | 2025-10-31 | 827956.9892 | 0 | 2025-12-12 | 757573.938 | DC Equipment | 675888.1
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | AC Labour | 340042.5
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 720090
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 70393.8
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 33546.6667
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 1105818.21 | 1900-01-29 | 1105818.21 | 1189051.8387 |  | 3 | 3. Mounting Structures | K2 Structure |  |  | 40621.45 | PO4364-DSHC-20251009 - RV Approved | Krannich - 15-10014095 | 2025-10-31 | 142264.2188 | 0 | 2025-12-12 | 365443.08 | Other | 0
3 | [9 empty] | 3 | 3. Mounting Structures |  |  |  | 45778.95 |  | krannich - 15-10014122 | 2025-10-31 | 160326.787 |  | 2025-12-18 |  | Total | 3359495.3667
3 | [9 empty] | 3 | 3. Mounting Structures |  |  |  | 50931.2 |  | krannich - 15-10014093 | 2025-10-31 | 178370.9686 |  | 2025-12-12 |  | Less 15% | 2855571.0617
3 | [9 empty] | 3 | 3. Mounting Structures |  |  |  | 202184.62 |  | Krannich - 15-10014094 | 2025-10-31 | 708089.8644 |  | 2025-12-12 |  | R/Wp | 2.0997
3 | [9 empty] | 3 | 3. Mounting Structures | Earthing plates |  |  | 71394.92 | PO4490-DSHC-20251125 - RV Approved | K2 Systems - Inv139402 | 2025-11-30 | 0 |  | 2025-11-28
[10 empty] | 3 | 3. Mounting Structures |  |  |  | -67046.2 |  | K2 Systems - Credit SACN42026 | 2026-01-31 | 0 |  | 2026-02-06
[10 empty] | 3 | 3. Mounting Structures | XS Clamps - K2 |  |  | 2283.7 | PO4616-DSHC-20260211 - RV Approved | K2 Systems - SAI1382026 | 2026-02-28 |  |  | 2026-02-06
[10 empty] | 3 | 3. Mounting Structures | Terragriff (254 clamps short returned) to be deducted from subbie |  |  | 3737.49 |  |  | 2026-02-28 | 0 |  | 2026-02-28
3 | [9 empty] | 3 | 3. Mounting Structures | Universal KL-Clamp |  |  | 15556.95 | PO4553-DSHC-20260116 - RV Approved | K2 Systems - InvSAI672026 | 2026-01-31 | 0 |  | 2026-01-23 |  | ACTUAL - JA Electrical | Installer Price
[23 empty] | AC Equipment | 231508.8
4 | DC Equipment | DC Cable Budget | 36274.45 |  | 441602 | 2025-12-31 | 1117490.1 | 1201602.2581 |  | 4 | 4. DC Equipment | DC Cable - old price | 14000 | 13.5 | 189000 |  | Menlo - INV0003320 | 2025-10-31 | 318264.9978 | 0 | 2025-12-12 | 713565.2 | DC Equipment | 169665.2
4 |  | DC Equipment Budget |  |  | 675888.1 | 2025-12-31 |  |  |  | 4 | 4. DC Equipment |  | 26000 | 13.65 | 354900 |  | Menlo - INV0003320 | 2025-10-31 | 597630.9402 |  | 2025-12-18 |  | AC Labour | 142795.4
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | DC Labour | 962496.8
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Offloading | 55490
4 | [5 empty] | 2025-08-31 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 169665.2 | 10% | 16966.52 |  | JA Electrical - Inv 1104 | 2025-10-31 | 28570.632 |  | 2025-11-06 |  | Scaffolding | 75760
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 25449.78 |  | JA Electrical - Inv 1105 | 2025-10-31 | 42855.948 |  | 2025-11-06 |  | Storage | 11407
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 10% | 16966.52 |  | JA ElectricalInv 1142 | 2025-12-31 | 28570.632 |  | 2025-12-12 |  | Site Ablutions | 17072
[10 empty] | 4 | 4. DC Equipment | AC Installation Complete |  | 7.5% | 12724.89 |  | JA Electrical Inv 1156 | 2026-01-31 | 21427.974 |  | 2026-02-13
[10 empty] | 4 | 4. DC Equipment | AC Installation Complete |  | 2.5% | 4241.63 |  |  | 2026-02-28 | 7142.658 |  | 2026-02-27
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 20% | 33933.04 |  | JA ElectricalInv 1142 | 2025-12-31 | 57141.264 |  | 2025-12-12 |  | Return of excess material | 14195
[10 empty] | 4 | 4. DC Equipment | DC Installation Complete |  | 2.5% | 4241.63 |  | JA Electrical Inv 1156 | 2026-01-31 | 7142.658 |  | 2026-02-13
[10 empty] | 4 | 4. DC Equipment | DC Installation Complete |  | 2.5% | 4241.63 |  |  | 2026-02-28 | 7142.658 |  | 2026-02-27
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 16966.52 |  |  | 2026-02-28 | 28570.632 |  | 2026-03-10 |  | Waste Skip | 22620
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 16966.52 |  |  | 2026-03-31 | 28570.632 |  | 2026-03-16 |  | Other | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 8483.26 |  |  | 2026-03-31 | 14285.316 |  | 2026-03-16 |  | Total | 1703010.2
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 8483.26 |  |  | 2026-03-31 | 14285.316 |  | 2026-04-08 |  | R/Wp | 1.2522
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 34000 | 2025-08-31 | 49000 | 52688.172 |  | 5 | 5. Monitoring | Smartlogger |  |  | 8598.34 |  | Menlo - INV0003320 | 2025-10-31 | 5015.4617 | 0.0040394 | 2025-12-12 | 91265.29
5 |  | Revenue Metering |  |  | 15000 | 2025-08-31 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 27301 | PO4416-DSHC-20251028 - RV Approved | Accuenergy Inv :ASAI-006727 | 2025-10-31 | 9478.94 |  | 2025-11-28
5 | [5 empty] | 2025-08-31 |  |  |  | 5 | 5. Monitoring | Techsitter |  |  | 11169 |  | Matriarch - INV-4742 | 2025-09-30 | 7261.7211 |  | 2025-08-31
[10 empty] | 5 | 5. Monitoring | DElivery of Techsitter |  |  | 335.86 |  | DSV Inv:180156930 | 2025-11-30 | 0 |  | 2025-12-31
5 | [5 empty] | 2025-08-31 |  |  |  | 5 | 5. Monitoring | Apex Device and Licenses |  |  | 44000 | PO4077-DSHC-20250630 - RV Approved | Rubicon INVWCRE-0069079 | 2025-09-30 | 28607.3712 |  | 2025-08-31
[10 empty] | 5 | 5. Monitoring | Above Apex allocated to Corporate Park |  |  | -44000 |  | Allocated to Corporate Park | 2025-10-31 | 0 |  | 2025-10-31
[10 empty] | 5 | 5. Monitoring | New Apex device |  |  | 40000 | PO4420-DSHC-20251029 - RV Approved | Rubicon - INVWCRE-0072121 | 2025-11-30 | 0 |  | 2025-12-30
[10 empty] | 5 | 5. Monitoring | Delivery of Apex |  |  | 285.59 |  | DSV Inv:180155155 | 2025-11-30 | 0 |  | 2025-12-30
5 | [5 empty] | 2025-08-07 |  |  |  | 5 | 5. Monitoring | UPS |  |  | 3575.5 | PO4070-DSHC-20250630 - RV Approved | Frontiline QTE107313 | 2025-09-30 | 2324.674 |  | 2025-08-07
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 1511034.3 | 2025-08-31 | 1511034.3 | 1624768.0645 |  | 6 | 6. AC Equipment | [7 empty] | 0 | 5.3091e-05 |  | 586437.82
6 | [5 empty] | 1900-01-29 |  |  |  | 6 | 6. AC Equipment | PVDB |  |  | 354929.22 | PO4330-DSHC-20250925 - MI Approved | Switchboard - 2-SOI002604 | 2025-11-30 | 983356.5392 |  | 2025-12-30
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [5 empty] | 2025-08-31 |  |  |  | 6 | 6. AC Equipment | Project Kick Off | 231508.8 | 10% | 23150.88 |  | JA Electrical - Inv 1104 | 2025-10-31 | 64141.1525 |  | 2025-11-06
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 34726.32 |  | JA Electrical - Inv 1105 | 2025-10-31 | 96211.7288 |  | 2025-11-06
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 10% | 23150.78 |  | JA ElectricalInv 1142 | 2025-12-31 | 64141.2873 |  | 2025-12-12
[10 empty] | 6. | 6. AC Equipment | AC Installation Complete |  | 7.5% | 17363.16 |  | JA Electrical Inv 1156 | 2026-01-31 | 48105.8808 |  | 2026-02-13
[10 empty] | 6. | 6. AC Equipment | AC Installation Complete |  | 2.5% | 5787.72 |  |  | 2026-02-28 | 16035.2936 |  | 2026-02-27
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 20% | 46301.66 |  | JA ElectricalInv 1142 | 2025-12-31 | 128282.0717 |  | 2025-12-12
[10 empty] | 6 | 6. AC Equipment | DC Installation Complete |  | 2.5% | 5787.72 |  |  | 2026-02-28 | 16035.2936 |  | 2026-02-27
[10 empty] | 6 | 6. AC Equipment | DC Installation Complete |  | 2.5% | 5787.72 |  | JA Electrical Inv 1156 | 2026-01-31 | 16035.2936 |  | 2026-02-13
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 23150.88 |  |  | 2026-02-28 | 64141.1744 |  | 2026-03-10
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 23150.88 |  |  | 2026-03-31 | 64141.1744 |  | 2026-03-16
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 11575.44 |  |  | 2026-03-31 | 32070.5872 |  | 2026-03-16
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 11575.44 |  |  | 2026-03-31 | 32070.5872 |  | 2026-04-08
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 300000 | 322580.6452 |  | 8 | 8. Product Add On | [7 empty] | 0 | 0.0035153 |  | 291826
8 |  | Transformer |  |  | 300000 | 2025-08-31 |  |  |  | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [5 empty] | 1900-01-29 |  |  |  | 8 | 8. Product Add On | Brick Face Inverter Rooms | 232956 | 75% | 174717 | PO4365-DSHC-20251013 - RV Approved | Van Staden Three : Inv 3021 | 2025-10-31 | 200089.1896 |  | 2025-10-16
8 | [9 empty] | 8 | 8. Product Add On |  |  | 25% | 58239 |  | Van Staden Three : Inv 3037 | 2025-10-31 | 66696.3965 |  | 2025-12-18
8 | [9 empty] | 8 | 8. Product Add On | Inverter stand |  |  | 48720 | PO4450-DSHC-20251107 - RV Approved | JA Electrical - Inv 1144 | 2025-12-31 | 55795.0555 |  | 2026-02-13
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | Grounding Washers |  |  | 10150 | PO4571-DSHC-20260123 - RV Approved | JA Electrical Inv 1156 | 2026-01-31 | 0 |  | 2026-02-13
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 340042.5 | 2025-08-31 | 1060132.5 | 1204696.0227 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0.0040054 |  | 1105292.21
9 |  | DC Installation Budget |  |  | 720090 | 2025-08-31 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 1105292.2 | 10% | 110529.22 |  | JA Electrical - Inv 1104 | 2025-10-31 | 120469.6023 |  | 2025-11-06
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 165793.83 |  | JA Electrical - Inv 1105 | 2025-10-31 | 180704.4034 |  | 2025-11-06
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 10% | 110529.22 |  | JA ElectricalInv 1142 | 2025-12-31 | 120469.6023 |  | 2025-12-12
[10 empty] | 9 | 9. AC & DC installation | AC Installation Complete |  | 7.5% | 82896.92 |  | JA Electrical Inv 1156 | 2026-01-31 | 90352.1963 |  | 2026-02-13
[10 empty] | 9 | 9. AC & DC installation | AC Installation Complete |  | 2.5% | 27632.31 |  |  | 2026-02-28 | 30117.4057 |  | 2026-02-27
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 20% | 221058.44 |  | JA ElectricalInv 1142 | 2025-12-31 | 240939.2045 |  | 2025-12-12
[10 empty] | 9 | 9. AC & DC installation | DC Installation Complete |  | 2.5% | 27632.305 |  | JA Electrical Inv 1156 | 2026-01-31 | 30117.4003 |  | 2026-02-13
[10 empty] | 9 | 9. AC & DC installation | DC Installation Complete |  | 2.5% | 27632.305 |  |  | 2026-02-28 | 30117.4003 |  | 2026-02-27
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 110529.22 |  |  | 2026-02-28 | 120469.6012 |  | 2026-03-10
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 110529.22 |  |  | 2026-03-31 | 120469.6012 |  | 2026-03-16
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 55264.61 |  |  | 2026-03-31 | 60234.8006 |  | 2026-03-16
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 55264.61 |  |  | 2026-03-31 | 60234.8006 |  | 2026-04-08
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-08-31 | 184440.4667 | 209591.4394 |  | 10 | 10. Site Logistics | [7 empty] | 0 | -0.0034785 |  | 302543.9
10 |  | Scaffolding |  |  | 70393.8 | 2025-08-31 |  |  |  | 10 | 10. Site Logistics | Security - Oct - Deposit |  |  | 18000 | PO4363-DSHC-20251009 - RV Approved | Cycad Security - INV0002672 | 2025-10-31 | 12469.7429 |  | 2025-10-16
[6 empty] | 1900-01-29 |  |  |  | 11 | 10. Site Logistics | Security - Oct - Balance |  |  | 18000 |  | Cycad Security - INV0002672 | 2025-10-31 | 12469.7429 |  | 2025-10-31
[6 empty] | 1900-01-29 |  |  |  | 12 | 10. Site Logistics | Security - Nov |  |  | 60000 |  | Cycad Security - INV0002699 | 2025-11-30 | 38348.8212 |  | 2025-11-28
[10 empty] | 12 | 10. Site Logistics | Security - Dec 02-11/12 |  |  | 10000 | PO4524-DSHC-20251208-MI - Approved | Cycad Security - INV0002713 | 2025-12-31 | 6927.6373 |  | 2025-12-12
[10 empty] | 13 | 10. Site Logistics | [6 empty] | 2026-01-31 | -20049.89
10 |  | Security |  |  | 72000 | 2025-08-31 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 33546.6667 | 2025-08-31 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [5 empty] | 2025-08-31 |  |  |  | 10 | 10. Site Logistics | Project Kick Off | 196544 | 10% | 19654.4 |  | JA Electrical - Inv 1104 | 2025-10-31 | 13615.8509 |  | 2025-11-06
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Site Establishment |  | 15% | 29481.6 |  | JA Electrical - Inv 1105 | 2025-10-31 | 20423.7763 |  | 2025-11-06
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | AC Installation Complete |  | 10% | 19654.4 |  | JA ElectricalInv 1142 | 2025-12-31 | 16832.8754 |  | 2025-12-12
[10 empty] | 10 | 10. Site Logistics | AC Installation Complete |  | 7.5% | 14740.8 |  | JA Electrical Inv 1156 | 2026-01-31 | 16832.8754 |  | 2026-02-13
[10 empty] | 10 | 10. Site Logistics | AC Installation Complete |  | 2.5% | 4913.6 |  |  | 2026-02-28 | 3403.9638 |  | 2026-02-27
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | DC Installation Complete |  | 20% | 39308.7 |  | JA ElectricalInv 1142 | 2025-12-31 | 27231.6415 |  | 2025-12-12
[10 empty] | 10 | 10. Site Logistics | DC Installation Complete |  | 2.5% | 4913.6 |  | JA Electrical Inv 1156 | 2026-01-31 | 16832.8754 |  | 2026-02-13
[10 empty] | 10 | 10. Site Logistics | DC Installation Complete |  | 2.5% | 4913.6 |  |  | 2026-02-28 | 3403.9638 |  | 2026-02-27
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 19654.4 |  |  | 2026-02-28 | 13615.8554 |  | 2026-03-10
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 19654.4 |  |  | 2026-02-28 | 13615.8554 |  | 2026-03-16
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 9827.2 |  |  | 2026-03-31 | 6807.9277 |  | 2026-03-16
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 9827.2 |  |  | 2026-03-31 | 6807.9277 |  | 2026-04-08
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 34004.25 | 2025-08-31 | 182012.75 | 206832.6705 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 34004.25 |  |  | 2026-03-31 | 39765.3909 | 0.00021007 | 2026-03-31 | 142343.85
11 |  | Structural sign off |  |  | 68008.5 | 2025-08-31 |  |  |  | 11 | 11. Due Dilligence | Structural sign off |  |  | 9019.6 |  | L & B consulting Inv: 1934 | 2025-09-30 | 14096.2195 |  | 2025-04-10
11 | [5 empty] | 2025-08-31 |  |  |  | 11 | 11. Due Dilligence | Site Inspection |  |  | 9620 |  | Ace Properties: Inv 3031 | 2025-09-30 | 15034.5505 |  | 2025-03-07
11 |  | Grid Study - Outside of CoCT |  |  | 80000 | 2025-08-31 |  |  |  | 11 | 11. Due Dilligence | Grid Study - Outside of CoCT |  |  | 79700 | PO4167-DSHC-20250728 - RV Approved | Okusha Engineering EE20 | 2025-09-30 | 123406.0137 |  | 2025-02-28
11 | [9 empty] | 11 | 11. Due Dilligence | Red Team |  |  | 10000 |  |  | 2026-03-31 | 14530.4957 |  | 2026-04-30
12 | BDP Commission | [5 empty] | 0 | 0 |  | 12 | 12. BDP Commission | [10 empty] | 0
12 | BDP Commission | [8 empty] | 12 | 12. BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 110470.5687 | 2025-08-31 | 429230.6344 | 487762.0846 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 130354.3043 |  |  | 2026-03-31 | 487762.0846 | 0 | 2026-04-30 | 130354.3043
13 |  | Management |  |  | 77714.2857 | 2025-08-31 |  |  |  | 13 | 13. Engineering | Management | [6 empty] | 0
13 |  | Project manager |  |  | 136000 | 2025-08-31 |  |  |  | 13 | 13. Engineering | Project manager | [6 empty] | 0
13 |  | Planner time |  |  | 52000 | 2025-08-31 |  |  |  | 13 | 13. Engineering | Planner time | [6 empty] | 0
13 |  | De Snagging |  |  | 53045.78 | 2025-08-31 |  |  |  | 13 | 13. Engineering | De Snagging | [6 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 23800 | 2025-09-05 | 23800 | 28000 |  | 14 | 14. General Expenses | Travel |  |  | 13986.75 |  | Expense Claim | 2025-09-30 | 16326.8878 | 0 | 2025-09-05 | 38589.8
14 | [5 empty] | 2025-07-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 10587.7 |  | Expense Claim | 2025-10-31 | 3732.1067 |  | 2025-11-06
14 | [5 empty] | 2025-08-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 5515.35 |  | Expense Claim | 2025-11-30 | 3279.4745 |  | 2025-12-05
14 | [5 empty] | 2025-09-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-12-31 | 0 |  | 2025-12-31
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2026-01-31 | 0 |  | 2026-02-05
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 8500 |  |  | 2026-02-28 | 4661.531 |  | 2026-03-12
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | [5 empty] | 0 | 2000000 |  | 15 | 15. Service Add On | [8 empty] | 0 |  | 465759.79
15 | [9 empty] | 15 | 15. Service Add On
15 | [5 empty] | 2025-11-30 |  |  |  | 15 | 15. Service Add On | Relocation of panels - JA Electrical |  |  | 56132.72 | PO4507-DSHC-20251201 - RV Approved | JA Electrical - Inv 1143 | 2025-12-31 |  |  | 2026-02-05
15 | [9 empty] | 15 | 15. Service Add On | Trenching - MI changed the cost back to R54437,44 (actual cost approved) |  |  | 54437.33 | PO4518-DSHC-20251203 - RV Approved | JA Electrical Inv 1156 | 2026-01-31 |  |  | 2026-02-13
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On | Supply and install cable |  |  | 95838 |  | JA Electrical Inv 1156 | 2026-01-31 |  |  | 2026-02-13
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On | Supply and Install Fiber cables |  |  | 21393.95 | PO4610-DSHC-20260205 - RV Approved |  | 2026-03-31 |  |  | 2026-03-31
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On | Supply & Install AC Cable with Kiosks |  |  | 237957.79 | PO4626-DSHC-20260217 - RV Approved |  | 2026-03-31 |  |  | 2026-03-31
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
| Panel Procurement Budget | 2857717.17 |  | 3072814.1613
| Inverter Procurement Budget | 770000 |  | 827956.9892
| Mounting Structure Budget | 1105818.21 |  | 1189051.8387
| DC Equipment Budget | 1117490.1 |  | 1201602.2581
| AC Equipment Budget | 1511034.3 |  | 1624768.0645
| Monitoring Budget | 49000 |  | 52688.172
| Optional Extras Budget | 0 |  | 0
| MV Metering Budget | 300000 |  | 322580.6452
| ADD ON | 0 |  | 0
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 340042.5 |  | 386411.9318
| DC Installer Budget | 720090 |  | 818284.0909
| In-House Expense Budget | 429230.6344 |  | 487762.0846
| Compliance Budget | 182012.75 |  | 206832.6705
| Offloading Budget | 8500 |  | 9659.0909
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 33546.6667 |  | 38121.2121
| On Site Security | 72000 |  | 81818.1818
| Roof Access Budget for Installers | 70393.8 |  | 79992.9545
| EPC Management Fee | 0 |  | 0
| ADD ON | 2000000 |  | 2000000
Expenses
| Total EE Expense Budget | 23800 |  | 28000
Note on U125: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Roedolph Venter can I please get assist with this

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 10428344.3462 | 10428344.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6013204.76 | 0 | 0 | 0 | 2225569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2189570.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6013204.76 | 6013204.76 | 6013204.76 | 6013204.76 | 8238773.76 | 8238773.76 | 8238773.76 | 8238773.76 | 8238773.76 | 8238773.76 | 8238773.76 | 8238773.76 | 8238773.76 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35
| Planned Expenditure | 9590676.1311 | 8484857.9211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3715850.6511 | 23800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4745207.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3715850.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 3739650.6511 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211 | 8484857.9211
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3715850.6511 | -3739650.6511 | -3739650.6511 | -3739650.6511 | -3739650.6511 | -3739650.6511 | -3739650.6511 | -3739650.6511 | -3739650.6511 | -3739650.6511 | -3739650.6511 | -3739650.6511 | -3739650.6511 | 2273554.1089 | 2273554.1089 | 2273554.1089 | 2273554.1089 | 4499123.1089 | -246084.1611 | -246084.1611 | -246084.1611 | -246084.1611 | -246084.1611 | -246084.1611 | -246084.1611 | -246084.1611 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289 | 1943486.4289
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 10428344.35 | 10428344.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006602.38 | 3006602.38 | 0 | 0 | 0 | 0 | 2225569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2189570.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006602.38 | 6013204.76 | 6013204.76 | 6013204.76 | 6013204.76 | 6013204.76 | 8238773.76 | 8238773.76 | 8238773.76 | 8238773.76 | 8238773.76 | 8238773.76 | 8238773.76 | 8238773.76 | 8238773.76 | 8238773.76 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35 | 10428344.35
| Actual + Planned Expenditure | 7658861.9823 | 7658861.9823 | 0 | 0 | 0 | 0 | 0 | 79700 | 9620 | 0 | 0 | 0 | 0 | 9019.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3575.5 | 0 | 0 | 55169 | 13986.75 | 0 | 0 | 0 | 0 | 0 | 192717 | 0 | -26000 | 436340.25 | 0 | 0 | 158695.92 | 5515.35 | 3263161.308 | 1618621.95 | 0 | 395550.67 | 0 | 0 | 15556.95 | 0 | -8629.78 | 379446.355 | 0 | 88888.005 | 0 | 178801.02 | 266128.93 | 0 | 297492.39 | 85150.51 | 0 | 0 | 140354.3043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 79700 | 89320 | 89320 | 89320 | 89320 | 89320 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 98339.6 | 101915.1 | 101915.1 | 101915.1 | 157084.1 | 171070.85 | 171070.85 | 171070.85 | 171070.85 | 171070.85 | 171070.85 | 363787.85 | 363787.85 | 337787.85 | 774128.1 | 774128.1 | 774128.1 | 932824.02 | 938339.37 | 4201500.678 | 5820122.628 | 5820122.628 | 6215673.298 | 6215673.298 | 6215673.298 | 6231230.248 | 6231230.248 | 6222600.468 | 6602046.823 | 6602046.823 | 6690934.828 | 6690934.828 | 6869735.848 | 7135864.778 | 7135864.778 | 7433357.168 | 7518507.678 | 7518507.678 | 7518507.678 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823 | 7658861.9823
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | -79700 | -89320 | -89320 | -89320 | -89320 | -89320 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -98339.6 | -101915.1 | -101915.1 | -101915.1 | -157084.1 | -171070.85 | -171070.85 | -171070.85 | -171070.85 | -171070.85 | -171070.85 | -363787.85 | -363787.85 | -337787.85 | -774128.1 | -774128.1 | -774128.1 | -932824.02 | 2068263.01 | 1811704.082 | 193082.132 | 193082.132 | -202468.538 | -202468.538 | 2023100.462 | 2007543.512 | 2007543.512 | 2016173.292 | 1636726.937 | 1636726.937 | 1547838.932 | 1547838.932 | 1369037.912 | 1102908.982 | 3292479.572 | 2994987.182 | 2909836.672 | 2909836.672 | 2909836.672 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677 | 2769482.3677
|  | CHECK | CHECK
| Revenue Recognition | 0.0083447 | 10428344.3378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207057.4377 | 0 | 0 | 0 | 6882663.6019 | 0 | 0 | 0 | 1024984.8349 | 0 | 0 | 0 | 0 | 746331.2715 | 0 | 0 | 0 | 226797.2638 | 0 | 0 | 0 | 358473.2863 | 0 | 0 | 0 | 0 | 982036.6418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 10428344.3378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207057.4377 | 207057.4377 | 207057.4377 | 207057.4377 | 7089721.0396 | 7089721.0396 | 7089721.0396 | 7089721.0396 | 8114705.8745 | 8114705.8745 | 8114705.8745 | 8114705.8745 | 8114705.8745 | 8861037.146 | 8861037.146 | 8861037.146 | 8861037.146 | 9087834.4098 | 9087834.4098 | 9087834.4098 | 9087834.4098 | 9446307.696 | 9446307.696 | 9446307.696 | 9446307.696 | 9446307.696 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378 | 10428344.3378

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | 2026-03-31 | Grand Total
(blank)
1. Panels |  |  | 3072814.1613 |  |  | 0 | 0 |  |  | 3072814.1613
2. Inverters |  |  | 827956.9892 |  |  | 0 |  |  |  | 827956.9892
3. Mounting Structures |  |  | 1189051.8387 | 0 |  |  | 0 | 0 |  | 1189051.8387
4. DC Equipment |  |  | 987322.518 |  | 85711.896 | 0 | 28570.632 | 42855.948 | 57141.264 | 1201602.2581
5. Monitoring |  | 38193.7663 | 14494.4017 | 0 |  | 0 |  |  |  | 52688.168
6. AC Equipment |  |  | 160352.8813 | 983356.5392 | 192423.3591 | 0 | 64141.1744 | 96211.7616 | 128282.3488 | 1624768.0645
8. Product Add On |  |  | 266785.5862 |  | 55795.0555 | 0 | 0 | 0 |  | 322580.6416
9. AC & DC installation |  |  | 301174.0057 |  | 361408.8068 | 0 | 120469.5966 | 180704.4072 | 240939.2024 | 1204696.0187
10. Site Logistics | 0 |  | 58979.1131 | 38348.8212 | 50992.1541 | 0 | 13615.8607 | 20423.7831 | 27231.7107 | 209591.4429
11. Due Dilligence |  | 152536.7836 | [5 empty] | 54295.8867 |  | 206832.6702
13. Engineering | 0 |  |  |  |  | 0 |  | 487762.0846 |  | 487762.0846
14. General Expenses |  | 16326.8878 | 3732.1067 | 3279.4745 | 0 | 0 | 0 | 4661.531 |  | 28000
15. Service Add On
12. BDP Commission
7.BESS
Grand Total | 0 | 207057.4377 | 6882663.6019 | 1024984.8349 | 746331.2715 | 0 | 226797.2638 | 886915.4021 | 453594.5259 | 10428344.3378

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | Grand Total
(blank)
1. Panels |  |  | 2653053 |  |  | 14813.8 |  |  | 2667866.8
2. Inverters |  |  | 757573.938 | [5 empty] | 757573.938
3. Mounting Structures |  |  | 339516.22 | 71394.92 |  | -51489.25 | 3737.49 |  | 363159.38
4. DC Equipment |  |  | 586316.3 |  | 50899.56 | 16966.52 | 25449.78 | 33933.04 | 713565.2
5. Monitoring |  | 58744.5 | -8100.66 | 40621.45 |  |  |  |  | 91265.29
6. AC Equipment |  |  | 57877.2 | 354929.22 | 69452.44 | 23150.88 | 34726.32 | 46301.76 | 586437.82
8. Product Add On |  |  | 232956 |  | 48720 | 10150 | 50000 |  | 341826
9. AC & DC installation |  |  | 276323.05 |  | 331587.66 | 110529.225 | 165793.835 | 221058.44 | 1105292.21
10. Site Logistics |  |  | 85136 | 60000 | 68963.1 | 19654.4 | 29481.6 | 39308.8 | 302543.9
11. Due Dilligence |  | 98339.6 |  |  |  |  | 44004.25 |  | 142343.85
13. Engineering | [6 empty] | 130354.3043 |  | 130354.3043
14. General Expenses |  | 13986.75 | 10587.7 | 5515.35 | 0 | 0 | 8500 |  | 38589.8
15. Service Add On |  |  |  |  | 56132.72 | 150275.33 |  | 21393.95 | 227802
12. BDP Commission
7.BESS
Grand Total |  | 171070.85 | 4991238.748 | 532460.94 | 625755.48 | 294050.905 | 492047.5793 | 361995.99 | 7468620.4923

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 0.20433 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.10453 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.070716 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 0.16924 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
Seshego Circle |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Seshego Circle | 0 | 0 | 0