## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | PLANNED |  | ACTUAL |  | FINANCIAL REVIEW | TIMELINE REVIEW |  | Allocated in 2024 | Budgeted | Acutal
1 | Planned Revenue | 2462259.0034 |  | 2505210.4734 |  | 2462259.0034 | Start Date | Sales | 848045.3402 | 1614213.6631 | 1657165.1331
2 | Planned Expenditure | 2105194.153 |  | 2103862.11 |  | 2040967.6575 | 2024-09-25 | COS | 730147.42 | 1301474.2175 | 1373714.69
3 | Planned Profit | 357064.8504 |  | 401348.3634 |  | 421291.3458 | End Date - PC | GP | 117897.9202 | 312739.4456 | 283450.4431
4 | Planned Margin | 14.5% |  | 16.02% |  | 17.11% | 2024-11-04
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Acceptance and Initial Deposit |  | 35% | 861790.6512 | 2024-07-18 | 004471 | 2024-07-15 | 2024-07-17
2 | Delivery of Inverters |  | 25% | 615564.7508 | 2024-10-02 | 004555 | 2024-10-02 | 2024-10-09
3 | Delivery of Panels |  | 25% | 615564.7508 | 2024-10-18 | 004576 | 2024-10-21 | 2024-11-28
4 | Practical Completion |  | 10% | 246225.9003 | 2024-11-20 | 004608 | 2024-11-14 | 2024-11-28
5 | Handover |  | 5% | 123112.9502 | 2024-12-16 | 004693 | 2025-02-26 | 2025-10-16
6 | VO - Walkways |  | 0% | 52281.12 | 2024-12-16 | 004693 | 2025-02-26 | 2025-10-16
7 | Credit Note - Walkways |  | 0% | -9329.65 |  | 004931 | 2026-01-23 | 2026-02-28
|  |  | 100% | 2505210.4734
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 876823.6657
2 | Delivery of Panels |  | 30% | 751563.142
3 | Delivery of Inverters |  | 20% | 501042.0947
4 | Practical Completion |  | 10% | 250521.0473
5 | Handover |  | 5% | 125260.5237
| Total |  | 100% | 2505210.4734
|  |  | 100% | 2505210.4734
Formulas:
PLANNED PAYMENT DATE = [PLANNED PAYMENT DATE, row above]
PAYMENT RECEIVED DATE = [TIMELINE REVIEW]+7

## Project Plan
[9 empty] | 2025-10-13 | 2025-10-13
| PROJECT PLAN | SA Metal - 22 Christiaan | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 250
| BUSINESS DEVELOPER | Peet
| PROJECT MANAGER | Lloyd
| CONTRACT VALUE | 2462259.0034
| Phase: | Compliance Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status |  | Comment
|  |  | 55 |  |  | 55 |  | 100% | 100%
1 | Project Initiation | 2024-08-14 | 37 | 2024-09-20 | 2024-08-14 | 37 | 2024-09-20 | 100% | 100%
1.1 | BD Handover | 2024-08-14 | 1 | 2024-08-15 | 2024-08-14 | 1 | 2024-08-15 | 100% | 100%
1.2 | Project Introduction | 2024-09-05 | 1 | 2024-09-06 | 2024-09-05 | 1 | 2024-09-06 | 100% | 100%
1.3 | HSE | 2024-09-05 | 15 | 2024-09-20 | 2024-09-05 | 15 | 2024-09-20 | 100% | 100%
1.4 | Installer Kick Off | 2024-09-13 | 1 | 2024-09-16 | 2024-09-13 | 1 | 2024-09-16 | 100% | 100%
1.5 | Project Review | 2024-09-12 | 1 | 2024-09-13 | 2024-09-12 | 1 | 2024-09-13 | 100% | 100%
2 | Site Establishment | 2024-09-25 | 1 | 2024-09-26 | 2024-09-25 | 1 | 2024-09-26 | 100% | 100%
2.1 | Installer on site & Roof Assessment | 2024-09-25 | 1 | 2024-09-26 | 2024-09-25 | 1 | 2024-09-26 | 100% | 100% |  | 88 | Net working Days
3 | AC Installation | 2024-09-27 | 35 | 2024-11-01 | 2024-09-27 | 35 | 2024-11-01 | 100% | 100% |  | 17.6 | Net Working Weeks
3.1 | Inverters delivered | 2024-09-25 | 1 | 2024-09-26 | 2024-09-30 | 1 | 2024-10-01 | 100% | 100% |  | 14.2045 | kW/Week Installationn Speed
3.2 | Inverters Mounted | 2024-09-26 | 1 | 2024-09-27 | 2024-10-01 | 1 | 2024-10-02 | 100% | 100%
3.3 | Solar DB lead time | 2024-09-25 | 30 | 2024-11-06 | 2024-09-25 | 30 | 2024-11-06 | 100% | 100%
3.4 | AC Works | 2024-09-26 | 10 | 2024-10-10 | 2024-10-01 | 10 | 2024-10-15 | 100% | 100%
3.5 | AC Tie - in | 2024-10-04 | 1 | 2024-10-07 | 2024-10-09 | 1 | 2024-10-10 | 100% | 100%
4 | DC Works | 2024-09-25 | 37 | 2024-11-01 | 2024-09-25 | 37 | 2024-11-01 | 100% | 100%
4.1 | Mounting Structure delivered | 2024-09-25 | 1 | 2024-09-26 | 2024-09-25 | 1 | 2024-09-26 | 100% | 100%
4.2 | Mounting Structure installation | 2024-09-25 | 8 | 2024-10-07 | 2024-09-25 | 8 | 2024-10-07 | 100% | 100%
4.3 | DC Cable delivered | 2024-09-25 | 1 | 2024-09-26 | 2024-09-25 | 1 | 2024-09-26 | 100% | 100%
4.3 | DC Stringing | 2024-11-01 | 5 | 2024-11-08 | 2024-11-01 | 5 | 2024-11-08 | 100% | 100%
5 | Module installation | 2024-10-11 | 33 | 2024-11-13 | 2024-10-11 | 33 | 2024-11-13 | 100% | 100%
5.1 | Module delivery | 2024-10-11 | 1 | 2024-10-14 | 2024-10-11 | 1 | 2024-10-14 | 100% | 100%
5.2 | Module mounting | 2024-10-11 | 15 | 2024-11-01 | 2024-10-11 | 15 | 2024-11-01 | 100% | 100%
6 | Commissioning | 2024-11-08 | 5 | 2024-11-13 | 2024-11-08 | 5 | 2024-11-13 | 100% | 100%
6.1 | Commissioning | 2024-11-13 | 1 | 2024-11-14 | 2024-11-13 | 1 | 2024-11-14 | 100% | 100%
6.2 | Practical Completion | 2024-11-13 | 4 | 2024-11-19 | 2024-11-13 | 4 | 2024-11-19 | 100% | 100%
7 | QA Inspections | 2024-11-13 | 28 | 2024-12-11 | 2024-11-13 | 28 | 2024-12-11 | 100% | 100%
7.1 | Red-Team Inspection | 2024-11-19 | 3 | 2024-11-22 | 2024-12-06 | 3 | 2024-12-11 | 100% | 100%
8 | Project Closure | 2024-12-08 | 52 | 2025-01-29 | 2024-12-08 | 52 | 2025-01-29 | 100% | 100%
8.1 | Equipment serial numbers | 2024-11-22 | 1 | 2024-11-25 | 2024-12-11 | 1 | 2024-12-12 | 100% | 100%
8.2 | Snags completion | 2024-11-25 | 5 | 2024-12-02 | 2024-12-12 | 28 | 2025-01-24 | 100% | 100%
8.3 | System Performance Monitoring | 2024-12-02 | 5 | 2024-12-09 | 2024-12-20 | 10 | 2025-01-07 | 100% | 100%
8.4 | Handover documentation | 2024-12-02 | 5 | 2024-12-09 | 2024-12-20 | 20 | 2025-01-21 | 100% | 100%
8.5 | Handover to Client | 2024-12-09 | 1 | 2024-12-10 | 2025-02-20 | 1 | 2025-08-29 | 100% | 100%
8.6 | Handover to Matriarch | 2024-11-21 | 1 | 2024-11-22 | 2025-04-29 | 1 | 2025-04-30 | 100% | 100%

## Data (hidden)
Public holidays |  | Drop down list
2024-01-01 | New Years Day | Approved
2024-03-21 | Human Rights day | Pending
2024-03-29 | Good Friday | Declined
2024-04-01 | Family Day | Abanded
2024-05-01 | Workers day
2024-06-17 | Youth Day Holiday
2024-08-09 | Womens Day
2024-09-24 | Heritage Day
2024-12-16 | Day of Reconciliation
2024-12-25 | Christmas Day
2024-12-26 | Day of Goodwill |  | Manual dates

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  |  | COSTED |  | PLANNED |  | ACTUAL | Difference from costed | Difference from planned
| EXPENDITURE |  | 2105194.153 |  | 2040967.6575 |  | 2103862.11 | 1332.043 | -62894.4525
| No. | Item | Costed Expenditure |  | Planned Expenditure |  | Actual Expenditure | Saving / Overrun | Saving / Overrun | Comments on variations from planned expenditure
| 1 | Panels | 690973.733 |  | 736862.5 |  | 647765.5 | 43208.233 | 89097
| 2 | Inverters | 157796 |  | 151514 |  | 138845.23 | 18950.77 | 12668.77
| 3 | Mounting Structures | 99864 |  | 58349.4 |  | 169924.22 | -70060.22 | -111574.82
| 4 | DC Equipment | 237064.3 |  | 242250 |  | 242250 | -5185.7 | 0
| 5 | Monitoring | 49000 |  | 80720.5 |  | 71452.01 | -22452.01 | 9268.49
| 6 | AC Equipment | 304429.82 |  | 212432 |  | 212863.6 | 91566.22 | -431.6
| 7 | Battery Systems | 0 |  | 0 |  | 0 | 0 | 0
| 8 | Product Add On | 0 |  | 0 |  | 158729.52 | -158729.52 | -158729.52
| 9 | AC & DC Installation | 208050 |  | 175013.8 |  | 175013.8 | 33036.2 | 0
| 10 | Site Logistics | 38356.3 |  | 122767 |  | 107767 | -69410.7 | 15000
| 11 | Due Dilligence | 89000 |  | 23020 |  | 14174.76 | 74825.24 | 8845.24
| 12 | BDP Commission | 63011.44 |  | 63043.34 |  | 63043.34 | -31.9 | 0
| 13 | Engineering | 163448.56 |  | 170795.1175 |  | 62400 | 101048.56 | 108395.1175 | RV: Matriarch defects percentage 1.25%
| 14 | General Expenses | 4200 |  | 4200 |  | 7385.64 | -3185.64 | -3185.64
| 15 | Service Add On | 0 |  | 0 |  | 32247.49 | -32247.49 | -32247.49
|  | check: | 0 | #REF! | 0 | #REF! | 0
Copy amounts in column H and paste as values at Project review.

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 2105194.153 | 2506224.1235 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY |  |  |  |  | 2103862.11
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | Project Related date | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS | PO NUMBER | COMMENTS
1 | Panels | Longi 570W - Costing Sheet | 438 | 1531.9035 | 670973.733 | 2024-12-10 | 690973.733 | 842650.8939 |  | 1 | 1. Panels | Canadian Solar 555W - Deposit - Herholdts | 450 | 1415.25 | 318431.25 | Herholdts Inv: INV875402 | 2024-07-31 | 396426.7151 | -0.00044533 | 2024-09-27 | 647765.5 | PO3244-SAM-20240719 - RV Approved |  | 19
1 |  | Jinko Solar 575W | [7 empty] | 1 | 1. Panels |  |  |  | 318431.25 | Herholdts Inv: INV875402 | 2024-07-31 | 396426.7151 |  | 2024-10-31 |  |  |  | BUDGET | Installer Allocation
1 | [9 empty] | 1 | 1. Panels | Storage handling Fee |  |  | 1300 | Supply Chain: Inv SCO04502 | 2024-10-31 | 1691.1153 |  | 2024-11-29 |  |  |  | AC Equipment | 304429.82
1 |  | Delivery |  |  | 20000 | 2024-12-10 |  |  |  | 1 | 1. Panels | Delivery |  |  | 8550 | Supply Chain: Inv SCO04533 | 2024-10-31 | 11122.3354 |  | 2024-11-29 |  |  |  | DC Equipment | 116936.3
1 | [9 empty] | 1 | 1. Panels | Storage |  |  | 1053 | Supply Chain: Inv SCO04502 | 2024-10-31 | 1369.8034 |  | 2024-11-29 |  |  |  | AC Labour | 145635
1 | [9 empty] | 1 | 1. Panels | Delivery and storage budget |  |  |  |  | 2024-11-30 | 35614.21 | [5 empty] | DC Labour | 62415
[24 empty] | Offloading | 8500
2 | Inverters | Huawei 100KTL | 2 | 78898 | 157796 | 2024-10-25 | 157796 | 192434.1463 |  | 2 | 2. Inverters | Huawei 100KTL | 2 | 68870 | 137740 | Kathea Inv518635 | 2024-09-30 | 190902.34 | 0 | 2024-10-30 | 138845.23 |  | MI: Kathea quote | Telehandler | 0
2 | [9 empty] | 2 | 2. Inverters | [6 empty] | 0 | [5 empty] | Storage | 0
2 | [9 empty] | 2 | 2. Inverters | Delivery |  |  | 1105.23 | Kathea Inv518635 | 2024-09-30 | 1531.8063 |  | 2024-10-30 |  |  |  | Scaffolding | 29856.3
2 | [9 empty] | 2 | 2. Inverters | [6 empty] | 0 | [5 empty] | Other | 0
[24 empty] | Total | 667772.42
3 | Mounting Structures | KlipLok Roof | 250000 | 0.45 | 99864 | 2024-10-25 | 99864 | 121785.3659 |  | 3 | 3. Mounting Structures | MS | 1 | 56499.4 | 56499.4 | Schletter Inv0891 | 2024-09-30 | 117065.6833 | 0 | 2024-09-23 | 169924.22 | PO3364-SAM22-20240918 - RV Approved |  | Less 15% | 567606.557 |  |  | 62178.86
3 | [9 empty] | 3 | 3. Mounting Structures |  |  |  | -56499.4 | Schletter Inv0891 | 2024-12-31 | 0 |  | 2024-12-31 |  |  |  | R/Wp | 2.2704
[10 empty] | 3 | 3. Mounting Structures |  |  |  | 44229.04 | Schletter Inv0891 | 2024-12-31 |  |  | 2024-12-31
3 | [9 empty] | 3 | 3. Mounting Structures | Delivery |  |  | 1850 | Schletter Inv0893 | 2024-09-30 | 3833.1648 |  | 2024-09-23
[10 empty] | 3 | 3. Mounting Structures | Seam Clamps |  |  | 155413 | Schletter Inv: INV1051 | 2024-11-30 | 0 |  | 2024-12-19
[10 empty] | 3 | 3. Mounting Structures | Seam Clamp Returned |  |  | -31995.68 | Schletter Credit: CRN0160 | 2024-11-30 |  |  | 2024-12-19
3 | [9 empty] | 3 | 3. Mounting Structures |  |  |  | 427.86 | DSV Inv: 180099596 | 2024-10-31 | 886.5178 |  | 2024-11-29 |  |  |  | ACTUAL - Cosmic Sun | Installer Price |  | ACTUAL - Thula Moya | Installer Price |  | ACTUAL - CornerStone | Installer Price
[24 empty] | AC Equipment | 79400 |  | AC Equipment | 146732 |  | AC Equipment | 62386.27 | *Removed 6 Comms Metering R25976,34
4 | DC Equipment | DC Cable | 6133 | 16 | 98128 | 2024-10-25 | 237064.3 | 289102.8049 |  | 4 | 4. DC Equipment | DC Cable | 8000 | 13.5 | 108000 | Herholdts Inv: INV922149 | 2024-10-31 | 128887.9378 | 0 | 2024-10-31 | 242250 | PO3315-MUL-20240823 - RV Approved | MI: Herholdts quote | DC Equipment | 84262.4 |  | DC Equipment | 134250 |  | DC Equipment | 145954.74
4 |  | DC Surge Arrestor | 4 | 5500 | 22000 | 2024-11-10 |  |  |  | 4 | 4. DC Equipment | Delivery |  |  | 0 |  |  | 0 | [5 empty] | AC Labour | 62500 |  | AC Labour | 62504 |  | AC Labour | 15154.29
4 |  | DC Cable Tray | 220 | 152 | 33440 | 2024-11-10 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 134250 | 10% | 13425 | Thula Moya Inv04436 | 2024-09-30 | 16021.4867 |  | 2024-09-25 |  | PO3367-SAM22-20240924 - RV Approved |  | DC Labour | 149000 | 0.846 | DC Labour | 112509.8 | 0.70006 | DC Labour | 191994.01 | 0.82859
4 |  | Earth Cable | 6133 | 13.5 | 82795.5 | 2024-10-25 |  |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 20137.5 | Thula Moya Inv04439 | 2024-09-30 | 24032.2301 |  | 2024-10-10 |  |  |  | Offloading | 8500 |  | Site Logistics | 47669 |  | Site Logistics | 92157
4 |  | Earth clamp | 43.8 | 16 | 700.8 | 2024-10-11 |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 26850 | Thula Moya IN04473 | 2024-10-31 | 32042.9734 |  | 2024-10-31 |  |  |  | Roof Access | 15000 |  | Sundries | 14986 |  | HSE | 7027.8
4 | [9 empty] | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 33562.5 | Thula Moya IN04474 | 2024-10-31 | 40053.7168 |  | 2024-10-31 |  |  |  | Container | 8500 |  | Accomodation | 45112 |  | COC | 3978
4 | [9 empty] | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 13425 | Thula Moya IN04475 | 2024-10-31 | 16021.4867 |  | 2024-11-14 |  |  |  | HSE | 4500 |  | Scaffolding | 0 |  | Travel | 17801.55
4 | [9 empty] | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 13425 | Thula Moya IN04476 | 2024-10-31 | 16021.4867 |  | 2024-12-05 |  |  |  | Other | 0 |  | Other | 0 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 6712.5 | Thula Moya IN04598 | 2025-01-31 | 8010.7434 |  | 2025-02-13 |  |  |  | Other | 0 |  | Other | 0 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 6712.5 | Thula Moya IN04599 | 2025-01-31 | 8010.7434 |  | 2025-03-06 |  |  |  | Other | 0 |  | Other | 0 |  | Other | 0
[24 empty] | Total | 411662.4 |  | Total | 563762.8 |  | Total | 536453.66
5 | Monitoring | Smartlogger 3000 | 1 | 26000 | 26000 | 2024-10-25 | 49000 | 59756.0976 |  | 5 | 5. Monitoring | Smartlogger 3000 | 1 | 8000 | 8000 | Solarworld SASIV-24-00517 | 2024-08-31 | 5922.2723 | 0.00081833 | 2024-09-30 | 71452.01 |  | MI: Kathea quote | R/Wp | 1.6466 |  | R/Wp | 2.2551 |  | R/Wp | 2.1458
5 |  | Comms DB |  |  | 8000 | 2024-10-25 |  |  |  | 5 | 5. Monitoring | CTs |  |  | 13970.5 | AccuEnergy ASAI-003743 | 2024-08-31 | 10342.1381 |  | 2024-09-30
5 |  | Revenue Grade Meter | 1 | 15000 | 15000 | 2024-11-22 |  |  |  | 5 | 5. Monitoring | Revenue Grade Meter | 1 | 11169 | 11169 | MATRIARCH - INV-3278 | 2024-11-30 | 11797.2369 |  | 2024-11-30
5 | [9 empty] | 5 | 5. Monitoring | SCADA |  |  | 35750 | Rubicon INVWCRE-0060133 | 2024-08-31 | 26465.1543 |  | 2024-09-27
5 | [9 empty] | 5 | 5. Monitoring | Frontline Comms Equipment |  |  | 2562.51 | Frontline Electrical: INV697940 | 2024-10-31 | 5229.2951 |  | 2024-10-10 |  | PO3387-SAM-20241007 - RV Approved | PO split across the portfolio
5 | [9 empty] | 5 | 5. Monitoring | [6 empty] | 0
6 | AC Equipment | [5 empty] | 304429.82 | 371255.8749 |  | 6 | 6. AC Equipment | [6 empty] | 0 | -0.002759 |  | 212863.6
[10 empty] | 1 | 6. AC Equipment | AC & Comms Board - Deposit | 40% | 65700 | 26280 | Cosmic Sun CS_SAMPVDB_001 | 2024-09-30 | 45928.2375 |  | 2024-09-27 |  | PO3375-SAMPort-20240930 - RV Approved
[10 empty] | 2 | 6. AC Equipment | AC & Comms Board - Balance | 60% |  | 39420 | Cosmic Sun CS_SAMPVDB_002 | 2024-10-31 | 68752.5091 |  | 2024-10-31
[10 empty] | 3 | 6. AC Equipment | Copper Stub Fabrication |  |  | 0 |  |  | 0 |  |  |  | PO3845-SAM14B-20250430 - RV Approved
[10 empty] | 4 | 6. AC Equipment | AC Cable |  |  | 432.1 | Gerhard Exp Claim | 2025-05-31 | 139.85 |  | 2025-06-09
[10 empty] | 5 | 6. AC Equipment | [6 empty] | 0
6 |  | Project Kick Off |  | 10% | 30442.982 | 2024-12-09 |  |  |  | 6 | 6. AC Equipment | Project Kick Off | 146732 | 10% | 14673.2 | Thula Moya Inv04436 | 2024-09-30 | 25643.6155 |  | 2024-09-25 |  | PO3367-SAM22-20240924 - RV Approved
6 | 304429.82 | Site Establishment |  | 15% | 45664.473 | 2024-09-25 |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 22009.3 | Thula Moya Inv04439 | 2024-09-30 | 38464.5494 |  | 2024-10-10
6 |  | AC Installation Complete |  | 20% | 60885.964 | 2024-11-01 |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 29346.4 | Thula Moya IN04473 | 2024-10-31 | 51287.231 |  | 2024-10-31
6 |  | DC Installation Complete |  | 25% | 76107.455 | 2024-11-01 |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 36683 | Thula Moya IN04474 | 2024-10-31 | 64109.0387 |  | 2024-10-31
6 |  | Commissioning Complete |  | 10% | 30442.982 | 2024-11-13 |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 14673.2 | Thula Moya IN04475 | 2024-10-31 | 25643.6155 |  | 2024-11-14
6 |  | Site De-establisment |  | 10% | 30442.982 | 2024-12-02 |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 14673.2 | Thula Moya IN04476 | 2024-10-31 | 25643.6155 |  | 2024-12-05
6 |  | Handover Document Complete |  | 5% | 15221.491 | 2024-12-09 |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 7336.6 | Thula Moya IN04598 | 2025-01-31 | 12821.8077 |  | 2025-02-13
6 |  | End of Defects Period |  | 5% | 15221.491 | 2025-01-08 |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 7336.6 | Thula Moya IN04599 | 2025-01-31 | 12821.8077 |  | 2025-03-06
7 | Battery Systems | [5 empty] | 0 | 0 |  | 7 | Battery Systems | [7 empty] | 0 |  | 0
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
8 | Product Add On | [5 empty] | 0 | 43965.12 |  | 8 | 8. Product Add On | Walkways transport |  |  | 4025 | Onvlee Engineering:Inv 01048652 | 2024-10-31 | 0 | 0 | 2024-10-10 | 158729.52
8 | [9 empty] | 8 | 8. Product Add On | Mounting Structure for Walkways |  |  | 4244.32 | Schletter INV0951 | 2024-10-31 | 0 |  | 2024-11-29 |  | PO3389-SAM-20241008 - RV Approved
8 | [9 empty] | 8 | 8. Product Add On | Walkways |  |  | 35695.8 | Onvlee Engineering:Inv 01048652 | 2024-10-31 | 0 |  | 2024-10-10 |  | PO3390-SAM-20241008 - RV Approved
[10 empty] | 8 | 8. Product Add On | [5 empty] | 2024-11-30 | 43965.12 |  | 2024-11-30
[10 empty] | 8 | 8. Product Add On | Installation of walkways |  |  | 8316 | Thula Moya IN04600 | 2025-01-31 |  |  | 2025-07-31
8 | [9 empty] | 8 | 8. Product Add On | Manufacture Cages Housing Inverters & DB |  |  | 72608.7 | Thula Moya Inv IN04471 | 2024-10-31 | 0 |  | 2024-10-31
[10 empty] | 8 | 8. Product Add On | Additional walkways |  |  | 9538.74 | Onvlee Engineering ONV1485 | 2025-08-31 |  |  | 2025-08-21
8 | [9 empty] | 8 | 8. Product Add On | Supply and install Tie in Breaker - Thula Moya |  |  | 24300.96 | Thula Moya IN04486 | 2024-10-31 | 0 |  | 2024-10-31 |  | PO3434-SAM-20241029 - RV Approved
Only services to be capture below, products above
9 | AC & DC Installation | Project Kick Off |  | 10% | 20805 | 2024-09-18 | 208050 | 244764.7059 |  | 9 | 9. AC & DC installation | Project Kick Off | 175013.8 | 10% | 17501.38 | Thula Moya Inv04436 | 2024-09-30 | 24476.4706 | 0 | 2024-09-25 | 175013.8 | PO3367-SAM22-20240924 - RV Approved
9 | 62415 | Site Establishment |  | 15% | 31207.5 | 2024-09-25 |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 26252.07 | Thula Moya Inv04439 | 2024-09-30 | 36714.7059 |  | 2024-10-10
9 | 145635 | AC Installation Complete |  | 20% | 41610 | 2024-11-01 |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 35002.76 | Thula Moya IN04473 | 2024-10-31 | 48952.9412 |  | 2024-10-31
9 |  | DC Installation Complete |  | 25% | 52012.5 | 2024-11-01 |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 43753.45 | Thula Moya IN04474 | 2024-10-31 | 61191.1765 |  | 2024-10-31
9 |  | Commissioning Complete |  | 10% | 20805 | 2024-11-13 |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 17501.38 | Thula Moya IN04475 | 2024-10-31 | 24476.4706 |  | 2024-11-14
9 |  | Site De-establisment |  | 10% | 20805 | 2024-12-02 |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 17501.38 | Thula Moya IN04476 | 2024-10-31 | 24476.4706 |  | 2024-12-05
9 |  | Handover Document Complete |  | 5% | 10402.5 | 2024-12-09 |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 8750.69 | Thula Moya IN04598 | 2025-01-31 | 12238.2353 |  | 2025-02-13
9 |  | End of Defects Period |  | 5% | 10402.5 | 2025-01-08 |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 8750.69 | Thula Moya IN04599 | 2025-01-31 | 12238.2353 |  | 2025-03-06
10 | Site Logistics | [5 empty] | 38356.3 | 45125.0588 |  | 10 | 10. Site Logistics | Security | [5 empty] | 0 | -0.0049434 |  | 107767
[10 empty] | 10 | 10. Site Logistics | [6 empty] | 0
[10 empty] | 10 | 10. Site Logistics | Project Kick Off | 107767 | 10% | 10776.7 | Thula Moya Inv04436 | 2024-09-30 | 3961.1559 |  | 2024-09-25 |  | PO3367-SAM22-20240924 - RV Approved
[10 empty] | 10 | 10. Site Logistics | Site Establishment |  | 15% | 16165.05 | Thula Moya Inv04439 | 2024-09-30 | 5941.7338 |  | 2024-10-10
[10 empty] | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 21553.4 | Thula Moya IN04473 | 2024-10-31 | 10403.3918 |  | 2024-10-31
[10 empty] | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 26941.75 | Thula Moya IN04474 | 2024-10-31 | 11281.2647 |  | 2024-10-31
[10 empty] | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 10776.7 | Thula Moya IN04475 | 2024-10-31 | 4512.5059 |  | 2024-11-14
[10 empty] | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 10776.7 | Thula Moya IN04476 | 2024-10-31 | 4512.5059 |  | 2024-12-05
[10 empty] | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 5388.35 | Thula Moya IN04598 | 2025-01-31 | 2256.2529 |  | 2025-02-13
[10 empty] | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 5388.35 | Thula Moya IN04599 | 2025-01-31 | 2256.2529 |  | 2025-03-06
10 |  | Offloading |  |  | 8500 | 2024-11-13 |  |  |  | 10 | 10. Site Logistics | [6 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [6 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [6 empty] | 0
10 |  | Scaffolding |  |  | 29856.3 | 2024-11-13 |  |  |  | 10 | 10. Site Logistics | [6 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2024-11-21 | 89000 | 104705.8824 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 5654.76 | Sun Spot Inv E005 | 2024-11-30 | 48923.0275 | -0.0014127 | 2025-01-16 | 14174.76
11 |  | Structural sign off |  |  | 18000 | 2024-09-25 |  |  |  | 11 | 11. Due Dilligence | Structural sign off |  |  | 2520 | L&B Consulting Inv1742 | 2024-08-31 | 11462.1557 |  | 2024-09-02
11 |  | SCADA - COCT |  |  | 60000 | 2024-10-25 |  |  |  | 11 | 11. Due Dilligence | [6 empty] | 0
11 | [9 empty] | 11 | 11. Due Dilligence | [6 empty] | 0
11 | [9 empty] | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 | MATRIARCH - INV-3413 | 2024-11-30 | 44320.7006 |  | 2024-11-30
12 | BDP Commission | Referral Fee |  |  | 63011.44 | 2024-12-10 | 63011.44 | 0 |  | 12 | BDP Commission | Referral Fee |  |  | 31521.67 | Green Co Inv: 0000518 | 2024-08-31 |  |  | 2024-09-02 | 63043.34
[10 empty] | 12 | BDP Commission | Referral Fee |  |  | 31521.67 | Green Co Inv: INV0000527 | 2024-11-30 |  |  | 2024-12-12
12 | BDP Commission | [8 empty] | 12 | BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 23431.68 | 2024-12-23 | 163448.56 | 185736.9965 |  | 13 | 13. Engineering | Matriarch Defects Period |  |  | 30778.2375 | MATRIARCH - INV-3414 | 2024-11-30 | 185736.9965 | 0 | 2024-11-30 | 62400
13 |  | Management |  |  | 19200 | 2024-12-23 |  |  |  | 13 | 13. Engineering | Performance Guarantee |  |  | 62400 | Matriarch - INV-5021 | 2025-08-31 |  |  | 2025-08-31
13 |  | Project manager |  |  | 65280 | 2024-12-23 |  |  |  | 13 | 13. Engineering | Matriarch Defects Period |  |  | -30778.2375 | Matriarch - CN-5022 | 2025-08-31 |  |  | 2025-08-31
13 |  | Planner time |  |  | 24960 | 2024-12-23 |  |  |  | 13 | 13. Engineering
13 |  | De Snagging |  |  | 30576.88 | 2024-12-23 |  |  |  | 13 | 13. Engineering
13 | [9 empty] | 13 | 13. Engineering
13 | [9 empty] | 13 | 13. Engineering
14 | General Expenses | Car travel to site |  |  | 4200 | 2024-12-23 | 4200 | 4941.1765 |  | 14 | 14. General Expenses | Car travel to site |  |  | 1522.75 | Expense Claim | 2024-08-31 | 1000.1896 | -0.0047921 | 2024-09-05 | 7385.64
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 1570.97 | Expense Claim | 2024-09-30 | 1154.7593 |  | 2024-10-04
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 1671 | Expense Claim | 2024-10-31 | 1393.1129 |  | 2024-11-07
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 0 | Expense Claim | 2024-11-30 | 0 |  | 2024-12-07
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 1109.72 | Expense Claim | 2025-01-31 | 654.7688 |  | 2025-02-07
[10 empty] | 14 | 14. General Expenses |  |  |  | 423.22 | Expense Claim | 2025-02-28 | 697.4606 |  | 2025-03-06
[10 empty] | 14 | 14. General Expenses |  |  |  | 1087.98 | Expense Claim | 2025-04-30 |  |  | 2025-05-08
14 | [9 empty] | 14 | 14. General Expenses
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | [7 empty] | 0 |  | 32247.49
15 | [9 empty] | 15 | 15. Service Add On | Defect Correction |  |  | 32247.49 | Cosmic Sun Inv: CS_SAM22_001 | 2025-05-31 |  |  | 2025-05-15 |  | PO3870-SAM22-202505 - RV Approved | We will recover the cost from Thula Moya
15 | [9 empty] | 15 | 15. Service Add On | Roof remedial work |  |  | 9731.71 | Thula Moya - IN04750 | 2025-07-31 |  |  | 2026-01-31 |  |  | TM to provide CN
15 | [9 empty] | 15 | 15. Service Add On |  |  |  | -9731.71 | Thula Moya - IC200104 | 2026-01-31 |  |  | 2026-01-31
2506183.247
Note on W32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs and @Thami Cambalele please take a look as this is marked off as paid but the invoice is showing as outstanding on QB Reply: @Tasneema van Harte,this was paid on 14 Nov, however it seems it was paid from Matriach?
Note on W33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Mizelda Isaacs and @Thami Cambalele please take a look at my comment for DC complte, same situation
Note on R129: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs and @Roedolph Venter they need to provide us with a creditnote please
Note on R130: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Roedolph Venter and @Mizelda Isaacs can we please finalize what is due to them

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2024-07-15 to 2026-10-05
PLANNED |  | CHECK | CHECK
| Planned Revenue | 2462259.0034 | 2514540.1234 | 861790.6512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 615564.7508 | 0 | 615564.7508 | 0 | 0 | 0 | 0 | 246225.9003 | 0 | 0 | 0 | 175394.0702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 1477355.402 | 1477355.402 | 2092920.1529 | 2092920.1529 | 2092920.1529 | 2092920.1529 | 2092920.1529 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234
| Planned Expenditure | 2105194.153 | 2105194.153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20805 | 94871.973 | 0 | 700.8 | 0 | 532583.5 | 230615.919 | 55440 | 89604.282 | 26000 | 0 | 51247.982 | 810052.146 | 0 | 167648.56 | 0 | 25623.991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20805 | 115676.973 | 115676.973 | 116377.773 | 116377.773 | 648961.273 | 879577.192 | 935017.192 | 1024621.474 | 1050621.474 | 1050621.474 | 1101869.456 | 1911921.602 | 1911921.602 | 2079570.162 | 2079570.162 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153 | 2105194.153
| PLANNED CashFlow |  |  | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 840985.6512 | 746113.6782 | 1361678.429 | 1360977.629 | 1976542.3799 | 1443958.8799 | 1213342.9609 | 1157902.9609 | 1068298.6789 | 1288524.5792 | 1288524.5792 | 1237276.5972 | 427224.4512 | 602618.5214 | 434969.9614 | 434969.9614 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704 | 409345.9704
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 2505210.4734 | 2505210.4734 | 861790.6512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 615564.7508 | 0 | 0 | 0 | 0 | 0 | 0 | 861790.6512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175394.0702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9329.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 1477355.402 | 1477355.402 | 1477355.402 | 1477355.402 | 1477355.402 | 1477355.402 | 1477355.402 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2339146.0532 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2514540.1234 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734 | 2505210.4734
| Actual + Planned Expenditure | 2103862.11 | 2103862.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35564.42 | 0 | 0 | 495186.93 | 23541.47 | 126847.23 | 0 | 0 | 955299.4 | 1671 | 56376.28 | 0 | 63522.4175 | 56376.28 | 31521.67 | 123417.32 | 0 | -12270.36 | 0 | 5654.76 | 0 | 0 | 1109.72 | 28188.14 | 0 | 0 | 28611.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1087.98 | 32247.49 | 0 | 0 | 0 | 432.1 | 0 | 0 | 0 | 0 | 0 | 0 | 8316 | 0 | 0 | 9538.74 | 31621.7625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35564.42 | 35564.42 | 35564.42 | 530751.35 | 554292.82 | 681140.05 | 681140.05 | 681140.05 | 1636439.45 | 1638110.45 | 1694486.73 | 1694486.73 | 1758009.1475 | 1814385.4275 | 1845907.0975 | 1969324.4175 | 1969324.4175 | 1957054.0575 | 1957054.0575 | 1962708.8175 | 1962708.8175 | 1962708.8175 | 1963818.5375 | 1992006.6775 | 1992006.6775 | 1992006.6775 | 2020618.0375 | 2020618.0375 | 2020618.0375 | 2020618.0375 | 2020618.0375 | 2020618.0375 | 2020618.0375 | 2020618.0375 | 2020618.0375 | 2021706.0175 | 2053953.5075 | 2053953.5075 | 2053953.5075 | 2053953.5075 | 2054385.6075 | 2054385.6075 | 2054385.6075 | 2054385.6075 | 2054385.6075 | 2054385.6075 | 2054385.6075 | 2062701.6075 | 2062701.6075 | 2062701.6075 | 2072240.3475 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11 | 2103862.11
| ACTUAL CashFlow |  |  | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 861790.6512 | 826226.2312 | 826226.2312 | 826226.2312 | 331039.3012 | 307497.8312 | 796215.352 | 796215.352 | 796215.352 | -159084.048 | -160755.048 | -217131.328 | -217131.328 | 581136.9057 | 524760.6257 | 493238.9557 | 369821.6357 | 369821.6357 | 382091.9957 | 382091.9957 | 376437.2357 | 376437.2357 | 376437.2357 | 375327.5157 | 347139.3757 | 347139.3757 | 347139.3757 | 318528.0157 | 318528.0157 | 318528.0157 | 318528.0157 | 318528.0157 | 318528.0157 | 318528.0157 | 318528.0157 | 318528.0157 | 317440.0357 | 285192.5457 | 285192.5457 | 285192.5457 | 285192.5457 | 284760.4457 | 284760.4457 | 284760.4457 | 284760.4457 | 284760.4457 | 284760.4457 | 284760.4457 | 276444.4457 | 276444.4457 | 276444.4457 | 266905.7057 | 235283.9432 | 235283.9432 | 235283.9432 | 235283.9432 | 235283.9432 | 235283.9432 | 235283.9432 | 410678.0134 | 410678.0134 | 410678.0134 | 410678.0134 | 410678.0134 | 410678.0134 | 410678.0134 | 410678.0134 | 410678.0134 | 410678.0134 | 410678.0134 | 410678.0134 | 410678.0134 | 410678.0134 | 410678.0134 | 410678.0134 | 410678.0134 | 410678.0134 | 410678.0134 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634 | 401348.3634
|  | CHECK | CHECK
| Revenue Recognition | -43924.2437 | 2506183.247 | 0 | 0 | 792853.4302 | 0 | 0 | 0 | 55191.91 | 0 | 0 | 0 | 0 | 535671.939 | 0 | 0 | 0 | 679962.5182 | 0 | 0 | 0 | 370357.2915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71308.8475 | 0 | 0 | 0 | 697.4606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 2506183.247 | 0 | 0 | 792853.4302 | 792853.4302 | 792853.4302 | 792853.4302 | 848045.3402 | 848045.3402 | 848045.3402 | 848045.3402 | 848045.3402 | 1383717.2793 | 1383717.2793 | 1383717.2793 | 1383717.2793 | 2063679.7974 | 2063679.7974 | 2063679.7974 | 2063679.7974 | 2434037.0889 | 2434037.0889 | 2434037.0889 | 2434037.0889 | 2434037.0889 | 2434037.0889 | 2434037.0889 | 2434037.0889 | 2434037.0889 | 2505345.9365 | 2505345.9365 | 2505345.9365 | 2505345.9365 | 2506043.397 | 2506043.397 | 2506043.397 | 2506043.397 | 2506043.397 | 2506043.397 | 2506043.397 | 2506043.397 | 2506043.397 | 2506043.397 | 2506043.397 | 2506043.397 | 2506043.397 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247 | 2506183.247
| Installer Expenditure |  | 455995.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45599.58 | 0 | 68398.87 | 0 | 0 | 205198.11 | 0 | 45599.58 | 0 | 0 | 45599.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22799.79 | 0 | 0 | 22799.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Installer Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45599.58 | 45599.58 | 113998.45 | 113998.45 | 113998.45 | 319196.56 | 319196.56 | 364796.14 | 364796.14 | 364796.14 | 410395.72 | 410395.72 | 410395.72 | 410395.72 | 410395.72 | 410395.72 | 410395.72 | 410395.72 | 410395.72 | 410395.72 | 433195.51 | 433195.51 | 433195.51 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3 | 455995.3

## Finance - Revenue
REVENUE RECOGNITION AMOUNT | (All)
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels |  | (blank) | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-05-31 | 2025-04-30 | 2025-07-31 | 2025-08-31 | Grand Total
(blank)
Battery Systems
BDP Commission
1. Panels |  |  | 792853.4302 |  |  | 14183.2541 | 35614.21 | [7 empty] | 842650.8943 | 49797.4641
2. Inverters | 0 |  |  |  | 192434.1463 | [9 empty] | 192434.1463 | 192434.1463
3. Mounting Structures |  |  |  |  | 120898.8481 | 886.5178 | 0 | 0 | [6 empty] | 121785.3659 | 121785.3659
4. DC Equipment |  | 0 |  |  | 40053.7168 | 233027.6014 |  |  | 16021.4867 | [5 empty] | 289102.8049 | 289102.8049
5. Monitoring | 0 |  |  | 42729.5647 |  | 5229.2951 | 11797.2369 | [7 empty] | 59756.0967 | 17026.532
6. AC Equipment | 0 | 0 |  |  | 110036.4024 | 235436.0097 |  |  | 25643.6155 |  | 139.85 |  |  |  | 371255.8777 | 371255.8777
8. Product Add On | [5 empty] | 0 | 43965.12 | [7 empty] | 43965.12 | 43965.12
9. AC & DC installation |  |  |  |  | 61191.1765 | 159097.0588 |  |  | 24476.4706 | [5 empty] | 244764.7059 | 244764.7059
10. Site Logistics | 0 | 0 |  |  | 9902.8896 | 30709.6682 |  |  | 4512.5059 | [5 empty] | 45125.0638 | 45125.0638
11. Due Dilligence | 0 |  |  | 11462.1557 |  |  | 93243.7281 | [7 empty] | 104705.8838 | 93243.7281
13. Engineering | [6 empty] | 185736.9965 | [7 empty] | 185736.9965 | 185736.9965
14. General Expenses |  |  |  | 1000.1896 | 1154.7593 | 1393.1129 | 0 |  | 654.7688 | 697.4606 |  |  |  |  | 4900.2913 | 3900.1016
15. Service Add On | [15 empty] | 0
Grand Total | 0 | 0 | 792853.4302 | 55191.91 | 535671.939 | 679962.5182 | 370357.2915 | 0 | 71308.8475 | 697.4606 | 139.85 |  |  |  | 2506183.247 | 1658137.9068
848045.3402

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-04-30 | 2025-05-31 | 2025-07-31 | 2025-08-31 | 2026-01-31 | Grand Total
Battery Systems
BDP Commission |  | 2024-08-31: 31521.67; 2024-11-30: 31521.67 | 63043.34
(blank)
1. Panels |  | 2024-07-31: 636862.5; 2024-10-31: 10903 | 647765.5
2. Inverters |  | 2024-09-30: 138845.23 | 138845.23
3. Mounting Structures |  | 2024-09-30: 58349.4; 2024-10-31: 427.86; 2024-11-30: 123417.32; 2024-12-31: -12270.36 | 169924.22
4. DC Equipment | 0 | 2024-09-30: 33562.5; 2024-10-31: 195262.5; 2025-01-31: 13425 | 242250
5. Monitoring |  | 2024-08-31: 57720.5; 2024-10-31: 2562.51; 2024-11-30: 11169 | 71452.01
6. AC Equipment | 0 | 2024-09-30: 62962.5; 2024-10-31: 134795.8; 2025-01-31: 14673.2; 2025-05-31: 432.1 | 212863.6
8. Product Add On |  | 2024-10-31: 140874.78; 2025-01-31: 8316; 2025-08-31: 9538.74 | 158729.52
9. AC & DC installation |  | 2024-09-30: 43753.45; 2024-10-31: 113758.97; 2025-01-31: 17501.38 | 175013.8
10. Site Logistics |  | 2024-09-30: 26941.75; 2024-10-31: 70048.55; 2025-01-31: 10776.7 | 107767
11. Due Dilligence |  | 2024-08-31: 2520; 2024-11-30: 11654.76 | 14174.76
13. Engineering |  | 2024-11-30: 30778.2375; 2025-08-31: 31621.7625 | 62400
14. General Expenses |  | 2024-08-31: 1522.75; 2024-09-30: 1570.97; 2024-10-31: 1671; 2024-11-30: 0; 2025-01-31: 1109.72; 2025-02-28: 423.22; 2025-04-30: 1087.98 | 7385.64
15. Service Add On |  | 2025-05-31: 32247.49; 2025-07-31: 9731.71; 2026-01-31: -9731.71 | 32247.49
Grand Total | 0 | 636862.5 | 93284.92 | 365985.8 | 670304.97 | 208540.9875 | -12270.36 | 65802 | 423.22 | 1087.98 | 32679.59 | 9731.71 | 41160.5025 | -9731.71 | 2103862.11

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | 157796 | 0 | 157796 | 0 | 157796
Inverters | 157796
Optimizers | 0
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | 99864 | 0 | 99864 | 0 | 99864
Mounting Structure | 99864
Delivery fee
|  | >Name< |  | >Name<
DC Cable | 98128 | 0 | 98128 | 0 | 98128
DC Cable | 98128
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
Smartlogger 3000 | 26000
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | 0 | 0 | #REF! | 0 | #REF!
SCADA | 0
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | 304429.82 | 1.2177 | 277892.91 | 1.1116 | 26536.91 |  | 0 | 304429.82
DC Equipment | 116936.3 | 0.46775 | 142158.25 | 0.56863 | -25221.95 |  | 0 | 116936.3
AC Labour | 145635 | 0.58254 | 96174 | 0.3847 | 49461 |  | 0 | 145635
DC Labour | 62415 | 0.24966 | 230160 | 0.92064 | -167745 |  | 0 | 62415
Offloading | 8500 |  | 0 |  | 8500 |  |  | 8500
Roof Access/Scaffolding | 0 |  | 29257.61 |  | -29257.61 |  |  | 0
Storage | 0 |  |  |  | 0 |  |  | 0
Telehandler | 29856.3
HSE | 0
Totals | 667772.42 |  | 775642.77 |  | -137726.65 | 0 |  | 637916.12
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | 304429.82
AC equipment | 0 | 0 |  |  | 0 |  | 0 | 116936.3
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | 145635
DC equipment | 0 | 0 |  |  | 0 |  |  | 62415
Storage | 0 |  |  |  | 0 |  |  | 8500
Panel lifting equipment | 8500 |  |  |  | 8500 |  |  | 0
Offloading | 29856.3 |  |  |  | 29856.3 |  |  | 0
Totals | #REF! |  | 0 |  | #REF! | 0 |  | 637916.12
Budget Summary
Budget | 667772.42
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
Loss | 667772.42
All amounts are exc VAT

## Decision Register (hidden)
SA Metal - 22 Christiaan |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | SA Metal - 22 Christiaan | 0 | 0 | 0