## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | PLANNED |  | ACTUAL |  | FINANCIAL REVIEW | TIMELINE REVIEW |  | Allocated in 2024 | Budgeted | Actual
1 | Planned Revenue | 1658747.6138 |  | 1729080.5538 |  | 1658747.6138 | Start Date | Sales | 573669.3282 | 1085078.2855 | 1155411.2255
2 | Planned Expenditure | 1414650.52 |  | 1424359.44 |  | 1374853.7252 | 2024-09-25 | COS | 446832.26 | 932047.4752 | 977527.18
3 | Planned Profit | 244097.0938 |  | 304721.1138 |  | 283893.8886 | End Date - PC | GP | 126837.0682 | 153030.8104 | 177884.0455
4 | Planned Margin | 14.72% |  | 17.62% |  | 17.11% | 2024-10-29
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Acceptance and Initial Deposit |  | 35% | 580561.6648 | 2024-07-18 | 004469 | 2024-07-15 | 2024-07-17
2 | Delivery of Inverters |  | 25% | 414686.9034 | 2024-10-02 | 004553 | 2024-10-02 | 2024-10-09
3 | Delivery of Panels |  | 25% | 414686.9034 | 2024-10-23 | 004575 | 2024-10-21 | 2024-11-28
4 | Practical Completion |  | 10% | 165874.7614 | 2024-12-02 | 004618 | 2024-11-28 | 2025-01-27
5 | Handover |  | 5% | 82937.3807 | 2025-02-05 | 004691 | 2025-02-26 | 2025-10-16
6 | VO - Walkways |  | 0% | 85610.22 | 2024-12-02 | 004618 | 2024-11-28 | 2025-01-27
7 | Credit Note - Walk ways |  | 0% | -15277.28 |  | 004931 | 2026-01-23 | 2026-03-31
|  |  | 100% | 1729080.5538
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 605178.1938
2 | Delivery of Panels |  | 30% | 518724.1661
3 | Delivery of Inverters |  | 20% | 345816.1108
4 | Practical Completion |  | 10% | 172908.0554
5 | Handover |  | 5% | 86454.0277
| Total |  | 100% | 1729080.5538
|  |  | 100% | 1729080.5538
Formulas:
PAYMENT RECEIVED DATE = [TIMELINE REVIEW]+7

## Project Plan
[9 empty] | 2025-10-13 | 2025-10-13
| PROJECT PLAN | SA Metal - 14 Christiaan_B | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 157
| BUSINESS DEVELOPER | Peet
| PROJECT MANAGER | Lloyd
| CONTRACT VALUE | 1658747.6138
| Phase: | Compliance Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status |  | Comment
|  |  | 65 |  |  | 65 |  | 100% | 100%
1 | Project Initiation | 2024-08-14 | 37 | 2024-09-20 | 2024-08-14 | 37 | 2024-09-20 | 100% | 100%
1.1 | BD Handover | 2024-08-14 | 1 | 2024-08-15 | 2024-08-14 | 1 | 2024-08-15 | 100% | 100%
1.2 | Project Introduction | 2024-09-05 | 1 | 2024-09-06 | 2024-09-05 | 1 | 2024-09-06 | 100% | 100%
1.3 | HSE | 2024-09-05 | 15 | 2024-09-20 | 2024-09-05 | 15 | 2024-09-20 | 100% | 100%
1.4 | Installer Kick Off | 2024-09-13 | 1 | 2024-09-16 | 2024-09-13 | 1 | 2024-09-16 | 100% | 100%
1.5 | Project Review | 2024-09-12 | 1 | 2024-09-13 | 2024-09-12 | 1 | 2024-09-13 | 100% | 100%
2 | Site Establishment | 2024-09-25 | 1 | 2024-09-26 | 2024-09-25 | 1 | 2024-09-26 | 100% | 100%
2.1 | Installer on site & Roof Assessment | 2024-09-25 | 1 | 2024-09-26 | 2024-09-25 | 1 | 2024-09-26 | 100% | 100% |  | 88 | Net working Days
3 | AC Installation | 2024-10-12 | 19 | 2024-10-31 | 2024-10-12 | 19 | 2024-10-31 | 100% | 100% |  | 17.6 | Net Working Weeks
3.1 | Inverters delivered | 2024-09-25 | 1 | 2024-09-26 | 2024-09-30 | 1 | 2024-10-01 | 100% | 100% |  | 8.9205 | kW/Week Installationn Speed
3.2 | Inverters Mounted | 2024-09-26 | 1 | 2024-09-27 | 2024-10-01 | 1 | 2024-10-02 | 100% | 100%
3.3 | Solar DB lead time | 2024-09-18 | 20 | 2024-10-17 | 2024-09-18 | 20 | 2024-10-17 | 100% | 100%
3.4 | AC Works | 2024-09-26 | 10 | 2024-10-10 | 2024-10-01 | 10 | 2024-10-15 | 100% | 100%
3.5 | AC Tie - in | 2024-10-04 | 1 | 2024-10-07 | 2024-10-09 | 1 | 2024-10-10 | 100% | 100%
4 | DC Works | 2024-09-25 | 61 | 2024-11-25 | 2024-09-25 | 61 | 2024-11-25 | 100% | 100%
4.1 | Mounting Structure delivered | 2024-09-25 | 1 | 2024-09-26 | 2024-09-25 | 1 | 2024-09-26 | 100% | 100%
4.2 | Mounting Structure installation | 2024-09-25 | 8 | 2024-10-07 | 2024-09-25 | 8 | 2024-10-07 | 100% | 100%
4.3 | DC Cable delivered | 2024-09-25 | 1 | 2024-09-26 | 2024-09-25 | 1 | 2024-09-26 | 100% | 100%
4.3 | DC Stringing | 2024-10-30 | 5 | 2024-11-06 | 2024-10-30 | 5 | 2024-11-06 | 100% | 100%
5 | Module installation | 2024-10-16 | 40 | 2024-11-25 | 2024-10-16 | 40 | 2024-11-25 | 100% | 100%
5.1 | Module delivery | 2024-10-16 | 1 | 2024-10-17 | 2024-10-16 | 1 | 2024-10-17 | 100% | 100%
5.2 | Module mounting | 2024-10-16 | 10 | 2024-10-30 | 2024-10-16 | 10 | 2024-10-30 | 100% | 100%
6 | Commissioning | 2024-11-25 | 9 | 2024-12-04 | 2024-11-25 | 9 | 2024-12-04 | 100% | 100%
6.1 | Commissioning | 2024-11-25 | 1 | 2024-11-26 | 2024-11-25 | 1 | 2024-11-26 | 100% | 100%
6.2 | Practical Completion | 2024-11-25 | 4 | 2024-11-29 | 2024-11-25 | 4 | 2024-11-29 | 100% | 100%
7 | QA Inspections | 2024-12-04 | 9 | 2024-12-13 | 2024-12-04 | 9 | 2024-12-13 | 100% | 100%
7.1 | Red-Team Inspection | 2024-11-29 | 3 | 2024-12-04 | 2024-11-29 | 3 | 2024-12-04 | 100% | 100%
8 | Project Closure | 2024-12-10 | 50 | 2025-01-29 | 2024-12-10 | 50 | 2025-01-29 | 100% | 100%
8.1 | Equipment serial numbers | 2024-12-04 | 1 | 2024-12-05 | 2024-12-04 | 1 | 2024-12-05 | 100% | 100%
8.2 | Snags completion | 2024-12-05 | 5 | 2024-12-12 | 2024-12-05 | 33 | 2025-01-24 | 100% | 100%
8.3 | System Performance Monitoring | 2024-12-12 | 5 | 2024-12-20 | 2024-12-12 | 5 | 2024-12-20 | 100% | 100%
8.4 | Handover documentation | 2024-12-12 | 5 | 2024-12-20 | 2024-12-12 | 5 | 2024-12-20 | 100% | 100%
8.5 | Handover to Client | 2025-01-29 | 1 | 2025-01-29 | 2025-02-20 | 1 | 2025-02-20 | 100% | 100%
8.6 | Handover to Matriarch | 2024-12-01 | 1 | 2024-12-02 | 2025-04-29 | 1 | 2025-04-30 | 100% | 100%

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  |  | COSTED |  | PLANNED |  | ACTUAL | Difference from costed | Difference from planned
| EXPENDITURE |  | 1414650.52 |  | 1374853.7252 |  | 1424359.44 | -9708.92 | -49505.7148
| No. | Item | Costed Expenditure |  | Planned Expenditure |  | Actual Expenditure | Saving / Overrun | Saving / Overrun | Comments on variations from planned expenditure
| 1 | Panels | 488302.31 |  | 501931 |  | 409353 | 78949.31 | 92578
| 2 | Inverters | 118044 |  | 121107.32 |  | 107975.24 | 10068.76 | 13132.08
| 3 | Mounting Structures | 70794 |  | 33895.6 |  | 33895.6 | 36898.4 | 0
| 4 | DC Equipment | 107427.6 |  | 143322 |  | 183222 | -75794.4 | -39900
| 5 | Monitoring | 49000 |  | 42820.5 |  | 34242.09 | 14757.91 | 8578.41
| 6 | AC Equipment | 276727.82 |  | 175564 |  | 182814 | 93913.82 | -7250
| 7 | Battery Systems | 0 |  | 0 |  | 0 | 0 | 0
| 8 | Product Add On | 0 |  | 0 |  | 136151.14 | -136151.14 | -136151.14
| 9 | AC & DC Installation | 131100 |  | 116305 |  | 116305 | 14795 | 0
| 10 | Site Logistics | 32270.5 |  | 100453 |  | 85453.26 | -53182.76 | 14999.74
| 11 | Due Dilligence | 29000 |  | 23020 |  | 12071.19 | 16928.81 | 10948.81
| 12 | BDP Commission | 43075.96 |  | 43075.96 |  | 43075.96 | 0 | 0
| 13 | Engineering | 66283.33 |  | 70734.3452 |  | 50400 | 15883.33 | 20334.3452 | RV: Matriarch defects percentage 1.25%
| 14 | General Expenses | 2625 |  | 2625 |  | 6991.68 | -4366.68 | -4366.68
| 15 | Service Add On | 0 |  | 0 |  | 22409.28 | -22409.28 | -22409.28
|  | check: | 0 | #REF! | 0 | #REF! | 0
Copy amounts in column H and paste as values at Project review.

## Data (hidden)
Public holidays |  | Drop down list
2024-01-01 | New Years Day | Approved
2024-03-21 | Human Rights day | Pending
2024-03-29 | Good Friday | Declined
2024-04-01 | Family Day | Abanded
2024-05-01 | Workers day
2024-06-17 | Youth Day Holiday
2024-08-09 | Womens Day
2024-09-24 | Heritage Day
2024-12-16 | Day of Reconciliation
2024-12-25 | Christmas Day
2024-12-26 | Day of Goodwill |  | Manual dates

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 1414650.52 | 1744357.8338 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY |  |  |  |  | 1424359.44
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | Project Related date | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS | PO NUMBER | COMMENTS
1 | Panels | Longi 570W - Costing Sheet | 276 | 1696.7475 | 468302.31 | 2024-12-15 | 488302.31 | 595490.622 |  | 1 | 1. Panels | Canadian Solar 555W - Deposit - Herholdts | 284 | 1415.25 | 200965.5 | Herholdts Inv: INV875402 | 2024-07-31 | 270795.8269 | 0.00044235 | 2024-09-27 | 409353 | PO3244-SAM-20240719 - RV Approved |  | 19
1 |  | Jinko Solar 575W | [7 empty] | 1 | 1. Panels |  |  |  | 200965.5 | Herholdts Inv: INV875402 | 2024-07-31 | 270795.8269 |  | 2024-10-31 |  |  |  | BUDGET | Installer Allocation
1 | [9 empty] | 1 | 1. Panels | Handling fees |  |  | 800 | Supply Chain: Inv SCO04502 | 2024-10-31 | 949.1441 |  | 2024-11-29 |  |  |  | AC Equipment | 276727.82
1 |  | Delivery |  |  | 20000 | 2024-12-15 |  |  |  | 1 | 1. Panels | Delivery |  |  | 5650 | Supply Chain: Inv SCO04533 | 2024-10-31 | 7532.7635 |  | 2024-11-29 |  |  |  | DC Equipment | 48499.6
1 | [9 empty] | 1 | 1. Panels | Storage |  |  | 972 | Supply Chain: Inv SCO04502 | 2024-10-31 | 1153.2101 |  | 2024-11-29 |  |  |  | AC Labour | 91770
1 | [9 empty] | 1 | 1. Panels | [5 empty] | 2024-11-30 | 44263.85 | [5 empty] | DC Labour | 39330
[24 empty] | Offloading | 8500
2 | Inverters | Huawei 100KTL | 1 | 78898 | 78898 | 2024-10-25 | 118044 | 143956.0976 |  | 2 | 2. Inverters | Huawei 100KTL | 1 | 68870 | 68870 | Kathea Inv518635 | 2024-09-30 | 85967.5552 | 0.0028805 | 2024-10-30 | 107975.24 |  | MI: Kathea quote | Telehandler | 0
2 |  | Huawei 50KTL | 1 | 39146 | 39146 | 2024-10-25 |  |  |  | 2 | 2. Inverters | Huawei 50KTL | 1 | 38000 | 38000 | Kathea Inv518655 | 2024-10-31 | 56608.9144 |  | 2024-11-29 |  |  | MI: Kathea quote | Storage | 0
2 | [9 empty] | 2 | 2. Inverters | Delivery |  |  | 1105.24 | Kathea Inv518635 | 2024-09-30 | 1379.6251 |  | 2024-10-30 |  |  |  | Scaffolding | 23770.5
2 | [9 empty] | 2 | 2. Inverters | [6 empty] | 0 | [5 empty] | Other | 0
[24 empty] | Total | 488597.92
3 | Mounting Structures | KlipLok Roof | 157000 | 0.45 | 70794 | 2024-10-25 | 70794 | 86334.1463 |  | 3 | 3. Mounting Structures | KlipLok Roof | 1.15 | 32045.6 | 32045.6 | Schletter INV0894 | 2024-09-30 | 66337.1231 | -0.0043965 | 2024-09-23 | 33895.6 | PO3362-SAM14B-20240918 - RV Approved |  | Less 15% | 415308.232
3 | [9 empty] | 3 | 3. Mounting Structures | IBR Roof |  |  | 0 |  | 2024-10-31 | 16167.37 |  | 2024-11-30 |  | PO3381-SAM14A-20241002 - RV Approved |  | R/Wp | 2.6453
3 | [9 empty] | 3 | 3. Mounting Structures | Delivery |  |  | 1850 | Schletter Inv0893 | 2024-09-30 | 3829.6577 |  | 2024-09-23
3 | [9 empty] | 3 | 3. Mounting Structures | [6 empty] | 0 | [5 empty] | ACTUAL - Cosmic Sun | Installer Price |  | ACTUAL - Thula Moya | Installer Price |  | ACTUAL - CornerStone | Installer Price
[24 empty] | AC Equipment | 68700 |  | AC Equipment | 112764 |  | AC Equipment | 50284.98 | * Excluded R25976,34 for Comms and metering
4 | DC Equipment | DC Cable | 2308 | 16 | 36928 | 2024-10-25 | 107427.6 | 131009.2683 |  | 4 | 4. DC Equipment | DC Cable | 4000 | 13.5 | 54000 | Herholdts Inv: INV922149 | 2024-10-31 | 49360.8831 | -0.0044764 | 2024-11-30 | 183222 | PO3315-MUL-20240823 - RV Approved | MI: Herholdts quote | DC Equipment | 74017.4 |  | DC Equipment | 89322 |  | DC Equipment | 146436.88
[11 empty] | 4. DC Equipment | DC Cable |  |  | 39900 | MENLO - INV0002444 | 2024-01-31 |  |  | 2025-03-28 |  |  | This was not on the tracker (extra DC Cable)
4 |  | DC Surge Arrestor | 4 | 5500 | 22000 | 2024-11-15 |  |  |  | 4 | 4. DC Equipment | Delivery |  |  | 0 |  |  | 0 | [5 empty] | AC Labour | 39250 |  | AC Labour | 42376 |  | AC Labour | 15154.29
4 |  | DC Cable Tray | 130 | 130 | 16900 | 2024-11-15 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 89322 | 10% | 8932.2 | Thula Moya In04434 | 2024-09-30 | 8164.8385 |  | 2024-09-25 |  | PO3366-SAM14B-202409 - RV Approved |  | DC Labour | 94750 | 0.90541 | DC Labour | 73929 | 0.78584 | DC Labour | 126363.55 | 0.9562
4 |  | Earth Cable | 2308 | 13.5 | 31158 | 2024-10-25 |  |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 13398.3 | Thula Moya IN04438 | 2024-09-30 | 12247.2578 |  | 2024-10-10 |  |  |  | Offloading | 0 |  | Site Logistics | 33116 |  | Site Logistics | 70278
4 |  | Earth clamp | 27.6 | 16 | 441.6 | 2024-10-16 |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 17864.4 | Thula Moya IN04477 | 2024-10-31 | 16329.677 |  | 2024-11-29 |  |  |  | Roof Access | 15000 |  | Sundries | 12113 |  | HSE | 7027.8
4 | [9 empty] | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 22330.5 | Thula Moya IN04478 | 2024-10-31 | 20412.0963 |  | 2025-01-30 |  |  |  | Container | 0 |  | Accomodation | 40224 |  | COC | 3978
4 | [9 empty] | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 8932.2 | Thula Moya IN04513 | 2024-11-30 | 8164.8385 |  | 2024-11-29 |  |  |  | HSE | 4500 |  | Scaffolding | 0 |  | Travel | 14818.05
4 | [9 empty] | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 8932.2 | Thula Moya IN04535 | 2024-11-30 | 8164.8385 |  | 2024-12-05 |  |  |  | Other | 0 |  | Other | 0 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 4466.1 | Thula Moya IN04595 | 2025-01-31 | 4082.4265 |  | 2025-02-13 |  |  |  | Other | 0 |  | Other | 0 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 4466.1 | Thula Moya IN04592 | 2025-01-31 | 4082.4165 |  | 2025-03-06 |  |  |  | Other | 0 |  | Other | 0 |  | Other | 0
[24 empty] | Total | 296217.4 |  | Total | 403844 |  | Total | 434341.55
5 | Monitoring | Smartlogger 3000 | 1 | 26000 | 26000 | 2024-10-25 | 49000 | 59756.0976 |  | 5 | 5. Monitoring | Smartlogger 3000 | 1 | 8000 | 8000 | Solarworld SASIV-24-00517 | 2024-08-31 | 11164.0168 | 0.0014869 | 2024-09-26 | 34242.09 |  |  | R/Wp | 1.8867 |  | R/Wp | 2.5723 |  | R/Wp | 2.7665
5 |  | Comms DB |  |  | 8000 | 2024-10-25 |  |  |  | 5 | 5. Monitoring | CTs |  |  | 11820.5 | AccuEnergy ASAI-003743 | 2024-08-31 | 16495.5325 |  | 2024-09-27
5 |  | Revenue Grade Meter | 1 | 15000 | 15000 | 2024-12-02 |  |  |  | 5 | 5. Monitoring | Revenue Grade Meter | 1 | 11169 | 11169 | MATRIARCH - INV-3278 | 2024-11-30 | 23106.5489 |  | 2024-11-30
[10 empty] | 5 | 5. Monitoring | Delivery of Techsitter |  |  | 129.63 | DSV Inv: 1048652 | 2024-10-31 | 206.4953 |  | 2024-11-30
5 | [9 empty] | 5 | 5. Monitoring |  |  |  | 110.45 | DSV Inv: 180131355 | 2025-05-31 | 0 |  | 2025-06-30
5 | [9 empty] | 5 | 5. Monitoring | Frontline Comms Equipment |  |  | 2562.51 | Frontline Electrical: INV697940 | 2024-10-31 | 7995.6634 |  | 2024-10-10 |  | PO3387-SAM-20241007 - RV Approved | PO split across the portfolio
5 | [9 empty] | 5 | 5. Monitoring | Attena Extension |  |  | 450 | Accuenergy Inv: ASAI-004425 | 2024-12-31 | 787.8392 |  | 2025-01-30 |  | PO3517-SAM-20241206 - RV Approved
6 | AC Equipment | [5 empty] | 276727.82 | 337472.948 |  | 6 | 6. AC Equipment | [6 empty] | 0 | 0 |  | 182814
[10 empty] | 6 | 6. AC Equipment | AC & Comms DB - Deposit | 40% | 62800 | 25120 | Cosmic Sun CS_SAMPVDB_001 | 2024-09-30 | 46371.287 |  | 2024-10-03 |  | PO3375-SAMPort-20240930 - RV Approved
[10 empty] | 6 | 6. AC Equipment | AC & Comms DB - Balance | 60% |  | 37680 | Cosmic Sun CS_SAMPVDB_002 | 2024-10-31 | 69556.9304 |  | 2024-10-31
[10 empty] | 6 | 6. AC Equipment | Powder Coat DB |  |  | 7250 | Cosmic Sun CS_SAMPVDB_003 | 2024-10-31 | 13383.4327 |  | 2024-10-17 |  | PO3400-SAM-20241011 - RV Approved
[10 empty] | 6 | 6. AC Equipment | [6 empty] | 0
6 |  | Project Kick Off |  | 10% | 27672.782 | 2024-12-20 |  |  |  | 6 | 6. AC Equipment | Project Kick Off | 112764 | 10% | 11276.4 | Thula Moya In04434 | 2024-09-30 | 20816.1298 |  | 2024-09-25 |  | PO3366-SAM14B-202409 - RV Approved
6 | 276727.82 | Site Establishment |  | 15% | 41509.173 | 2024-09-25 |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 16914.6 | Thula MoyaIN04438 | 2024-09-30 | 31224.1947 |  | 2024-10-10
6 |  | AC Installation Complete |  | 20% | 55345.564 | 2024-10-31 |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 22552.8 | Thula Moya IN04477 | 2024-10-31 | 41632.2596 |  | 2024-11-29
6 |  | DC Installation Complete |  | 25% | 69181.955 | 2024-11-25 |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 28191 | Thula Moya IN04478 | 2024-10-31 | 52040.3245 |  | 2025-01-30
6 |  | Commissioning Complete |  | 10% | 27672.782 | 2024-12-04 |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 11276.4 | Thula Moya IN04513 | 2024-11-30 | 20816.1298 |  | 2024-11-29
6 |  | Site De-establisment |  | 10% | 27672.782 | 2024-12-12 |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 11276.4 | Thula Moya IN04535 | 2024-11-30 | 20816.1298 |  | 2024-12-05
6 |  | Handover Document Complete |  | 5% | 13836.391 | 2024-12-20 |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 5638.2 | Thula Moya IN04595 | 2025-01-31 | 10408.0649 |  | 2025-02-13
6 |  | End of Defects Period |  | 5% | 13836.391 | 2025-01-19 |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 5638.2 | Thula Moya IN04592 | 2025-01-31 | 10408.0649 |  | 2025-03-06
7 | Battery Systems | [5 empty] | 0 | 0 |  | 7 | Battery Systems | [7 empty] | 0 |  | 0
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
8 | Product Add On | [5 empty] | 0 | 85610.22 |  | 8 | 8. Product Add On | Walkways Transport |  |  | 4025 | Onvlee Engineering: Inv 01048652 | 2024-10-31 | 3135.0872 | 0 | 2024-10-10 | 136151.14
8 | [9 empty] | 8 | 8. Product Add On | Mounting Structure for Walkways |  |  | 4244.32 | Schletter INV0951 | 2024-10-31 | 3305.9164 |  | 2024-11-29 |  | PO3389-SAM-20241008 - RV Approved
8 | [9 empty] | 8 | 8. Product Add On | Walkways |  |  | 77340.9 | Onvlee Engineering: Inv 01048652 | 2024-10-31 | 60241.1098 |  | 2024-10-10 |  | PO3390-SAM-20241008 - RV Approved
8 | [9 empty] | 8 | 8. Product Add On | Supply and install tie in Breaker - Thula Moya |  |  | 24300.96 | Thula Moya IN04488 | 2024-10-31 | 18928.1066 |  | 2024-11-01 |  | PO3432-SAM-20241029 - RV Approved
8 | [9 empty] | 8 | 8. Product Add On | Installation of walkways |  |  | 19387.2 | Thula Moya IN04593 | 2025-01-31 | 0 |  | 2025-07-31 |  |  | TC: Added cost, it was not on the tracker
[11 empty] | 8. Product Add On | 1000A Cooper Stub. Poly Angle& Copper Stub |  |  | 6852.76 | Switchboard - INV 2-SOI001940 | 2025-04-30 |  |  | 2025-05-29
Only services to be capture below, products above
9 | AC & DC Installation | Project Kick Off |  | 10% | 13110 | 2024-09-18 | 131100 | 154235.2941 |  | 9 | 9. AC & DC installation | Project Kick Off | 116305 | 10% | 11630.5 | Thula Moya In04434 | 2024-09-30 | 15423.5294 | 0 | 2024-09-25 | 116305 | PO3366-SAM14B-202409 - RV Approved
9 | 39330 | Site Establishment |  | 15% | 19665 | 2024-09-25 |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 17445.75 | Thula Moya IN04438 | 2024-09-30 | 23135.2941 |  | 2024-10-10
9 | 91770 | AC Installation Complete |  | 20% | 26220 | 2024-10-31 |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 23261 | Thula Moya IN04477 | 2024-10-31 | 30847.0588 |  | 2024-11-29
9 |  | DC Installation Complete |  | 25% | 32775 | 2024-11-25 |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 29076.25 | Thula Moya IN04478 | 2024-10-31 | 38558.8235 |  | 2025-01-30
9 |  | Commissioning Complete |  | 10% | 13110 | 2024-12-04 |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 11630.5 | Thula Moya IN04513 | 2024-11-30 | 15423.5294 |  | 2024-11-29
9 |  | Site De-establisment |  | 10% | 13110 | 2024-12-12 |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 11630.5 | Thula Moya IN04535 | 2024-11-30 | 15423.5294 |  | 2024-12-05
9 |  | Handover Document Complete |  | 5% | 6555 | 2024-12-20 |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 5815.25 | Thula Moya IN04595 | 2025-01-31 | 7711.7647 |  | 2025-02-13
9 |  | End of Defects Period |  | 5% | 6555 | 2025-01-19 |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 5815.25 | Thula Moya IN04592 | 2025-01-31 | 7711.7647 |  | 2025-03-06
10 | Site Logistics | [5 empty] | 32270.5 | 37965.2941 |  | 10 | 10. Site Logistics | Security | [5 empty] | 0 | 0.0039345 |  | 85453.26 |  | MI: Security of R15k removed as per Lloyd email 19/11
[10 empty] | 10 | 10. Site Logistics | [6 empty] | 0
[10 empty] | 10 | 10. Site Logistics | Project Kick Off | 85453 | 10% | 8545.3 | Thula Moya In04434 | 2024-09-30 | 3229.6178 |  | 2024-09-25 |  | PO3366-SAM14B-202409 - RV Approved
[10 empty] | 10 | 10. Site Logistics | Site Establishment |  | 15% | 12817.96 | Thula Moya IN04438 | 2024-09-30 | 4844.4305 |  | 2024-10-10
[10 empty] | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 17090.6 | Thula Moya IN04477 | 2024-10-31 | 6459.1995 |  | 2024-11-29
[10 empty] | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 21363.5 | Thula Moya IN04478 | 2024-10-31 | 8074.1189 |  | 2024-12-05
10 |  | Offloading |  |  | 8500 | 2024-12-04 |  |  |  | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 8545.3 | Thula Moya IN04513 | 2024-11-30 | 5780.7079 |  | 2024-11-29
10 | [9 empty] | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 8545.3 | Thula Moya IN04535 | 2024-11-30 | 5780.6979 |  | 2024-12-05
10 | [9 empty] | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 4272.65 | Thula Moya IN04595 | 2025-01-31 | 1898.2589 |  | 2025-02-13
10 |  | Scaffolding |  |  | 23770.5 | 2024-12-04 |  |  |  | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 4272.65 | Thula Moya IN04592 | 2025-01-31 | 1898.2589 |  | 2025-03-06
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2024-12-01 | 29000 | 34117.6471 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 3551.19 | Sun Spot Inv E005 | 2024-11-30 | 10036.9762 | 0.0022236 | 2025-01-16 | 12071.19
11 |  | Structural sign off |  |  | 18000 | 2024-09-25 |  |  |  | 11 | 11. Due Dilligence | Structural sign off |  |  | 2520 | L&B Consulting Inv1742 | 2024-08-31 | 3734.8597 |  | 2024-09-02
11 | [9 empty] | 11 | 11. Due Dilligence | [6 empty] | 0
11 | [9 empty] | 11 | 11. Due Dilligence | [6 empty] | 0
11 | [9 empty] | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 | MATRIARCH - INV-3413 | 2024-11-30 | 20345.8089 |  | 2024-11-29
12 | BDP Commission | Referral Fee |  |  | 43075.96 | 2025-01-29 | 43075.96 | 0 |  | 12 | BDP Commission | Referral Fee |  |  | 21537.98 | Green Co Inv: INV0000518 | 2024-08-31 |  |  | 2024-09-05 | 43075.96
[10 empty] | 12 | BDP Commission | Referral Fee |  |  | 21537.98 | Green Co Inv: INV0000527 | 2024-11-30 |  |  | 2024-12-12
12 | BDP Commission | [8 empty] | 12 | BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 16283.33 | 2025-01-02 | 66283.33 | 75321.9635 |  | 13 | 13. Engineering | Matriarch Defects Period |  |  | 20734.3452 | MATRIARCH - INV-3414 | 2024-11-30 | 75321.9635 | 0 | 2024-11-30 | 50400
13 |  | Management |  |  | 4000 | 2025-01-02 |  |  |  | 13 | 13. Engineering | Performance Guarantee |  |  | 50400 | Matriarch - INV-5021 | 2025-08-31 | 0 |  | 2025-08-31
13 |  | Project manager |  |  | 20400 | 2025-01-02 |  |  |  | 13 | 13. Engineering | Matriarch Defects Period |  |  | -20734.3452 | Matriarch - CN-5022 | 2025-08-31 | 0 |  | 2025-08-31
13 |  | Planner time |  |  | 5200 | 2025-01-02 |  |  |  | 13 | 13. Engineering |  |  |  | 0 |  |  | 0
13 |  | De Snagging |  |  | 20400 | 2025-01-02 |  |  |  | 13 | 13. Engineering |  |  |  | 0 |  |  | 0
13 | [9 empty] | 13 | 13. Engineering
13 | [9 empty] | 13 | 13. Engineering
14 | General Expenses | Car travel to site |  |  | 2625 | 2025-01-02 | 2625 | 3088.2353 |  | 14 | 14. General Expenses | Car travel to site |  |  | 1022.78 | Expense Claim | 2024-08-31 | 683.2653 | 0.0038281 | 2024-09-05 | 6991.68
14 | [9 empty] | 14 | 14. General Expenses |  | 1 571.0 |  | 1570.98 | Expense Claim | 2024-09-30 | 920.7636 |  | 2024-10-04
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 1671 | Expense Claim | 2024-10-31 | 806.0625 |  | 2024-11-08
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 25.56 | Expense Claim | 2024-11-30 | 226.05 |  | 2024-12-06
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 0 | Expense Claim | 2024-12-31 | 0 |  | 2025-01-09
[10 empty] | 14 | 14. General Expenses |  |  |  | 1016.02 | Expense Claim | 2025-01-31 | 452.09 |  | 2025-02-07
[10 empty] | 14 | 14. General Expenses |  |  |  | 597.36 | Expense Claim | 2025-02-28 | 0 |  | 2025-03-06
[10 empty] | 14 | 14. General Expenses |  |  |  | 1087.98 | Expense Claim | 2025-04-30 |  |  | 2025-05-08
14 | [9 empty] | 14 | 14. General Expenses
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | [7 empty] | 0 |  | 22409.28
15 | [9 empty] | 15 | 15. Service Add On | Defect Correction |  |  | 22409.28 | Cosmic Sun Inv: CS_SAM14B_001 | 2025-05-31 |  |  | 2025-05-15 |  | PO3871-SAM14B-20250512 - RV Approved | We will recover the cost from Thula Moya
15 | [9 empty] | 15 | 15. Service Add On | Moving inverter and reprogramming meters |  |  | 19463.42 | Thula Moya - IN04750 | 2025-07-31 |  |  | 2026-01-31 |  |  | Thula Moya to provide CN for this
15 | [9 empty] | 15 | 15. Service Add On |  |  |  | -19463.42 | Thula Moya - IC200104 | 2026-01-31 |  |  | 2026-01-31
1744357.8279
Note on W28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date
Note on W29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the date as not the full milestone was paid
Note on W93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date as it hasn’t been paid
Note on R122: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Roedolph Venter was this recovered from Thula Moya

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2024-07-15 to 2026-07-13
PLANNED |  | CHECK | CHECK
| Planned Revenue | 1658747.6138 | 1744357.8338 | 580561.6648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414686.9034 | 0 | 0 | 414686.9034 | 0 | 0 | 0 | 0 | 0 | 251484.9814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82937.3807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 995248.5683 | 995248.5683 | 995248.5683 | 1409935.4717 | 1409935.4717 | 1409935.4717 | 1409935.4717 | 1409935.4717 | 1409935.4717 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338
| Planned Expenditure | 1414650.52 | 1414650.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13110 | 79174.173 | 0 | 0 | 441.6 | 290924 | 81565.564 | 0 | 38900 | 0 | 112956.955 | 88053.282 | 529085.092 | 48064.173 | 0 | 68908.33 | 0 | 20391.391 | 0 | 43075.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13110 | 92284.173 | 92284.173 | 92284.173 | 92725.773 | 383649.773 | 465215.337 | 465215.337 | 504115.337 | 504115.337 | 617072.292 | 705125.574 | 1234210.666 | 1282274.839 | 1282274.839 | 1351183.169 | 1351183.169 | 1371574.56 | 1371574.56 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52 | 1414650.52
| PLANNED CashFlow |  |  | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 567451.6648 | 488277.4918 | 902964.3953 | 902964.3953 | 902522.7953 | 1026285.6987 | 944720.1347 | 944720.1347 | 905820.1347 | 905820.1347 | 792863.1797 | 956294.8791 | 427209.7871 | 379145.6141 | 379145.6141 | 310237.2841 | 310237.2841 | 289845.8931 | 289845.8931 | 246769.9331 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138 | 329707.3138
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 1729080.5538 | 1744357.8338 | 580561.6648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414686.9034 | 0 | 0 | 0 | 0 | 0 | 0 | 414686.9034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251484.9814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82937.3807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15277.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 995248.5683 | 995248.5683 | 995248.5683 | 995248.5683 | 995248.5683 | 995248.5683 | 995248.5683 | 1409935.4717 | 1409935.4717 | 1409935.4717 | 1409935.4717 | 1409935.4717 | 1409935.4717 | 1409935.4717 | 1409935.4717 | 1409935.4717 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1661420.4531 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1744357.8338 | 1729080.5538 | 1729080.5538 | 1729080.5538 | 1729080.5538 | 1729080.5538 | 1729080.5538 | 1729080.5538 | 1729080.5538 | 1729080.5538 | 1729080.5538 | 1729080.5538 | 1729080.5538 | 1729080.5538 | 1729080.5538 | 1729080.5538 | 1729080.5538
| Actual + Planned Expenditure | 1424359.44 | 1424359.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25080.76 | 0 | 0 | 295066 | 26690.98 | 144505.02 | 7250 | 0 | 332921.7 | 1671 | 0 | 0 | 262852.4952 | 61773.46 | 21537.98 | 0 | 0 | 0 | 0 | 3551.19 | 0 | 80047.75 | 1016.02 | 20192.2 | 0 | 0 | 20789.56 | 0 | 0 | 39900 | 0 | 0 | 0 | 0 | 0 | 1087.98 | 22409.28 | 0 | 6852.76 | 0 | 0 | 0 | 0 | 110.45 | 0 | 0 | 0 | 19387.2 | 0 | 0 | 0 | 29665.6548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25080.76 | 25080.76 | 25080.76 | 320146.76 | 346837.74 | 491342.76 | 498592.76 | 498592.76 | 831514.46 | 833185.46 | 833185.46 | 833185.46 | 1096037.9552 | 1157811.4152 | 1179349.3952 | 1179349.3952 | 1179349.3952 | 1179349.3952 | 1179349.3952 | 1182900.5852 | 1182900.5852 | 1262948.3352 | 1263964.3552 | 1284156.5552 | 1284156.5552 | 1284156.5552 | 1304946.1152 | 1304946.1152 | 1304946.1152 | 1344846.1152 | 1344846.1152 | 1344846.1152 | 1344846.1152 | 1344846.1152 | 1344846.1152 | 1345934.0952 | 1368343.3752 | 1368343.3752 | 1375196.1352 | 1375196.1352 | 1375196.1352 | 1375196.1352 | 1375196.1352 | 1375306.5852 | 1375306.5852 | 1375306.5852 | 1375306.5852 | 1394693.7852 | 1394693.7852 | 1394693.7852 | 1394693.7852 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44 | 1424359.44
| ACTUAL CashFlow |  |  | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 580561.6648 | 555480.9048 | 555480.9048 | 555480.9048 | 260414.9048 | 233723.9248 | 503905.8083 | 496655.8083 | 496655.8083 | 163734.1083 | 162063.1083 | 162063.1083 | 162063.1083 | 313897.5165 | 252124.0565 | 230586.0765 | 230586.0765 | 230586.0765 | 230586.0765 | 230586.0765 | 227034.8865 | 227034.8865 | 398472.1179 | 397456.0979 | 377263.8979 | 377263.8979 | 377263.8979 | 356474.3379 | 356474.3379 | 356474.3379 | 316574.3379 | 316574.3379 | 316574.3379 | 316574.3379 | 316574.3379 | 316574.3379 | 315486.3579 | 293077.0779 | 293077.0779 | 286224.3179 | 286224.3179 | 286224.3179 | 286224.3179 | 286224.3179 | 286113.8679 | 286113.8679 | 286113.8679 | 286113.8679 | 266726.6679 | 266726.6679 | 266726.6679 | 266726.6679 | 237061.0131 | 237061.0131 | 237061.0131 | 237061.0131 | 237061.0131 | 237061.0131 | 237061.0131 | 319998.3938 | 319998.3938 | 319998.3938 | 319998.3938 | 319998.3938 | 319998.3938 | 319998.3938 | 319998.3938 | 319998.3938 | 319998.3938 | 319998.3938 | 319998.3938 | 319998.3938 | 319998.3938 | 319998.3938 | 319998.3938 | 319998.3938 | 319998.3938 | 319998.3938 | 319998.3938 | 319998.3938 | 319998.3938 | 319998.3938 | 319998.3938 | 304721.1138 | 304721.1138 | 304721.1138 | 304721.1138 | 304721.1138 | 304721.1138 | 304721.1138 | 304721.1138 | 304721.1138 | 304721.1138 | 304721.1138 | 304721.1138 | 304721.1138 | 304721.1138 | 304721.1138 | 304721.1138
|  | CHECK | CHECK
| Revenue Recognition | -85610.2141 | 1744357.8279 | 0 | 0 | 541591.6539 | 0 | 0 | 0 | 32077.6744 | 0 | 0 | 0 | 0 | 323891.3041 | 0 | 0 | 0 | 523684.6476 | 0 | 0 | 0 | 273671.5986 | 0 | 0 | 0 | 0 | 787.8392 | 0 | 0 | 0 | 48653.1101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 1744357.8279 | 0 | 0 | 541591.6539 | 541591.6539 | 541591.6539 | 541591.6539 | 573669.3282 | 573669.3282 | 573669.3282 | 573669.3282 | 573669.3282 | 897560.6324 | 897560.6324 | 897560.6324 | 897560.6324 | 1421245.28 | 1421245.28 | 1421245.28 | 1421245.28 | 1694916.8787 | 1694916.8787 | 1694916.8787 | 1694916.8787 | 1694916.8787 | 1695704.7179 | 1695704.7179 | 1695704.7179 | 1695704.7179 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279 | 1744357.8279
| Installer Expenditure |  | 318391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31839.1 | 0 | 47758.65 | 0 | 0 | 0 | 0 | 0 | 0 | 95517.3 | 31839.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79597.75 | 0 | 15919.55 | 0 | 0 | 15919.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Installer Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31839.1 | 31839.1 | 79597.75 | 79597.75 | 79597.75 | 79597.75 | 79597.75 | 79597.75 | 79597.75 | 175115.05 | 206954.15 | 206954.15 | 206954.15 | 206954.15 | 206954.15 | 206954.15 | 206954.15 | 206954.15 | 286551.9 | 286551.9 | 302471.45 | 302471.45 | 302471.45 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391 | 318391

## Finance - Revenue
REVENUE RECOGNITION AMOUNT | (All)
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels |  | (blank) | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2024-01-31 | 2025-04-30 | 2025-05-31 | 2025-07-31 | 2025-08-31 | 2026-01-31 | Grand Total
(blank)
Battery Systems
BDP Commission
1. Panels |  |  | 541591.6539 |  |  | 9635.1177 | 44263.85 | [9 empty] | 595490.6216
2. Inverters | 0 |  |  |  | 87347.1803 | 56608.9144 | [10 empty] | 143956.0947
3. Mounting Structures | 0 |  |  |  | 70166.7807 | 16167.37 | [10 empty] | 86334.1507
4. DC Equipment |  | 0 |  |  | 20412.0963 | 86102.6564 | 16329.677 |  | 8164.843 | [7 empty] | 131009.2728
5. Monitoring |  |  |  | 27659.5493 |  | 8202.1586 | 23106.5489 | 787.8392 |  |  |  |  | 0 |  |  |  | 59756.0961
6. AC Equipment | 0 |  |  |  | 98411.6114 | 176612.9472 | 41632.2596 |  | 20816.1298 | [7 empty] | 337472.948
8. Product Add On | [5 empty] | 85610.22 |  |  | 0 | [7 empty] | 85610.22
9. AC & DC installation |  |  |  |  | 38558.8235 | 69405.8823 | 30847.0588 |  | 15423.5294 | [7 empty] | 154235.2941
10. Site Logistics | 0 | 0 |  |  | 8074.0482 | 14533.3184 | 11561.4057 |  | 3796.5179 | [7 empty] | 37965.2902
11. Due Dilligence | 0 |  |  | 3734.8597 |  |  | 30382.7851 | [9 empty] | 34117.6448
13. Engineering |  | 0 |  |  |  |  | 75321.9635 | [7 empty] | 0 |  | 75321.9635
14. General Expenses |  |  |  | 683.2653 | 920.7636 | 806.0625 | 226.05 | 0 | 452.09 | 0 | [6 empty] | 3088.2315
15. Service Add On
Grand Total | 0 | 0 | 541591.6539 | 32077.6744 | 323891.3041 | 523684.6476 | 273671.5986 | 787.8392 | 48653.1101 | 0 |  |  | 0 |  | 0 |  | 1744357.8279
|  |  | 541591.65 | 32077.67 | 323891.3 | 523684.65 | 270284.01 | 787.84 | 48653.11 |  |  | 1740970.23
|  |  | 0.0038805 | 0.0043619 | 0.0041386 | -0.0023669 | 3387.5886 | -0.00080147 | 5.337e-05 |  |  | -1740970.23

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2024-01-31 | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-04-30 | 2025-05-31 | 2025-07-31 | 2025-08-31 | 2026-01-31 | Grand Total
Battery Systems
BDP Commission |  |  | 2024-08-31: 21537.98; 2024-11-30: 21537.98 | 43075.96
(blank)
1. Panels |  |  | 2024-07-31: 401931; 2024-10-31: 7422 | 409353
2. Inverters |  |  | 2024-09-30: 69975.24; 2024-10-31: 38000 | 107975.24
3. Mounting Structures |  |  | 2024-09-30: 33895.6; 2024-10-31: 0 | 33895.6
4. DC Equipment | 0 | 39900 | 2024-09-30: 22330.5; 2024-10-31: 94194.9; 2024-11-30: 17864.4; 2025-01-31: 8932.2 | 183222
5. Monitoring |  |  | 2024-08-31: 19820.5; 2024-10-31: 2692.14; 2024-11-30: 11169; 2024-12-31: 450; 2025-05-31: 110.45 | 34242.09
6. AC Equipment |  |  | 2024-09-30: 53311; 2024-10-31: 95673.8; 2024-11-30: 22552.8; 2025-01-31: 11276.4 | 182814
8. Product Add On |  |  | 2024-10-31: 109911.18; 2025-01-31: 19387.2; 2025-04-30: 6852.76 | 136151.14
9. AC & DC installation |  |  | 2024-09-30: 29076.25; 2024-10-31: 52337.25; 2024-11-30: 23261; 2025-01-31: 11630.5 | 116305
10. Site Logistics |  |  | 2024-09-30: 21363.26; 2024-10-31: 38454.1; 2024-11-30: 17090.6; 2025-01-31: 8545.3 | 85453.26
11. Due Dilligence |  |  | 2024-08-31: 2520; 2024-11-30: 9551.19 | 12071.19
13. Engineering | 0 |  | 2024-11-30: 20734.3452; 2025-08-31: 29665.6548 | 50400
14. General Expenses |  |  |  | 1022.78 | 1570.98 | 1671 | 25.56 | 0 | 1016.02 | 597.36 | 1087.98 |  |  |  |  | 6991.68
15. Service Add On |  |  | 2025-05-31: 22409.28; 2025-07-31: 19463.42; 2026-01-31: -19463.42 | 22409.28
Grand Total | 0 | 39900 | 401931 | 44901.26 | 231522.83 | 440356.37 | 143786.8752 | 450 | 60787.62 | 597.36 | 7940.74 | 22519.73 | 19463.42 | 29665.6548 | -19463.42 | 1424359.44

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate | [5 empty] | FINANCIAL CLOSE CERTIFICATE
Project Name: | SA Metal - 14 Christiaan_B
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion: |  |  |  | 1. Financial Close | 1. Financial Close
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | 118044 | 0 | 118044 | 0 | 118044
Inverters | 78898
Optimizers | 39146
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | 70794 | 0 | 70794 | 0 | 70794
Mounting Structure | 70794
Delivery fee
|  | >Name< |  | >Name<
DC Cable | 36928 | 0 | 36928 | 0 | 36928
DC Cable | 36928
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
Smartlogger 3000 | 26000
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | 0 | 0 | #REF! | 0 | #REF!
SCADA | 0
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | 276727.82 | 1.7626 | 277892.91 | 1.77 | -1165.09 |  | 0 | 276727.82
DC Equipment | 48499.6 | 0.30891 | 142158.25 | 0.90547 | -93658.65 |  | 0 | 48499.6
AC Labour | 91770 | 0.58452 | 96174 | 0.61257 | -4404 |  | 0 | 91770
DC Labour | 39330 | 0.25051 | 230160 | 1.466 | -190830 |  | 0 | 39330
Offloading | 8500 |  | 0 |  | 8500 |  |  | 8500
Roof Access/Scaffolding | 0 |  | 29257.61 |  | -29257.61 |  |  | 0
Storage | 0 |  |  |  | 0 |  |  | 0
Telehandler | 23770.5
HSE | 0
Totals | 488597.92 |  | 775642.77 |  | -310815.35 | 0 |  | 464827.42
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | 276727.82
AC equipment | 0 | 0 |  |  | 0 |  | 0 | 48499.6
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | 91770
DC equipment | 0 | 0 |  |  | 0 |  |  | 39330
Storage | 0 |  |  |  | 0 |  |  | 8500
Panel lifting equipment | 8500 |  |  |  | 8500 |  |  | 0
Offloading | 23770.5 |  |  |  | 23770.5 |  |  | 0
Totals | #REF! |  | 0 |  | #REF! | 0 |  | 464827.42
Budget Summary
Budget | 488597.92
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
Loss | 488597.92
All amounts are exc VAT

## Decision Register (hidden)
SA Metal - 14 Christiaan_B |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | SA Metal - 14 Christiaan_B | 0 | 0 | 0