## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[9 empty] | 2026-02-24 | 2026-02-24
| PROJECT PLAN | Corporate Park | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 257
| PROJECT DEVELOPER | Natasha Watkins-Baker
| PROJECT MANAGERS | Eon Van Rensberg
| CONTRACT VALUE | 2655906.3007
| Phase: | DLP
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Status | Comment
|  |  | 31 |  |  | 86 |  | 100% | 100%
1 | Project Initiation | 2025-04-22 | 63 | 2025-06-24 | 2025-04-22 | 62 | 2025-06-23 | 100% | 100%
1.1 | BD Handover | 2025-04-22 | 1 | 2025-04-23 | 2025-04-22 | 1 | 2025-04-23 | 100% | 100%
1.2 | Project Introduction | 2025-06-09 | 1 | 2025-06-10 | 2025-06-07 | 1 | 2025-06-09 | 100% | 100%
1.3 | HSE | 2025-06-09 | 10 | 2025-06-24 | 2025-06-07 | 10 | 2025-06-23 | 100% | 100%
1.4 | Installer Kick Off | 2025-06-09 | 1 | 2025-06-10 | 2025-06-07 | 1 | 2025-06-09 | 100% | 100%
1.5 | Project Review | 2025-06-09 | 1 | 2025-06-10 | 2025-06-03 | 1 | 2025-06-04 | 100% | 100%
2 | Site Establishment | 2025-06-23 | 1 | 2025-06-24 | 2025-06-07 | 17 | 2025-06-24 | 100% | 100%
2.1 | Solar Contractor Establishment | 2025-06-23 | 1 | 2025-06-24 | 2025-06-23 | 1 | 2025-06-24 | 100% | 100% |  | 63 | Net Work Days
3 | AC Installation | 2025-06-02 | 46 | 2025-07-18 | 2025-06-02 | 94 | 2025-09-04 | 100% | 100% |  | 12.6 | Total Weeks
3.1 | Inverters delivered | 2025-06-24 | 1 | 2025-06-25 | 2025-06-24 | 1 | 2025-06-25 | 100% | 100% |  | 20.3968 | kW/Week Installation Rate
3.2 | Inverters Mounted | 2025-06-25 | 5 | 2025-07-02 | 2025-07-22 | 2 | 2025-07-24 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-06-02 | 25 | 2025-07-08 | 2025-06-02 | 61 | 2025-08-27 | 100% | 100%
3.4 | AC Works | 2025-07-08 | 8 | 2025-07-18 | 2025-08-27 | 5 | 2025-09-03 | 100% | 100%
3.5 | AC Tie-In | 2025-07-08 | 3 | 2025-07-11 | 2025-09-03 | 1 | 2025-09-04 | 100% | 100%
4 | DC Works | 2025-06-23 | 29 | 2025-07-22 | 2025-06-23 | 51 | 2025-08-13 | 100% | 100%
4.1 | Lifeline Installation (If Applicable) | [6 empty] | 0% | 0%
4.1 | Mounting Structure delivered | 2025-06-23 | 1 | 2025-06-24 | 2025-06-23 | 1 | 2025-06-24 | 100% | 100%
4.2 | Mounting Structure installation | 2025-06-24 | 14 | 2025-07-14 | 2025-06-24 | 7 | 2025-07-20 | 100% | 100%
4.3 | DC Cable delivered | 2025-06-23 | 1 | 2025-06-24 | 2025-06-24 | 1 | 2025-06-25 | 100% | 100%
4.3 | DC Stringing | 2025-07-14 | 6 | 2025-07-22 | 2025-07-17 | 19 | 2025-08-13 | 100% | 100%
5 | Module installation | 2025-07-07 | 10 | 2025-07-17 | 2025-06-24 | 57 | 2025-08-20 | 100% | 100%
5.1 | Module delivery | 2025-07-07 | 1 | 2025-07-08 | 2025-06-24 | 1 | 2025-06-25 | 100% | 100%
5.2 | Module mounting | 2025-07-08 | 7 | 2025-07-17 | 2025-08-08 | 8 | 2025-08-20 | 100% | 100%
6 | Commissioning | 2025-07-22 | 2 | 2025-07-24 | 2025-09-11 | 6 | 2025-09-17 | 100% | 100%
6.1 | Commissioning | 2025-07-22 | 1 | 2025-07-23 | 2025-09-11 | 1 | 2025-09-12 | 100% | 100%
6.2 | Practical Completion | 2025-07-23 | 1 | 2025-07-24 | 2025-09-12 | 3 | 2025-09-17 | 100% | 100%
7 | QA Inspections | 2025-07-24 | 1 | 2025-07-25 | 2025-09-12 | 3 | 2025-09-15 | 100% | 100%
7.1 | Red-Team Inspection | 2025-07-24 | 1 | 2025-07-25 | 2025-09-12 | 1 | 2025-09-15 | 100% | 100%
8 | Project Closure | 2025-07-25 | 13 | 2025-08-07 | 2025-09-15 | 133 | 2026-01-26 | 100% | 100%
8.1 | Equipment serial numbers | 2025-07-25 | 2 | 2025-07-29 | 2025-09-15 | 2 | 2025-09-17 | 100% | 100%
8.2 | Snags completion | 2025-07-25 | 4 | 2025-07-31 | 2025-09-16 | 2 | 2025-09-18 | 100% | 100%
8.3 | System Performance Monitoring | 2025-07-31 | 5 | 2025-08-07 | 2025-09-18 | 5 | 2025-09-26 | 100% | 100%
8.4 | Handover documentation | 2025-07-25 | 4 | 2025-07-31 | 2025-09-16 | 4 | 2025-09-22 | 100% | 100%
8.5 | Handover to Client | 2025-07-31 | 1 | 2025-08-01 | 2026-01-23 | 1 | 2026-01-26 | 100% | 100% | Portfolio Handover
8.6 | Handover to Matriarch | 2025-07-27 | 5 | 2025-08-01 | 2025-10-15 | 10 | 2025-10-29 | 100% | 100%
Formulas:
Planned Start = MIN([Planned Start, row below]:E16)
Planned Start = [Planned Start, row above]
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = [Actual Start, row above]
Actual End = MAX([Actual End, row below]:K16)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C14)
Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 2655906.3007 |  | 2655906.3007 |  |  |  | Start Date | 2371815.3877 | 2087502.2068 | 284090.91 | 141847.23 | 284090.91 | 141847.23
2 | Planned Expenditure | 2415274.7995 |  | 2220751.0868 | VO PM Limit | Current VO Total
3 | Planned Profit | 240631.5012 |  | 435155.2139 | 12031.5751 | 39935 |  | End Date - PC
4 | Planned Margin | 9.06% |  | 16.38%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE |  | MILESTONE NOTES & COMMENTS
1 | Deposit |  | 20% | 531181.2601 |  | 2025-04-30 | 004728 | 2025-04-30 | 2025-04-30
2 | Delivery of Panels |  | 20% | 531181.2601 |  | 2025-07-14 | 004728 | 2025-04-30 | 2025-07-04
3 | Delivery of Inverters |  | 15% | 398385.9451 |  | 2025-07-01 | 004728 | 2025-04-30 | 2025-07-04
4 | Commissioning Complete |  | 15% | 398385.9451 |  | 2025-07-31 | 004728 | 2025-04-30 | 2025-09-18
5 | Final Completion Issued |  | 25% | 663976.5752 |  | 2025-08-01 | 004728 | 2025-04-30 | 2025-08-22
6 | Handover |  | 5% | 132795.315 |  | 2026-02-02 | 004728 | 2025-04-30 | 2025-09-26
7 | - |  | 0% | 0
|  |  | 100% | 2655906.3007
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 929567.2052
2 | Delivery of Panels |  | 30% | 796771.8902
3 | Delivery of Inverters |  | 20% | 531181.2601
4 | Practical Completion |  | 10% | 265590.6301
5 | Handover |  | 5% | 132795.315
| Total |  | 100% | 2655906.3007
|  |  | 100% | 2655906.3007

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 2415274.7995 |  | 2220751.0868 | 194523.7127
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 560797.4 |  | 512827 | 47970.4
2 | 2. Inverters | 160000 |  | 137740.7 | 22259.3
3 | 3. Mounting Structures | 115830 |  | 82657.4 | 33172.6
4 | 4. DC Equipment | 203544 |  | 206242.264 | -2698.264
5 | 5. Monitoring | 49000 |  | 101514.84 | -52514.84
6 | 6. AC Equipment | 306751.8174 |  | 208384.924 | 98366.8934
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 250000 |  | 49132.22 | 200867.78
9 | 9. AC & DC installation | 210650 |  | 289124 | -78474
10 | 10. Site Logistics | 60396.6667 |  | 65924.73 | -5528.0633
11 | 11. Due Dilligence | 29000 |  | 22077.23 | 6922.77
12 | 12. BDP Commission | 52821.549 |  | 0 | 52821.549
13 | 13. Engineering | 112108.3664 |  | 33198.8288 | 78909.5376
14 | 14. General Expenses | 4375 |  | 33819.85 | -29444.85
15 | 15. Service Add On | 300000 |  | 478107.1 | -178107.1
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 2415274.7995 | 2655906.3007 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 2220751.0868
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 560797.4 | 2025-07-29 | 560797.4 | 637269.7727 |  | 1 | 1. Panels | Jinko 620W - Menlo | 415 | 1233.8 | 512027 | PO3909-DIP-PH2-CORP-20250514 | Menlo INV0003028 | 2025-06-30 | 637269.7727 | 0 | 2025-07-29 | 512827
1 |  | Delivery Budget | [7 empty] | 1 | 1. Panels |  |  | 1.99 |  |  |  |  | 0
1 | [5 empty] | 2025-11-07 |  |  |  | 1 | 1. Panels |  |  | 800 | 800 |  | Menlo - INV0003230 | 2025-09-30 | 0 |  | 2025-11-06
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 306751.8174
2 | Inverters | Inverter Budget |  |  | 160000 | 2025-07-29 | 160000 | 181818.1818 |  | 2 | 2. Inverters | Huawei 100KTL | 2 | 68870 | 137740.7 | PO3909-DIP-PH2-CORP-20250514 | Menlo INV0003028 | 2025-06-30 | 181818.1818 | 0 | 2025-07-29 | 137740.7 | DC Equipment | 117304
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | AC Labour | 64350
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 146300
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 20355
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 1541.6667
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 115830 | 2025-07-29 | 115830 | 131625 |  | 3 | 3. Mounting Structures | Schletter Structure |  |  | 82657.4 | PO3902-DSS-20250603 - RV Approved | Schletter - INV1883 | 2025-06-30 | 131625 | 0 | 2025-07-29 | 82657.4 | Other | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Total | 665102.4841
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Less 15% | 565337.1114
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | R/Wp | 2.1998
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL | Installer Price
[23 empty] | AC Equipment | 108910.56
4 | DC Equipment | DC Cable Budget | 7084 |  | 86240 | 2025-07-29 | 203544 | 231300 |  | 4 | 4. DC Equipment | DC Cable - Menlo | 6000 | 13.4 | 80400 | PO3909-DIP-PH2-CORP-20250514 | Menlo INV0003028 | 2025-06-30 | 90168.3275 | 0 | 2025-07-29 | 206242.264 | DC Equipment | 125842.26
4 |  | DC Equipment Budget |  |  | 117304 | 2025-07-29 |  |  |  | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | AC Labour | 98004
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | DC Labour | 191120
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Logistics | 49778
4 | [5 empty] | 2025-06-19 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 125842.26 | 10% | 11730.4 |  | The Greenway - INV0001397 | 2025-06-30 | 13155.6038 |  | 2025-06-19 |  | Scaffolding
[6 empty] | 2025-06-26 |  |  |  | 4 | 4. DC Equipment | Project Kick Off (top up) |  |  | 853.83 |  | The Greenway - INV0001403 | 2025-06-30 | 957.5675 |  | 2025-06-26
4 | [5 empty] | 2025-06-26 |  |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 18876.339 |  | The Greenway - INV0001404 | 2025-06-30 | 21169.7502 |  | 2025-06-26 |  | Storage
4 | [5 empty] | 2025-09-25 |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 25168.452 |  | The Greenway- INV0001426 | 2025-07-31 | 28226.3336 |  | 2025-09-25 |  | Telehandler | 0
4 | [5 empty] | 2025-09-25 |  |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 31460.565 |  | The Greenway- INV0001426 | 2025-07-31 | 35282.917 |  | 2025-09-25 |  | HSE | 0
4 | [5 empty] | 2025-09-25 |  |  |  | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 12584.226 |  | The Greenway- INV0001426 | 2025-07-31 | 14113.1668 |  | 2025-09-25 |  | Other | 0
4 | [5 empty] | 2025-09-25 |  |  |  | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 12584.226 |  | The Greenway- INV0001426 | 2025-07-31 | 14113.1668 |  | 2025-09-25 |  | Other | 0
4 | [5 empty] | 2025-10-02 |  |  |  | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 6292.113 |  | The Greenway- INV0001426 | 2025-07-31 | 7056.5834 |  | 2026-01-15 |  | Total | 573654.82
4 | [5 empty] | 2025-10-31 |  |  |  | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 6292.113 |  | The Greenway- INV0001426 | 2025-07-31 | 7056.5834 |  | 2026-01-15 |  | R/Wp | 2.2321
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 34000 | 2025-07-17 | 49000 | 55681.8182 |  | 5 | 5. Monitoring | Smartlogger - Menlo |  |  | 8598.35 | PO3909-DIP-PH2-CORP-20250514 | Menlo INV0002936 | 2025-05-31 | 9244.4169 | 0.0013887 | 2025-07-17 | 101514.84
[6 empty] | 2025-11-08 |  |  |  | 5 | 5. Monitoring |  |  |  | 8598.34 |  | Menlo INV0003243 | 2025-09-30 | 0 |  | 2025-11-06
[10 empty] | 5 | 5. Monitoring | Smartlogger - Menlo RMA replacement |  |  | -8598.35 |  |  |  | 0
5 |  | Revenue Metering |  |  | 15000 | 2025-05-31 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 27555 | PO3839-DIP-Ph2-Corp-20250429 - RV Approved | Accuenergy Inv: ASAI-005365 | 2025-04-30 | 10673.107 |  | 2025-05-31
[6 empty] | 2025-07-29 |  |  |  | 5 | 5. Monitoring |  |  |  | 214.29 |  | Accenergy - INV ASAI-005800 | 2025-06-30 | 117.9608 |  | 2025-07-29
5 | [5 empty] | 1900-01-29 |  |  |  | 5 | 5. Monitoring | Techsitter |  |  | 11169 |  | Matriarch - INV-4999 | 2025-08-31 | 7650.358 |  | 2025-09-30
5 | [5 empty] | 2025-05-22 |  |  |  | 5 | 5. Monitoring | UPS |  |  | 2250.5 |  | Frontline INV725690 | 2025-05-31 | 1267.6392 |  | 2025-05-22
5 | [5 empty] | 2025-08-31 |  |  |  | 5 | 5. Monitoring | Apex Device and License - Allocated to IconSA KZN |  |  | 44000 | PO4176-DCP-20250728 - RV Approved | Rubicon INVWCRE-0069677 | 2025-07-31 | 22474.8193 |  | 2025-08-31
[10 empty] | 5 | 5. Monitoring | Apex Device and License - Allocated to IconSA KZN |  |  | -44000 |  | Allocated to Icon SA - KZN | 2025-10-31 |  |  | 2025-10-31
[10 empty] | 5 | 5. Monitoring | Apex Device allocated from Seshego Circle |  |  | 44000 | PO4077-DSHC-20250630 - RV Approved | Allocated from Seshego Circle | 2025-10-31 |  |  | 2025-10-31
[6 empty] | 2025-09-30 |  |  |  | 5 | 5. Monitoring | Delivery of Apex |  |  | 193.15 |  | DSV Inv: 180144979 | 2025-08-31 | 105.9445 |  | 2025-09-30
5 | [5 empty] | 2025-06-05 |  |  |  | 5 | 5. Monitoring | GivEnergy - Transceiver Kit |  |  | 7534.56 | PO3972-DIP-Ph2-Corp P-20250530 - RV Approved | GivEnergy: INV000009 | 2025-06-30 | 4147.5709 |  | 2025-06-05
5 | [5 empty] | 2025-06-06 |  |  |  | 5 | 5. Monitoring | [7 empty] | 0
2025-06-07
6 | AC Equipment | AC Equipment Budget |  |  | 306751.8174 | 2025-06-08 | 306751.8174 | 348581.6107 |  | 6 | 6. AC Equipment | [7 empty] | 0 | 0.0028194 |  | 208384.924
6 | [5 empty] | 1900-01-29 |  |  |  | 6 | 6. AC Equipment | PVDB |  |  | 99474.36 | PO3930-DIP-Ph2-Corp P-20250519 - RV Approved | Switchboard 2-SOI002242 | 2025-08-31 | 165848.3605 |  | 2025-09-30
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [5 empty] | 2025-06-19 |  |  |  | 6 | 6. AC Equipment | Project Kick Off | 108910.56 | 10% | 9472.63 |  | The Greenway - INV0001397 | 2025-06-30 | 16036.9872 |  | 2025-06-19
[6 empty] | 2025-06-26 |  |  |  |  | 6. AC Equipment | Project Kick Off (top up) |  |  | 1418.43 |  | The Greenway - INV0001403 | 2025-06-30 | 2401.3757 |  | 2025-06-26
6 | [5 empty] | 2025-06-26 |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 16336.584 |  | The Greenway - INV0001404 | 2025-06-30 | 27657.5343 |  | 2025-06-26
6 | [5 empty] | 2025-09-25 |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 21782.112 |  | The Greenway- INV0001426 | 2025-07-31 | 36436.6267 |  | 2025-09-25
6 | [5 empty] | 2025-09-25 |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 27227.64 |  | The Greenway- INV0001426 | 2025-07-31 | 45545.7834 |  | 2025-09-25
6 | [5 empty] | 2025-09-25 |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 10891.056 |  | The Greenway- INV0001426 | 2025-07-31 | 18218.3133 |  | 2025-09-25
6 | [5 empty] | 2025-09-25 |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 10891.056 |  | The Greenway- INV0001426 | 2025-07-31 | 18218.3133 |  | 2025-09-25
6 | [5 empty] | 2025-10-02 |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 5445.528 |  | The Greenway- INV0001426 | 2025-07-31 | 9109.1567 |  | 2025-12-18
6 | [5 empty] | 2025-10-31 |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 5445.528 |  | The Greenway- INV0001426 | 2025-07-31 | 9109.1567 |  | 2026-01-15
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 250000 | 284090.9091 |  | 8 | 8. Product Add On | [7 empty] | 0 | -0.0009045 |  | 49132.22
8 |  | MV Metering |  |  | 250000 | 2025-09-30 |  |  |  | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | E-Stop |  |  | 5203 | PO4383-DCP-20251020 - RV Approved | The Greenway - INV0001510 | 2025-10-31 | 16658.2669 |  | 2026-02-13
[10 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [5 empty] | 0 |  |  |  | 8 | 8. Product Add On | Inverter Cage with roof - Deposit | 75% | 35400 | 26550 | PO4483-DCP-20251124 - RV Approved | Van Staden Three - Inv3075 | 2025-11-30 | 188952.7162 |  | 2025-11-28
8 | [9 empty] | 8 | 8. Product Add On | Inverter Cage with roof - Balance | 25% |  | 8850 |  | Van Staden Three - Inv3110 | 2025-12-31 | 51172.2154 |  | 2026-01-09
8 | [9 empty] | 8 | 8. Product Add On | Waterpoints |  |  | 8529.22 |  | Toys 4Boys - 12392 | 2025-10-31 | 27307.7115 |  | 2025-11-28
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 64350 | 2025-09-30 | 210650 | 247823.5294 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0 |  | 289124
9 |  | DC Installation Budget |  |  | 146300 | 2025-06-19 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 289124 | 10% | 21065 |  | The Greenway - INV0001397 | 2025-06-30 | 18055.9298 |  | 2025-06-19
[6 empty] | 2025-06-26 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off (top up) |  |  | 7847.4 |  | The Greenway - INV0001403 | 2025-06-30 | 6726.4231 |  | 2025-06-26
9 | [5 empty] | 2025-06-26 |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 43368.6 |  | The Greenway - INV0001404 | 2025-06-30 | 37173.5294 |  | 2025-06-26
9 | [5 empty] | 2025-09-25 |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 57824.8 |  | The Greenway- INV0001426 | 2025-08-31 | 49564.7059 |  | 2025-09-25
9 | [5 empty] | 2025-09-25 |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 72281 |  | The Greenway- INV0001426 | 2025-08-31 | 61955.8824 |  | 2025-09-25
9 | [5 empty] | 2025-09-25 |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 28912.4 |  | The Greenway- INV0001426 | 2025-08-31 | 24782.3529 |  | 2025-09-25
9 | [5 empty] | 2025-09-25 |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 28912.4 |  | The Greenway- INV0001426 | 2025-08-31 | 24782.3529 |  | 2025-09-25
9 | [5 empty] | 2025-10-02 |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 14456.2 |  | The Greenway- INV0001426 | 2025-08-31 | 12391.1765 |  | 2025-12-18
9 | [5 empty] | 2025-10-31 |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 14456.2 |  | The Greenway- INV0001426 | 2025-08-31 | 12391.1765 |  | 2026-01-15
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-09-30 | 60396.6667 | 71054.902 |  | 10 | 10. Site Logistics | [7 empty] | 0 | -0.0036449 |  | 65924.73
10 |  | Scaffolding |  |  | 20355 | 2025-09-30 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Security |  |  | 30000 | 2025-09-30 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 1541.6667 | 2025-09-30 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [5 empty] | 2025-06-19 |  |  |  | 10 | 10. Site Logistics | Project Kick Off | 69585 | 10% | 3039.66 |  | The Greenway - INV0001397 | 2025-06-30 | 2064.1886 |  | 2025-06-19
[6 empty] | 2025-06-26 |  |  |  | 10 | 10. Site Logistics | Project Kick Off (top up) |  |  | 2196.44 |  | The Greenway - INV0001403 | 2025-06-30 | 1316.1557 |  | 2025-06-26
[6 empty] | 2025-08-31 |  |  |  | 10 | 10. Site Logistics |  |  |  | 2196.44 |  | The Greenway - INV0001403 | 2025-08-31 | 0 |  | 2025-08-31
[6 empty] | 2025-08-31 |  |  |  | 10 | 10. Site Logistics |  |  |  | -1938.13 |  | The Greenway - INV0001403 | 2025-08-31 |  |  | 2025-08-31
10 | [5 empty] | 2025-06-26 |  |  |  | 10 | 10. Site Logistics | Site Establishment |  | 15% | 7854.15 |  | The Greenway - INV0001404 | 2025-06-30 | 5070.5267 |  | 2025-06-26
[6 empty] | 2025-08-31 |  |  |  | 10 | 10. Site Logistics |  |  |  | -7466.7 |  | The Greenway - INV0001404 | 2025-08-31 | 0 |  | 2025-08-31
[6 empty] | 2025-08-31 |  |  |  | 10 | 10. Site Logistics |  |  |  | 7854.15 |  | The Greenway - INV0001404 | 2025-08-31 | 0 |  | 2025-08-31
10 | [5 empty] | 2025-09-25 |  |  |  | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 13917 |  | The Greenway- INV0001426 | 2025-07-31 | 20529.7792 |  | 2025-09-25
10 | [5 empty] | 2025-09-25 |  |  |  | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 17396.25 |  | The Greenway- INV0001426 | 2025-07-31 | 19124.6615 |  | 2025-09-25
10 | [5 empty] | 2025-09-25 |  |  |  | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 6958.5 |  | The Greenway- INV0001426 | 2025-07-31 | 7649.8646 |  | 2025-09-25
[6 empty] | 2025-08-31 |  |  |  | 10 | 10. Site Logistics |  |  |  | 6958.49 |  | The Greenway- INV0001426 | 2025-08-31 | 0 |  | 2025-08-31
[6 empty] | 2025-08-31 |  |  |  | 10 | 10. Site Logistics |  |  |  | -6958.5 |  | The Greenway- INV0001426 | 2025-08-31 | 0 |  | 2025-08-31
10 | [5 empty] | 2025-09-25 |  |  |  | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 6958.5 |  | The Greenway- INV0001426 | 2025-07-31 | 7649.8646 |  | 2025-09-25
[6 empty] | 2025-08-31 |  |  |  | 10 | 10. Site Logistics |  |  |  | -6958.5 |  | The Greenway- INV0001426 | 2025-08-31 | 0 |  | 2025-08-31
[6 empty] | 2025-08-31 |  |  |  | 10 | 10. Site Logistics |  |  |  | 6958.49 |  | The Greenway- INV0001426 | 2025-08-31 | 0 |  | 2025-08-31
10 | [5 empty] | 2025-10-02 |  |  |  | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 3479.25 |  | The Greenway- INV0001426 | 2025-07-31 | 3824.9323 |  | 2025-12-18
10 | [5 empty] | 2025-10-31 |  |  |  | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 3479.25 |  | The Greenway- INV0001426 | 2025-07-31 | 3824.9323 |  | 2026-01-15
10 | [5 empty] | 2025-08-31 |  |  |  | 10 | 10. Site Logistics | Contingency |  |  | 3479.24 |  | The Greenway- INV0001426 | 2025-08-31 | 0 |  | 2025-08-31
10 | [5 empty] | 2025-08-31 |  |  |  | 10 | 10. Site Logistics |  |  |  | -3479.25 |  | The Greenway- INV0001426 | 2025-08-31 | 0 |  | 2025-08-31
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2025-09-18 | 29000 | 34117.6471 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 7057.63 |  | Sunspot - E027 | 2025-07-31 | 14423.516 | -0.0005975 | 2025-09-18 | 22077.23
11 |  | Structural Sign Off |  |  | 18000 | 2025-04-10 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 9019.6 | PO3745-DIP-Ph2-20250313 - RV Approved | L&B Consulting - Invoice 1934 | 2025-04-30 | 11826.7587 |  | 2025-04-10
11 | [5 empty] | 2025-08-31 |  |  |  | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 |  | Matriarch - INV-4987 | 2025-08-31 | 7867.373 |  | 2025-08-31
11 | [9 empty] | 11 | 11. Due Dilligence | [7 empty] | 0
11 | [9 empty] | 11 | 11. Due Dilligence | [7 empty] | 0
12 | BDP Commission | Referral Fee |  |  | 44017.9575 | 2025-08-31 | 52821.549 | 0 |  | 12 | 12. BDP Commission | Referral Fee | [9 empty] | 0
12 | BDP Commission | PD Fee |  |  | 8803.5915 | 2025-08-31 |  |  |  | 12 | 12. BDP Commission | PD Fee
2025-08-31
13 | Engineering | Matriarch Defects Period |  |  | 21199.6236 | 2025-08-31 | 112108.3664 | 127395.8709 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 33198.8288 |  | Matriarch - INV-4986 | 2025-08-31 | 127395.8709 | 0 | 2025-08-31 | 33198.8288
13 |  | Management |  |  | 14285.7143 | 2025-08-31 |  |  |  | 13 | 13. Engineering | Management |  |  | 0 |  |  |  | 0
13 |  | Project manager |  |  | 42500 | 2025-08-31 |  |  |  | 13 | 13. Engineering | Project manager |  |  | 0 |  |  |  | 0
13 |  | Planner time |  |  | 18571.4286 | 2025-08-31 |  |  |  | 13 | 13. Engineering | Planner time |  |  | 0 |  |  |  | 0
13 |  | De Snagging |  |  | 15551.6 | 2025-08-31 |  |  |  | 13 | 13. Engineering | De Snagging |  |  | 0 |  |  |  | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 4375 | 2025-05-08 | 4375 | 5147.0588 |  | 14 | 14. General Expenses | Travel |  |  | 7750 |  | Site Visit | 2025-04-30 | 3545.7516 | 0.0039511 | 2025-05-08 | 33819.85
14 | [5 empty] | 2025-04-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claims | 2025-04-30 | 0 |  | 2025-04-30
14 | [5 empty] | 2025-06-09 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 7624.05 |  | Expense Claims | 2025-05-31 | 1196.4605 |  | 2025-06-09
14 | [5 empty] | 2025-07-04 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 12174.8 |  | Expense Claims | 2025-06-30 | 287.3428 |  | 2025-07-04
14 | [5 empty] | 2025-07-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claims | 2025-07-31 | 0 |  | 2025-07-31
14 | [5 empty] | 2025-09-05 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 3061.43 |  | Expense Claims | 2025-08-31 | 117.5 |  | 2025-09-05
14 | [5 empty] | 2025-09-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 1307.83 |  | Expense Claims | 2025-09-30 | 0 |  | 2025-10-10
14 | [5 empty] | 2025-10-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 1901.74 |  | Expense Claims | 2025-10-31 | 0 |  | 2025-11-06
14 | [5 empty] | 2025-11-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  |  | 0
14 | [5 empty] | 2025-12-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  |  | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | Welcome Bonus |  |  | 300000 | 2025-07-11 | 300000 | 300000 |  | 15 | 15. Service Add On | Welcome Bonus - Site Establishment |  |  | 199000 |  | Luxanio Trading - 23407/202506/274904/I | 2025-06-30 | 150000 | 0 | 2025-07-11 | 478107.1
15 | [5 empty] | 2025-09-25 |  |  |  | 15 | 15. Service Add On | Welcome Bonus - Commissioning |  |  | 199000 |  | Luxanio Trading - 23407/202506/274904/I | 2025-06-30 | 150000 |  | 2025-09-25
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | Courier of EE Sonel Meter for Curve Testing |  |  | 237.1 |  | DSV Inv:180147748 | 2025-09-30 | 0 |  | 2025-10-31
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | Standing time and delay - VO | 50% | 79870 | 39935 |  | Greenway Solar INV0001515 | 2025-10-31 |  |  | 2025-11-06
15 | [9 empty] | 15 | 15. Service Add On |  | 50% |  | 39935 |  | Greenway Solar INV0001515 | 2025-10-31 |  |  | 2026-02-05
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
| Panel Procurement Budget | 560797.4 |  | 637269.7727
| Inverter Procurement Budget | 160000 |  | 181818.1818
| Mounting Structure Budget | 115830 |  | 131625
| DC Equipment Budget | 203544 |  | 231300
| AC Equipment Budget | 306751.8174 |  | 348581.6107
| Monitoring Budget | 49000 |  | 55681.8182
| Optional Extras Budget | 0 |  | 0
| MV Metering Budget | 250000 |  | 284090.9091
| ADD ON | 0 |  | 0
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 64350 |  | 75705.8824
| DC Installer Budget | 146300 |  | 172117.6471
| In-House Expense Budget | 112108.3664 |  | 127395.8709
| Compliance Budget | 29000 |  | 34117.6471
| Offloading Budget | 8500 |  | 10000
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 1541.6667 |  | 1813.7255
| On Site Security | 30000 |  | 35294.1176
| Roof Access Budget for Installers | 20355 |  | 23947.0588
| EPC Management Fee | 0 |  | 0
| ADD ON | 300000 |  | 300000
Expenses
| Total EE Expense Budget | 8750 |  | 5147.0588
Note on W170: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please add a payment date
Note on W172: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 2655906.3007 | 2655906.3007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 531181.2601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 398385.9451 | 0 | 531181.2601 | 0 | 1062362.5203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132795.315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 531181.2601 | 531181.2601 | 531181.2601 | 531181.2601 | 531181.2601 | 531181.2601 | 531181.2601 | 531181.2601 | 531181.2601 | 929567.2052 | 929567.2052 | 1460748.4654 | 1460748.4654 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2523110.9856 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007
| Planned Expenditure | 2415274.7995 | 2415274.7995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 4375 | 0 | 0 | 15000 | 306751.8174 | 0 | 146300 | 0 | 0 | 300000 | 34000 | 0 | 1040171.4 | 0 | 0 | 0 | 164929.9154 | 0 | 0 | 11000 | 0 | 374746.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 18000 | 18000 | 18000 | 22375 | 22375 | 22375 | 37375 | 344126.8174 | 344126.8174 | 490426.8174 | 490426.8174 | 490426.8174 | 790426.8174 | 824426.8174 | 824426.8174 | 1864598.2174 | 1864598.2174 | 1864598.2174 | 1864598.2174 | 2029528.1328 | 2029528.1328 | 2029528.1328 | 2040528.1328 | 2040528.1328 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995 | 2415274.7995
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18000 | -18000 | -18000 | 513181.2601 | 508806.2601 | 508806.2601 | 508806.2601 | 493806.2601 | 187054.4427 | 187054.4427 | 40754.4427 | 40754.4427 | 439140.3878 | 139140.3878 | 636321.648 | 636321.648 | 658512.7682 | 658512.7682 | 658512.7682 | 658512.7682 | 493582.8528 | 493582.8528 | 493582.8528 | 482582.8528 | 482582.8528 | 107836.1861 | 107836.1861 | 107836.1861 | 107836.1861 | 107836.1861 | 107836.1861 | 107836.1861 | 107836.1861 | 107836.1861 | 107836.1861 | 107836.1861 | 107836.1861 | 107836.1861 | 107836.1861 | 107836.1861 | 107836.1861 | 107836.1861 | 107836.1861 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012 | 240631.5012
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 2655906.3007 | 2655906.3007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 531181.2601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 929567.2052 | 0 | 0 | 0 | 0 | 0 | 0 | 663976.5752 | 0 | 0 | 0 | 398385.9451 | 132795.315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 531181.2601 | 531181.2601 | 531181.2601 | 531181.2601 | 531181.2601 | 531181.2601 | 531181.2601 | 531181.2601 | 531181.2601 | 1460748.4654 | 1460748.4654 | 1460748.4654 | 1460748.4654 | 1460748.4654 | 1460748.4654 | 1460748.4654 | 2124725.0405 | 2124725.0405 | 2124725.0405 | 2124725.0405 | 2523110.9856 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007 | 2655906.3007
| Actual + Planned Expenditure | 2220751.0868 | 2229349.4368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9019.6 | 0 | 0 | 0 | 7750 | 0 | 2250.5 | 27555 | 7534.56 | 7624.05 | 45307.69 | 98751.773 | 12174.8 | 199000 | 8598.35 | 0 | 813039.39 | 0 | 0 | 0 | 83844.5588 | 3061.43 | 0 | 7057.63 | 584750.183 | 110836.51 | 1307.83 | 0 | 0 | 237.1 | 51235.08 | 0 | 0 | 35079.22 | 0 | 0 | 23380.978 | 0 | 0 | 8850 | 35965.204 | 0 | 0 | 39935 | 5203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9019.6 | 9019.6 | 9019.6 | 9019.6 | 16769.6 | 16769.6 | 19020.1 | 46575.1 | 54109.66 | 61733.71 | 107041.4 | 205793.173 | 217967.973 | 416967.973 | 425566.323 | 425566.323 | 1238605.713 | 1238605.713 | 1238605.713 | 1238605.713 | 1322450.2718 | 1325511.7018 | 1325511.7018 | 1332569.3318 | 1917319.5148 | 2028156.0248 | 2029463.8548 | 2029463.8548 | 2029463.8548 | 2029700.9548 | 2080936.0348 | 2080936.0348 | 2080936.0348 | 2116015.2548 | 2116015.2548 | 2116015.2548 | 2139396.2328 | 2139396.2328 | 2139396.2328 | 2148246.2328 | 2184211.4368 | 2184211.4368 | 2184211.4368 | 2224146.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368 | 2229349.4368
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9019.6 | -9019.6 | -9019.6 | 522161.6601 | 514411.6601 | 514411.6601 | 512161.1601 | 484606.1601 | 477071.6001 | 469447.5501 | 424139.8601 | 325388.0871 | 1242780.4924 | 1043780.4924 | 1035182.1424 | 1035182.1424 | 222142.7524 | 222142.7524 | 222142.7524 | 886119.3275 | 802274.7688 | 799213.3388 | 799213.3388 | 1190541.6539 | 738586.7859 | 627750.2759 | 626442.4459 | 626442.4459 | 626442.4459 | 626205.3459 | 574970.2659 | 574970.2659 | 574970.2659 | 539891.0459 | 539891.0459 | 539891.0459 | 516510.0679 | 516510.0679 | 516510.0679 | 507660.0679 | 471694.8639 | 471694.8639 | 471694.8639 | 431759.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639 | 426556.8639
|  | CHECK | CHECK
| Revenue Recognition | 0.0030123 | 2655906.2977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26045.6173 | 0 | 0 | 0 | 11708.5166 | 0 | 0 | 0 | 0 | 1497219.7287 | 0 | 0 | 0 | 341988.471 | 0 | 0 | 0 | 494853.054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43965.9784 | 0 | 0 | 0 | 188952.7162 | 0 | 0 | 0 | 0 | 51172.2154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 2655906.2977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26045.6173 | 26045.6173 | 26045.6173 | 26045.6173 | 37754.1339 | 37754.1339 | 37754.1339 | 37754.1339 | 37754.1339 | 1534973.8626 | 1534973.8626 | 1534973.8626 | 1534973.8626 | 1876962.3336 | 1876962.3336 | 1876962.3336 | 1876962.3336 | 2371815.3877 | 2371815.3877 | 2371815.3877 | 2371815.3877 | 2371815.3877 | 2371815.3877 | 2371815.3877 | 2371815.3877 | 2371815.3877 | 2415781.366 | 2415781.366 | 2415781.366 | 2415781.366 | 2604734.0822 | 2604734.0822 | 2604734.0822 | 2604734.0822 | 2604734.0822 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977 | 2655906.2977

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | Grand Total
(blank)
1. Panels |  |  |  | 637269.7727 |  |  | 0 |  |  |  | 0 | 637269.7727
2. Inverters |  |  |  | 181818.1818 | [6 empty] | 0 | 181818.1818
3. Mounting Structures |  |  |  | 131625 | [6 empty] | 0 | 131625
4. DC Equipment |  |  |  | 124493.6815 | 105848.751 | [5 empty] | 0 | 230342.4325
5. Monitoring | 0 | 10673.107 | 10512.0561 | 4265.5318 | 22474.8193 | 7756.3026 | 0 |  |  |  |  | 55681.8168
6. AC Equipment |  |  |  | 46095.8972 | 136637.3501 | 165848.3605 |  |  |  |  | 0 | 348581.6079
8. Product Add On | 0 | [6 empty] | 43965.9784 | 188952.7162 | 51172.2154 | 0 | 284090.91
9. AC & DC installation |  |  |  | 61955.8824 |  | 185867.6471 |  |  |  |  | 0 | 247823.5294
10. Site Logistics | 0 |  |  | 8450.871 | 62604.0346 | 0 |  |  |  |  | 0 | 71054.9056
11. Due Dilligence |  | 11826.7587 |  |  | 14423.516 | 7867.373 |  |  |  |  | 0 | 34117.6477
13. Engineering | 0 |  |  |  |  | 127395.8709 |  |  |  |  | 0 | 127395.8709
14. General Expenses | 0 | 3545.7516 | 1196.4605 | 287.3428 | 0 | 117.5 | 0 | 0 |  |  | 0 | 5147.0549
15. Service Add On |  |  |  | 300000 |  |  | 0 |  |  |  | 0 | 300000
12. BDP Commission
7.BESS
4. DC Equipment |  |  |  | 957.5675 | [7 empty] | 957.5675
Grand Total | 0 | 26045.6173 | 11708.5166 | 1497219.7287 | 341988.471 | 494853.054 | 0 | 43965.9784 | 188952.7162 | 51172.2154 | 0 | 2655906.2977

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | Grand Total
(blank)
1. Panels |  |  |  | 512027 |  |  | 800 |  |  |  | 512827
2. Inverters |  |  |  | 137740.7 | [6 empty] | 137740.7
3. Mounting Structures |  |  |  | 82657.4 | [6 empty] | 82657.4
4. DC Equipment |  |  |  | 111006.739 | 94381.695 | [5 empty] | 205388.434
5. Monitoring | -8598.35 | 27555 | 10848.85 | 7748.85 | 44000 | 11362.15 | 8598.34 | 0 |  |  | 101514.84
6. AC Equipment |  |  |  | 27227.644 | 81682.92 | 99474.36 |  |  |  |  | 208384.924
8. Product Add On | [7 empty] | 13732.22 | 26550 | 8850 | 49132.22
9. AC & DC installation |  |  |  | 72281 |  | 216843 |  |  |  |  | 289124
10. Site Logistics |  |  |  | 13090.25 | 52188.75 | 645.73 |  |  |  |  | 65924.73
11. Due Dilligence |  | 9019.6 |  |  | 7057.63 | 6000 |  |  |  |  | 22077.23
13. Engineering | 0 |  |  |  |  | 33198.8288 |  |  |  |  | 33198.8288
14. General Expenses | 0 | 7750 | 7624.05 | 12174.8 | 0 | 3061.43 | 1307.83 | 1901.74 |  |  | 33819.85
15. Service Add On |  |  |  | 398000 |  |  | 237.1 | 79870 |  |  | 478107.1
12. BDP Commission
7.BESS
4. DC Equipment |  |  |  | 853.83 | [6 empty] | 853.83
Grand Total | -8598.35 | 44324.6 | 18472.9 | 1374808.213 | 279310.995 | 370585.4988 | 10943.27 | 95503.96 | 26550 | 8850 | 2220751.0868

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 1.0813 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.55314 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.37422 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 0.89556 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
Corporate Park |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Corporate Park | 0 | 0 | 0