## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[9 empty] | 2026-02-27 | 2026-02-27
| PROJECT PLAN | Cascades Lifestyle Center | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 1510
| PROJECT DEVELOPER | Dayne Sage
| PROJECT MANAGERS | Lloyd Brown
| CONTRACT VALUE | 9650000
| Phase: | Commercial Close Out
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status |  | Comment
|  |  | 97 |  |  | 108 |  | 89.58%
1 | M1: Mobilisation |  |  |  | 2024-05-10 | 113 | 2024-08-31 | 100%
1.1 | Signed Project Task Order |  |  |  | 2024-06-11 | 36 | 2024-07-17 | 100%
1.2 | Proof of Required Insurance Policies per Master Contract Details (Deferred to M2) |  |  |  | 2024-07-05 | 57 | 2024-08-31 | 100% |  | M2
1.3 | Pre-Installation Roof Condition Report |  |  |  | 2024-06-20 | 20 | 2024-07-10 | 100%
1.4 | Structural Report |  |  |  | 2024-07-17 | 0 | 2024-07-17 | 100%
1.5 | Lightning Risk Assessment (BOQ & Quote) |  |  |  | 2024-05-10 | 105 | 2024-08-23 | 100%
1.6 | Detailed Design Drawings Package |  |  |  | 2024-06-24 | 53 | 2024-08-16 | 100%
1.7 | Bill of Materials |  |  |  | 2024-07-05 | 13 | 2024-07-18 | 100%
1.8 | Project Timeline/Programme |  |  |  | 2024-07-05 | 42 | 2024-08-16 | 100%
1.9 | H&S Plan Approved by Candi |  |  |  | 2024-07-16 | 31 | 2024-08-16 | 100%
1.10 | Signed Contractor Code of Conduct |  |  |  | 2024-07-05 | 5 | 2024-07-10 | 100%
1.11 | Grid Connection Application submitted to Municipality |  |  |  | 2024-05-28 | 43 | 2024-07-10 | 100%
2 | M2: Delivery of Major Components |  |  |  | 2024-07-05 | 84 | 2024-09-27 | 100%
2.1 | H&S File Approved by CANDI |  |  |  | 2024-07-05 | 35 | 2024-08-26 | 100%
2.2 | Construction Design Package Approved by Candi |  |  |  | 2024-07-30 | 59 | 2024-09-27 | 100% |  | Final approval Tie in 1 / Approved in theory
2.3 | Evidence demonstrating arrival to site of all Major Components |  |  |  | 2024-08-06 | 43 | 2024-09-18 | 100%
2.3.1 | Delivery of Inverters |  |  |  | 2024-08-06 | 0 | 2024-08-06 | 100%
2.3.2 | Delivery of Modules |  |  |  | 2024-08-22 | 21 | 2024-09-12 | 100%
2.3.2.1 | Delivery of Batch 1 |  |  |  | 2024-08-22 | 0 | 2024-08-22 | 100%
2.3.2.2 | Delivery of Batch 2 |  |  |  | 2024-09-05 | 0 | 2024-09-05 | 100%
2.3.2.3 | Delivery of Batch 3 |  |  |  | 2024-09-12 | 0 | 2024-09-12 | 100%
2.3.3 | Delivery of Mounting Structure |  |  |  | 2024-08-06 | 0 | 2024-08-06 | 100%
2.3.4 | Delivery of DC Cable |  |  |  | 2024-08-26 | 0 | 2024-08-26 | 100%
2.3.5 | Delivery of DBs |  |  |  | 2024-08-21 | 1 | 2024-09-18 | 100%
2.3.5.1 | PVDB 1&2 |  |  |  | 2024-09-17 | 1 | 2024-09-18 | 100%
2.3.5.2 | Comms DB, Meters, Sensors, Etc (Supplied by Candi) |  |  |  | 2024-08-21 | 1 | 2024-08-22 | 100%
2.4 | Photos of each of the aforementioned subsystem materials delivered to site |  |  |  | 2024-09-18 | 9 | 2024-09-27 | 100%
3 | Emergent Energy Construction |  |  |  | 2024-08-06 | 115 | 2024-11-29 | 100%
3.1 | Fixed Anchor Point & Lifeline Approvals |  |  |  | 2024-08-14 | 2 | 2024-08-16 | 100%
3.2 | Fixed Anchor Point & Lifeline Installation |  |  |  | 2024-08-16 | 5 | 2024-08-23 | 100%
3.3 | Fixed Anchor Point & Lifeline Sign Off |  |  |  | 2024-08-23 | 4 | 2024-08-29 | 100%
3.4 | SteelWork Fabrication (Offsite) |  |  |  | 2024-08-06 | 15 | 2024-08-28 | 100%
3.5 | SteelWork Installation (onsite) - CRITICAL PATH |  |  |  | 2024-10-09 | 16 | 2024-10-31 | 100%
3.6 | SteelWork Sign Off |  |  |  | 2024-10-31 | 1 | 2024-11-01 | 100%
3.7 | Mounting Structure Installation |  |  |  | 2024-08-28 | 12 | 2024-09-13 | 100%
3.8 | DC Cable Tray Installation & Earthing |  |  |  | 2024-08-31 | 43 | 2024-10-31 | 100% |  | Dependant on the approval from Candi
3.9 | DC Cable Stringing |  |  |  | 2024-10-31 | 4 | 2024-11-06 | 100% |  | Dependant on the approval from Candi
3.10 | DC Cable Termination |  |  |  | 2024-10-31 | 5 | 2024-11-07 | 100%
3.11 | String Voltage Tests |  |  |  | 2024-11-07 | 3 | 2024-11-12 | 100%
3.12 | Module Lifting - Batch 1 |  |  |  | 2024-09-05 | 5 | 2024-09-12 | 100%
3.13 | Module Mounting Batch 1 |  |  |  | 2024-09-12 | 4 | 2024-09-18 | 100%
3.14 | Module Lifting - Batch 2 |  |  |  | 2024-09-05 | 5 | 2024-09-12 | 100%
3.15 | Module Mounting Batch 2 |  |  |  | 2024-09-18 | 4 | 2024-09-25 | 100%
3.16 | Module Lifting - Batch 3 |  |  |  | 2024-09-08 | 5 | 2024-09-13 | 100%
3.17 | Module Mounting Batch 3 |  |  |  | 2024-09-25 | 5 | 2024-10-02 | 100%
3.18 | Inverter Installation - Tie In 1 |  |  |  | 2024-11-01 | 4 | 2024-11-07 | 100%
3.19 | Inverter Installation - Tie In 2 |  |  |  | 2024-10-14 | 5 | 2024-10-21 | 100%
3.20 | PVDB Installation - Tie In 1 |  |  |  | 2024-11-01 | 4 | 2024-11-07 | 100%
3.21 | PVDB Installation - Tie In 2 |  |  |  | 2024-10-21 | 9 | 2024-11-01 | 100%
3.22 | Candi Comms Board Installation |  |  |  | 2024-11-01 | 8 | 2024-11-13 | 100%
3.23 | Cable Tray Installation - Tie In 1 |  |  |  | 2024-08-31 | 43 | 2024-10-31 | 100%
3.24 | Cable Tray Installation - Tie In 2 |  |  |  | 2024-08-31 | 40 | 2024-10-28 | 100%
3.25 | Inverter AC Cable Installation - Tie In 1 |  |  |  | 2024-11-01 | 3 | 2024-11-06 | 100%
3.26 | Inverter AC Cable Installation - Tie In 2 |  |  |  | 2024-11-01 | 3 | 2024-11-06 | 100%
3.27 | AC Supply Cable Installation - Tie In 1 |  |  |  | 2024-11-06 | 2 | 2024-11-08 | 100%
3.28 | AC Supply Cable Installation - Tie In 2 |  |  |  | 2024-11-06 | 2 | 2024-11-08 | 100%
3.29 | AC Soft Commissioning |  |  |  | 2024-11-08 | 2 | 2024-11-12 | 100%
3.30 | Comms Soft Commissioning |  |  |  | 2024-11-08 | 3 | 2024-11-13 | 100%
3.31 | DC Soft Commissioning |  |  |  | 2024-11-07 | 4 | 2024-11-13 | 100%
3.32 | Shutdown Tie In 1 |  |  |  | 2024-11-10 | 1 | 2024-11-11 | 100%
3.33 | Shutdown Tie In 2 |  |  |  | 2024-11-10 | 1 | 2024-11-11 | 100%
3.34 | System Energising |  |  |  | 2024-11-12 | 2 | 2024-11-14 | 100%
3.35 | Production Monitoring |  |  |  | 2024-11-14 | 5 | 2024-11-21 | 100%
3.36 | PrEng Signoff |  |  |  | 2024-11-28 | 1 | 2024-11-29 | 100%
4 | M3: Practical Completion |  |  |  | 2024-11-08 | 11 | 2024-11-19 | 100%
4.1 | Commissioning Form/Checklist |  |  |  | 2024-11-08 | 7 | 2024-11-19 | 100%
4.2 | Evidence demonstrating achievement of all Capacity Tests |  |  |  | 2024-11-08 | 7 | 2024-11-19 | 100% |  | Done by Candi
4.3 | Electrical Certificate of Compliance |  |  |  | 2024-11-12 | 1 | 2024-11-13 | 100%
4.4 | Completed Quantum PVForm |  |  |  | 2024-11-08 | 7 | 2024-11-19 | 100%
4.5 | Site Rubble Removal |  |  |  | 2024-11-08 | 3 | 2024-11-13 | 100%
4.6 | Creation of Snag List - M4 |  |  |  | 2024-12-09 | 1 | 2024-12-10 | 100%
5 | M4: Provisional Acceptance |  |  |  | 2024-12-09 | 102 | 2025-03-21 | 100%
5.1 | Close out of Snag List |  |  |  | 2025-01-20 | 5 | 2025-01-27 | 100%
5.1.1 | Platform Installation at Tie-In 2 |  |  |  | 2025-02-10 | 24 | 2025-03-14 | 100%
5.2 | Successful audit of HSE file by Candi |  |  |  | 2025-03-14 | 3 | 2025-03-19 | 100%
5.3 | Training of designated CANDI and/or Customer personnel |  |  |  | 2024-12-09 | 1 | 2024-12-10 | 100%
5.4 | Completed asset register of all components on site including serial numbers |  |  |  | 2025-02-10 | 5 | 2025-02-17 | 100%
5.5 | Successful reception of data on CANDI servers |  |  |  | 2025-02-17 | 1 | 2025-02-18 | 100%
5.6 | As-built drawings package |  |  |  | 2024-12-09 | 5 | 2024-12-17 | 100%
5.7 | Final as-built EYA |  |  |  | 2025-03-14 | 5 | 2025-03-21 | 100%
5.8 | Handover of equipment warranty documents, Owners Manuals & Datasheets |  |  |  | 2025-03-14 | 5 | 2025-03-21 | 100%
5.9 | Signed Milestone 3 - Certificate of Practical Completion |  |  |  | 2024-12-10 | 0 | 2024-12-10 | 100%
5.10 | Guaranteed PR achieved during Acceptance Test |  |  |  | 2024-12-13 | 3 | 2024-12-19 | 100%
6 | M5: Final Acceptance | [6 empty] | 37.5%
| Request subdeliverables from Candi |  |  |  | 2025-03-22 | 5 | 2025-03-27 | 0%
| NERSA Application |  |  |  | 2024-11-29 | 190 | 2025-08-27 | 75%
1 | Project Initiation | 2024-06-11 | 16 | 2024-06-27 | 2024-06-24 | 17 | 2024-07-11 | 100% | 17
1.1 | BD Handover | 2024-06-18 | 1 | 2024-06-19 | 2024-06-24 | 1 | 2024-06-25 | 100%
1.2 | Project Introduction | 2024-06-19 | 1 | 2024-06-20 | 2024-06-25 | 1 | 2024-06-26 | 100%
1.3 | HSE | 2024-06-11 | 10 | 2024-06-21 | 2024-06-26 | 10 | 2024-07-06 | 100%
1.4 | Installer Kick Off | 2024-06-26 | 1 | 2024-06-27 | 2024-07-06 | 1 | 2024-07-08 | 100%
1.5 | Project Review | 2024-06-21 | 3 | 2024-06-26 | 2024-07-08 | 3 | 2024-07-11 | 100%
2 | Site Establishment | 2024-07-30 | 1 | 2024-07-31 | 2024-07-30 | 1 | 2024-07-31 | 100% | 1
2.1 | Installer on site & Roof Assessment | 2024-07-30 | 1 | 2024-07-31 | 2024-07-30 | 1 | 2024-07-31 | 100% |  |  | 112
3 | AC Installation | 2024-07-30 | 86 | 2024-10-24 | 2024-07-30 | 105 | 2024-11-12 | 100% | 105 |  | 22.4
3.1 | Inverters delivered | 2024-07-30 | 2 | 2024-08-01 | 2024-07-30 | 2 | 2024-08-01 | 100%
3.2 | Landing Area for Inverters Tie In 1 | 2024-07-30 | 10 | 2024-08-14 | 2024-10-09 | 16 | 2024-10-31 | 100% |  |  | 67.4107
3.3 | DB Room Prep for Inverters Tie In 2 | 2024-07-30 | 5 | 2024-08-06 | 2024-10-14 | 5 | 2024-10-21 | 100% |  | changed to outside mount
3.4 | Inverters Mounted Tie In 1 | 2024-08-14 | 2 | 2024-08-16 | 2024-11-01 | 4 | 2024-11-07 | 100%
3.5 | Inverters Mounted Tie In 2 | 2024-08-06 | 2 | 2024-08-08 | 2024-10-14 | 5 | 2024-10-21 | 100%
3.6 | Solar DB lead time Tie In 1 | 2024-07-30 | 30 | 2024-09-11 | 2024-07-30 | 30 | 2024-09-11 | 100%
3.7 | Solar DB lead time Tie In 2 | 2024-07-30 | 30 | 2024-09-11 | 2024-07-30 | 30 | 2024-09-11 | 100%
3.8 | AC Works Tie In 1 | 2024-08-14 | 40 | 2024-10-10 | 2024-11-06 | 2 | 2024-11-08 | 100%
3.9 | AC Works Tie In 2 | 2024-08-06 | 40 | 2024-10-03 | 2024-11-06 | 2 | 2024-11-08 | 100%
3.10 | Monitoring Equipment Delivered | 2024-07-30 | 1 | 2024-07-31 | 2024-11-08 | 1 | 2024-11-11 | 100%
3.11 | Monitoring Equipment installed | 2024-08-14 | 40 | 2024-10-10 | 2024-11-08 | 1 | 2024-11-11 | 100%
3.12 | Monitoring Equipment Testing | 2024-10-10 | 10 | 2024-10-24 | 2024-11-08 | 1 | 2024-11-11 | 100%
3.13 | AC Tie - in - 1 | 2024-09-11 | 2 | 2024-09-13 | 2024-11-08 | 2 | 2024-11-12 | 100%
3.14 | AC Tie - in - 2 | 2024-09-16 | 2 | 2024-09-18 | 2024-11-10 | 2 | 2024-11-12 | 100%
4 | DC Works | 2024-07-30 | 90 | 2024-10-28 | 2024-07-30 | 99 | 2024-11-06 | 100% | 99
4.1 | Lifeline Installation | 2024-07-30 | 5 | 2024-08-06 | 2024-07-30 | 5 | 2024-08-06 | 100%
4.1 | Mounting Structure delivered | 2024-07-30 | 1 | 2024-07-31 | 2024-07-30 | 1 | 2024-07-31 | 100%
4.2 | Mounting Structure installation | 2024-07-31 | 20 | 2024-08-29 | 2024-07-31 | 20 | 2024-08-29 | 100%
4.3 | DC Cable delivered | 2024-08-19 | 1 | 2024-08-20 | 2024-08-19 | 1 | 2024-08-20 | 100%
4.3 | DC Stringing | 2024-09-08 | 35 | 2024-10-28 | 2024-10-31 | 4 | 2024-11-06 | 100%
5 | Module installation | 2024-08-19 | 57 | 2024-10-15 | 2024-08-19 | 44 | 2024-10-02 | 100% | 44
5.1 | Module delivery | 2024-08-19 | 1 | 2024-08-20 | 2024-08-19 | 1 | 2024-08-20 | 100%
5.2 | Module mounting | 2024-08-19 | 40 | 2024-10-15 | 2024-09-12 | 20 | 2024-10-02 | 100%
6 | Commissioning | 2024-10-28 | 7 | 2024-11-04 | 2024-11-08 | 11 | 2024-11-19 | 100% | 11
6.1 | Commissioning | 2024-10-28 | 3 | 2024-10-31 | 2024-11-08 | 7 | 2024-11-19 | 100%
6.2 | Practical Completion | 2024-10-28 | 5 | 2024-11-04 | 2024-11-08 | 5 | 2024-11-15 | 100%
7 | QA Inspections | 2024-11-04 | 7 | 2024-11-11 | 2024-12-09 | 2 | 2024-12-11 | 100% | 2
7.1 | Red-Team Inspection | 2024-11-04 | 5 | 2024-11-11 | 2024-12-09 | 2 | 2024-12-11 | 100%
8 | Project Closure | 2024-11-06 | 30 | 2024-12-06 | 2024-11-17 | 54 | 2025-01-10 | 100% | 54
8.1 | Equipment serial numbers | 2024-11-11 | 2 | 2024-11-13 | 2024-12-11 | 2 | 2024-12-13 | 100%
8.2 | Snags completion | 2024-11-13 | 10 | 2024-11-27 | 2024-12-13 | 10 | 2025-01-01 | 100%
8.3 | System Performance Monitoring | 2024-11-27 | 5 | 2024-12-04 | 2025-01-01 | 5 | 2025-01-08 | 100%
8.4 | Handover documentation | 2024-11-27 | 4 | 2024-12-03 | 2025-01-01 | 4 | 2025-01-07 | 100%
8.5 | Handover to Client | 2024-12-03 | 3 | 2024-12-06 | 2025-01-07 | 3 | 2025-01-10 | 100%
8.6 | Handover to Matriarch | 2024-11-06 | 5 | 2024-11-13 | 2024-11-17 | 5 | 2024-11-22 | 100%
Formulas:
Actual Start = MIN([Actual Start, row below]:I22)
Actual Start = WORKDAY.INTL([Actual End, row above],0,1,Data!$C3:C14)
Actual End = MAX([Actual End, row below]:K22)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C14)
Planned Start = MIN([Planned Start, row below]:E111)
Planned Start = [Planned End, row above]
Planned End = MAX([Planned End, row below]:G111)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | PLANNED |  | ACTUAL |  | FINANCIAL REVIEW | TIMELINE REVIEW |  | Allocated in 2024 | Budgeted | Actual
1 | Planned Revenue | 9650000 |  | 9734366 |  | 9650000 | Start Date | Sales | 5633108.3665 | 4091891.6335 | 4101257.6335
2 | Planned Expenditure | 8749927.1757 |  | 6993121.79 |  | 7262932.2139 | TBC | COS | 3426357.08 | 3444874.4885 | 3566764.71
3 | Planned Profit | 900072.8243 |  | 2741244.21 |  | 2387067.7861 | End Date - PC | GP | 2206751.2865 | 647017.145 | 534492.9235
4 | Planned Margin | 9.327% |  | 28.16% |  | 24.74% | TBC
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | M1 - Mobilisation |  | 20% | 1930000 | 2024-08-06 | 004486 | 2024-07-19 | 2024-07-26
2 | M2 - Upon delivery to site of all Major Equipment |  | 55% | 5307500 | 2024-08-08 | 004564 | 2024-10-14 | 2024-10-30
3 | M3 - Upon receipt of the Practical Completion Certificate |  | 10% | 965000 | 2024-11-04 | 004624 | 2024-12-04 | 2025-01-16
4 | M4 - Upon receipt of the Provisional Acceptance Certificate |  | 10% | 965000 | 2024-11-27 | 004816 | 2025-08-18 | 2025-08-29
5 | M5 - Upon receipt of the Final Acceptance Certificate |  | 5% | 482500 | 2025-11-27 |  |  | 2026-08-31
6 | VO - Anchor Point |  | 0% | 75000 | 2024-11-27 | 004780 | 2025-07-03 | 2025-08-18
7 | VO - Waterpoint Clamps |  | 0% | 9366 | 2025-02-28 | 004780 | 2025-07-03 | 2025-08-18
|  |  | 100% | 9734366
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 3407028.1
2 | Delivery of Panels |  | 30% | 2920309.8
3 | Delivery of Inverters |  | 20% | 1946873.2
4 | Practical Completion |  | 10% | 973436.6
5 | Handover |  | 5% | 486718.3
| Total |  | 100% | 9734366
|  |  | 100% | 9734366
Formulas:
PLANNED PAYMENT DATE = [PLANNED PAYMENT DATE, row above]+365

## Data (hidden)
Public holidays |  | Drop down list
2024-01-01 | New Years Day | Approved
2024-03-21 | Human Rights day | Pending
2024-03-29 | Good Friday | Declined
2024-04-01 | Family Day | Abanded
2024-05-01 | Workers day
2024-06-17 | Youth Day Holiday
2024-08-09 | Womens Day
2024-09-24 | Heritage Day
2024-12-16 | Day of Reconciliation
2024-12-25 | Christmas Day
2024-12-26 | Day of Goodwill |  | Manual dates

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  |  | COSTED |  | ACTUAL | Difference from costed
| EXPENDITURE |  | 8749927.1757 |  | 6993121.79 | 1756805.3857
| No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
| 1 | Panels | 0 |  | 0 | 0
| 2 | Inverters | 864000 |  | 757680 | 106320
| 3 | Mounting Structures | 679320 |  | 619184.87 | 60135.13
| 4 | DC Equipment | 1357297 |  | 810195 | 547102
| 5 | Monitoring | 49000 |  | 28480 | 20520
| 6 | AC Equipment | 3348396.2957 |  | 1177114.15 | 2171282.1457
| 7 | Battery Systems | 0 |  | 0 | 0
| 8 | Product Add On | 255000 |  | 1488603.66 | -1233603.66
| 9 | AC & DC Installation | 1281800 |  | 1500000 | -218200
| 10 | Site Logistics | 529807.5 |  | 24394.2 | 505413.3
| 11 | Due Dilligence | 200220 |  | 116600 | 83620
| 12 | BDP Commission | 158836.38 |  | 264727.3 | -105890.92
| 13 | Engineering | 0 |  | 120625 | -120625 | RV: Matriarch defects percentage 1.25%
| 14 | General Expenses | 26250 |  | 85517.61 | -59267.61
| 15 | Service Add On | 0 |  | 0 | 0
|  | check: | 0 | #REF! | 0
Copy amounts in column H and paste as values at Project review.

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 8749927.1757 | 9734366.0588 |  | ACTUAL EXPENDITURE BREAKDOWN | [6 empty] | FINANCE ONLY |  |  |  |  | 6993121.79
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | Project Related date | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS | COMMENTS
1 | Panels | Panels will be free-issued | 2720 | 1484.97 | [5 empty] | 1 | 1. Panels | [12 empty] | 19
1 | [9 empty] | 1 | 1. Panels | [12 empty] | BUDGET | Installer Allocation
1 | [9 empty] | 1 | 1. Panels | [12 empty] | AC Equipment | 3348396.2957
1 | [9 empty] | 1 | 1. Panels | [12 empty] | DC Equipment | 757137
1 | [9 empty] | 1 | 1. Panels | [12 empty] | AC Labour | 377400
1 | [9 empty] | 1 | 1. Panels | [12 empty] | DC Labour | 904400
[24 empty] | Offloading | 8500
2 | Inverters | Huawei 100KTL | 12 | 72000 | 864000 | 2024-08-29 | 864000 | 956194.3311 |  | 2 | 2. Inverters | Huawei 100KTL - Aarden Solar | 11 | 68880 | 757680 | PO3260-CAS-20240725 - RV Approved | Arden Inv: NV-05927 | 2024-08-31 | 956194.3311 | 0 | 2024-10-04 | 757680 | Aarden Solar quote - 30 days from statement | Roof Access/Scaffolding | 115057.5
2 | [9 empty] | 2 | 2. Inverters | Price include deilvery | [11 empty] | Storage | 46250
2 | [9 empty] | 2 | 2. Inverters | [12 empty] | Telehandler | 0
2 | [9 empty] | 2 | 2. Inverters | [12 empty] | Other | 0
[24 empty] | Total | 5557140.7957
3 | Mounting Structures | KlipLok Roof | 1509600 | 0.45 | 679320 | 2024-08-29 | 679320 | 751807.7928 |  | 3 | 3. Mounting Structures | KlipLok/Novatexi Roof - Lumax | 1 | 364557.56 | 364557.56 |  | Lumax Inv: INV00045783 | 2024-08-31 | 723092.4635 | 0.0018009 | 2024-09-27 | 619184.87 |  | Less 15% | 4723569.6763 | [SM: Target Installation Price]
3 | [9 empty] | 3 | 3. Mounting Structures | LUMAX additional Clamps |  |  | 14477.25 | PO3346-CAS-2024090 - RV Approved | Lumax Inv: INV0046571 | 2024-09-30 | 16828.079 |  | 2024-10-30 |  |  | R/Wp | 3.1282
3 | [9 empty] | 3 | 3. Mounting Structures | DC Cable Tray Clamps |  |  | 11908 | PO3379-CAS-20241002 - RV Approved | Lumax Inv: INV0047410 | 2024-10-31 | 11887.2485 |  | 2024-11-29
[10 empty] | 3 | 3. Mounting Structures | Test Clamps |  |  | 2352.38 | PO3797-CAS-20250410 - RV Approved | Lumax - Inv 1001/70001421 | 2025-04-30 | 0 |  | 2025-05-29
[10 empty] | 3 | 3. Mounting Structures
[10 empty] | 3 | 3. Mounting Structures |  |  |  | 6831.28 | PO4021-CAS-20250623 - RV Approved | Lumax - INV 1001/70002518 | 2025-06-30 |  |  | 2025-07-29 |  | TC: added cost PO4021-CAS-20250623
[10 empty] | 3 | 3. Mounting Structures
[10 empty] | 3 | 3. Mounting Structures | Mid Clamps |  |  | 1823 | PO4015-CAS-20250620 - RV Approved | Lumax - Inv 1001/70002494 | 2025-06-30 |  |  | 2025-07-29
[10 empty] | 3 | 3. Mounting Structures | Lumax Replacement Clamps |  |  | 197641.6 | PO3961-CAS-20250527 - RV Approved | Lumax INV1001/70002085 | 2025-05-31 |  |  | 2025-06-27
[10 empty] | 3 | 3. Mounting Structures | Delivery |  |  | 2950 |  | Lumax INV1001/70002084 | 2025-05-31 |  |  | 2025-06-27
[10 empty] | 3 | 3. Mounting Structures | Return of MS to Lumax |  |  | 10295.19 |  | DSV Inv: 180138260 | 2025-07-31 |  |  | 2025-08-29
[10 empty] | 3 | 3. Mounting Structures | MS Scrapped |  |  | -3017.39 |  | Scrapped MS | 2025-11-30 |  |  | 2025-11-24
3 | [9 empty] | 3 | 3. Mounting Structures | Waterpoints Clamps |  |  | 9366 | PO3652-CAS-20250212 - RV Approved | Schletter - INV1422 | 2025-02-28 | 0 |  | 2025-03-28 |  | We are doing Candi a favour here, they have issued a PO to us for the procurement of this equipment. | ACTUAL | Installer Price
[24 empty] | AC Equipment | 0
4 | DC Equipment | DC Cable | 37510 | 16 | 600160 | 2024-09-18 | 1357297 | 1502129.2789 |  | 4 | 4. DC Equipment | DC Cable - Menlo | 44000 | 13.52 | 594880 | PO3313-CAS-20240822 - RV Approved | Menlo Inv: 0001925 | 2024-08-31 | 1160037.7476 | 0.0043202 | 2024-11-04 | 810195 |  | DC Equipment | 0
4 |  | DC Surge Arrestor | 4 | 5500 | 22000 | 2024-10-08 |  |  |  | 4 | 4. DC Equipment | DC Cable - Menlo | 1000 | 13.52 | 13520 |  | Menlo Inv: 0001926 | 2024-08-31 | 26361.3549 |  | 2024-11-04 |  |  | AC Labour | 0
[10 empty] | 4 | 4. DC Equipment | Delivery |  |  | 450 |  | Menlo Inv: 0002198 | 2024-11-30 | 0 |  | 2025-01-06
[10 empty] | 4 | 4. DC Equipment | DC Cable allocated from Stock | 1500 | 13.09 | 19635 |  | Allocated from Stock | 2024-08-31 | 0 |  | 2024-08-31
[10 empty] | 4 | 4. DC Equipment | DC Cable allocated from Stock | 1500 | 13.14 | 19710 |  | Allocated from Stock | 2024-08-31 | 0 |  | 2024-08-31
4 |  | DC Cable Tray | 220 | 1020 | 224400 | 2024-09-18 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 162000 | 10% | 16200 | PO3211-CAS-20240703 | Luken Inv0556 | 2024-07-31 | 31531.5767 |  | 2024-07-25 |  |  | DC Labour | 0
4 | [9 empty] | 4 | 4. DC Equipment | Site Establishment |  | 15% | 24300 |  | Luken Inv0559 | 2024-07-31 | 47297.3651 |  | 2024-08-08 |  |  | Offloading | 0
4 | [9 empty] | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 32400 |  | Luken Inv0593 | 2024-11-30 | 60154.1597 |  | 2024-11-14 |  |  | Roof Access/Scaffolding | 0
4 | [9 empty] | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 40500 |  | Luken Inv 0576 | 2024-10-31 | 86641.006 |  | 2024-10-10 |  |  | Compliance | 0
4 | [9 empty] | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 16200 |  | Luken Inv 0594 | 2024-11-30 | 30035.3548 |  | 2024-11-21 |  |  | Travel | 0
4 | [9 empty] | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 16200 |  | Luken Inv 0595 | 2024-11-30 | 30035.3548 |  | 2024-11-21 |  |  | Other | 0
4 |  | Earth Cable | 37510 | 13.5 | 506385 | 2024-09-18 |  |  |  | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 8100 |  | Luken Inv 0598 | 2024-11-30 | 15017.6774 |  | 2024-12-05 |  |  | Other | 0
4 |  | Earth clamp | 272 | 16 | 4352 | 2024-10-28 |  |  |  | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 8100 |  | Luken Inv 0599 | 2024-11-30 | 15017.6774 |  | 2025-08-21 |  |  | Other | 0 | Labour | Equipment
[24 empty] | Total | 2400000 | 1500000 | 900000
5 | Monitoring | Smartlogger 3000 | 1 | 26000 | 26000 | 2024-08-29 | 49000 | 54228.6137 |  | 5 | 5. Monitoring | [7 empty] | 0 | -0.0017634 |  | 28480 |  | R/Wp | 1.5894 |  | 738000 | AC
5 |  | Comms DB |  |  | 8000 | 2024-08-29 |  |  |  | 5 | 5. Monitoring | CTs |  |  | 24770 | PO3317-CAS-20240826 - RV Approved | AccuEnergy - IN ASAI-003703 | 2024-08-31 | 11215.1854 |  | 2024-09-27 | [5 empty] | 162000 | DC
5 |  | Revenue Grade Meter | 1 | 15000 | 15000 | 2024-11-13 |  |  |  | 5 | 5. Monitoring | Replacement CTs |  |  | 3710 | PO3556-CAS-20250122 - RV Approved | Acccuenergy - ASAI-004594 | 2025-01-31 | 0 |  | 2025-02-27
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | Candi Monitoring Box Wiring | [6 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | Tester - EE Stock |  |  | 0 |  | Removed | 2024-10-31 | 43013.43 |  | 2024-11-30
6 | AC Equipment | Project Kick Off |  | 10% | 334839.6296 | 2024-07-23 | 3348396.2957 | 3705691.6158 |  | 6 | 6. AC Equipment | [7 empty] | 0 | -0.0005485 |  | 1177114.15
6 | [9 empty] | 6 | 6. AC Equipment | AC Board Tie In 1 - SOLAR PVDB 1 |  | 185475.16 | 185475.16 |  | Switchboard - INV 2-SOI001204 | 2024-08-31 | 611631.5138 |  | 2024-10-24
6 | [9 empty] | 6 | 6. AC Equipment | AC Board Tie In 2 - SOLAR PVDB 2 |  | 200263.12 | 200263.12 |  | Switchboard - INV 2-SOI001204 | 2024-08-31 | 660396.9785 |  | 2024-10-24
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | AC Cable - Corrected Tie in |  |  | 53375.87 | PO3613-CAS-20250203 - RV Approved | Luken Inv0618 | 2025-02-28 | 22070.738 |  | 2025-02-07
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | Project Kick Off | 738000 | 10% | 73800 | PO3211-CAS-20240703 | Luken Inv0556 | 2024-07-31 | 243366.3123 |  | 2024-07-25
6 | 3348396.2957 | Site Establishment |  | 15% | 502259.4443 | 2024-07-30 |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 110700 |  | Luken Inv0559 | 2024-07-31 | 365049.4685 |  | 2024-08-08
6 |  | AC Installation Complete |  | 20% | 669679.2591 | 2024-10-24 |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 147600 |  | Luken Inv0593 | 2024-11-30 | 464661.8873 |  | 2024-11-14
6 |  | DC Installation Complete |  | 25% | 837099.0739 | 2024-10-28 |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 184500 |  | Luken Inv 0576 | 2024-10-31 | 608415.7809 |  | 2024-10-10
6 |  | Commissioning Complete |  | 10% | 334839.6296 | 2024-11-04 |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 73800 |  | Luken Inv 0594 | 2024-11-30 | 243366.3123 |  | 2024-11-21
6 |  | Site De-establisment |  | 10% | 334839.6296 | 2024-11-27 |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 73800 |  | Luken Inv 0595 | 2024-11-30 | 243366.3123 |  | 2024-11-21
6 |  | Handover Document Complete |  | 5% | 167419.8148 | 2024-12-03 |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 36900 |  | Luken Inv 0598 | 2024-11-30 | 121683.1562 |  | 2024-12-05
6 |  | End of Defects Period |  | 5% | 167419.8148 | 2025-03-03 |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 36900 |  | Luken Inv 0599 | 2024-11-30 | 121683.1562 |  | 2025-08-21
7 | Battery Systems | [5 empty] | 0 | 0 |  | 7 | Battery Systems | [8 empty] | 0 |  | 0
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
8 | Product Add On | Welcome Bonus | 1 | 255000 | 255000 | 2025-03-03 | 255000 | 366576.1324 |  | 8 | 8. Product Add On | [7 empty] | 0 | -0.0027259 |  | 1488603.66
8 | [9 empty] | 8 | 8. Product Add On | Platform Supports |  |  | 61627.5 | PO3467-CAS-20241119 - RV Approved | Anthony's Steel Inv INA28450 | 2024-11-30 | 13306.0134 |  | 2024-11-28
8 | [9 empty] | 8 | 8. Product Add On | Steel Work For Both Tie Ins | 50% | 260060.56 | 130030.28 | PO3210-CAS-20240703 | Anthony's Steel: Inv INA28238 | 2024-07-31 | 53875.0901 |  | 2024-07-31
[10 empty] | 8 | 8. Product Add On | Balance Payable | 50% |  | 130030.28 |  | aNThony's Steel: Inv INA28243 | 2024-07-31 | 53875.0901 |  | 2024-11-28
[10 empty] | 8 | 8. Product Add On | Platform Tie In 2 | 50% | 291115 | 145557.5 | PO3512-CAS-20241205 - RV Approved | Anthony's Steel: INV INA28494 | 2024-12-31 | 31427.3668 |  | 2024-12-12
[10 empty] | 8 | 8. Product Add On | Platform Tie In 2 | 50% |  | 145557.5 |  | Anthony's Steel INVINA28646 | 2025-03-31 | 0 |  | 2025-04-03
[10 empty] | 8 | 8. Product Add On | Anchor Points - Active Rope ATS - Deposit | 50% | 38068 | 19034 | PO3262-CAS-20240726 - RV Approved | ATS Africa Inv: INV-0318 | 2024-07-31 | 7886.3051 |  | 2025-02-27
[10 empty] | 8 | 8. Product Add On | Anchor Points - Active Rope ATS - Balance | 50% |  | 19034 |  | ATS Africa Inv: INV-0318 | 2024-07-31 | 7886.3051 |  | 2025-02-27
[10 empty] | 8 | 8. Product Add On | VO - Anchor Point | [5 empty] | 2025-06-30 | 84366
[10 empty] | 8 | 8. Product Add On | Temp Lifelines |  |  | 38800 |  | ATS Africa Inv: INV-0337 | 2024-11-30 | 0 |  | 2024-11-14
[10 empty] | 8 | 8. Product Add On | Panel Clean |  |  | 27281 | PO704-CAS-20241107 - RV Approved | Camperdown Solar Inv INA11114 | 2024-11-30 | 4508.7895 |  | 2024-12-05
[10 empty] | 8 | 8. Product Add On | Luken Solar AC Cable VO |  |  | 266859.84 | PO3443-CAS-20241031 - RV Approved | Luken Inv0591 | 2024-10-31 | 38723.4205 |  | 2024-11-14
8 | [9 empty] | 8 | 8. Product Add On | Luken Solar Tie In Breakers |  |  | 68259.15 | PO3455-CAS-20241106 - RV Approved | Luken Inv0592 | 2024-11-30 | 15664.6151 |  | 2024-11-14
[10 empty] | 8 | 8. Product Add On
[10 empty] | 8 | 8. Product Add On |  | 434782.61 | 30% | 130434.783 | PO3962-CAS-20250527 - RV Approved | Luken Inv-0648 | 2025-05-31 | 13742.7693 |  | 2025-05-29
[10 empty] | 8 | 8. Product Add On | Luken Corrective Installation - On Completion |  | 60% | 260869.566 |  | Luken Inv-0651 | 2025-06-30 | 41314.37 |  | 2025-07-03
[10 empty] | 8 | 8. Product Add On | Luken Corrective Installation - Retention |  | 10% | 43478.261 |  | Luken Inv-0652 | 2025-06-30 | 0 |  | 2026-01-30
[10 empty] | 8 | 8. Product Add On
[10 empty] | 8 | 8. Product Add On | Repair Damaged Downpipe |  |  | 1750 | PO4206-CAS-20250807 - RV Approved | Anthony's Wedlding - INA28967 | 2025-08-31 |  |  | 2026-02-05
[10 empty] | 8 | 8. Product Add On
[10 empty] | 8 | 8. Product Add On
[10 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
Only services to be capture below, products above
9 | AC & DC Installation | Project Kick Off |  | 10% | 128180 | 2024-07-23 | 1281800 | 1508000 |  | 9 | 9. AC & DC installation | Project Kick Off | 1500000 | 10% | 150000 | PO3211-CAS-20240703 | Luken Inv0556 | 2024-07-31 | 150800 | 0 | 2024-07-25 | 1500000
9 | 904400 | Site Establishment |  | 15% | 192270 | 2024-07-30 |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 225000 |  | Luken Inv 0559 | 2024-07-31 | 226200 |  | 2024-08-08
9 | 377400 | AC Installation Complete |  | 20% | 256360 | 2024-10-24 |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 300000 |  | Luken Inv0593 | 2024-11-30 | 301600 |  | 2024-11-14
9 |  | DC Installation Complete |  | 25% | 320450 | 2024-10-28 |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 375000 |  | Luken Inv 0576 | 2024-10-31 | 377000 |  | 2024-10-10
9 |  | Commissioning Complete |  | 10% | 128180 | 2024-11-04 |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 150000 |  | Luken Inv 0594 | 2024-11-30 | 150800 |  | 2024-11-21
9 |  | Site De-establisment |  | 10% | 128180 | 2024-11-27 |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 150000 |  | Luken Inv 0595 | 2024-11-30 | 150800 |  | 2024-11-21
9 |  | Handover Document Complete |  | 5% | 64090 | 2024-12-03 |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 75000 |  | Luken Inv 0598 | 2024-11-30 | 75400 |  | 2024-12-05
9 |  | End of Defects Period |  | 5% | 64090 | 2025-03-03 |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 75000 |  | Luken Inv 0599 | 2024-11-30 | 75400 |  | 2025-08-21
10 | Site Logistics | Scaffolding |  |  | 115057.5 | 2024-07-30 | 529807.5 | 623303 |  | 10 | 10. Site Logistics | Security Budget | [6 empty] | 0 | -0.00052344 |  | 24394.2
10 |  | Offloading |  |  | 8500 | 2024-11-04 |  |  |  | 10 | 10. Site Logistics | Security Panel Delivery |  |  | 22200 | PO3293-CAS-20240814 - RV Approved | BEST Inv: 0000020 | 2024-08-31 | 265082.8851 |  | 2024-09-19
10 |  | Site Storage |  |  | 46250 | 2024-12-03 |  |  |  | 10 | 10. Site Logistics | Security additional days |  |  | 2194.2 |  | BEST Inv:O0000020 | 2024-10-31 | 358220.1155 |  | 2024-10-10
10 |  | Security |  |  | 360000 | 2024-12-03 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 37740 | 2024-11-06 | 200220 | 235552.9412 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off - Matthews Group |  |  | 26800 | PO3269-CAS-20240731 - RV Approved | MG Engineering Inv0002 | 2024-11-30 | 35385.7557 | -0.0032603 | 2025-04-24 | 116600
11 |  | Structural sign off |  |  | 75480 | 2024-07-30 |  |  |  | 11 | 11. Due Dilligence | 2x Site visits from L&B and 1x from Candi |  |  | 0 |  |  |  | 0
[10 empty] | 11 | 11. Due Dilligence | Structural Assessment |  |  | 5500 |  | L&B Invoice: 0996 | 2024-06-30 | 4635.2099 |  | 2022-10-20
[10 empty] | 11 | 11. Due Dilligence |  |  |  | 11600 |  | L&B Invoice:1646 | 2024-06-30 | 9776.0791 |  | 2024-05-23
[10 empty] | 11 | 11. Due Dilligence | SSEG Extras |  |  | 0
11 |  | Grid Study - Outside of CoCT |  |  | 80000 | 2024-08-29 |  |  |  | 11 | 11. Due Dilligence | Grid Study - Outside of CoCT |  |  | 63200 | PO3926-CAS-20250516 - RV Approved | Okhusa Electrical: EE016 | 2025-05-31 | 96604.8118 |  | 2026-01-07
11 |  | Lightning Risk Assessment |  |  | 7000 | 2024-07-30 |  |  |  | 11 | 11. Due Dilligence | Lightning Risk Assessment |  |  | 9500 | PO3213-CAS-20240703 | LPS Invoice: IN305966 | 2024-07-31 | 8403.1278 |  | 2024-08-08
11 | [9 empty] | 11 | 11. Due Dilligence | SSEG Inspection |  |  | 0 | PO3907-CAS-20250514 - RV Approved |  | 2025-06-30 | 80747.96 |  | 2025-06-05
12 | BDP Commission | BDP Commission |  |  | 158836.38 | 2024-12-06 | 158836.38 | 0 |  | 12 | BDP Commission | BDP Commission |  |  | 132363.65 |  | Mont Blanc Inv: 273 | 2024-08-31 |  |  | 2024-08-08 | 264727.3
12 | BDP Commission | [8 empty] | 12 | BDP Commission |  |  |  | 132363.65 |  | Mont Blanc Inv: 273 | 2024-08-31 |  |  | 2024-11-22
13 | Engineering | Matriarch Defects Period |  | 103873.0099 |  |  | 0 | 0 |  | 13 | 13. Engineering | Matriarch Defects Period |  | 103873.0099 | 120625 |  | MATRIARCH - INV-3414 | 2024-11-30 |  | 0 | 2024-11-30 | 120625
13 |  | Management |  | 120000 | [5 empty] | 13 | 13. Engineering | Management |  | 120000 | 0 |  |  | 2024-11-30 |  |  | 2025-08-31
13 |  | Project manager |  | 408000 | [5 empty] | 13 | 13. Engineering | Project manager |  | 408000 | 0 |  |  | 2024-11-30 |  |  | 2025-08-31
13 |  | Planner time |  | 156000 | [5 empty] | 13 | 13. Engineering | Planner time |  | 156000 | 0 |  |  | 2024-11-30 |  |  | 2025-08-31
13 |  | De Snagging |  | 116252.8 | [5 empty] | 13 | 13. Engineering | De Snagging |  | 116252.8 | 0 |  |  | 2024-11-30 |  |  | 2025-08-31
13 | [9 empty] | 13 | 13. Engineering
13 | [9 empty] | 13 | 13. Engineering
14 | General Expenses | Car travel to site |  |  | 26250 | 2024-11-22 | 26250 | 30882.3529 |  | 14 | 14. General Expenses | Car travel to site |  |  | 11927.09 |  | Expense Claim | 2024-06-30 | 2544.0381 | -0.00070199 | 2024-07-05 | 85517.61
[10 empty] | 14 | 14. General Expenses | Car travel to site |  |  | 1370.52 |  | Expense Claim | 2024-07-31 | 304.4695 |  | 2024-08-06
[10 empty] | 14 | 14. General Expenses | Car travel to site |  |  | 20912.77 |  | Expense Claim | 2024-08-31 | 5665.4689 |  | 2024-09-05
[10 empty] | 14 | 14. General Expenses | Car travel to site |  |  | 11749.01 |  | Expense Claim | 2024-09-30 | 2937.86 |  | 2024-10-04
[10 empty] | 14 | 14. General Expenses | Car travel to site |  |  | 10391.33 |  | Expense Claim | 2024-10-31 | 10206.25 |  | 2024-11-08
[10 empty] | 14 | 14. General Expenses | Car travel to site |  |  | 7950.72 |  | Expense Claim | 2024-11-30 | 3217.9857 |  | 2024-12-06
14 | [9 empty] | 14 | 14. General Expenses | Car travel to site |  |  | 1766.96 |  | Expense Claim | 2024-12-31 | 801.6625 |  | 2025-01-09
14 | [9 empty] | 14 | 14. General Expenses | Car travel to site |  |  | 10295.2 |  | Expense Claim | 2025-01-31 | 3956.2688 |  | 2025-02-07
14 | [9 empty] | 14 | 14. General Expenses | Car travel to site |  |  | 0 |  | Expense Claim | 2025-02-28 | 0 |  | 2025-03-07
14 | [9 empty] | 14 | 14. General Expenses | Car travel to site |  |  | 0 |  | Expense Claim | 2025-03-31 | 0 |  | 2025-04-07
[10 empty] | 14 | 14. General Expenses | Car travel to site |  |  | 9154.01 |  | Expense Claim | 2025-04-30 | 1248.3503 |  | 2025-05-08
14 | [9 empty] | 14 | 14. General Expenses | Car travel to site |  |  | 0 |  | Expense Claim | 2025-08-31 | 0 |  | 2025-09-07
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | APEX Call Out Fee |  |  | 7200 |  | THULA MOYA - IN04542 | 2025-05-31 |  | 0 | 2025-06-26 | 0
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
9734366.0622
Note on Q47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Lloyd Brown have you ordered CTs yet? Reply: i am in process of sending po for approval
Note on W93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Roedolph Venter please update the payment date
Note on W95: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Lloyd Brown, please advise if we can pay this, currently it is forecasted to be paid on Thursday. Please load on ClickUp
Note on W116: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date
Note on Q120: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Roedolph Venter are we able to firm up this amount or remove if we not going to incur it Reply: Will do, moving it to Feb for now. Because council is going to take some time. Reply: Removed it
Note on W149: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2024-06-17 to 2026-09-14
PLANNED |  | CHECK | CHECK
| Planned Revenue | 9650000 | 9734366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7237500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 965000 | 0 | 0 | 1040000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 482500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7237500 | 7237500 | 7237500 | 7237500 | 7237500 | 7237500 | 7237500 | 7237500 | 7237500 | 7237500 | 7237500 | 7237500 | 7237500 | 8202500 | 8202500 | 8202500 | 9242500 | 9242500 | 9242500 | 9242500 | 9242500 | 9242500 | 9242500 | 9242500 | 9242500 | 9242500 | 9242500 | 9242500 | 9242500 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366 | 9734366
| Planned Expenditure | 8749927.1757 | 8749927.1757 | 0 | 0 | 0 | 0 | 0 | 463019.6296 | 892066.9443 | 0 | 0 | 0 | 1657320 | 0 | 0 | 1330945 | 0 | 0 | 22000 | 0 | 926039.2591 | 1161901.0739 | 509259.6296 | 15000 | 26250 | 463019.6296 | 796596.1948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 486509.8148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 463019.6296 | 1355086.5739 | 1355086.5739 | 1355086.5739 | 1355086.5739 | 3012406.5739 | 3012406.5739 | 3012406.5739 | 4343351.5739 | 4343351.5739 | 4343351.5739 | 4365351.5739 | 4365351.5739 | 5291390.833 | 6453291.907 | 6962551.5365 | 6977551.5365 | 7003801.5365 | 7466821.1661 | 8263417.3609 | 8263417.3609 | 8263417.3609 | 8263417.3609 | 8263417.3609 | 8263417.3609 | 8263417.3609 | 8263417.3609 | 8263417.3609 | 8263417.3609 | 8263417.3609 | 8263417.3609 | 8263417.3609 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757 | 8749927.1757
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | -463019.6296 | -1355086.5739 | 5882413.4261 | 5882413.4261 | 5882413.4261 | 4225093.4261 | 4225093.4261 | 4225093.4261 | 2894148.4261 | 2894148.4261 | 2894148.4261 | 2872148.4261 | 2872148.4261 | 1946109.167 | 784208.093 | 1239948.4635 | 1224948.4635 | 1198698.4635 | 1775678.8339 | 979082.6391 | 979082.6391 | 979082.6391 | 979082.6391 | 979082.6391 | 979082.6391 | 979082.6391 | 979082.6391 | 979082.6391 | 979082.6391 | 979082.6391 | 979082.6391 | 988448.6391 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 501938.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243 | 984438.8243
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 9734366 | 9251866 | 0 | 0 | 0 | 0 | 0 | 1930000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5307500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 965000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84366 | 965000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 482500 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 1930000 | 1930000 | 1930000 | 1930000 | 1930000 | 1930000 | 1930000 | 1930000 | 1930000 | 1930000 | 1930000 | 1930000 | 1930000 | 1930000 | 7237500 | 7237500 | 7237500 | 7237500 | 7237500 | 7237500 | 7237500 | 7237500 | 7237500 | 7237500 | 7237500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8202500 | 8286866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9251866 | 9734366 | 9734366 | 9734366
| Actual + Planned Expenditure | 6993121.79 | 6983221.79 | 0 | 0 | 11927.09 | 0 | 0 | 240000 | 130030.28 | 503234.17 | 0 | 0 | 39345 | 20912.77 | 0 | 22200 | 389327.56 | 769429.01 | 602194.2 | 0 | 385738.28 | 14477.25 | 618791.33 | 853918.99 | 612363.65 | 324190.78 | 155231.72 | 145557.5 | 0 | 0 | 0 | 2216.96 | 0 | 0 | 0 | 63671.07 | 0 | 0 | 41778 | 0 | 0 | 0 | 9366 | 145557.5 | 0 | 0 | 26800 | 0 | 9154.01 | 0 | 0 | 132787.163 | 0 | 0 | 0 | 207791.6 | 260869.566 | 0 | 0 | 0 | 8654.28 | 0 | 0 | 120000 | 10295.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3017.39 | 0 | 0 | 0 | 0 | 0 | 63200 | 0 | 0 | 43478.261 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 11927.09 | 11927.09 | 11927.09 | 251927.09 | 381957.37 | 885191.54 | 885191.54 | 885191.54 | 924536.54 | 945449.31 | 945449.31 | 967649.31 | 1356976.87 | 2126405.88 | 2728600.08 | 2728600.08 | 3114338.36 | 3128815.61 | 3747606.94 | 4601525.93 | 5213889.58 | 5538080.36 | 5693312.08 | 5838869.58 | 5838869.58 | 5838869.58 | 5838869.58 | 5841086.54 | 5841086.54 | 5841086.54 | 5841086.54 | 5904757.61 | 5904757.61 | 5904757.61 | 5946535.61 | 5946535.61 | 5946535.61 | 5946535.61 | 5955901.61 | 6101459.11 | 6101459.11 | 6101459.11 | 6128259.11 | 6128259.11 | 6137413.12 | 6137413.12 | 6137413.12 | 6270200.283 | 6270200.283 | 6270200.283 | 6270200.283 | 6477991.883 | 6738861.449 | 6738861.449 | 6738861.449 | 6738861.449 | 6747515.729 | 6747515.729 | 6747515.729 | 6867515.729 | 6877810.919 | 6877810.919 | 6877810.919 | 6877810.919 | 6877810.919 | 6877810.919 | 6877810.919 | 6877810.919 | 6877810.919 | 6877810.919 | 6877810.919 | 6877810.919 | 6877810.919 | 6874793.529 | 6874793.529 | 6874793.529 | 6874793.529 | 6874793.529 | 6874793.529 | 6937993.529 | 6937993.529 | 6937993.529 | 6981471.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79 | 6983221.79
| ACTUAL CashFlow |  |  | 0 | 0 | -11927.09 | -11927.09 | -11927.09 | 1678072.91 | 1548042.63 | 1044808.46 | 1044808.46 | 1044808.46 | 1005463.46 | 984550.69 | 984550.69 | 962350.69 | 573023.13 | -196405.88 | -798600.08 | -798600.08 | -1184338.36 | 4108684.39 | 3489893.06 | 2635974.07 | 2023610.42 | 1699419.64 | 1544187.92 | 1398630.42 | 1398630.42 | 1398630.42 | 1398630.42 | 1396413.46 | 2361413.46 | 2361413.46 | 2361413.46 | 2297742.39 | 2297742.39 | 2297742.39 | 2255964.39 | 2255964.39 | 2255964.39 | 2255964.39 | 2246598.39 | 2101040.89 | 2101040.89 | 2101040.89 | 2074240.89 | 2074240.89 | 2065086.88 | 2065086.88 | 2065086.88 | 1932299.717 | 1932299.717 | 1932299.717 | 1932299.717 | 1724508.117 | 1463638.551 | 1463638.551 | 1463638.551 | 1463638.551 | 1454984.271 | 1454984.271 | 1454984.271 | 1419350.271 | 2374055.081 | 2374055.081 | 2374055.081 | 2374055.081 | 2374055.081 | 2374055.081 | 2374055.081 | 2374055.081 | 2374055.081 | 2374055.081 | 2374055.081 | 2374055.081 | 2374055.081 | 2377072.471 | 2377072.471 | 2377072.471 | 2377072.471 | 2377072.471 | 2377072.471 | 2313872.471 | 2313872.471 | 2313872.471 | 2270394.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2268644.21 | 2751144.21 | 2751144.21 | 2751144.21
|  | CHECK | CHECK
| Revenue Recognition | -84366.0622 | 9734366.0622 | 0 | 16955.3272 | 0 | 0 | 0 | 0 | 1196475.1104 | 0 | 0 | 0 | 4419677.9289 | 0 | 0 | 0 | 0 | 19765.939 | 0 | 0 | 0 | 1534107.2513 | 0 | 0 | 0 | 2171104.208 | 0 | 0 | 0 | 0 | 32229.0293 | 0 | 0 | 0 | 3956.2688 | 0 | 0 | 0 | 22070.738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1248.3503 | 0 | 0 | 0 | 110347.5811 | 0 | 0 | 0 | 0 | 206428.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 9734366.0622 | 0 | 16955.3272 | 16955.3272 | 16955.3272 | 16955.3272 | 16955.3272 | 1213430.4376 | 1213430.4376 | 1213430.4376 | 1213430.4376 | 5633108.3665 | 5633108.3665 | 5633108.3665 | 5633108.3665 | 5633108.3665 | 5652874.3055 | 5652874.3055 | 5652874.3055 | 5652874.3055 | 7186981.5568 | 7186981.5568 | 7186981.5568 | 7186981.5568 | 9358085.7648 | 9358085.7648 | 9358085.7648 | 9358085.7648 | 9358085.7648 | 9390314.7941 | 9390314.7941 | 9390314.7941 | 9390314.7941 | 9394271.0628 | 9394271.0628 | 9394271.0628 | 9394271.0628 | 9416341.8008 | 9416341.8008 | 9416341.8008 | 9416341.8008 | 9416341.8008 | 9416341.8008 | 9416341.8008 | 9416341.8008 | 9416341.8008 | 9417590.1511 | 9417590.1511 | 9417590.1511 | 9417590.1511 | 9527937.7322 | 9527937.7322 | 9527937.7322 | 9527937.7322 | 9527937.7322 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622 | 9734366.0622
| Installer Expenditure |  | 2400000 | 0 | 0 | 0 | 0 | 0 | 240000 | 0 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 480000 | 480000 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Installer Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 240000 | 240000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1680000 | 2160000 | 2160000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2280000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-11-30 | Grand Total
Battery Systems
BDP Commission |  |  |  | 264727.3 | [13 empty] | 264727.3
(blank)
1. Panels
2. Inverters |  |  |  | 757680 | [13 empty] | 757680
3. Mounting Structures |  |  |  | 364557.56 | 14477.25 | 11908 |  |  |  | 9366 |  | 2352.38 | 200591.6 | 8654.28 | 10295.19 |  | -3017.39 | 619184.87
4. DC Equipment |  |  | 40500 | 647745 |  | 40500 | 81450 | [10 empty] | 810195
5. Monitoring |  |  |  | 24770 |  | 0 |  |  | 3710 | [8 empty] | 28480
6. AC Equipment |  |  | 184500 | 385738.28 |  | 184500 | 369000 |  |  | 53375.87 | [7 empty] | 1177114.15
8. Product Add On |  |  | 298128.56 |  |  | 266859.84 | 195967.65 | 145557.5 |  |  | 145557.5 |  | 130434.783 | 304347.827 |  | 1750 |  | 1488603.66
9. AC & DC installation |  |  | 375000 |  |  | 375000 | 750000 | [10 empty] | 1500000
10. Site Logistics |  |  |  | 22200 |  | 2194.2 | [11 empty] | 24394.2
11. Due Dilligence | 0 | 17100 | 9500 |  |  |  | 26800 | [5 empty] | 63200 | 0 |  |  |  | 116600
13. Engineering | [6 empty] | 120625 | [10 empty] | 120625
14. General Expenses |  | 11927.09 | 1370.52 | 20912.77 | 11749.01 | 10391.33 | 7950.72 | 1766.96 | 10295.2 | 0 | 0 | 9154.01 |  |  |  | 0 |  | 85517.61
15. Service Add On | [12 empty] | 7200 |  |  |  |  | 7200
Grand Total | 0 | 29027.09 | 908999.08 | 2488330.91 | 26226.26 | 891353.37 | 1551793.37 | 147324.46 | 14005.2 | 62741.87 | 145557.5 | 11506.39 | 401426.383 | 313002.107 | 10295.19 | 1750 | -3017.39 | 7000321.79
3426357.08
0
3426357.08

## Finance - Revenue
REVENUE RECOGNITION AMOUNT | (All)
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels |  | (blank) | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-11-30 | Grand Total
(blank)
Battery Systems
BDP Commission
1. Panels
2. Inverters |  |  |  |  | 956194.3311 | [13 empty] | 956194.3311
3. Mounting Structures |  |  |  |  | 723092.4635 | 16828.079 | 11887.2485 |  |  |  | 0 |  | 0 | [5 empty] | 751807.791
4. DC Equipment |  |  |  | 78828.9418 | 1186399.1026 |  | 86641.006 | 150260.2242 | [10 empty] | 1502129.2746
5. Monitoring | 0 | 0 |  |  | 11215.1854 |  | 43013.43 |  |  | 0 | [8 empty] | 54228.6154
6. AC Equipment | 0 |  |  | 608415.7809 | 1272028.4923 |  | 608415.7809 | 1194760.8243 |  |  | 22070.738 | [7 empty] | 3705691.6164
8. Product Add On | 0 | 0 |  | 123522.7905 |  |  | 38723.4205 | 33479.4181 | 31427.3668 |  |  | 0 |  | 13742.7693 | 125680.37 |  |  |  | 366576.1352 | 7336627.7636
9. AC & DC installation |  |  |  | 377000 |  |  | 377000 | 754000 | [10 empty] | 1508000
10. Site Logistics | 0 | 0 |  |  | 265082.8851 |  | 358220.1155 | [11 empty] | 623303.0005
11. Due Dilligence |  | 0 | 14411.2891 | 8403.1278 |  |  |  | 35385.7557 | [5 empty] | 96604.8118 | 80747.96 |  |  |  | 235552.9444
13. Engineering
14. General Expenses |  |  | 2544.0381 | 304.4695 | 5665.4689 | 2937.86 | 10206.25 | 3217.9857 | 801.6625 | 3956.2688 | 0 | 0 | 1248.3503 |  |  |  | 0 |  | 30882.3536
15. Service Add On
Grand Total | 0 | 0 | 16955.3272 | 1196475.1104 | 4419677.9289 | 19765.939 | 1534107.2513 | 2171104.208 | 32229.0293 | 3956.2688 | 22070.738 | 0 | 1248.3503 | 110347.5811 | 206428.33 |  | 0 |  | 9734366.0622
5633108.3665
-9734366.0622

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate | [5 empty] | FINANCIAL CLOSE CERTIFICATE
Project Name: | Cascades Lifestyle Center
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion: |  |  |  | 1. Financial Close | 1. Financial Close
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | 864000 | 0 | 864000 | 0 | 864000
Inverters | 864000
Optimizers | 0
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | 679320 | 0 | 679320 | 0 | 679320
Mounting Structure | 679320
Delivery fee
|  | >Name< |  | >Name<
DC Cable | 600160 | 0 | 600160 | 0 | 600160
DC Cable | 600160
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
Smartlogger 3000 | 26000
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | 255000 | 0 | #REF! | 0 | #REF!
SCADA | 255000
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | 3348396.2957 | 2.2175 | 277892.91 | 0.18404 | 3070503.3857 |  | 0 | 3348396.2957
DC Equipment | 757137 | 0.50142 | 142158.25 | 0.094145 | 614978.75 |  | 0 | 757137
AC Labour | 377400 | 0.24993 | 96174 | 0.063691 | 281226 |  | 0 | 377400
DC Labour | 904400 | 0.59894 | 230160 | 0.15242 | 674240 |  | 0 | 904400
Offloading | 8500 |  | 0 |  | 8500 |  |  | 8500
Roof Access/Scaffolding | 115057.5 |  | 29257.61 |  | 85799.89 |  |  | 115057.5
Storage | 46250 |  |  |  | 46250 |  |  | 46250
Telehandler | 0
HSE | 0
Totals | 5557140.7957 |  | 775642.77 |  | 4781498.0257 | 0 |  | 5557140.7957
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | 3348396.2957
AC equipment | 0 | 0 |  |  | 0 |  | 0 | 757137
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | 377400
DC equipment | 506385 | 0.33535 |  |  | 506385 |  |  | 904400
Storage | 0 |  |  |  | 0 |  |  | 8500
Panel lifting equipment | 169807.5 |  |  |  | 169807.5 |  |  | 115057.5
Offloading | 0 |  |  |  | 0 |  |  | 46250
Totals | #REF! |  | 0 |  | #REF! | 0 |  | 5557140.7957
Budget Summary
Budget | 5557140.7957
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
Loss | 5557140.7957
All amounts are exc VAT

## Decision Register (hidden)
Cascades Lifestyle Center |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Cascades Lifestyle Center | 0 | 0 | 0