## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[10 empty] | 2026-02-26 | 2026-02-26
| PROJECT PLAN | Gillwell Mall | [7 empty] | 0 | 1
| PROJECT SIZE (kWp) | 1043
| PROJECT DEVELOPER | Natasha Watkins-Baker
| PROJECT MANAGERS | Lloyd Brown
| CONTRACT VALUE | 9566688.9258
| Phase: | Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Expected Status |  | Comment
|  |  | 78 |  |  | 138 |  | 99.54% | 97.92%
1 | Project Initiation | 2025-04-22 | 24 | 2025-05-16 | 2025-04-29 | 17 | 2025-05-16 | 100% | 100% | 17
1.1 | BD Handover | 2025-04-22 | 1 | 2025-04-23 | 2025-05-13 | 1 | 2025-05-14 | 100% | 100%
1.2 | Project Introduction | 2025-05-15 | 1 | 2025-05-16 | 2025-05-15 | 1 | 2025-05-16 | 100% | 100%
1.3 | HSE | 2025-04-22 | 10 | 2025-05-07 | 2025-04-29 | 10 | 2025-05-14 | 100% | 100%
1.4 | Installer Kick Off | 2025-05-08 | 1 | 2025-05-09 | 2025-05-14 | 1 | 2025-05-15 | 100% | 100%
1.5 | Project Review | 2025-05-08 | 1 | 2025-05-09 | 2025-05-08 | 1 | 2025-05-09 | 100% | 100%
2 | Site Establishment | 2025-05-22 | 1 | 2025-05-23 | 2025-05-22 | 1 | 2025-05-23 | 100% | 100% | 1
2.1 | Solar Contractor Establishment | 2025-05-22 | 1 | 2025-05-23 | 2025-05-22 | 1 | 2025-05-23 | 100% | 100% | 1 |  | 97 | Net Work Days
3 | AC Installation | 2025-05-01 | 71 | 2025-07-11 | 2025-05-01 | 156 | 2025-10-04 | 100% | 100% | 156 |  | 19.4 | Total Weeks
3.1 | Inverters delivered | 2025-05-23 | 1 | 2025-05-26 | 2025-05-28 | 1 | 2025-05-29 | 100% | 100% |  |  | 53.7629 | kW/Week Installation Rate
3.2 | Inverters Mounted | 2025-05-26 | 5 | 2025-06-02 | 2025-07-24 | 5 | 2025-07-31 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-05-01 | 25 | 2025-06-05 | 2025-05-01 | 40 | 2025-06-27 | 100% | 100%
3.4 | AC Works | 2025-06-05 | 25 | 2025-07-11 | 2025-07-24 | 49 | 2025-09-11 | 100% | 100%
3.5 | AC Tie-In | 2025-06-05 | 3 | 2025-06-10 | 2025-10-04 | 0 | 2025-10-04 | 100% | 100%
4 | DC Works | 2025-05-22 | 64 | 2025-07-25 | 2025-05-23 | 132 | 2025-10-02 | 100% | 100% | 132
4.1 | Lifeline Installation (If Applicable) | [6 empty] | 0%
4.1 | Mounting Structure delivered | 2025-05-22 | 1 | 2025-05-23 | 2025-05-23 | 1 | 2025-05-26 | 100% | 100%
4.2 | Mounting Structure installation | 2025-05-23 | 15 | 2025-06-13 | 2025-05-26 | 15 | 2025-06-17 | 100% | 100%
4.3 | DC Cable delivered | 2025-05-22 | 1 | 2025-05-23 | 2025-05-23 | 1 | 2025-05-26 | 100% | 100%
4.3 | DC Stringing | 2025-07-05 | 15 | 2025-07-25 | 2025-06-14 | 77 | 2025-10-02 | 100% | 100%
5 | Module installation | 2025-06-06 | 32 | 2025-07-08 | 2025-06-10 | 115 | 2025-10-03 | 100% | 100% | 1900-04-24
5.1 | Module delivery | 2025-06-06 | 1 | 2025-06-09 | 2025-06-10 | 1 | 2025-06-11 | 100% | 100%
5.2 | Module mounting | 2025-06-09 | 20 | 2025-07-08 | 2025-06-18 | 76 | 2025-10-03 | 100% | 100%
6 | Commissioning | 2025-07-25 | 14 | 2025-08-08 | 2025-10-04 | 3 | 2025-10-07 | 100% | 100% | 3
6.1 | Commissioning | 2025-07-25 | 5 | 2025-08-01 | 2025-10-04 | 1 | 2025-10-06 | 100% | 100%
6.2 | Practical Completion | 2025-08-01 | 5 | 2025-08-08 | 2025-10-06 | 1 | 2025-10-07 | 100% | 100%
7 | QA Inspections | 2025-08-08 | 7 | 2025-08-15 | 2025-10-07 | 7 | 2025-10-14 | 100% | 100% | 1900-01-06
7.1 | Red-Team Inspection | 2025-08-08 | 5 | 2025-08-15 | 2025-10-07 | 5 | 2025-10-14 | 100% | 100%
8 | Project Closure | 2025-08-15 | 33 | 2025-09-17 | 2025-10-14 | 146 | 2026-03-09 | 96.3% | 83.33% | 1900-05-19 14:13
8.1 | Equipment serial numbers | 2025-08-15 | 2 | 2025-08-19 | 2025-10-14 | 2 | 2025-10-16 | 100% | 100%
8.2 | Snags completion | 2025-08-15 | 7 | 2025-08-26 | 2025-10-25 | 4 | 2025-10-30 | 100% | 100%
8.3 | System Performance Monitoring | 2025-08-26 | 5 | 2025-09-02 | 2025-10-30 | 5 | 2025-11-06 | 100% | 100%
8.4 | Handover documentation | 2025-09-02 | 10 | 2025-09-16 | 2025-10-25 | 10 | 2025-11-07 | 100% | 100%
8.5 | Handover to Client | 2025-09-16 | 1 | 2025-09-17 | 2026-03-06 | 1 | 2026-03-09 | 0% | 0% |  | Portfolio handover tbc
8.6 | Handover to Matriarch | 2025-08-28 | 5 | 2025-09-04 | 2025-11-01 | 5 | 2025-11-07 | 100% | 100%
plus one day rainfall 13 september
plus one day winds to strong on 16 september
Formulas:
Planned Start = MIN([Planned Start, row below]:E16)
Planned Start = WORKDAY.INTL([Planned End, row above],0,1,Data!$C3:C14)
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = [Actual End, row above]
Actual End = MAX([Actual End, row below]:K16)
Actual End = MAX([Actual End, row below])
Expected Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 9566688.9258 |  | 9566688.9258 |  |  |  | Start Date | 9286734.1241 | 7550252.8916 | 4243.8044 | 162278.53 | 4243.8044 | 162278.53
2 | Planned Expenditure | 8916891.6108 |  | 7712531.4216 | VO PM Limit | Current VO Total
3 | Planned Profit | 649797.315 |  | 1854157.5042 | 32489.8658 | 647382.57 |  | End Date - PC
4 | Planned Margin | 6.792% |  | 19.38%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE |  | MILESTONE NOTES & COMMENTS
1 | Deposit |  | 20% | 1913337.7852 |  | 2025-04-30 | 004731 | 2025-05-01 | 2025-04-30
2 | Delivery of Panels |  | 20% | 1913337.7852 |  | 2025-06-13 | 004731 | 2025-05-01 | 2025-06-20
3 | Delivery of Inverters |  | 15% | 1435003.3389 |  | 2025-05-30 | 004731 | 2025-05-01 | 2025-06-06
4 | Commissioning Complete |  | 15% | 1435003.3389 |  | 2025-08-15 | 004731 | 2025-05-01 | 2025-10-10
5 | Final Completion Issued |  | 25% | 2391672.2314 |  | 2025-09-09 | 004731 | 2025-05-01 | 2025-10-17
6 | Handover |  | 5% | 478334.4463 |  | 2026-03-16 | 004731 | 2025-05-01 | 2025-11-10
7 | VO - Damaged Panels recovered from Installer |  | 0% | 0 |  |  |  | 2025-10-31 | 2025-11-07
|  |  | 100% | 9566688.9258
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 3348341.124
2 | Delivery of Panels |  | 30% | 2870006.6777
3 | Delivery of Inverters |  | 20% | 1913337.7852
4 | Practical Completion |  | 10% | 956668.8926
5 | Handover |  | 5% | 478334.4463
| Total |  | 100% | 9566688.9258
|  |  | 100% | 9566688.9258
Formulas:
PAYMENT RECEIVED DATE = [INVOICE RAISED DATE]+7

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 8916891.6108 |  | 7712531.4216 | 1204360.1892
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 2190166.44 |  | 2067265.53 | 122900.91
2 | 2. Inverters | 560000 |  | 551748.64 | 8251.36
3 | 3. Mounting Structures | 847503.72 |  | 205256.6 | 642247.12
4 | 4. DC Equipment | 805143.2 |  | 1327973.5 | -522830.3
5 | 5. Monitoring | 49000 |  | 98397.12 | -49397.12
6 | 6. AC Equipment | 1197554.4 |  | 411874.58 | 785679.82
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 0 |  | 191728.57 | -191728.57
9 | 9. AC & DC installation | 812490 |  | 1095150 | -282660
10 | 10. Site Logistics | 214921.5333 |  | 17700 | 197221.5333
11 | 11. Due Dilligence | 158183 |  | 111542.46 | 46640.54
12 | 12. BDP Commission | 162449.3288 |  | 0 | 162449.3288
13 | 13. Engineering | 301279.9887 |  | 119583.6116 | 181696.3771
14 | 14. General Expenses | 18200 |  | 21560.81 | -3360.81
15 | 15. Service Add On | 1600000 |  | 1492750 | 107250
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 8916891.6108 | 9566688.9258 | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 7712531.4216
605
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | ERROR on REV | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 2190166.44 | 2025-07-29 | 2190166.44 | 2406776.3077 | 1 | 1. Panels | Longi 605W Krannich | 1724 | 1175.95 | 2027345.73 | PO3935-DIP-Ph2-Gillwell-20250519 - RV Approved | Krannich - INV 15-10012801 | 2025-05-31 | 2277667.0782 | 0.0038954 | 2025-07-29 | 2067265.53
1 |  | Delivery Budget |  |  |  | 2025-07-29 |  |  | 1 | 1. Panels | EPR Tax |  |  | 34393.8 |  | Krannich - INV 15-10012801 | 2025-05-31 | 38640.4868 |  | 2025-07-29
1 | [5 empty] | 2025-07-29 |  |  | 1 | 1. Panels | Chemitek |  |  | 5526 |  | Krannich - INV 15-10012801 | 2025-05-31 | 6208.3088 |  | 2025-07-29
1 | [8 empty] | 1 | 1. Panels | Delivery Fee | [5 empty] | 2025-06-30 | 84260.43
1 | [5 empty] | 2025-11-26 |  |  | 1 | 1. Panels
1 | [8 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[22 empty] | AC Equipment | 1197554.4
2 | Inverters | Inverter Budget |  |  | 560000 | 2025-07-24 | 560000 | 615384.6154 | 2 | 2. Inverters | Huawei 100KTL (Krannich) | 8 | 68870 | 550960 | PO3935-DIP-Ph2-Gillwell-20250519 - RV Approved | Krannich - INV 15-10012764 | 2025-05-31 | 614505.0175 | 0 | 2025-07-24 | 551748.64 | DC Equipment | 466343.2
2 | [5 empty] | 2025-07-24 |  |  | 2 | 2. Inverters | EPR Fees |  |  | 788.64 |  | Krannich - INV 15-10012764 | 2025-05-31 | 879.5979 |  | 2025-07-24 |  | AC Labour | 260610
2 | [8 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 551880
2 | [8 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [8 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 55968.2
2 | [8 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 25653.3333
2 | [8 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 847503.72 | 2025-06-27 | 847503.72 | 931322.7692 | 3 | 3. Mounting Structures | Schletter Structure |  | 0.19019 | 197792.6 | PO3921-DIP2GILL-20250515 - RV Approved | Schletter - INV1787 | 2025-05-31 | 775603.6493 | 0.004535 | 2025-06-27 | 205256.6 | Other | 0
3 | [5 empty] | 0 |  |  | 3 | 3. Mounting Structures | Seam clamps (kliplock) - PE stock | 300 | 24.88 | 7464 |  | Allocated from PE Stockroom | 2025-05-31 | 29268.5653 |  | 2025-05-31 |  | Total | 2566509.1333
3 | [8 empty] | 3 | 3. Mounting Structures | Available Budget |  |  | 0 |  |  | 2025-08-31 | 126450.55 |  |  |  | Less 15% | 2181532.7633
3 | [8 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | R/Wp | 2.0916
3 | [8 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [8 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL - Cosmic Sun | Installer Price | ACTUAL - Luken Solar | Installer Price
[22 empty] | AC Equipment | 162066 | AC Equipment | 252255
4 | DC Equipment | DC Cable Budget | 27830 |  | 338800 | 2025-07-17 | 805143.2 | 884772.7473 | 4 | 4. DC Equipment | DC Cable Krannich | 28000 | 13.89 | 388920 | PO3935-DIP-Ph2-Gillwell-20250519 - RV Approved | Krannich - INV 15-10012737 | 2025-05-31 | 443450.4746 | 0.00093273 | 2025-07-17 | 1327973.5 | DC Equipment | 312053.5 | DC Equipment | 310965
4 |  | DC Equipment Budget |  |  | 466343.2 | 2025-07-17 |  |  | 4 | 4. DC Equipment | Delivery Fee |  |  | 75000 |  | Krannich - INV 15-10012737 | 2025-05-31 | 85515.7503 |  | 2025-07-17 |  | AC Labour | 344190 | AC Labour | 302000
4 | [5 empty] | 2025-07-29 |  |  | 4 | 4. DC Equipment | Additional DC Cable - Rubicon - VO | 40000 | 13.8 | 552000 | PO4022-DGW-20250623 - RV Approved | Rubicon INVCRE-0068802 | 2025-06-30 | 110923.8242 |  | 2025-07-29 |  | DC Labour | 750960 | DC Labour | 741000
4 | [8 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Offloading | 13200 | Offloading | 0
4 | [5 empty] | 2025-05-15 |  |  | 4 | 4. DC Equipment | Project Kick Off | 312053.5 | 10% | 31205.35 | PO3883-DIP2GILL-20250503 - RV Approved | CS_GWM_001 | 2025-05-31 | 35580.6522 |  | 2025-05-15 |  | Scaffolding | 0 | Scaffolding | 0
4 | [5 empty] | #REF! |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 46808.025 |  | CS_GWM_002 | 2025-05-31 | 53370.9784 |  | 2025-05-29 |  | Storage | 0 | Storage | 0
4 | [5 empty] | 2025-08-07 |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 62410.7 |  | CS_GWM_004 | 2025-06-30 | 41581.6178 |  | 2025-08-07 |  | Telehandler | 0 | Telehandler | 0
4 | [5 empty] | 2025-10-09 |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 78013.375 |  | CS_GWM_003 | 2025-06-30 | 51977.0222 |  | 2025-10-09 |  | HSE | 4500 | HSE | 0
4 | [5 empty] | #REF! |  |  | 4 | 4. DC Equipment | Commissioning Complete | 158696.95 | 10% | 31205.35 |  | Cosmic Sun - CS_GWM_005 | 2025-08-31 | 20790.8089 |  | 2025-10-16 |  | Other | 0 | Other | 0
4 | [5 empty] | 2025-11-12 |  |  | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 31205.35 |  | Cosmic Sun - CS_GWM_006 | 2025-08-31 | 20790.8089 |  | 2025-10-24 |  | Other | 0 | Other | 0
4 | [5 empty] | 2025-11-30 |  |  | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 15602.675 |  | Cosmic Sun - CS_GWM_007 | 2025-08-31 | 10395.4044 |  | 2025-10-24 |  | Total | 1586969.5 | Total | 1606220
4 | [5 empty] | 2025-12-05 |  |  | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 15602.675 |  | Cosmic Sun - CS_GWM_008 | 2025-08-31 | 10395.4044 |  | 2025-12-18 |  | R/Wp | 1.5215 | R/Wp | 1.54
4 | [8 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [8 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [8 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 34000 | 2025-07-24 | 49000 | 53846.1538 | 5 | 5. Monitoring | Smartlogger Krannich |  |  | 8333.33 | PO3935-DIP-Ph2-Gillwell-20250519 - RV Approved | Krannich - INV 15-10012764 | 2025-05-31 | 10483.1003 | 0.0046256 | 2025-07-24 | 98397.12
5 |  | Revenue Metering |  |  | 15000 | 2025-05-29 |  |  | 5 | 5. Monitoring | CTs, Meters, Router, Ethernet Switch, Power Supply |  |  | 28665 | PO3827-DIP-Ph2-Gill-20250429 - RV Approved | Accuenergy - Inv ASAI-005353 | 2025-04-30 | 10654.7475 |  | 2025-05-29
[6 empty] | 2025-07-29 |  |  | 5 | 5. Monitoring |  |  |  | 214.29 |  | Accuenergy - Inv ASAI-005800 | 2025-06-30 | 164.1466 |  | 2025-07-29
5 | [5 empty] | 2025-06-30 |  |  | 5 | 5. Monitoring | Techsitter |  |  | 14934 |  | Matriarch Inv: 4451 | 2025-06-30 | 8172.378 |  | 2025-06-30
5 | [5 empty] | 2025-07-29 |  |  | 5 | 5. Monitoring | APEX Emulator & Licenses |  |  | 4000 | PO3971-GILL-20250529 - RV Approved | Rubicon INVWCRE-0068579 | 2025-06-30 | 2188.9321 |  | 2025-07-29
5 | [5 empty] | 2025-05-22 |  |  | 5 | 5. Monitoring | UPS |  |  | 2250.5 | PO3863-DIP Ph2-20250509 - RV Approved | Frontline INV725690 | 2025-05-31 | 1285.7536 |  | 2025-05-22
5 | [5 empty] | 2025-07-29 |  |  | 5 | 5. Monitoring | Apex Edge Device |  |  | 40000 | PO3986-DIP-Ph2-Gill-20250609 - RV Approved | Rubicon INWCRE-0068504 | 2025-06-30 | 20897.0911 |  | 2025-07-29
5 | [8 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 1197554.4 | 2025-08-29 | 1197554.4 | 1315993.8462 | 6 | 6. AC Equipment | [7 empty] | 0 | -0.0029361 |  | 411874.58
6 | [5 empty] | 2025-08-30 |  |  | 6 | 6. AC Equipment | PVDB |  |  | 249808.58 | PO3872-DIP-Ph2-Gill-20250512 - RV Approved | Switchboard Inv: 2-SOI002100 | 2025-06-30 | 798171.5065 |  | 2025-08-30
6 | [8 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [8 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [8 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [8 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [5 empty] | 2025-05-15 |  |  | 6 | 6. AC Equipment | Project Kick Off | 162066 | 10% | 16206.6 | PO3883-DIP2GILL-20250503 - RV Approved | CS_GWM_001 | 2025-05-31 | 52579.4911 |  | 2025-05-15
6 | [5 empty] | #REF! |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 24309.9 |  | CS_GWM_002 | 2025-05-31 | 78869.2367 |  | 2025-05-29
6 | [5 empty] | 2025-08-07 |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 32413.2 |  | CS_GWM_004 | 2025-06-30 | 101571.3279 |  | 2025-08-07
6 | [5 empty] | 2025-10-09 |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 40516.5 |  | CS_GWM_003 | 2025-06-30 | 129455.5849 |  | 2025-10-09
6 | [5 empty] | #REF! |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 16206.6 |  | Cosmic Sun - CS_GWM_005 | 2025-08-31 | 51782.234 |  | 2025-10-16
6 | [5 empty] | 2025-11-12 |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 16206.6 |  | Cosmic Sun - CS_GWM_006 | 2025-08-31 | 51782.234 |  | 2025-10-24
6 | [5 empty] | 2025-11-30 |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 8103.3 |  | Cosmic Sun - CS_GWM_007 | 2025-08-31 | 25891.117 |  | 2025-10-24
6 | [5 empty] | 2025-12-05 |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 8103.3 |  | Cosmic Sun - CS_GWM_008 | 2025-08-31 | 25891.117 |  | 2025-12-18
6 | [8 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [8 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [8 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [8 empty] | 7 | 7.BESS
7 | [8 empty] | 7 | 7.BESS
7 | [8 empty] | 7 | 7.BESS
7 | [8 empty] | 7 | 7.BESS
7 | [8 empty] | 7 | 7.BESS
7 | [8 empty] | 7 | 7.BESS
7 | [8 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 0 | 0 | 8 | 8. Product Add On | Estop |  |  | 12500 | PO4395-GILL-20251023 - RV Approved | Cosmic Sun - CS_GWM_010 | 2025-11-30 |  | 0 | 2025-11-27 | 191728.57
8 | [8 empty] | 8 | 8. Product Add On
8 | [5 empty] | 2025-09-30 |  |  | 8 | 8. Product Add On | Waterpoints |  |  | 12930 | PO4317-GILL-20250916 - RV Approved | Sizisa Ukhanyo Developments Inv: A0018 | 2025-09-30 |  |  | 2025-09-30
8 | [8 empty] | 8 | 8. Product Add On
8 | [8 empty] | 8 | 8. Product Add On | Inverter Cage Modification |  |  | 36463 | PO4575-DIP2GILL-20260126 - RV Approved | The Engineering Hub INV/2026/01/0250 | 2026-01-31 |  |  | 2026-02-28
8 | [5 empty] | 2025-07-31 |  |  | 8 | 8. Product Add On | Inverter Cage |  |  | 92203 | PO3979-GILL-20250603 - RV Approved | The Engineering Hub INV/2025/06/0578 | 2025-06-30 |  |  | 2025-07-31
8 | [5 empty] | 2025-10-02 |  |  | 8 | 8. Product Add On | Longi 610w panels (replacement - damaged by installer) - VO |  |  | 97632.57 |  | Krannich - INV 15-10013984 | 2025-09-30 | 0 |  | 2025-11-28
8 | [8 empty] | 8 | 8. Product Add On | CS payment for broken panels - VO |  |  | -60000 |  | Emergent Invoice: 004910 | 2026-01-31 |  |  | 2026-01-29
9 | AC & DC Installation | AC Installation Budget |  |  | 260610 | 2025-05-14 | 812490 | 955870.5882 | 9 | 9. AC & DC installation | [7 empty] | 0 | 0 |  | 1095150
9 |  | DC Installation Budget |  |  | 551880 | 2025-05-15 |  |  | 9 | 9. AC & DC installation | Project Kick Off | 1095150 | 10% | 109515 | PO3883-DIP2GILL-20250503 - RV Approved | CS_GWM_001 | 2025-05-31 | 95587.0588 |  | 2025-05-15
9 | [5 empty] | #REF! |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 164272.5 |  | CS_GWM_002 | 2025-05-31 | 143380.5882 |  | 2025-05-29
9 | [5 empty] | 2025-08-07 |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 219030 |  | CS_GWM_004 | 2025-06-30 | 191174.1176 |  | 2025-08-07
9 | [5 empty] | 2025-10-09 |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 273787.5 |  | CS_GWM_003 | 2025-06-30 | 238967.6471 |  | 2025-10-09
9 | [5 empty] | #REF! |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 109515 |  | Cosmic Sun - CS_GWM_005 | 2025-08-31 | 95587.0588 |  | 2025-10-16
9 | [5 empty] | 2025-11-12 |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 109515 |  | Cosmic Sun - CS_GWM_006 | 2025-08-31 | 95587.0588 |  | 2025-10-24
9 | [5 empty] | 2025-11-30 |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 54757.5 |  | Cosmic Sun - CS_GWM_007 | 2025-08-31 | 47793.5294 |  | 2025-10-24
9 | [5 empty] | 2025-12-05 |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 54757.5 |  | Cosmic Sun - CS_GWM_008 | 2025-08-31 | 47793.5294 |  | 2025-12-18
9 | [8 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [8 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [8 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-05-15 | 214921.5333 | 252848.8627 | 10 | 10. Site Logistics | [7 empty] | 0 | 0.0031063 |  | 17700
10 |  | Scaffolding |  |  | 55968.2 | 2025-05-15 |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Security |  |  | 124800 | 2025-05-15 |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 25653.3333 | 2025-05-15 |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [5 empty] | 2025-05-15 |  |  | 10 | 10. Site Logistics | Project Kick Off | 17700 | 10% | 1770 | PO3883-DIP2GILL-20250503 - RV Approved | CS_GWM_001 | 2025-05-31 | 3140.649 |  | 2025-05-15
10 | [5 empty] | #REF! |  |  | 10 | 10. Site Logistics | Site Establishment |  | 15% | 2655 |  | CS_GWM_002 | 2025-05-31 | 4710.9735 |  | 2025-05-29
10 | [5 empty] | 2025-08-07 |  |  | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 3540 |  | CS_GWM_004 | 2025-06-30 | 50569.7725 |  | 2025-08-07
10 | [5 empty] | 2025-10-09 |  |  | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 4425 |  | CS_GWM_003 | 2025-06-30 | 118572.8057 |  | 2025-10-09
10 | [5 empty] | #REF! |  |  | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 1770 |  | Cosmic Sun - CS_GWM_005 | 2025-08-31 | 25284.8863 |  | 2025-10-16
10 | [5 empty] | 2025-11-12 |  |  | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 1770 |  | Cosmic Sun - CS_GWM_006 | 2025-08-31 | 25284.8863 |  | 2025-10-24
10 | [5 empty] | 2025-11-30 |  |  | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 885 |  | Cosmic Sun - CS_GWM_007 | 2025-08-31 | 12642.4431 |  | 2025-10-24
10 | [5 empty] | 2025-12-05 |  |  | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 885 |  | Cosmic Sun - CS_GWM_008 | 2025-08-31 | 12642.4431 |  | 2025-12-18
10 | [8 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [8 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [8 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 26061 | 2025-08-31 | 158183 | 186097.6471 | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 28642.46 |  | Sunspot E027 | 2025-07-31 | 42577.5034 | 0.0029164 | 2025-11-28 | 111542.46
11 |  | Structural Sign Off |  |  | 52122 | 2025-08-31 |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 9700 | PO3745-DIP-Ph2-20250313 - RV Approved | L&B Consulting - Invoice 1934 | 2025-04-30 | 16876.6857 |  | 2025-04-10
11 |  | Grid Study |  |  | 80000 | 2025-08-31 |  |  | 11 | 11. Due Dilligence | Grid Study |  |  | 63200 | PO3813-GILL-20250417 - RV Approved | Okusha Engineering Inv EE13 | 2025-04-30 | 109959.4366 |  | 2026-03-31
11 | [5 empty] | 2025-08-31 |  |  | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 10000 |  | Matriarch - INV-4987 | 2025-08-31 | 16684.0185 |  | 2025-08-31
11 | [5 empty] | 2025-08-31 |  |  | 11 | 11. Due Dilligence | [7 empty] | 0
2025-08-31
12 | BDP Commission | Referral Fee |  |  | 121836.9966 | 2025-08-31 | 162449.3288 | 0 | 12 | 12. BDP Commission | Referral Fee | [9 empty] | 0
12 | BDP Commission | PD Fee |  |  | 40612.3322 | 2025-08-31 |  |  | 12 | 12. BDP Commission | PD Fee
2025-08-31
13 | Engineering | Matriarch Defects Period |  |  | 85437.0287 | 2025-08-31 | 301279.9887 | 342363.6235 | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 119583.6116 |  | Matriarch - INV-4987 | 2025-08-31 | 342363.6235 | 0 | 2025-08-31 | 119583.6116
13 |  | Management |  |  | 40000 | 2025-08-31 |  |  | 13 | 13. Engineering | Management |  |  | 0 |  |  |  | 0
13 |  | Project manager |  |  | 81600 | 2025-08-31 |  |  | 13 | 13. Engineering | Project manager |  |  | 0 |  |  |  | 0
13 |  | Planner time |  |  | 52000 | 2025-08-31 |  |  | 13 | 13. Engineering | Planner time |  |  | 0 |  |  |  | 0
13 |  | De Snagging |  |  | 42242.96 | 2025-08-31 |  |  | 13 | 13. Engineering | De Snagging |  |  | 0 |  |  |  | 0
13 | [8 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 18200 | 2025-03-31 | 18200 | 21411.7647 | 14 | 14. General Expenses | Travel |  |  | 0 |  |  | 2025-04-30 | 0 | 0.00016953 | 2025-03-31 | 21560.81
14 | [5 empty] | 2025-04-30 |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  | 2025-04-30 | 0 |  | 2025-04-30
14 | [5 empty] | 2025-06-09 |  |  | 14 | 14. General Expenses | Travel |  |  | 3116.87 |  | Expense Claim | 2025-05-31 | 7781.1238 |  | 2025-06-09
14 | [5 empty] | 2025-07-04 |  |  | 14 | 14. General Expenses | Travel |  |  | 7517.79 |  | Expense Claim | 2025-06-30 | 8170.6963 |  | 2025-07-04
14 | [5 empty] | 2025-07-31 |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-07-31 | 0 |  | 2025-07-31
14 | [5 empty] | 2025-09-05 |  |  | 14 | 14. General Expenses | Travel |  |  | 5923.19 |  | Expense Claim | 2025-08-31 | 1216.14 |  | 2025-09-05
14 | [5 empty] | 2025-09-30 |  |  | 14 | 14. General Expenses | Travel |  |  | 5002.96 |  | Expense Claim | 2025-09-30 | 1151.0944 |  | 2025-10-10
14 | [5 empty] | 2025-10-31 |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-10-31 | 0 |  | 2025-10-31
14 | [5 empty] | 2025-11-30 |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-11-30 | 3092.71 |  | 2025-11-30
14 | [5 empty] | 2025-12-31 |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  |  | 0
14 | [8 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [8 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | Welcome Bonus |  |  | 1600000 | 2025-06-26 | 1600000 | 1600000 | 15 | 15. Service Add On | Welcome Bonus - Site Establishment |  |  | 717500 |  | Gillwell Taxi - 23397/202506/274841/I | 2025-06-30 | 767500 | 0 | 2025-06-26 | 1492750
15 | [5 empty] | 2025-10-10 |  |  | 15 | 15. Service Add On | Welcome Bonus - Commissioning Complete |  |  | 717500 |  | Gillwell Taxi - 23397/202506/274841/I | 2025-06-30 | 767500 |  | 2025-10-30
15 | [8 empty] | 15 | 15. Service Add On | [6 empty] | 2025-08-31 | 65000
15 | [8 empty] | 15 | 15. Service Add On | Community Engagement |  |  | 0 |  |  |  | 0
15 | [8 empty] | 15 | 15. Service Add On | Cosmic Sun - Establishment and Re-establishment - VO |  |  | 57750 |  | Cosmic Sun - CS_GWM_009 | 2025-09-30 | 0 |  | 2025-10-02
15 | [8 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [8 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [8 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [8 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [8 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [8 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [8 empty] | 15 | 15. Service Add On | [7 empty] | 0
| Panel Procurement Budget | 2190166.44 |  | 2406776.3077
| Inverter Procurement Budget | 560000 |  | 615384.6154
| Mounting Structure Budget | 847503.72 |  | 931322.7692
| DC Equipment Budget | 805143.2 |  | 884772.7473
| AC Equipment Budget | 1197554.4 |  | 1315993.8462
| Monitoring Budget | 49000 |  | 53846.1538
| Optional Extras Budget | 0 |  | 0
| MV Metering Budget | 0 |  | 0
| ADD ON | 0 |  | 0
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 260610 |  | 306600
| DC Installer Budget | 551880 |  | 649270.5882
| In-House Expense Budget | 301279.9887 |  | 342363.6235
| Compliance Budget | 158183 |  | 186097.6471
| Offloading Budget | 8500 |  | 10000
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 25653.3333 |  | 30180.3922
| On Site Security | 124800 |  | 146823.5294
| Roof Access Budget for Installers | 55968.2 |  | 65844.9412
| EPC Management Fee | 0 |  | 0
| ADD ON | 1600000 |  | 1600000
Expenses
| Total EE Expense Budget | 18200 |  | 21411.7647
Note on H120: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date
Note on W120: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 9566688.9258 | 9566688.9258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1913337.7852 | 0 | 0 | 0 | 1435003.3389 | 0 | 1913337.7852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1435003.3389 | 0 | 0 | 0 | 2391672.2314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 478334.4463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1913337.7852 | 1913337.7852 | 1913337.7852 | 1913337.7852 | 3348341.124 | 3348341.124 | 5261678.9092 | 5261678.9092 | 5261678.9092 | 5261678.9092 | 5261678.9092 | 5261678.9092 | 5261678.9092 | 5261678.9092 | 5261678.9092 | 6696682.2481 | 6696682.2481 | 6696682.2481 | 6696682.2481 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258
| Planned Expenditure | 8916891.6108 | 8916891.6108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18200 | 0 | 0 | 0 | 0 | 0 | 1027411.5333 | 0 | 15000 | 0 | 0 | 0 | 2447503.72 | 0 | 0 | 805143.2 | 594000 | 2190166.44 | 0 | 0 | 0 | 1819466.7174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18200 | 18200 | 18200 | 18200 | 18200 | 18200 | 1045611.5333 | 1045611.5333 | 1060611.5333 | 1060611.5333 | 1060611.5333 | 1060611.5333 | 3508115.2533 | 3508115.2533 | 3508115.2533 | 4313258.4533 | 4907258.4533 | 7097424.8933 | 7097424.8933 | 7097424.8933 | 7097424.8933 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108 | 8916891.6108
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18200 | -18200 | -18200 | -18200 | 1895137.7852 | 1895137.7852 | 867726.2518 | 867726.2518 | 2287729.5907 | 2287729.5907 | 4201067.3759 | 4201067.3759 | 1753563.6559 | 1753563.6559 | 1753563.6559 | 948420.4559 | 354420.4559 | -1835745.9841 | -1835745.9841 | -400742.6453 | -400742.6453 | -2220209.3627 | -2220209.3627 | 171462.8687 | 171462.8687 | 171462.8687 | 171462.8687 | 171462.8687 | 171462.8687 | 171462.8687 | 171462.8687 | 171462.8687 | 171462.8687 | 171462.8687 | 171462.8687 | 171462.8687 | 171462.8687 | 171462.8687 | 171462.8687 | 171462.8687 | 171462.8687 | 171462.8687 | 171462.8687 | 171462.8687 | 171462.8687 | 171462.8687 | 171462.8687 | 171462.8687 | 171462.8687 | 171462.8687 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315 | 649797.315
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 9566688.9258 | 9566688.9258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1913337.7852 | 0 | 0 | 0 | 0 | 1435003.3389 | 0 | 1913337.7852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1435003.3389 | 2391672.2314 | 0 | 0 | 0 | 478334.4463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1913337.7852 | 1913337.7852 | 1913337.7852 | 1913337.7852 | 1913337.7852 | 3348341.124 | 3348341.124 | 5261678.9092 | 5261678.9092 | 5261678.9092 | 5261678.9092 | 5261678.9092 | 5261678.9092 | 5261678.9092 | 5261678.9092 | 5261678.9092 | 5261678.9092 | 5261678.9092 | 5261678.9092 | 5261678.9092 | 5261678.9092 | 5261678.9092 | 5261678.9092 | 6696682.2481 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9088354.4795 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258 | 9566688.9258
| Actual + Planned Expenditure | 7712531.4216 | 7712531.4216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9700 | 0 | 0 | 0 | 0 | 158696.95 | 2250.5 | 274174.425 | 0 | 3116.87 | 0 | 915292.6 | 22451.79 | 0 | 463920 | 560081.97 | 2755682.82 | 317393.9 | 0 | 0 | 379392.1916 | 5923.19 | 0 | 0 | 0 | 70680 | 401745.335 | 158696.95 | 238045.425 | 717500 | 0 | 0 | 0 | 138775.03 | 0 | 0 | 79348.475 | 0 | 0 | 0 | 0 | 0 | -60000 | 0 | 0 | 0 | 36463 | 0 | 0 | 0 | 0 | 63200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9700 | 9700 | 9700 | 9700 | 9700 | 168396.95 | 170647.45 | 444821.875 | 444821.875 | 447938.745 | 447938.745 | 1363231.345 | 1385683.135 | 1385683.135 | 1849603.135 | 2409685.105 | 5165367.925 | 5482761.825 | 5482761.825 | 5482761.825 | 5862154.0166 | 5868077.2066 | 5868077.2066 | 5868077.2066 | 5868077.2066 | 5938757.2066 | 6340502.5416 | 6499199.4916 | 6737244.9166 | 7454744.9166 | 7454744.9166 | 7454744.9166 | 7454744.9166 | 7593519.9466 | 7593519.9466 | 7593519.9466 | 7672868.4216 | 7672868.4216 | 7672868.4216 | 7672868.4216 | 7672868.4216 | 7672868.4216 | 7612868.4216 | 7612868.4216 | 7612868.4216 | 7612868.4216 | 7649331.4216 | 7649331.4216 | 7649331.4216 | 7649331.4216 | 7649331.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216 | 7712531.4216
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9700 | -9700 | -9700 | 1903637.7852 | 1903637.7852 | 1744940.8352 | 1742690.3352 | 1468515.9102 | 2903519.249 | 2900402.379 | 4813740.1642 | 3898447.5642 | 3875995.7742 | 3875995.7742 | 3412075.7742 | 2851993.8042 | 96310.9842 | -221082.9158 | -221082.9158 | -221082.9158 | -600475.1074 | -606398.2974 | -606398.2974 | -606398.2974 | -606398.2974 | -677078.2974 | 356179.7065 | 2589154.9879 | 2351109.5629 | 1633609.5629 | 1633609.5629 | 2111944.0092 | 2111944.0092 | 1973168.9792 | 1973168.9792 | 1973168.9792 | 1893820.5042 | 1893820.5042 | 1893820.5042 | 1893820.5042 | 1893820.5042 | 1893820.5042 | 1953820.5042 | 1953820.5042 | 1953820.5042 | 1953820.5042 | 1917357.5042 | 1917357.5042 | 1917357.5042 | 1917357.5042 | 1917357.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042 | 1854157.5042
|  | CHECK | CHECK
| Revenue Recognition | 0.017245 | 9566688.9085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137490.8698 | 0 | 0 | 0 | 4758508.5345 | 0 | 0 | 0 | 0 | 3491818.9006 | 0 | 0 | 0 | 42577.5034 | 0 | 0 | 0 | 1132049.2959 | 0 | 0 | 0 | 0 | 1151.0944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3092.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 9566688.9085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137490.8698 | 137490.8698 | 137490.8698 | 137490.8698 | 4895999.4043 | 4895999.4043 | 4895999.4043 | 4895999.4043 | 4895999.4043 | 8387818.3049 | 8387818.3049 | 8387818.3049 | 8387818.3049 | 8430395.8082 | 8430395.8082 | 8430395.8082 | 8430395.8082 | 9562445.1041 | 9562445.1041 | 9562445.1041 | 9562445.1041 | 9562445.1041 | 9563596.1985 | 9563596.1985 | 9563596.1985 | 9563596.1985 | 9563596.1985 | 9563596.1985 | 9563596.1985 | 9563596.1985 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085 | 9566688.9085
0

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 |  | 2026-01-31 | Grand Total
(blank)
1. Panels |  |  | 2322515.8738 | 84260.43 | [5 empty] | 0 |  | 2406776.3038
2. Inverters |  |  | 615384.6154 | [6 empty] | 0 |  | 615384.6154
3. Mounting Structures |  |  | 804872.2147 |  |  | 126450.55 |  |  |  | 0 |  | 931322.7647
4. DC Equipment |  |  | 617917.8555 | 204482.4642 |  | 62372.4267 |  |  |  | 0 |  | 884772.7463
5. Monitoring |  | 10654.7475 | 11768.8539 | 31422.5478 | [5 empty] | 0 |  | 53846.1492
6. AC Equipment |  |  | 131448.7279 | 1029198.4193 |  | 155346.7019 |  |  |  | 0 |  | 1315993.8491
8. Product Add On | [6 empty] | 0 |  |  |  |  | 0
9. AC & DC installation |  |  | 238967.6471 | 430141.7647 |  | 286761.1765 |  |  |  | 0 |  | 955870.5882
10. Site Logistics | 0 |  | 7851.6226 | 169142.5782 |  | 75854.6588 |  |  |  | 0 |  | 252848.8596
11. Due Dilligence |  | 126836.1222 |  |  | 42577.5034 | 16684.0185 |  |  |  | 0 |  | 186097.6441
13. Engineering | 0 |  |  |  |  | 342363.6235 |  |  |  | 0 |  | 342363.6235
14. General Expenses | 0 | 0 | 7781.1238 | 8170.6963 | 0 | 1216.14 | 1151.0944 | 0 | 3092.71 | 0 |  | 21411.7645
15. Service Add On | 0 |  |  | 1535000 |  | 65000 | 0 |  |  | 0 |  | 1600000
12. BDP Commission
7.BESS
Grand Total | 0 | 137490.8698 | 4758508.5345 | 3491818.9006 | 42577.5034 | 1132049.2959 | 1151.0944 | 0 | 3092.71 | 0 |  | 9566688.9085
|  | 137490.87 | 4758508.53 | 3492604.85 | 42577.5 | 1131263.35 | 1151.0944 | 0 | 3092.71 |  |  | 9566688.9044
|  | -0.00023948 | 0.0045288 | -785.9494 | 0.0033659 | 785.9459
9566688.9258
9566688.9044
0.021376

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2026-01-31 | Grand Total
(blank)
1. Panels |  |  | 2067265.53 | [7 empty] | 2067265.53
2. Inverters |  |  | 551748.64 | [7 empty] | 551748.64
3. Mounting Structures |  |  | 205256.6 |  |  | 0 |  |  |  |  | 205256.6
4. DC Equipment |  |  | 541933.375 | 692424.075 |  | 93616.05 |  |  |  |  | 1327973.5
5. Monitoring |  | 28665 | 10583.83 | 59148.29 | [6 empty] | 98397.12
6. AC Equipment |  |  | 40516.5 | 322738.28 |  | 48619.8 |  |  |  |  | 411874.58
8. Product Add On |  |  |  | 92203 |  |  | 110562.57 |  | 12500 | -23537 | 191728.57
9. AC & DC installation |  |  | 273787.5 | 492817.5 |  | 328545 |  |  |  |  | 1095150
10. Site Logistics |  |  | 4425 | 7965 |  | 5310 |  |  |  |  | 17700
11. Due Dilligence |  | 72900 |  |  | 28642.46 | 10000 |  |  |  |  | 111542.46
13. Engineering | 0 |  |  |  |  | 119583.6116 |  |  |  |  | 119583.6116
14. General Expenses | 0 | 0 | 3116.87 | 7517.79 | 0 | 5923.19 | 5002.96 | 0 | 0 |  | 21560.81
15. Service Add On | 0 |  |  | 1435000 |  |  | 57750 |  |  |  | 1492750
12. BDP Commission
7.BESS
Grand Total | 0 | 101565 | 3698633.845 | 3109813.935 | 28642.46 | 611597.6516 | 173315.53 | 0 | 12500 | -23537 | 7712531.4216

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate | [5 empty] | FINANCIAL CLOSE CERTIFICATE
Project Name: | Gillwell Mall
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion: |  |  |  | 1. Financial Close | 1. Financial Close
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 0.26644 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.1363 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.092209 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 0.22067 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
Gillwell Mall |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Gillwell Mall | 0 | 0 | 0