## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[9 empty] | 2026-02-09 | 2026-02-09
| PROJECT PLAN | Randfontein | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 370
| PROJECT DEVELOPER | Natasha Watkins-Baker
| PROJECT MANAGERS | JT Moorosi
| CONTRACT VALUE | 3355439
| Phase: | Construction
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Expected Status | Comment
|  |  | 44 |  |  | 253 |  | 54.77% | 60.16%
1 | Project Initiation | 2025-04-22 | 42 | 2025-06-03 | 2025-04-29 | 17 | 2025-05-16 | 100% | 100%
1.1 | BD Handover | 2025-04-22 | 1 | 2025-04-23 | 2025-05-13 | 1 | 2025-05-14 | 100% | 100%
1.2 | Project Introduction | 2025-06-02 | 1 | 2025-06-03 | 2025-05-15 | 1 | 2025-05-16 | 100% | 100%
1.3 | HSE | 2025-04-22 | 10 | 2025-05-07 | 2025-04-29 | 10 | 2025-05-14 | 100% | 100%
1.4 | Installer Kick Off | 2025-05-26 | 1 | 2025-05-27 | 2025-05-14 | 1 | 2025-05-15 | 100% | 100%
1.5 | Project Review | 2025-05-26 | 1 | 2025-05-27 | 2025-05-08 | 1 | 2025-05-09 | 100% | 100%
2 | Site Establishment | 2025-06-09 | 1 | 2025-06-10 | 2025-06-10 | 1 | 2025-06-11 | 100% | 100%
2.1 | Solar Contractor Establishment | 2025-06-09 | 1 | 2025-06-10 | 2025-06-10 | 1 | 2025-06-11 | 100% | 100% |  | 160 | Net Work Days
3 | AC Installation | 2025-05-19 | 60 | 2025-07-18 | 2025-05-20 | 204 | 2025-12-10 | 100% | 100% |  | 32 | Total Weeks
3.1 | Inverters delivered | 2025-06-10 | 1 | 2025-06-11 | 2025-06-23 | 1 | 2025-06-24 | 100% | 100% |  | 11.5625 | kW/Week Installation Rate
3.2 | Inverters Mounted | 2025-06-11 | 5 | 2025-06-19 | 2025-11-17 | 5 | 2025-11-24 | 100% | 100% | DB Room readiness hold up
3.3 | Solar DB Lead Time | 2025-05-19 | 25 | 2025-06-24 | 2025-05-20 | 30 | 2025-07-02 | 100% | 100%
3.4 | AC Works | 2025-06-24 | 18 | 2025-07-18 | 2025-11-17 | 9 | 2025-11-28 | 100% | 100%
3.5 | AC Tie-In | 2025-06-24 | 3 | 2025-06-27 | 2025-12-05 | 3 | 2025-12-10 | 100% | 100%
4 | DC Works | 2025-06-09 | 39 | 2025-07-18 | 2025-06-10 | 248 | 2026-02-13 | 38.18% | 81.31%
4.1 | Lifeline Installation (If Applicable) | [6 empty] | 0% | 0%
4.1 | Mounting Structure delivered | 2025-06-09 | 1 | 2025-06-10 | 2025-06-10 | 1 | 2025-06-11 | 100% | 100%
4.2 | Mounting Structure installation | 2025-06-10 | 15 | 2025-07-02 | 2025-06-11 | 6 | 2025-06-20 | 100% | 100%
4.3 | DC Cable delivered | 2025-06-09 | 1 | 2025-06-10 | 2025-06-23 | 1 | 2025-06-24 | 100% | 100%
4.3 | DC Stringing | 2025-07-11 | 5 | 2025-07-18 | 2026-01-26 | 14 | 2026-02-13 | 10% | 77.78% | Waiting on combiner box order
5 | Module installation | 2025-06-25 | 19 | 2025-07-14 | 2025-06-23 | 171 | 2025-12-11 | 100% | 100%
5.1 | Module delivery | 2025-06-25 | 1 | 2025-06-26 | 2025-06-23 | 1 | 2025-06-24 | 100% | 100%
5.2 | Module mounting | 2025-06-26 | 12 | 2025-07-14 | 2025-11-24 | 13 | 2025-12-11 | 100% | 100%
6 | Commissioning | 2025-07-18 | 5 | 2025-07-23 | 2026-02-13 | 5 | 2026-02-18 | 0% | 0%
6.1 | Commissioning | 2025-07-18 | 1 | 2025-07-21 | 2026-02-13 | 1 | 2026-02-16 | 0% | 0% | delayed due to combiner box order
6.2 | Practical Completion | 2025-07-21 | 2 | 2025-07-23 | 2026-02-16 | 2 | 2026-02-18 | 0% | 0%
7 | QA Inspections | 2025-07-23 | 1 | 2025-07-24 | 2026-02-16 | 1 | 2026-02-17 | 0% | 0%
7.1 | Red-Team Inspection | 2025-07-23 | 1 | 2025-07-24 | 2026-02-16 | 1 | 2026-02-17 | 0% | 0%
8 | Project Closure | 2025-07-24 | 15 | 2025-08-08 | 2026-02-17 | 16 | 2026-03-05 | 0% | 0%
8.1 | Equipment serial numbers | 2025-07-24 | 2 | 2025-07-28 | 2026-02-17 | 2 | 2026-02-19 | 0% | 0%
8.2 | Snags completion | 2025-07-24 | 5 | 2025-07-31 | 2026-02-17 | 5 | 2026-02-24 | 0% | 0%
8.3 | System Performance Monitoring | 2025-07-31 | 5 | 2025-08-07 | 2026-02-24 | 5 | 2026-03-03 | 0% | 0%
8.4 | Handover documentation | 2025-07-24 | 9 | 2025-08-06 | 2026-02-17 | 9 | 2026-03-02 | 0% | 0%
8.5 | Handover to Client | 2025-08-06 | 1 | 2025-08-07 | 2026-03-02 | 1 | 2026-03-03 | 0% | 0%
8.6 | Handover to Matriarch | 2025-08-02 | 5 | 2025-08-08 | 2026-02-26 | 5 | 2026-03-05 | 0% | 0%
Plus one day for multiple delays 15 September
Plus one day for rain delay 29 September
Formulas:
Planned Start = MIN([Planned Start, row below]:E16)
Planned Start = WORKDAY.INTL([Planned End, row above],0,1,Data!$C3:C39)
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C39)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = WORKDAY.INTL([Actual End, row above],0,1,Data!$C3:C39)
Actual End = MAX([Actual End, row below]:K16)
Actual End = MAX([Actual End, row below])
Expected Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 3355439 |  | 3355439 |  |  |  | Start Date | 3047401.8199 | 2488410.0019 | 286911.3693 | 710293.7315 | 17130.6528 | 515262.67
2 | Planned Expenditure | 3002994.7437 |  | 3198703.7334 | VO PM Limit | Current VO Total
3 | Planned Profit | 352444.2563 |  | 156735.2666 | 17622.2128 | 383215.86 |  | End Date - PC
4 | Planned Margin | 10.5% |  | 4.671%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE |  | MILESTONE NOTES & COMMENTS
1 | Deposit |  | 20% | 671087.8 |  | 2025-04-30 | 004736 | 2025-05-01 | 2025-04-30
2 | Delivery of Panels |  | 20% | 671087.8 |  | 2025-07-02 | 004736 | 2025-05-01 | 2025-07-04
3 | Delivery of Inverters |  | 15% | 503315.85 |  | 2025-06-17 | 004736 | 2025-05-01 | 2025-06-20
4 | Commissioning Complete |  | 15% | 503315.85 |  | 2025-07-30 | 004736 | 2025-05-01 | 2026-02-25
5 | Final Completion Issued |  | 25% | 838859.75 |  | 2025-07-31 | 004736 | 2025-05-01 | 2026-02-24
6 | Handover |  | 5% | 167771.95 |  | 2026-03-10 | 004736 | 2025-05-01 | 2026-03-10
7 | - |  | 0% | 0
|  |  | 100% | 3355439
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
| confirmed | [5 empty] | 578813.2275
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 1174403.65
2 | Delivery of Panels |  | 30% | 1006631.7
3 | Delivery of Inverters |  | 20% | 671087.8
4 | Practical Completion |  | 10% | 335543.9
5 | Handover |  | 5% | 167771.95
| Total |  | 100% | 3355439
|  |  | 100% | 3355439

## Data
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-17
2025-12-18
2025-12-19
2025-12-20
2025-12-21
2025-12-22
2025-12-23
2025-12-24
2025-12-25
2025-12-26
2025-12-27
2025-12-28
2025-12-29
2025-12-30
2025-12-31
2026-01-01
2026-01-02
2026-01-03
2026-01-04
2026-01-05
2026-01-06
2026-01-07
2026-01-08
2026-01-09
2026-01-10
2026-01-11 | Christmas Day
2026-01-12 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 3002994.7437 |  | 3198703.7334 | -195708.9897
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 777559.09 |  | 745481.4 | 32077.69
2 | 2. Inverters | 210000 |  | 206611.05 | 3388.95
3 | 3. Mounting Structures | 300883.17 |  | 67376.8 | 233506.37
4 | 4. DC Equipment | 304127.7 |  | 380751.1409 | -76623.4409
5 | 5. Monitoring | 49000 |  | 43124.63 | 5875.37
6 | 6. AC Equipment | 392189.7261 |  | 209725.1493 | 182464.5768
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 0 |  | 285374.09 | -285374.09
9 | 9. AC & DC installation | 288452.5 |  | 483120.2421 | -194667.7421
10 | 10. Site Logistics | 58027.9333 |  | 54333.8537 | 3694.0796
11 | 11. Due Dilligence | 116504.5 |  | 29473.04 | 87031.46
12 | 12. BDP Commission | 77365.8165 |  | 0 | 77365.8165
13 | 13. Engineering | 122409.3077 |  | 41942.9875 | 80466.3202
14 | 14. General Expenses | 6475 |  | 5251.35 | 1223.65
15 | 15. Service Add On | 300000 |  | 646138 | -346138
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 3002994.7437 | 3355439.0188 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 3198703.7334
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 777559.09 | 2025-07-29 | 777559.09 | 883589.875 |  | 1 | 1. Panels | Jinko 620W - Menlo | 597 | 1233.8 | 281646.11 | PO3905-DIP-PH2-RANDF-20250514 | Menlo INV0003029 | 2025-06-30 | 883589.875 | 0 | 2025-07-29 | 745481.4
1 |  | Delivery Budget |  |  |  | 2025-08-14 |  |  |  | 1 | 1. Panels |  |  | 1.99 | 454932.49 |  | Menlo INV0003029 | 2025-06-30 | 0 |  | 2025-08-14
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels |  |  |  | 4601.4 |  | Menlo - INV0003274 | 2025-09-30 | 0 |  | 2025-11-19
1 | [9 empty] | 1 | 1. Panels | Jinko 620W - Menlo - VO | 3 | 1233.8 | 3701.4 |  | MSA Energy INV0003445 | 2025-11-30 | 0 |  | 2026-01-23
1 | [9 empty] | 1 | 1. Panels | Transport |  |  | 600 |  | MSA Energy INV0003445 | 2025-11-30 | 0 |  | 2026-01-23 |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 392189.7261
2 | Inverters | Inverter Budget |  |  | 210000 | 2025-07-29 | 210000 | 238636.3636 |  | 2 | 2. Inverters | Huawei 100KTL - Menlo | 3 | 68870.35 | 206611.05 | PO3905-DIP-PH2-RANDF-20250514 | Menlo INV0003029 | 2025-06-30 | 238636.3636 | 0 | 2025-07-29 | 206611.05 | DC Equipment | 182845.7
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | AC Labour | 92522.5
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 195930
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 25764.6
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 4563.3333
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 300883.17 | 2025-07-29 | 300883.17 | 341912.6932 |  | 3 | 3. Mounting Structures | Schletter Structure |  |  | 66124.8 | PO3945-DRS-20250521 - RV Approved | Schletter - INV1846 | 2025-06-30 | 341912.6932 | 0 | 2025-07-29 | 67376.8 | Other | 0
3 | [9 empty] | 3 | 3. Mounting Structures | End Clamps Top Up - Schletter |  |  | 1252 | PO4595-DRS-20260202 - RV Approved |  | 2026-02-28 | 0 |  | 2026-03-30 |  | Total | 902315.8594
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Less 15% | 766968.4805
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | R/Wp | 2.0729
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL - Thula Moya | Installer Price
[23 empty] | AC Equipment | 92394.5344
4 | DC Equipment | DC Cable Budget | 9962.45 |  | 121282 | 2025-07-29 | 304127.7 | 345599.6591 |  | 4 | 4. DC Equipment | DC Cable - menlo | 8000 | 13.4 | 107200 | PO3905-DIP-PH2-RANDF-20250514 | Menlo INV0003016 | 2025-06-30 | 126768.5888 | -0.00047399 | 2025-07-29 | 380751.1409 | DC Equipment | 185051.2892
4 |  | DC Equipment Budget |  |  | 182845.7 | 2025-07-29 |  |  |  | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | AC Labour | 149328.0762
4 | [9 empty] | 4 | 4. DC Equipment | Aditional DC Cable - Rubicon - VO | 6000 | 14 | 84000 | PO4572-DRS-20260123 - RV Approved | Rubicon - INVCRED-0137907 | 2026-01-31 |  |  | 2026-03-02 |  | DC Labour | 333792.1704
4 | [9 empty] | 4 | 4. DC Equipment | Delivery Extra DC - Rubicon - VO | 1 |  | 4500 |  | Rubicon - INVCRED-0137907 | 2026-01-31 |  |  | 2026-03-02 |  | Offloading | 9090.5891
4 | [5 empty] | 2025-05-15 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 185051.2892 | 10% | 18505.1289 | PO3878-DRS-20250513 - RV Approved | Thula Moya Inv: IN04721 | 2025-05-31 | 21883.107 |  | 2025-05-15 |  | Scaffolding | 33154.9112
4 | [5 empty] | 2025-05-15 |  |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 27757.6934 |  | Thula Moya Inv: IN04721 | 2025-05-31 | 32824.6606 |  | 2025-05-15 |  | Storage | 5473.9606
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 37010.2578 |  | Thula Moya IN04801 | 2025-07-31 | 43766.2142 |  | 2026-01-15 |  | Telehandler | 0
4 | [5 empty] | 2025-07-10 |  |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 14% | 25907.18 |  | Thula Moya IN04775 | 2025-07-31 | 30636.3493 |  | 2025-07-10 |  | HSE | 2014.469
[6 empty] | 2025-09-11 |  |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 11% | 20355.6418 |  | Thula Moya IN04841 | 2025-08-31 | 24071.56 |  | 2025-09-11
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 18505.1289 |  | Thula Moya IN04842 | 2025-08-31 | 21883.1182 |  | 2026-02-25 |  | Other | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 18505.11 |  | Thula Moya IN04843 | 2025-08-31 | 21883.0958 |  | 2026-03-03 |  | Other | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 9252.5 |  | Thula Moya IN04844 | 2025-08-31 | 10941.4829 |  | 2026-03-03 |  | Total | 810300
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 9252.5 |  | Thula Moya IN04845 | 2025-08-31 | 10941.4829 |  | 2026-03-26 |  | R/Wp | 2.19
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 34000 | 2025-07-17 | 49000 | 55681.8182 |  | 5 | 5. Monitoring | Smartlogger - Menlo |  |  | 8598.35 | PO3905-DIP-PH2-RANDF-20250514 | Menlo INV0002934 | 2025-05-31 | 12277.0934 | -0.0044773 | 2025-07-17 | 43124.63
5 |  | Revenue Metering |  |  | 15000 | 2025-05-29 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 13695 | PO3836-DIP-Ph2-Rand-20250429 - RV Approved | Accuenergy Inv: ASAI005362 | 2025-04-30 | 19114.2374 |  | 2025-05-29
[6 empty] | 2025-07-29 |  |  |  | 5 | 5. Monitoring |  |  |  | 214.28 |  | Accuenergy - Inv ASAI-005800 | 2025-06-30 | 332.1028 |  | 2025-07-29
5 | [5 empty] | 2025-06-30 |  |  |  | 5 | 5. Monitoring | Techsitter |  |  | 11169 |  | Matriarch Inv: 4451 | 2025-06-30 | 20789.4531 |  | 2025-06-30
5 | [5 empty] | 2025-05-22 |  |  |  | 5 | 5. Monitoring | UPS |  |  | 2250.5 | PO3863-DIP Ph2-20250509 - RV Approved | Frontline INV725690 | 2025-05-31 | 3168.936 |  | 2025-05-22
5 | [9 empty] | 5 | 5. Monitoring | Grid CTs and Router - AccuEnergy |  |  | 7197.5 | PO4603-DRS-20260204 - RV Approved | Accuenergy - ASAI-007333 | 2026-02-28 | 0 |  | 2026-03-30
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 392189.7261 | 2025-07-28 | 392189.7261 | 445670.1433 |  | 6 | 6. AC Equipment | [7 empty] | 0 | -0.00045099 |  | 209725.1493
6 | [5 empty] | 2025-07-29 |  |  |  | 6 | 6. AC Equipment | PVDB |  |  | 117330.71 | PO3882-DIP-Ph2-Rand-20250513 - RV Approved | Switchboard Inv 2-SOI002095 | 2025-06-30 | 248633.7059 |  | 2025-07-29
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [5 empty] | 2025-05-15 |  |  |  | 6 | 6. AC Equipment | Project Kick Off | 92394.5344 | 10% | 9239.4534 | PO3878-DRS-20250513 - RV Approved | Thula Moya Inv: IN04721 | 2025-05-31 | 19912.5326 |  | 2025-05-15
6 | [5 empty] | 2025-05-15 |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 13859.1802 |  | Thula Moya Inv: IN04721 | 2025-05-31 | 29868.7988 |  | 2025-05-15
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 18478.9069 |  | Thula Moya IN04801 | 2025-07-31 | 39268.0304 |  | 2026-01-15
6 | [5 empty] | 2025-07-10 |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 14% | 12935.23 |  | Thula Moya IN04775 | 2025-07-31 | 27487.611 |  | 2025-07-10
[6 empty] | 2025-09-11 |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 11% | 10163.3988 |  | Thula Moya IN04841 | 2025-08-31 | 21597.586 |  | 2025-09-11
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 9239.46 |  | Thula Moya IN04842 | 2025-08-31 | 19634.0376 |  | 2026-02-25
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 9239.41 |  | Thula Moya IN04843 | 2025-08-31 | 19633.9313 |  | 2026-03-03
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 4619.7 |  | Thula Moya IN04844 | 2025-08-31 | 9816.955 |  | 2026-03-03
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 4619.7 |  | Thula Moya IN04845 | 2025-08-31 | 9816.955 |  | 2026-03-26
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS |  |  | 401105.424
7 | [9 empty] | 7 | 7.BESS |  |  | 334254.52
8 | Product Add On | [5 empty] | 0 | 0 |  | 8 | 8. Product Add On | DC VO - DC Cable and Trunking - ThulaMoya |  |  | 245754.52 | PO4488-DRS-20251124 - RV Approved | Thula Moya IN04963 | 2025-11-30 |  | 0 | 2026-02-05 | 285374.09
8 | [9 empty] | 8 | 8. Product Add On
8 | [5 empty] | 2025-06-26 |  |  |  | 8 | 8. Product Add On | Site delays - VO |  | 18219.57 | 18219.57 |  | Thula Moya IN04758 | 2025-06-30 |  |  | 2025-06-26
8 | [9 empty] | 8 | 8. Product Add On
8 | [5 empty] | 1900-01-29 |  |  |  | 8 | 8. Product Add On | Waterpoint - Plumbryt - Deposit |  |  | 17120 | PO4548-DRS-20260108 - RV Apporved | Plumbryt Inv 023 | 2026-01-31 |  |  | 2026-01-29
8 | [9 empty] | 8 | 8. Product Add On | Waterpoint - Plumbryt - Balance |  |  | 4280 |  | Plumbryt Inv 023 | 2026-01-31 |  |  | 2026-02-12
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
8 | [9 empty] | 8 | 8. Product Add On
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 92522.5 | 2025-05-14 | 288452.5 | 339355.8824 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0.00079448 |  | 483120.2421
9 |  | DC Installation Budget |  |  | 195930 | 2025-05-15 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 483120.2466 | 10% | 48312.0247 | PO3878-DRS-20250513 - RV Approved | Thula Moya Inv: IN04721 | 2025-05-31 | 33935.5882 |  | 2025-05-15
9 | [5 empty] | 2025-05-15 |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 72468.037 |  | Thula Moya Inv: IN04721 | 2025-05-31 | 50903.3824 |  | 2025-05-15
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 96624.0493 |  | Thula Moya IN04801 | 2025-07-31 | 67871.1771 |  | 2026-01-15
9 | [5 empty] | 2025-07-10 |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 14% | 67636.83 |  | Thula Moya IN04775 | 2025-07-31 | 47509.8208 |  | 2025-07-10
[6 empty] | 2025-09-11 |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 11% | 53143.2271 |  | Thula Moya IN04841 | 2025-08-31 | 37329.1474 |  | 2025-09-11
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 48312.0247 |  |  | 2026-02-28 | 33935.5886 |  | 2026-02-25
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 48312.0247 |  |  | 2026-03-31 | 33935.5886 |  | 2026-03-03
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 24156.0123 |  |  | 2026-03-31 | 16967.7943 |  | 2026-03-03
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 24156.0123 |  |  | 2026-03-31 | 16967.7943 |  | 2026-03-26
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-07-09 | 58027.9333 | 68268.1569 |  | 10 | 10. Site Logistics | [7 empty] | 0 | 0.0044755 |  | 54333.8537
10 |  | Scaffolding |  |  | 25764.6 | 2025-07-10 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
[6 empty] | 2025-07-11 |  |  |  | 10 | 10. Site Logistics | Security- June |  |  | 4600 |  | Jerry & Son iNV 7 | 2025-06-30 | 4257.6439 |  | 2025-07-11
[6 empty] | 2025-07-12 |  |  |  | 10 | 10. Site Logistics | [6 empty] | 2025-08-31 | 21125.83
[6 empty] | 2025-07-13 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
[6 empty] | 2025-07-14 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Security |  |  | 19200 | 2025-07-15 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 4563.3333 | 2025-07-16 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [5 empty] | 2025-05-15 |  |  |  | 10 | 10. Site Logistics | Project Kick Off | 49733.9298 | 10% | 4973.393 | PO3878-DRS-20250513 - RV Approved | Thula Moya Inv: IN04721 | 2025-05-31 | 2617.0823 |  | 2025-05-15
10 | [5 empty] | 2025-05-15 |  |  |  | 10 | 10. Site Logistics | Site Establishment |  | 15% | 7460.0895 |  | Thula Moya Inv: IN04721 | 2025-05-31 | 3925.6235 |  | 2025-05-15
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 9946.786 |  | Thula Moya IN04801 | 2025-07-31 | 6306.9194 |  | 2026-01-15
10 | [5 empty] | 2025-07-10 |  |  |  | 10 | 10. Site Logistics | DC Installation Complete |  | 14% | 6962.75 |  | Thula Moya IN04775 | 2025-07-31 | 4414.8434 |  | 2025-07-10
[6 empty] | 2025-09-11 |  |  |  | 10 | 10. Site Logistics | DC Installation Complete |  | 11% | 5470.7323 |  | Thula Moya IN04841 | 2025-08-31 | 6873.7405 |  | 2025-09-11
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 4973.41 |  | Thula Moya IN04842 | 2025-08-31 | 6248.8764 |  | 2026-02-25
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 4973.3 |  | Thula Moya IN04843 | 2025-08-31 | 6248.7382 |  | 2026-03-03
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 2486.6965 |  | Thula Moya IN04844 | 2025-08-31 | 3124.4275 |  | 2026-03-03
10 | [5 empty] | #REF! |  |  |  | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 2486.6965 |  | Thula Moya IN04845 | 2025-08-31 | 3124.4275 |  | 2026-03-26
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2025-06-23 | 116504.5 | 137064.1176 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 10160.8 |  | Sunspot E027 | 2025-07-31 | 48966.6625 | -0.002858 | 2026-03-04 | 29473.04
11 |  | Structural Sign Off |  |  | 18504.5 | 2025-06-24 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 8212.24 | PO3745-DIP-Ph2-20250313 - RV Approved | L&B Consulting - Invoice 1934 | 2025-04-30 | 37133.6275 |  | 2025-04-10
11 |  | Grid Study |  |  | 80000 | 2025-06-25 |  |  |  | 11 | 11. Due Dilligence | Grid Study |  |  | 0 |  |  |  | 0
11 |  | Lightning Risk Assessment |  |  | 7000 | 2025-06-26 |  |  |  | 11 | 11. Due Dilligence | Lightning Risk Assessment |  |  | 5100 | PO3844-Dipula Ph2-20250430 - RV Approved | LPS Inv: IN306837 | 2025-04-30 | 23060.8823 |  | 2025-06-26
11 | [5 empty] | 2025-06-27 |  |  |  | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 |  |  | 2026-02-28 | 27902.9481 |  | 2026-03-30
2025-06-28
12 | BDP Commission | Referral Fee |  |  | 64471.5138 | 2025-06-29 | 77365.8165 | 0 |  | 12 | 12. BDP Commission | Referral Fee | [9 empty] | 0
12 | BDP Commission | PD Fee |  |  | 12894.3028 | 2025-06-30 |  |  |  | 12 | 12. BDP Commission | PD Fee
13 | Engineering | Matriarch Defects Period |  |  | 31209.3077 | 2025-10-31 | 122409.3077 | 139101.4861 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 41942.9875 |  |  | 2026-02-28 | 139101.4861 | 0 | 2026-01-31 | 41942.9875
13 |  | Management |  |  | 16000 | 2025-10-31 |  |  |  | 13 | 13. Engineering | Management |  |  | 0 |  |  | 2025-10-31 | 0 |  | 2025-10-31
13 |  | Project manager |  |  | 40800 | 2025-10-31 |  |  |  | 13 | 13. Engineering | Project manager |  |  | 0 |  |  | 2025-10-31 | 0 |  | 2025-10-31
13 |  | Planner time |  |  | 20800 | 2025-10-31 |  |  |  | 13 | 13. Engineering | Planner time |  |  | 0 |  |  | 2025-10-31 | 0 |  | 2025-10-31
13 |  | De Snagging |  |  | 13600 | 2025-10-31 |  |  |  | 13 | 13. Engineering | De Snagging |  |  | 0 |  |  | 2025-10-31 | 0 |  | 2025-10-31
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 6475 | 2025-04-30 | 6475 | 7617.6471 |  | 14 | 14. General Expenses | Travel |  |  | 0 |  |  | 2025-04-30 | 0 | 0.0026956 | 2025-04-30 | 5251.35
14 | [5 empty] | 2025-06-09 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 1399.43 |  | Expense Claim | 2025-05-31 | 3189.8824 |  | 2025-06-09
14 | [5 empty] | 2025-07-04 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 1699.57 |  | Expense Claim | 2025-06-30 | 2182.6953 |  | 2025-07-04
14 | [5 empty] | 2025-08-07 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 502.18 |  | Expense Claim | 2025-07-31 | 230.2591 |  | 2025-08-07
14 | [5 empty] | 2025-08-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 380.32 |  | Expense Claim | 2025-08-31 | 625.8681 |  | 2025-08-31
14 | [5 empty] | 2025-09-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-09-30 | 0 |  | 2025-10-09
14 | [5 empty] | 2025-10-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 125.19 |  | Expense Claim | 2025-10-31 | 176.5472 |  | 2025-11-06
14 | [5 empty] | 2025-11-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-11-30 | 0 |  | 2025-11-30
14 | [5 empty] | 2025-12-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 244.66 |  | Expense Claim | 2025-12-31 | 242.8756 |  | 2026-01-08
14 | [5 empty] | 2026-01-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 300 |  |  | 2026-01-31 | 323.1722 |  | 2026-02-05
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 300 |  |  | 2026-02-28 | 323.1722 |  | 2026-03-05
[10 empty] | 14 | 14. General Expenses | Travel |  |  | 300 |  |  | 2026-03-31 | 323.1722 |  | 2026-04-09
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | Welcome Bonus |  |  | 300000 | 2025-07-11 | 300000 | 352941.1765 |  | 15 | 15. Service Add On | Welcome Bonus - Site establishment |  |  | 251500 |  | Luxanio Trading - 23402/202506/274899/I | 2025-06-30 | 168114.9733 | -5.3476e-05 | 2025-07-11 | 646138
15 | [5 empty] | 2025-08-31 |  |  |  | 15 | 15. Service Add On | Welcome Bonus - Commissioning |  |  | 251500 |  | Luxanio Trading - 23402/202506/274899/I | 2025-06-30 | 168114.9733 |  | 2026-02-25
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [5 empty] | 2025-09-11 |  |  |  | 15 | 15. Service Add On | Roof Remediation - VO | 50% | 143138 | 27040.37 |  | Thula Moya IN04886 | 2025-09-30 | 5570.41 |  | 2025-09-11
[6 empty] | 2025-10-02 |  |  |  | 15 | 15. Service Add On |  |  | 71569 | 44528.63 |  | Thula Moya IN04886 | 2025-09-30 | 5570.41 |  | 2025-10-02
15 | [5 empty] | 2025-10-15 |  |  |  | 15 | 15. Service Add On |  |  |  | 71569 |  | Thula Moya IN04886 | 2025-09-30 | 5570.41 |  | 2025-12-04
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
15 | [9 empty] | 15 | 15. Service Add On | [7 empty] | 0
| Panel Procurement Budget | 777559.09 |  | 883589.875
| Inverter Procurement Budget | 210000 |  | 238636.3636
| Mounting Structure Budget | 300883.17 |  | 341912.6932
| DC Equipment Budget | 304127.7 |  | 345599.6591
| AC Equipment Budget | 392189.7261 |  | 445670.1433
| Monitoring Budget | 49000 |  | 55681.8182
| Optional Extras Budget | 0 |  | 0
| MV Metering Budget | 0 |  | 0
| ADD ON | 0 |  | 0
| Battery System | 0 |  | 0
| Generator | 0 |  | 0
Services
| AC Installer Budget | 92522.5 |  | 108850
| DC Installer Budget | 195930 |  | 230505.8824
| In-House Expense Budget | 122409.3077 |  | 139101.4861
| Compliance Budget | 116504.5 |  | 137064.1176
| Offloading Budget | 8500 |  | 10000
| Roof Access Budget for Equipment | 0 |  | 0
| Site storage | 4563.3333 |  | 5368.6275
| On Site Security | 19200 |  | 22588.2353
| Roof Access Budget for Installers | 25764.6 |  | 30311.2941
| EPC Management Fee | 0 |  | 0
| ADD ON | 300000 |  | 352941.1765
Expenses
| Total EE Expense Budget | 6475 |  | 7617.6471

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 3355439 | 3355439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671087.8 | 0 | 0 | 0 | 0 | 0 | 0 | 503315.85 | 0 | 671087.8 | 0 | 0 | 0 | 1342175.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167771.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671087.8 | 671087.8 | 671087.8 | 671087.8 | 671087.8 | 671087.8 | 671087.8 | 1174403.65 | 1174403.65 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3187667.05 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439
| Planned Expenditure | 3002994.7437 | 3002994.7437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6475 | 0 | 288452.5 | 0 | 15000 | 0 | 0 | 0 | 180976.0138 | 12894.3028 | 334264.6 | 57763.3333 | 0 | 1984759.6861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122409.3077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6475 | 6475 | 294927.5 | 294927.5 | 309927.5 | 309927.5 | 309927.5 | 309927.5 | 490903.5138 | 503797.8165 | 838062.4165 | 895825.7498 | 895825.7498 | 2880585.4359 | 2880585.4359 | 2880585.4359 | 2880585.4359 | 2880585.4359 | 2880585.4359 | 2880585.4359 | 2880585.4359 | 2880585.4359 | 2880585.4359 | 2880585.4359 | 2880585.4359 | 2880585.4359 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437 | 3002994.7437
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 664612.8 | 664612.8 | 376160.3 | 376160.3 | 361160.3 | 361160.3 | 361160.3 | 864476.15 | 683500.1362 | 1341693.6335 | 1007429.0335 | 949665.7002 | 949665.7002 | 307081.6141 | 307081.6141 | 307081.6141 | 307081.6141 | 307081.6141 | 307081.6141 | 307081.6141 | 307081.6141 | 307081.6141 | 307081.6141 | 307081.6141 | 307081.6141 | 307081.6141 | 184672.3063 | 184672.3063 | 184672.3063 | 184672.3063 | 184672.3063 | 184672.3063 | 184672.3063 | 184672.3063 | 184672.3063 | 184672.3063 | 184672.3063 | 184672.3063 | 184672.3063 | 184672.3063 | 184672.3063 | 184672.3063 | 184672.3063 | 184672.3063 | 184672.3063 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563 | 352444.2563
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 3355439 | 3355439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671087.8 | 0 | 0 | 0 | 0 | 0 | 0 | 503315.85 | 0 | 671087.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1342175.6 | 0 | 167771.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671087.8 | 671087.8 | 671087.8 | 671087.8 | 671087.8 | 671087.8 | 671087.8 | 1174403.65 | 1174403.65 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 1845491.45 | 3187667.05 | 3187667.05 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439 | 3355439
| Actual + Planned Expenditure | 3198703.7334 | 3198703.7334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8212.24 | 0 | 0 | 0 | 0 | 202575 | 2250.5 | 13695 | 0 | 1399.43 | 0 | 23319.57 | 12868.57 | 369541.99 | 8598.35 | 0 | 779126.95 | 502.18 | 454932.49 | 0 | 380.32 | 0 | 116173.37 | 0 | 0 | 44528.63 | 0 | 0 | 0 | 0 | 125.19 | 0 | 4601.4 | 0 | 71569 | 0 | 0 | 0 | 0 | 244.66 | 162060 | 4301.4 | 59062.9875 | 246054.52 | 4280 | 0 | 332530.0236 | 220505.5535 | 0 | 0 | 40514.9088 | 14449.5 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8212.24 | 8212.24 | 8212.24 | 8212.24 | 8212.24 | 210787.24 | 213037.74 | 226732.74 | 226732.74 | 228132.17 | 228132.17 | 251451.74 | 264320.31 | 633862.3 | 642460.65 | 642460.65 | 1421587.6 | 1422089.78 | 1877022.27 | 1877022.27 | 1877402.59 | 1877402.59 | 1993575.96 | 1993575.96 | 1993575.96 | 2038104.59 | 2038104.59 | 2038104.59 | 2038104.59 | 2038104.59 | 2038229.78 | 2038229.78 | 2042831.18 | 2042831.18 | 2114400.18 | 2114400.18 | 2114400.18 | 2114400.18 | 2114400.18 | 2114644.84 | 2276704.84 | 2281006.24 | 2340069.2275 | 2586123.7475 | 2590403.7475 | 2590403.7475 | 2922933.7711 | 3143439.3246 | 3143439.3246 | 3143439.3246 | 3183954.2334 | 3198403.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334 | 3198703.7334
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8212.24 | -8212.24 | -8212.24 | 662875.56 | 662875.56 | 460300.56 | 458050.06 | 444355.06 | 444355.06 | 442955.63 | 946271.48 | 922951.91 | 1581171.14 | 1211629.15 | 1203030.8 | 1203030.8 | 423903.85 | 423401.67 | -31530.82 | -31530.82 | -31911.14 | -31911.14 | -148084.51 | -148084.51 | -148084.51 | -192613.14 | -192613.14 | -192613.14 | -192613.14 | -192613.14 | -192738.33 | -192738.33 | -197339.73 | -197339.73 | -268908.73 | -268908.73 | -268908.73 | -268908.73 | -268908.73 | -269153.39 | -431213.39 | -435514.79 | -494577.7775 | -740632.2975 | -744912.2975 | -744912.2975 | 264733.2789 | 44227.7254 | 211999.6754 | 211999.6754 | 171484.7666 | 157035.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666 | 156735.2666
|  | CHECK | CHECK
| Revenue Recognition | -0.019183 | 3355439.0192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79308.7472 | 0 | 0 | 0 | 214506.6872 | 0 | 0 | 0 | 0 | 2203333.0681 | 0 | 0 | 0 | 316457.8872 | 0 | 0 | 0 | 254921.2601 | 0 | 0 | 0 | 0 | 16711.23 | 0 | 0 | 0 | 176.5472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242.8756 | 0 | 0 | 0 | 323.1722 | 0 | 0 | 0 | 201263.195 | 0 | 0 | 0 | 0 | 68194.3493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 3355439.0192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79308.7472 | 79308.7472 | 79308.7472 | 79308.7472 | 293815.4345 | 293815.4345 | 293815.4345 | 293815.4345 | 293815.4345 | 2497148.5026 | 2497148.5026 | 2497148.5026 | 2497148.5026 | 2813606.3898 | 2813606.3898 | 2813606.3898 | 2813606.3898 | 3068527.6499 | 3068527.6499 | 3068527.6499 | 3068527.6499 | 3068527.6499 | 3085238.8799 | 3085238.8799 | 3085238.8799 | 3085238.8799 | 3085415.4271 | 3085415.4271 | 3085415.4271 | 3085415.4271 | 3085415.4271 | 3085415.4271 | 3085415.4271 | 3085415.4271 | 3085415.4271 | 3085658.3027 | 3085658.3027 | 3085658.3027 | 3085658.3027 | 3085981.4749 | 3085981.4749 | 3085981.4749 | 3085981.4749 | 3287244.6699 | 3287244.6699 | 3287244.6699 | 3287244.6699 | 3287244.6699 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192 | 3355439.0192

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | 2026-03-31 | Grand Total
(blank)
1. Panels |  |  |  | 736578.6 |  |  | 4601.4 |  | 4301.4 | [5 empty] | 745481.4
2. Inverters |  |  |  | 206611.05 | [10 empty] | 206611.05
3. Mounting Structures |  |  |  | 66124.8 | [10 empty] | 66124.8
4. DC Equipment |  |  | 46262.8223 | 107200 | 62917.4378 | 75870.8807 | [8 empty] | 292251.1409
5. Monitoring |  | 13695 | 10848.85 | 11383.28 | [10 empty] | 35927.13
6. AC Equipment |  |  | 23098.6336 | 117330.71 | 31414.1369 | 37881.6688 | [8 empty] | 209725.1493
8. Product Add On |  |  |  | 18219.57 |  |  |  |  | 245754.52 |  |  | 21400 |  |  | 285374.09
9. AC & DC installation |  |  | 120780.0617 |  | 164260.8793 | 53143.2271 | [6 empty] | 120780.0617 | 24156.0123 | 483120.2421
10. Site Logistics |  |  | 12433.4825 | 4600 | 16909.536 | 20390.8353 | [8 empty] | 54333.8537
11. Due Dilligence |  | 13312.24 |  |  | 10160.8 | [5 empty] | 0 | 6000 |  |  | 29473.04
13. Engineering | [7 empty] | 0 |  |  |  | 41942.9875 |  |  | 41942.9875
14. General Expenses |  | 0 | 1399.43 | 1699.57 | 502.18 | 380.32 | 0 | 125.19 | 0 | 244.66 |  |  | 600 | 300 | 5251.35
15. Service Add On |  |  |  | 503000 |  |  | 143138 | [7 empty] | 646138
12. BDP Commission
7.BESS
Grand Total |  | 27007.24 | 214823.28 | 1772747.58 | 286164.97 | 187666.9319 | 147739.4 | 125.19 | 250055.92 | 244.66 | 0 | 69342.9875 | 121380.0617 | 24456.0123 | 3101754.2334

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | 2026-03-31 | Grand Total
(blank)
1. Panels |  |  |  | 883589.875 |  |  | 0 |  | 0 |  | 0 |  |  |  | 883589.875
2. Inverters |  |  |  | 238636.3636 | [6 empty] | 0 |  |  |  | 238636.3636
3. Mounting Structures | 0 |  |  | 341912.6932 | [6 empty] | 0 |  |  |  | 341912.6932
4. DC Equipment |  |  | 54707.7676 | 126768.5888 | 74402.5635 | 89720.7396 |  |  |  |  | 0 |  |  |  | 345599.6596
5. Monitoring |  | 19114.2374 | 15446.0294 | 21121.5559 | [6 empty] | 0 |  |  |  | 55681.8227
6. AC Equipment |  |  | 49781.3314 | 248633.7059 | 66755.6414 | 80499.465 |  |  |  |  | 0 |  |  |  | 445670.1437
8. Product Add On
9. AC & DC installation |  |  | 84838.9706 |  | 115380.9979 | 37329.1474 |  |  |  |  | 0 |  | 84838.9714 | 16967.7943 | 339355.8816
10. Site Logistics | 0 |  | 6542.7058 | 4257.6439 | 10721.7628 | 46746.04 |  |  |  |  | 0 |  |  |  | 68268.1524
11. Due Dilligence |  | 60194.5099 |  |  | 48966.6625 | [5 empty] | 0 | 27902.9481 |  |  | 137064.1205
13. Engineering | [7 empty] | 0 |  |  | 0 | 139101.4861 |  |  | 139101.4861
14. General Expenses |  | 0 | 3189.8824 | 2182.6953 | 230.2591 | 625.8681 | 0 | 176.5472 | 0 | 242.8756 | 0 |  | 646.3444 | 323.1722 | 7617.6444
15. Service Add On |  |  |  | 336229.9465 |  |  | 16711.23 |  |  |  | 0 |  |  |  | 352941.1765
12. BDP Commission
7.BESS
Grand Total | 0 | 79308.7472 | 214506.6872 | 2203333.0681 | 316457.8872 | 254921.2601 | 16711.23 | 176.5472 | 0 | 242.8756 | 0 | 167004.4342 | 85485.3158 | 17290.9665 | 3355439.0192
|  | 79308.75 | 214506.69 | 2203333.07 | 317008.94 | 254406.21 | [6 empty] | 3068563.66
|  | -0.0027686 | -0.0027593 | -0.0018951 | -551.0528 | 515.0501

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate | [5 empty] | FINANCIAL CLOSE CERTIFICATE
Project Name: | Randfontein
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion: |  |  |  | 1. Financial Close | 1. Financial Close
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 0.75106 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.38421 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.25993 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 0.62205 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
Randfontein |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Randfontein | 0 | 0 | 0