## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Project Plan
[9 empty] | 2026-03-09 | 2026-03-09
| PROJECT PLAN | Upper East Side Hotel | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 454
| PROJECT DEVELOPER | Peet Verreynne
| PROJECT MANAGERS | Justin Franke
| CONTRACT VALUE | 6640297.88
| Phase: | QA
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Expected Status | Comment
|  |  | 101 |  |  | 206 |  | 94.53% | 95.67%
1 | Project Initiation | 2025-04-09 | 111 | 2025-07-29 | 2025-04-09 | 111 | 2025-07-29 | 100% | 100%
1.1 | BD Handover | 2025-04-09 | 1 | 2025-04-10 | 2025-04-09 | 1 | 2025-04-10 | 100% | 100%
1.2 | Project Introduction | 2025-07-22 | 1 | 2025-07-23 | 2025-07-22 | 1 | 2025-07-23 | 100% | 100%
1.3 | HSE | 2025-07-15 | 10 | 2025-07-29 | 2025-07-15 | 10 | 2025-07-29 | 100% | 100%
1.4 | Installer Kick Off | 2025-07-17 | 1 | 2025-07-18 | 2025-07-17 | 1 | 2025-07-18 | 100% | 100%
1.5 | Project Review | 2025-07-22 | 1 | 2025-07-23 | 2025-07-22 | 1 | 2025-07-23 | 100% | 100%
2 | Site Establishment | 2025-07-29 | 1 | 2025-07-30 | 2025-07-29 | 1 | 2025-07-30 | 100% | 100%
2.1 | Solar Contractor Establishment | 2025-07-29 | 1 | 2025-07-30 | 2025-07-29 | 1 | 2025-07-30 | 100% | 100%
2.2 | Roof Replacement | 2025-07-31 | 60 | 2025-10-24 | 2025-07-31 | 76 | 2025-11-17 | 100% | 100%
2.3 | Anchor Point Install |  |  |  | 2025-11-17 | 2 | 2025-11-19 | 100% | 100%
3 | AC Installation | 2025-07-22 | 37 | 2025-08-28 | 2025-07-22 | 134 | 2025-12-03 | 100% | 100%
3.1 | Inverters delivered | 2025-07-30 | 1 | 2025-07-31 | 2025-07-30 | 1 | 2025-07-31 | 100% | 100%
3.2 | Inverters Mounted | 2025-07-31 | 1 | 2025-08-01 | 2025-08-06 | 1 | 2025-08-07 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-07-22 | 20 | 2025-08-19 | 2025-07-22 | 70 | 2025-10-29 | 100% | 100%
3.4 | AC Works | 2025-08-19 | 7 | 2025-08-28 | 2025-11-22 | 7 | 2025-12-02 | 100% | 100%
3.5 | AC Tie-In | 2025-08-19 | 3 | 2025-08-22 | 2025-11-28 | 3 | 2025-12-03 | 100% | 100%
4 | DC Works | 2025-07-30 | 93 | 2025-10-31 | 2025-07-31 | 202 | 2026-02-18 | 100% | 100%
4.1 | Lifeline Installation (If Applicable) | [6 empty] | 0% | 0%
4.1 | Mounting Structure delivered | 2025-07-30 | 1 | 2025-07-31 | 2025-07-31 | 1 | 2025-08-01 | 100% | 100%
4.2 | DC install -1 | 2025-10-10 | 15 | 2025-10-31 | 2026-01-12 | 27 | 2026-02-18 | 100% | 100%
4.3 | DC install -2 |  |  |  | 2026-01-12 | 12 | 2026-01-28 | 100% | 100%
4.4 | DC install -3 |  |  |  | 2025-11-10 | 35 | 2026-01-26 | 100% | 100%
4.5 | DC install -4 |  |  |  | 2025-11-03 | 35 | 2026-01-19 | 100% | 100%
4.6 | DC Cable delivered | 2025-07-30 | 1 | 2025-07-31 | 2025-07-31 | 1 | 2025-08-01 | 100% | 100%
5 | Module installation | 2025-10-15 | 21 | 2025-11-05 | 2025-11-05 | 84 | 2026-01-28 | 100% | 100%
5.1 | Module delivery | 2025-10-17 | 1 | 2025-10-20 | 2025-11-05 | 1 | 2025-11-06 | 100% | 100%
5.2 | Module mounting | 2025-10-15 | 15 | 2025-11-05 | 2025-11-06 | 39 | 2026-01-28 | 100% | 100%
6 | Commissioning | 2025-11-05 | 2 | 2025-11-07 | 2026-02-19 | 1 | 2026-02-20 | 100% | 100%
6.1 | Commissioning | 2025-11-05 | 1 | 2025-11-06 | 2026-02-19 | 1 | 2026-02-20 | 100% | 100%
6.2 | Practical Completion | 2025-11-06 | 1 | 2025-11-07 | 2026-02-19 | 1 | 2026-02-20 | 100% | 100%
7 | QA Inspections | 2025-11-07 | 3 | 2025-11-10 | 2026-02-24 | 1 | 2026-02-25 | 100% | 100%
7.1 | Red-Team Inspection | 2025-11-07 | 1 | 2025-11-10 | 2026-02-24 | 1 | 2026-02-25 | 100% | 100%
8 | Project Closure | 2025-11-07 | 17 | 2025-11-24 | 2026-02-20 | 31 | 2026-03-23 | 56.25% | 65.38%
8.1 | Equipment serial numbers | 2025-11-10 | 2 | 2025-11-12 | 2026-02-25 | 2 | 2026-02-27 | 100% | 100%
8.2 | Snags completion | 2025-11-10 | 4 | 2025-11-14 | 2026-02-27 | 2 | 2026-03-03 | 100% | 100%
8.3 | System Performance Monitoring | 2025-11-07 | 5 | 2025-11-14 | 2026-02-20 | 5 | 2026-02-27 | 100% | 100%
8.4 | Handover documentation | 2025-11-14 | 5 | 2025-11-21 | 2026-02-25 | 9 | 2026-03-10 | 50% | 92.31%
8.5 | Handover to Client | 2025-11-21 | 1 | 2025-11-24 | 2026-03-20 | 1 | 2026-03-23 | 0% | 0% | tbc
8.6 | Handover to Matriarch | 2025-11-16 | 5 | 2025-11-21 | 2026-03-09 | 5 | 2026-03-16 | 0% | 0%
[11 empty] | Project Initiation | 2025-04-09 | 111 | 2025-07-29
[11 empty] | Site Establishment | 2025-07-29 | 1 | 2025-07-30
[11 empty] | AC Installation | 2025-07-22 | 134 | 2025-12-03
[11 empty] | DC Works | 2025-07-31 | 202 | 2026-02-18
[11 empty] | Module installation | 2025-11-05 | 84 | 2026-01-28
[11 empty] | Commissioning | 2026-02-19 | 1 | 2026-02-20
[11 empty] | QA Inspections | 2026-02-24 | 1 | 2026-02-25
[11 empty] | Project Closure | 2026-02-20 | 31 | 2026-03-23
Formulas:
Planned Start = MIN([Planned Start, row below]:E16)
Planned Start = [Planned Start, row above]-7
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C41)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = [Actual Start, row above]-7
Actual End = MAX([Actual End, row below]:K16)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C41)
Expected Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  |  | FINANCIAL REVIEW | TIMELINE REVIEW | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 6640297.88 |  | 8633666.5757 |  |  |  | Start Date | 5845601.406 | 4720834.625 | 2739029.1105 | 3126191.7585 | 2465961.0462 | 3064548.035
2 | Planned Expenditure | 5836403.21 |  | 7847026.3835 | VO PM LIMIT | CURRENT VO Total
3 | Planned Profit | 803894.67 |  | 786640.1922 | 40194.7335 | 0 |  | End Date - PC
4 | Planned Margin | 12.11% |  | 9.111%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE |  | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE |  | MILESTONE NOTES & COMMENTS
1 | Deposit |  | 35% | 2324104.258 |  | 2025-04-30 | 004723 | 2025-04-24 | 2025-04-25
2 | Delivery of Panels |  | 30% | 1992089.364 |  | 2025-10-31 | 004723 | 2025-04-24 | 2025-11-14
3 | Delivery of Inverters |  | 20% | 1328059.576 |  | 2025-08-13 | 004723 | 2025-04-24 | 2025-08-08
4 | Installation Complete |  | 10% | 664029.788 |  | 2025-11-19 | 004723 | 2025-04-24 | 2025-11-14
5 | Commissioning Complete |  | 5% | 332014.894 |  | 2025-11-21 | 004723 | 2025-04-24 | 2025-11-14
6 | Additional Roof Revenue |  | 0% | 1993368.6957 |  | 2025-11-30 | 004881 | 2025-11-24 | 2025-12-18
7 | - |  | 0% | 0
|  |  | 100% | 8633666.5757
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 3021783.3015
2 | Delivery of Panels |  | 30% | 2590099.9727
3 | Delivery of Inverters |  | 20% | 1726733.3151
4 | Practical Completion |  | 10% | 863366.6576
5 | Handover |  | 5% | 431683.3288
| Total |  | 100% | 8633666.5757
|  |  | 100% | 8633666.5757

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation
2025-12-17 | Builders Break
2025-12-18 | Builders Break
2025-12-19 | Builders Break
2025-12-20 | Builders Break
2025-12-21 | Builders Break
2025-12-22 | Builders Break
2025-12-23 | Builders Break
2025-12-24 | Builders Break
2025-12-25 | Builders Break
2025-12-26 | Builders Break
2025-12-27 | Builders Break
2025-12-28 | Builders Break
2025-12-29 | Builders Break
2025-12-30 | Builders Break
2025-12-31 | Builders Break
2026-01-01 | Builders Break
2026-01-02 | Builders Break
2026-01-03 | Builders Break
2026-01-04 | Builders Break
2026-01-05 | Builders Break
2026-01-06 | Builders Break
2026-01-07 | Builders Break
2026-01-08 | Builders Break
2026-01-09 | Builders Break
2026-01-10 | Builders Break
2026-01-11 | Builders Break
2026-01-12 | Builders Break
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 5836403.21 |  | 7847026.3835 | -2010623.1735
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 1222111.84 |  | 888586 | 333525.84
2 | 2. Inverters | 400000 |  | 216421.11 | 183578.89
3 | 3. Mounting Structures | 181584 |  | 123340.5 | 58243.5
4 | 4. DC Equipment | 525691.6 |  | 631372 | -105680.4
5 | 5. Monitoring | 174000 |  | 87937 | 86063
6 | 6. AC Equipment | 567347.29 |  | 235040 | 332307.29
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 2000000 |  | 4913552.36 | -2913552.36
9 | 9. AC & DC installation | 371510 |  | 476700 | -105190
10 | 10. Site Logistics | 58106.5 |  | 151047.48 | -92940.98
11 | 11. Due Dilligence | 94047 |  | 61934.13 | 32112.87
12 | 12. BDP Commission | 0 |  | 0 | 0
13 | 13. Engineering | 234129.98 |  | 58003.7235 | 176126.2565
14 | 14. General Expenses | 7875 |  | 3092.08 | 4782.92
15 | 15. Service Add On | 0 |  | 0 | 0
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 5836403.21 | 6640297.875 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 7847026.3835
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | ERROR on REV |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 1222111.84 | 2025-09-26 | 1222111.84 | 1492013.321 |  | 1 | 1. Panels | Jinko 590W | 770 | 1150.5 | 885885 | PO4155-UES-20250723 - RV Approved | Menlo INV0003168 | 2025-08-31 | 1492013.321 | 0 | 2025-10-24 | 888586
1 |  | Delivery Budget | [7 empty] | 1 | 1. Panels | Replacement panels | 2 | 1150.5 | 2301 |  | MSA Energy INV0003593 | 2026-02-28 | 0 |  | 2026-04-06
1 | [9 empty] | 1 | 1. Panels | Transport |  |  | 400 |  | MSA Energy INV0003593 | 2026-02-28 | 0 |  | 2026-04-06
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 567347.29
2 | Inverters | Inverter Budget |  |  | 400000 | 2025-09-26 | 400000 | 488339.372 |  | 2 | 2. Inverters | SMA Core 2 - 110kVA | 4 | 53700.89 | 214803.56 | PO4153-UES-20250723 - RV Approved | Krannich INV15-10013383 | 2025-07-31 | 484689.4815 | 0 | 2025-09-26 | 216421.11 | DC Equipment | 292451.6
2 | [5 empty] | 2025-09-26 |  |  |  | 2 | 2. Inverters | EPR |  |  | 396.44 |  | Krannich INV15-10013383 | 2025-07-31 | 894.5396 |  | 2025-09-26 |  | AC Labour | 113490
2 | [5 empty] | 2025-09-26 |  |  |  | 2 | 2. Inverters | Freight |  |  | 1221.11 |  | Krannich INV15-10013383 | 2025-07-31 | 2755.3509 |  | 2025-09-26 |  | DC Labour | 258020
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 44056.5
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | #REF!
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 181584 | 2025-08-30 | 181584 | 221686.5413 |  | 3 | 3. Mounting Structures | Schletter Structure |  |  | 122040.5 | PO4150-UES-20250722 - RV Approved | Schletter - INV1994 | 2025-07-31 | 221686.5413 | 0 | 2025-08-30 | 123340.5 | Other | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Total | #REF!
3 | [9 empty] | 3 | 3. Mounting Structures | Mid Clamps |  |  | 1300 | PO4594-UESH-20260129 - RV Approved |  | 2026-02-28 | 0 |  | 2026-03-31 |  | Less 15% | #REF!
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | R/Wp | #REF!
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL Cosmic Sun | Installer Price | ACTUAL Cosmic Sun AC Only | Installer Price
[23 empty] | AC Equipment | 235040 | AC Equipment | 267902.5
4 | DC Equipment | DC Cable Budget |  |  | 233240 | 2025-08-31 | 525691.6 | 641789.7645 |  | 4 | 4. DC Equipment | DC Cable | 18000 | 13.5 | 243000 |  | Rubicon INVWCRE-0069676 | 2025-07-31 | 308594.2885 | 0 | 2025-08-31 | 631372 | DC Equipment | 262372 | 0
4 |  | DC Equipment Budget |  |  | 292451.6 | 2025-08-31 |  |  |  | 4 | 4. DC Equipment | DC Cable | 9000 | 14 | 126000 | PO4570-UESH-20260122 - RV Approved | Rubicon INVRED-0137860 | 2026-01-31 | 0 |  | 2026-02-28 |  | AC Labour | 136200 | AC Labour | 136200
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | DC Labour | 340500 | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Offloading | 8800 | 0
4 | [5 empty] | 2025-08-14 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 262372 | 10% | 26237.2 | PO4157-UESH-20250724 - RV Approved | Cosmic Sun - CS_UES_001 | 2025-07-31 | 33319.5476 |  | 2025-08-14 |  | Scaffolding |  | 0
4 | [5 empty] | 2025-07-31 |  |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 39355.8 |  | Cosmic Sun - CS_UES_002 | 2025-07-31 | 49979.3214 |  | 2025-07-31 |  | Storage | 9157.5 | 0 | 0
4 | [5 empty] | 2025-09-18 |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 52474.4 |  | Cosmic Sun - CS_UES_003 | 2025-08-31 | 66639.0952 |  | 2025-12-18 |  | Roof Access | 128590 | 0 | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 65593 |  | Cosmic Sun - CS_UES_003 | 2025-08-31 | 83298.869 |  | 2026-02-26 |  | HSE | 4500 | HSE | 4500
4 | [5 empty] | 2025-09-25 |  |  |  | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 26237.2 |  | Cosmic Sun - CS_UES_003 | 2025-08-31 | 33319.5476 |  | 2026-03-05 |  | Other | 0 | Other | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 26237.2 |  | Cosmic Sun - CS_UES_003 | 2025-08-31 | 33319.5476 |  | 2026-03-10 |  | Other | 0 | Other | 0
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 13118.6 |  | Cosmic Sun - CS_UES_003 | 2025-08-31 | 16659.7738 |  | 2026-03-10 |  | Total | 1125159.5 | Total | 408602.5
4 | [5 empty] | #REF! |  |  |  | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 13118.6 |  | Cosmic Sun - CS_UES_003 | 2025-08-31 | 16659.7738 |  | 2026-04-02 |  | R/Wp | 2.4783 | R/Wp | 0.90001
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
5 | Monitoring | Monitoring Budget |  |  | 159000 | 2025-07-28 | 174000 | 212427.6268 |  | 5 | 5. Monitoring | [8 empty] | 48475.1946 |  | 87937
5 |  | Revenue Metering |  |  | 15000 | 2025-07-29 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 22768 | PO4061-UES-20250630 - RV Approved | AccuEnergy ASAI-005840 | 2025-06-30 | 41886.5158 |  | 2025-07-29
5 | [5 empty] | 2025-07-31 |  |  |  | 5 | 5. Monitoring | Techsitter |  |  | 11169 |  | Matriarch - INV-4742 | 2025-07-31 | 20823.8251 |  | 2025-07-31
5 | [5 empty] | 2025-08-31 |  |  |  | 5 | 5. Monitoring | APEX |  |  | 54000 | PO4076-UES-20250630 - RV Approved | Rubicon INVWCRE-0069106 | 2025-07-31 | 101242.0912 |  | 2025-08-31
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 567347.29 | 2025-08-31 | 567347.29 | 692645.0446 |  | 6 | 6. AC Equipment | [7 empty] | 0 | 0 |  | 235040
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [5 empty] | 2025-08-14 |  |  |  | 6 | 6. AC Equipment | Project Kick Off | 235040 | 10% | 23504 |  | Cosmic Sun - CS_UES_001 | 2025-07-31 | 69264.5045 |  | 2025-08-14
6 | [5 empty] | 2025-07-31 |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 35256 |  | Cosmic Sun - CS_UES_002 | 2025-07-31 | 103896.7567 |  | 2025-07-31
6 | [5 empty] | 2025-09-18 |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 47008 |  | Cosmic Sun - CS_UES_003 | 2025-08-31 | 138529.0089 |  | 2025-12-18
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 58760 |  | Cosmic Sun - CS_UES_003 | 2025-08-31 | 173161.2612 |  | 2026-02-26
6 | [5 empty] | 2025-09-25 |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 23504 |  | Cosmic Sun - CS_UES_003 | 2025-08-31 | 69264.5045 |  | 2026-03-05
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 23504 |  | Cosmic Sun - CS_UES_003 | 2025-08-31 | 69264.5045 |  | 2026-03-10
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 11752 |  | Cosmic Sun - CS_UES_003 | 2025-08-31 | 34632.2522 |  | 2026-03-10
6 | [5 empty] | #REF! |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 11752 |  | Cosmic Sun - CS_UES_003 | 2025-08-31 | 34632.2522 |  | 2026-04-02
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | [5 empty] | 2000000 | 2000000 |  | 8 | 8. Product Add On | [7 empty] | 0 | -1993368.6954 |  | 4913552.36
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 |  | Roof Replacement Budget |  |  | 2000000 | 2025-05-15 |  |  |  | 8 | 8. Product Add On | Roof Replacement - Deposit |  | 2642000 | 1329750 | PO3855-UESH-20250507 - RV Approved | WC Ideal Solutions Inv: INV-0398 | 2025-05-31 | 1027779.9272 |  | 2025-05-15
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [5 empty] | 2025-05-28 |  |  |  | 8 | 8. Product Add On | Roof Replacement - Deposit Credit Note |  |  | -1329750 |  | WC Ideal Solutions - CN-0400 | 2025-05-31 | -1027779.9272 |  | 2025-05-28
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [5 empty] | 2025-07-31 |  |  |  | 8 | 8. Product Add On | Roof Replacement - Deposit | 2500000 | 25% | 625000 |  | FMS Property - INV21346 | 2025-07-31 | 471698.1132 |  | 2025-07-31
8 | [5 empty] | 2025-07-31 |  |  |  | 8 | 8. Product Add On | Roof Replacement - Weekly Completion |  | 15% | 375000 |  | FMS Property - INV21346 | 2025-08-31 | 341245.4113 |  | 2025-07-31
8 | [5 empty] | 2025-07-31 |  |  |  | 8 | 8. Product Add On | Roof Replacement - Weekly Completion |  | 15% | 375000 |  | FMS Property - INV21346 | 2025-08-31 | 341045.4013 |  | 2025-07-31
8 | [5 empty] | 2025-07-31 |  |  |  | 8 | 8. Product Add On | Roof Replacement - Weekly Completion |  | 15% | 375000 |  | FMS Property - INV21346 | 2025-08-31 | 163720.2513 |  | 2025-07-31
8 | [5 empty] | 2025-07-31 |  |  |  | 8 | 8. Product Add On | Roof Replacement - Handover |  | 30% | 750000 |  | FMS Property - INV21346 | 2025-08-31 | 682290.8226 |  | 2025-07-31
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [5 empty] | 0 |  |  |  | 8 | 8. Product Add On | Anchor Points | 120203.36 | 50% | 60101.68 | PO4378-UESH-20251017 - RV Approved | INV000336 | 2025-10-31 | 0 |  | 2025-10-24
8 | [5 empty] | 0 |  |  |  | 8 | 8. Product Add On |  |  | 50% | 60101.68 |  | INV000336 | 2025-10-31 | 0 |  | 2025-11-07
8 | [5 empty] | 2025-10-09 |  |  |  | 8 | 8. Product Add On | Lithium Battery |  |  | 975 |  | Red Pole - SO-35912 | 2025-09-30 | 0 |  | 2025-10-09
8 | [9 empty] | 8 | 8. Product Add On | Additional Roof Capex | [5 empty] | 2025-11-30 |  |  | 2025-11-30
8 | [9 empty] | 8 | 8. Product Add On |  |  |  | 2292374 |  | FMS Property - INV22455 | 2025-11-30 | 1993368.6957 |  | 2025-12-18
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 113490 | 2025-08-14 | 371510 | 437070.5883 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0 |  | 476700
9 |  | DC Installation Budget |  |  | 258020 | 2025-08-14 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 476700 | 10% | 47670 |  | Cosmic Sun - CS_UES_001 | 2025-07-31 | 43707.0588 |  | 2025-08-14
9 | [5 empty] | 2025-07-31 |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 71505 |  | Cosmic Sun - CS_UES_002 | 2025-07-31 | 65560.5882 |  | 2025-07-31
9 | [5 empty] | 2025-09-18 |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 95340 |  | Cosmic Sun - CS_UES_003 | 2025-11-30 | 87414.1177 |  | 2025-12-18
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 119175 |  | Cosmic Sun - CS_UES_003 | 2026-02-28 | 109267.6471 |  | 2026-02-26
9 | [5 empty] | 2025-09-25 |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 47670 |  | Cosmic Sun - CS_UES_003 | 2026-02-28 | 43707.0588 |  | 2026-03-05
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 47670 |  | Cosmic Sun - CS_UES_003 | 2026-02-28 | 43707.0588 |  | 2026-03-10
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 23835 |  | Cosmic Sun - CS_UES_003 | 2026-02-28 | 21853.5294 |  | 2026-03-10
9 | [5 empty] | #REF! |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 23835 |  | Cosmic Sun - CS_UES_003 | 2026-02-28 | 21853.5294 |  | 2026-04-02
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-08-14 | 58106.5 | 68360.5882 |  | 10 | 10. Site Logistics | [7 empty] | 0 | 0.0032113 |  | 151047.48
10 |  | Scaffolding |  |  | 44056.5 | 2025-08-14 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Security |  |  | 0 | 2025-08-14 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 5550 | 2025-08-14 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | Project Kick Off | 151047.5 | 10% | 15104.75 |  | Cosmic Sun - CS_UES_001 | 2025-07-31 | 6836.0588 |  | 2025-08-14
10 | [9 empty] | 10 | 10. Site Logistics | Site Establishment |  | 15% | 22657.125 |  | Cosmic Sun - CS_UES_002 | 2025-07-31 | 10254.0882 |  | 2025-07-31
[10 empty] | 10 | 10. Site Logistics |  |  |  | -0.01 |  | Cosmic Sun - CS_UES_002 | 2025-08-31 | 0 |  | 2025-08-31
10 | [9 empty] | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 30209.5 |  | Cosmic Sun - CS_UES_003 | 2025-11-30 | 13672.1095 |  | 2025-12-18
[10 empty] | 10 | 10. Site Logistics |  |  |  | -0.01 |  | Cosmic Sun - CS_UES_003 | 2025-08-31 | 0 |  | 2025-08-31
10 | [9 empty] | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 37761.875 |  | Cosmic Sun - CS_UES_003 | 2026-02-28 | 17090.1493 |  | 2026-02-26
10 | [9 empty] | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 15104.75 |  | Cosmic Sun - CS_UES_003 | 2026-02-28 | 6836.0597 |  | 2026-03-05
10 | [9 empty] | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 15104.75 |  | Cosmic Sun - CS_UES_003 | 2026-02-28 | 6836.0597 |  | 2026-03-10
10 | [9 empty] | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 7552.375 |  | Cosmic Sun - CS_UES_003 | 2026-02-28 | 3418.0299 |  | 2026-03-10
10 | [9 empty] | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 7552.375 |  | Cosmic Sun - CS_UES_003 | 2026-02-28 | 3418.0299 |  | 2026-04-02
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11349 | 2025-07-24 | 94047 | 110643.5294 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 7875 |  | SunSpot Investments E041 | 2026-02-28 | 11797.3494 | 0.0045722 | 2026-03-13 | 61934.13
11 |  | Structural Sign Off |  |  | 22698 | 2025-07-24 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off |  |  | 10650 | PO3799-UES-20250411 - RV Approved | L&B Consulting - INV-1963 | 2025-04-30 | 17839.4157 |  | 2025-07-24
11 |  | Grid Study |  |  | 60000 | 2025-07-24 |  |  |  | 11 | 11. Due Dilligence | Grid Study |  |  | 35409.13 | PO4381-UESH-20251020 - RV Approved | City of Cape Town - 708360339 | 2025-10-31 | 66714.9915 |  | 2025-10-24
11 | [5 empty] | 2025-08-31 |  |  |  | 11 | 11. Due Dilligence | Red Team |  |  | 8000 |  | Matriarch - INV-6571 | 2026-02-28 | 14291.7683 |  | 2026-03-31
11 | [9 empty] | 11 | 11. Due Dilligence | [7 empty] | 0
12 | BDP Commission | [5 empty] | 0 | 0 |  | 12 | 12. BDP Commission | [10 empty] | 0
12 | BDP Commission | [8 empty] | 12 | 12. BDP Commission
13 | Engineering | Matriarch Defects Period - 0.8% |  |  | 44929.98 | 2025-08-31 | 234129.98 | 266056.793 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 58003.7235 |  |  | 2026-03-31 | 266056.793 | 0 | 2026-03-31 | 58003.7235
13 |  | Management |  |  | 32000 | 2025-08-31 |  |  |  | 13 | 13. Engineering | Management |  |  | 0 |  |  | 2026-03-31 | 0 |  | 2026-03-31
13 |  | Project manager |  |  | 81600 | 2025-08-31 |  |  |  | 13 | 13. Engineering | Project manager |  |  | 0 |  |  | 2026-03-31 | 0 |  | 2026-03-31
13 |  | Planner time |  |  | 41600 | 2025-08-31 |  |  |  | 13 | 13. Engineering | Planner time |  |  | 0 |  |  | 2026-03-31 | 0 |  | 2026-03-31
13 |  | De Snagging |  |  | 34000 | 2025-08-31 |  |  |  | 13 | 13. Engineering | De Snagging |  |  | 0 |  |  | 2026-03-31 | 0 |  | 2026-03-31
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 7875 | 2025-05-08 | 7875 | 9264.7059 |  | 14 | 14. General Expenses | Travel |  |  | 119 |  | Expense Claim | 2025-04-30 | 154.4334 | 560.8516 | 2025-05-08 | 3092.08
14 | [5 empty] | 2025-06-09 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 199.92 |  | Expense Claim | 2025-05-31 | 282.3941 |  | 2025-06-09
14 | [5 empty] | 2025-06-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-06-30 | 0 |  | 2025-06-30
14 | [5 empty] | 2025-08-07 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 233.24 |  | Expense Claim | 2025-07-31 | 540.8934 |  | 2025-08-07
14 | [5 empty] | 2025-08-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-08-31 | 0 |  | 2025-08-31
14 | [5 empty] | 2025-09-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-09-30 | 0 |  | 2025-09-30
14 | [5 empty] | 2025-10-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 95.2 |  | Expense Claim | 2025-10-31 | 295.24 |  | 2025-11-06
14 | [5 empty] | 2025-11-30 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-11-30 | 0 |  | 2025-11-30
14 | [5 empty] | 2025-12-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 104.72 |  | Expense Claim | 2025-12-31 | 419.6222 |  | 2026-01-08
14 | [5 empty] | 2026-01-31 |  |  |  | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2026-01-31 | 0 |  | 2026-02-05
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 780 |  |  | 2026-02-28 | 2337.0904 |  | 2026-03-07
[10 empty] | 14 | 14. General Expenses | Travel |  |  | 780 |  |  | 2026-03-31 | 2337.0904 |  | 2026-04-09
[10 empty] | 14 | 14. General Expenses | Travel |  |  | 780 |  |  | 2026-04-30 | 2337.0904 |  | 2026-05-07
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | [8 empty] | 0 |  | 0
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
| Panel Procurement Budget | 1492013.321 | 1492013.3212 | -0.00017648
| Inverter Procurement Budget | 488339.372 | 488339.372 | -9.1861e-06
| Mounting Structure Budget | 221686.5413 | 221686.5413 | -1.729e-05
| DC Equipment Budget | 641789.7645 | 641789.7645 | -3.6261e-05
| AC Equipment Budget | 692645.0446 | 692645.0446 | 4.1342e-05
| Monitoring Budget | 212427.6268 | 212427.6268 | -2.3996e-05
| Optional Extras Budget | 0 | 0 | 0
| MV Metering Budget | 0 | 0 | 0
| ADD ON | 2500000 | 2000000 | 500000
| Battery System | 0 | 0 | 0
| Generator | 0 | 0 | 0
| Services |  |  | 0
0
| AC Installer Budget | 133517.6471 | 133517.6471 | 4.1176e-05
| DC Installer Budget | 303552.9412 | 303552.9412 | 2.3529e-05
| In-House Expense Budget | 266056.793 | 266056.793 | 3.4585e-06
| Compliance Budget | 110643.5294 | 110643.5294 | -1.1765e-05
| Offloading Budget | 10000 | 10000 | 0
| Roof Access Budget for Equipment | 0 | 0 | 0
| Site storage | 6529.4118 | 6529.4118 | 2.9412e-07
| On Site Security | 0 | 0 | 0
| Roof Access Budget for Installers | 51831.1765 | 51831.1765 | -5.8824e-07
| EPC Management Fee | 0 | 0 | 0
| ADD ON | 0 | 0 | 0
0
| Expenses |  |  | 0
| Total EE Expense Budget | 9264.7059 | 9264.7059 | -3.5294e-07
Note on W97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date
Note on W99: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 6640297.88 | 8633666.5757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2324104.258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1328059.576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1992089.364 | 0 | 0 | 996044.682 | 1993368.6957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2324104.258 | 2324104.258 | 2324104.258 | 2324104.258 | 2324104.258 | 2324104.258 | 2324104.258 | 2324104.258 | 2324104.258 | 2324104.258 | 2324104.258 | 2324104.258 | 2324104.258 | 2324104.258 | 2324104.258 | 3652163.834 | 3652163.834 | 3652163.834 | 3652163.834 | 3652163.834 | 3652163.834 | 3652163.834 | 3652163.834 | 3652163.834 | 3652163.834 | 3652163.834 | 5644253.198 | 5644253.198 | 5644253.198 | 6640297.88 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757 | 8633666.5757
| Planned Expenditure | 5836403.21 | 5836403.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7875 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94047 | 174000 | 0 | 429616.5 | 0 | 1508752.87 | 0 | 0 | 0 | 1622111.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7875 | 2007875 | 2007875 | 2007875 | 2007875 | 2007875 | 2007875 | 2007875 | 2007875 | 2007875 | 2007875 | 2101922 | 2275922 | 2275922 | 2705538.5 | 2705538.5 | 4214291.37 | 4214291.37 | 4214291.37 | 4214291.37 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21 | 5836403.21
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2324104.258 | 2316229.258 | 316229.258 | 316229.258 | 316229.258 | 316229.258 | 316229.258 | 316229.258 | 316229.258 | 316229.258 | 316229.258 | 316229.258 | 222182.258 | 48182.258 | 48182.258 | 946625.334 | 946625.334 | -562127.536 | -562127.536 | -562127.536 | -562127.536 | -2184239.376 | -2184239.376 | -2184239.376 | -2184239.376 | -2184239.376 | -192150.012 | -192150.012 | -192150.012 | 803894.67 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657 | 2797263.3657
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 8633666.5757 | 11621800.6217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2324104.258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1328059.576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2988134.046 | 0 | 2988134.046 | 0 | 0 | 0 | 0 | 1993368.6957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2324104.258 | 2324104.258 | 2324104.258 | 2324104.258 | 2324104.258 | 2324104.258 | 2324104.258 | 2324104.258 | 2324104.258 | 2324104.258 | 2324104.258 | 2324104.258 | 2324104.258 | 2324104.258 | 2324104.258 | 3652163.834 | 3652163.834 | 3652163.834 | 3652163.834 | 3652163.834 | 3652163.834 | 3652163.834 | 3652163.834 | 3652163.834 | 3652163.834 | 3652163.834 | 3652163.834 | 6640297.88 | 6640297.88 | 9628431.926 | 9628431.926 | 9628431.926 | 9628431.926 | 9628431.926 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217 | 11621800.6217
| Actual + Planned Expenditure | 7847026.3835 | 7847026.3835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 1329750 | 0 | -1329750 | 0 | 199.92 | 0 | 0 | 0 | 0 | 0 | 10650 | 2702710.925 | 233.24 | 112515.95 | 0 | 419040.48 | 0 | 0 | 0 | 216421.11 | 0 | 975 | 0 | 981395.81 | 0 | 60196.88 | 0 | 0 | 0 | 0 | 0 | 2517405.9 | 0 | 0 | 104.72 | 0 | 0 | 0 | 0 | 0 | 0 | 407289.875 | 113295.95 | 176648.925 | 0 | 0 | 123561.6985 | 3481 | 0 | 0 | 0 | 780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 1329869 | 1329869 | 119 | 119 | 318.92 | 318.92 | 318.92 | 318.92 | 318.92 | 318.92 | 10968.92 | 2713679.845 | 2713913.085 | 2826429.035 | 2826429.035 | 3245469.515 | 3245469.515 | 3245469.515 | 3245469.515 | 3461890.625 | 3461890.625 | 3462865.625 | 3462865.625 | 4444261.435 | 4444261.435 | 4504458.315 | 4504458.315 | 4504458.315 | 4504458.315 | 4504458.315 | 4504458.315 | 7021864.215 | 7021864.215 | 7021864.215 | 7021968.935 | 7021968.935 | 7021968.935 | 7021968.935 | 7021968.935 | 7021968.935 | 7021968.935 | 7429258.81 | 7542554.76 | 7719203.685 | 7719203.685 | 7719203.685 | 7842765.3835 | 7846246.3835 | 7846246.3835 | 7846246.3835 | 7846246.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835 | 7847026.3835
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2324104.258 | 2324104.258 | 2323985.258 | 994235.258 | 994235.258 | 2323985.258 | 2323985.258 | 2323785.338 | 2323785.338 | 2323785.338 | 2323785.338 | 2323785.338 | 2323785.338 | 2313135.338 | -389575.587 | 938250.749 | 825734.799 | 825734.799 | 406694.319 | 406694.319 | 406694.319 | 406694.319 | 190273.209 | 190273.209 | 189298.209 | 189298.209 | -792097.601 | 2196036.445 | 2135839.565 | 5123973.611 | 5123973.611 | 5123973.611 | 5123973.611 | 5123973.611 | 4599936.4067 | 4599936.4067 | 4599936.4067 | 4599831.6867 | 4599831.6867 | 4599831.6867 | 4599831.6867 | 4599831.6867 | 4599831.6867 | 4599831.6867 | 4192541.8117 | 4079245.8617 | 3902596.9367 | 3902596.9367 | 3902596.9367 | 3779035.2382 | 3775554.2382 | 3775554.2382 | 3775554.2382 | 3775554.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382 | 3774774.2382
|  | CHECK | CHECK
| Revenue Recognition | -1944332.6365 | 8584630.5165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17993.8491 | 0 | 0 | 0 | 282.3941 | 0 | 0 | 0 | 0 | 41886.5158 | 0 | 0 | 0 | 1995743.0491 | 0 | 0 | 0 | 3789695.598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67010.2315 | 0 | 0 | 0 | 2094454.9228 | 0 | 0 | 0 | 0 | 419.6222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306413.3602 | 0 | 0 | 0 | 0 | 268393.8834 | 0 | 0 | 0 | 2337.0904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 8584630.5165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17993.8491 | 17993.8491 | 17993.8491 | 17993.8491 | 18276.2431 | 18276.2431 | 18276.2431 | 18276.2431 | 18276.2431 | 60162.7589 | 60162.7589 | 60162.7589 | 60162.7589 | 2055905.808 | 2055905.808 | 2055905.808 | 2055905.808 | 5845601.406 | 5845601.406 | 5845601.406 | 5845601.406 | 5845601.406 | 5845601.406 | 5845601.406 | 5845601.406 | 5845601.406 | 5912611.6375 | 5912611.6375 | 5912611.6375 | 5912611.6375 | 8007066.5602 | 8007066.5602 | 8007066.5602 | 8007066.5602 | 8007066.5602 | 8007486.1824 | 8007486.1824 | 8007486.1824 | 8007486.1824 | 8007486.1824 | 8007486.1824 | 8007486.1824 | 8007486.1824 | 8313899.5426 | 8313899.5426 | 8313899.5426 | 8313899.5426 | 8313899.5426 | 8582293.426 | 8582293.426 | 8582293.426 | 8582293.426 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165 | 8584630.5165

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | Grand Total
(blank)
1. Panels | [5 empty] | 1492013.321 |  |  |  |  | 0 |  | 0 |  |  | 1492013.321
2. Inverters |  |  |  |  | 488339.372 | [5 empty] | 0 |  |  |  |  | 488339.372
3. Mounting Structures |  |  |  |  | 221686.5413 | [5 empty] | 0 |  | 0 |  |  | 221686.5413
4. DC Equipment |  |  |  |  | 391893.1575 | 249896.607 |  |  |  |  | 0 | 0 |  |  |  | 641789.7645
5. Monitoring | 0 |  |  | 41886.5158 | 122065.9164 | [5 empty] | 0 |  | 47453.858 |  |  | 211406.2902
6. AC Equipment |  |  |  |  | 173161.2612 | 519483.7835 |  |  |  |  | 0 |  |  |  |  | 692645.0446
8. Product Add On | 0 |  | 0 |  | 471698.1132 | 1528301.8865 | 0 | 0 | 1993368.6957 |  | 0 |  |  |  |  | 3993368.6954
9. AC & DC installation |  |  |  |  | 109267.6471 |  |  |  | 87414.1177 |  | 0 |  | 240388.8236 |  |  | 437070.5883
10. Site Logistics | 0 |  |  |  | 17090.1471 | 0 |  |  | 13672.1095 |  | 0 |  | 37598.3285 |  |  | 68360.585
11. Due Dilligence |  | 17839.4157 | [5 empty] | 66714.9915 |  |  | 0 |  | 26089.1189 |  |  | 110643.526
13. Engineering | [10 empty] | 0 |  | 266056.793 |  |  | 266056.793
14. General Expenses |  | 154.4334 | 282.3941 | 0 | 540.8934 | 0 | 0 | 295.24 | 0 | 419.6222 | 0 | 0 | 2337.0904 | 2337.0904 | 2337.0904 | 8703.8543
15. Service Add On
12. BDP Commission
7.BESS
Grand Total | 0 | 17993.8491 | 282.3941 | 41886.5158 | 1995743.0491 | 3789695.598 | 0 | 67010.2315 | 2094454.9228 | 419.6222 | 0 | 0 | 619924.0124 | 2337.0904 | 2337.0904 | 8632084.3757
101086.2271

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | Grand Total
(blank)
1. Panels | [5 empty] | 885885 | [5 empty] | 2701 |  |  | 888586
2. Inverters |  |  |  |  | 216421.11 | [9 empty] | 216421.11
3. Mounting Structures |  |  |  |  | 122040.5 | [6 empty] | 1300 |  |  | 123340.5
4. DC Equipment |  |  |  |  | 308593 | 196779 |  |  |  |  | 126000 |  |  |  | 631372
5. Monitoring |  |  |  | 22768 | 65169 | [6 empty] | 36324.44 |  |  | 124261.44
6. AC Equipment |  |  |  |  | 58760 | 176280 | [8 empty] | 235040
8. Product Add On |  |  | 0 |  | 625000 | 1875000 | 975 | 120203.36 | 2292374 | [5 empty] | 4913552.36
9. AC & DC installation |  |  |  |  | 119175 |  |  |  | 95340 |  |  | 262185 |  |  | 476700
10. Site Logistics |  |  |  |  | 37761.875 | -0.02 |  |  | 30209.5 |  |  | 83076.125 |  |  | 151047.48
11. Due Dilligence |  | 10650 | [5 empty] | 35409.13 |  |  |  | 19349 |  |  | 65408.13
13. Engineering | [11 empty] | 247203.7235 |  |  | 247203.7235
14. General Expenses |  | 119 | 199.92 | 0 | 233.24 | 0 | 0 | 95.2 | 0 | 104.72 | 0 | 780 | 780 | 780 | 3092.08
15. Service Add On
12. BDP Commission
7.BESS
Grand Total |  | 10769 | 199.92 | 22768 | 1553153.725 | 3133943.98 | 975 | 155707.69 | 2417923.5 | 104.72 | 126000 | 652919.2885 | 780 | 780 | 8076024.8235
1258943.98

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate | [5 empty] | FINANCIAL CLOSE CERTIFICATE
Project Name: | Upper East Side Hotel
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion: |  |  |  | 1. Financial Close | 1. Financial Close
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 0.6121 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 0.31312 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 0.21184 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 0.50696 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
Upper East Side Hotel |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Upper East Side Hotel | 0 | 0 | 0