## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate |  |  |  | FINANCIAL CLOSE CERTIFICATE
Project Name: | Mahikeng Builders Express
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Product Agreement | Y
EPC Agreement | Y
O&M Agreeement | NA
Cost Proposal | NA
Deposit Received | N
Risks / Notes
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-27

## Certificate - Planning
Emergent Energy – Planning Phase Completion Certificate |  |  |  | PLANNING CERTIFICATE
Project Name: | Mahikeng Builders Express
Client Representative:
Programme Manager: | Roedolph Venter
Project Manager: | Eon Van Rensberg
Project Engineer:
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Project Introduction Presentation
Project Brief
Engineering Pack
BOQ
PO – Material & Equipment
PO - Contractors
HSE – NOC
HSE – EE File
HSE – Contractor File
SSEG Application
Risks / Notes
Acknowledgement and Acceptance:
Role | Name | Signature | Date

## Change Register
Change Register
ID | Description | Supporting Image (If Applicable) | Impact | Proposed Date | Proposed By | Status | Approved By | Approved Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
DEC011
DEC012
DEC013
DEC014
DEC015
DEC016
DEC017
DEC018
DEC019
DEC020
DEC021
DEC022
DEC023
DEC024
DEC025
DEC026
DEC027
DEC028
DEC029
DEC030

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC | Approved |  | 24/10/2025
7.1 Agreement | Approved
13.2 Agreement | Approved
EE File | Approved |  | 27/10/2025
Subbie File | Approved
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application | Pending |  | 2025-10-16 | Awaiting SSEG-SLD from Engineering
PTI
Commissioning Approval
NERSA Registration

## Project Plan
[9 empty] | 2026-02-16 | 2026-02-16
| PROJECT PLAN | Mahikeng Builders Express |  |  | Net Work Days |  | 27 |  | 0 | 1
| PROJECT SIZE (kWp) | 250 |  |  | Total Weeks |  | 5.4
| PROJECT DEVELOPER | Kirsten Marwick |  |  | kW/Week Installation Rate |  | 46.2963
| PROJECT MANAGERS | Eon Van Rensburg
| CONTRACT VALUE | 2581531
| Phase: | Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration | Planned End | Actual Start | Duration | Actual End | Status | Expected Status | Comment
[6 empty] | 36 |  | 91.28% | 90.62% |  | 2026-02-16 | 2026-02-16
[11 empty] | 1 | 0
1 | Project Initiation | 2025-10-09 | 27 | 2025-11-05 | 2025-10-09 | 27 | 2025-11-05 | 100% | 100%
1.1 | Project Charter Handover | 2025-10-09 | 1 | 2025-10-10 | 2025-10-09 | 1 | 2025-10-10 | 100% | 100% |  | Milestone | Start Date | Duration | End Date
1.2 | HSE Readiness and Signoff | 2025-10-10 | 18 | 2025-11-05 | 2025-10-10 | 18 | 2025-11-05 | 100% | 100% | Greenway to only send file tomorrow | Project Initiation | 2025-10-09 | 27 | 2025-11-05
1.3 | Project Introduction | 2025-10-13 | 1 | 2025-10-14 | 2025-10-13 | 1 | 2025-10-14 | 100% | 100% |  | Site Establishment | 2025-10-29 | 1 | 2025-10-30
1.4 | Contract & Design Sign off | 2025-10-23 | 1 | 2025-10-24 | 2025-10-23 | 1 | 2025-10-24 | 100% | 100%
1.5 | Installer Kick Off | 2025-10-21 | 1 | 2025-10-22 | 2025-10-21 | 1 | 2025-10-22 | 100% | 100% |  | AC Installation | 2025-10-24 | 34 | 2025-11-27
1.6 | Project Review | 2025-10-21 | 1 | 2025-10-22 | 2025-10-21 | 1 | 2025-10-22 | 100% | 100% |  | DC Works | 2025-10-30 | 12 | 2025-11-11
[11 empty] | Module installation | 2025-10-30 | 19 | 2025-11-18
2 | Site Establishment | 2025-10-27 | 1 | 2025-10-28 | 2025-10-29 | 1 | 2025-10-30 | 100% | 100% |  | Commissioning (Practical Completion - JBCC) | 2025-11-27 | 7 | 2025-12-04
2.1 | Solar Contractor Establishment | 2025-10-27 | 1 | 2025-10-28 | 2025-10-29 | 1 | 2025-10-30 | 100% | 100% |  | QA Inspections (Works Completion - JBCC) | 2025-11-27 | 76 | 2026-02-11
[11 empty] | Project Closure (Final Completion - JBCC) | 2025-11-28 | 88 | 2026-02-24
3 | AC Installation | 2025-10-24 | 27 | 2025-11-20 | 2025-10-24 | 34 | 2025-11-27 | 100% | 100%
3.1 | Inverters delivered | 2025-10-28 | 1 | 2025-10-29 | 2025-10-30 | 1 | 2025-10-31 | 100% | 100%
3.2 | Inverters Mounted | 2025-10-29 | 1 | 2025-10-30 | 2025-11-18 | 1 | 2025-11-19 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-10-24 | 15 | 2025-11-14 | 2025-10-24 | 20 | 2025-11-21 | 100% | 100%
3.4 | AC Works | 2025-11-11 | 7 | 2025-11-20 | 2025-11-18 | 7 | 2025-11-27 | 100% | 100%
3.5 | AC Tie-In | 2025-11-11 | 1 | 2025-11-12 | 2025-11-18 | 1 | 2025-11-19 | 100% | 100%
4 | DC Works | 2025-10-27 | 28 | 2025-11-24 | 2025-10-30 | 12 | 2025-11-11 | 90.91% | 75%
4.1 | Mounting Structure delivered | 2025-10-27 | 1 | 2025-10-28 | 2025-10-30 | 1 | 2025-10-31 | 100% | 100%
4.2 | Mounting Structure installation | 2025-10-28 | 4 | 2025-11-03 | 2025-10-31 | 4 | 2025-11-06 | 100% | 100%
4.3 | DC Cable delivered | 2025-10-27 | 1 | 2025-10-28 | 2025-10-30 | 1 | 2025-10-31 | 100% | 100%
4.4 | DC Stringing | 2025-11-17 | 5 | 2025-11-24 | 2025-11-04 | 5 | 2025-11-11 | 100% | 100%
5 | Module installation | 2025-11-18 | 9 | 2025-11-27 | 2025-10-30 | 19 | 2025-11-18 | 100% | 100%
5.1 | Module delivery | 2025-11-18 | 1 | 2025-11-19 | 2025-10-30 | 1 | 2025-10-31 | 100% | 100%
5.2 | Module mounting | 2025-11-19 | 6 | 2025-11-27 | 2025-11-06 | 8 | 2025-11-18 | 100% | 100%
6 | Commissioning (Practical Completion - JBCC) | 2025-11-27 | 7 | 2025-12-04 | 2025-11-27 | 7 | 2025-12-04 | 100% | 100%
6.1 | Commissioning (Energy Flowing) | 2025-11-27 | 1 | 2025-11-28 | 2025-11-27 | 1 | 2025-11-28 | 100% | 100%
6.2 | Practical Completion Achieved | 2025-11-27 | 5 | 2025-12-04 | 2025-11-27 | 5 | 2025-12-04 | 100% | 100%
6.3 | System Performance Monitoring | 2025-11-27 | 5 | 2025-12-04 | 2025-11-27 | 5 | 2025-12-04 | 100% | 100%
7 | QA Inspections (Works Completion - JBCC) | 2025-11-27 | 8 | 2025-12-05 | 2025-11-27 | 76 | 2026-02-11 | 81.67% | 100%
7.1 | Red-Team Inspection | 2025-11-27 | 1 | 2025-11-28 | 2025-11-27 | 1 | 2025-11-28 | 100% | 100%
7.2 | Snags completion | 2025-11-28 | 5 | 2025-12-05 | 2025-11-28 | 11 | 2026-01-19 | 80% | 100%
7.3 | Blue-Log Commissioning |  |  |  | 2026-02-05 | 4 | 2026-02-11 | 0% | 100% | in progress
8 | Project Closure (Final Completion - JBCC) | 2025-11-28 | 12 | 2025-12-10 | 2025-11-28 | 88 | 2026-02-24 | 57.69% | 49.95%
8.1 | Handover documentation | 2025-11-28 | 7 | 2025-12-09 | 2025-11-28 | 10 | 2025-12-12 | 75% | 100%
8.2 | Handover to Client | 2025-12-09 | 1 | 2025-12-10 | 2026-02-19 | 1 | 2026-02-20 | 0% | 0%
8.3 | Handover to Matriarch | 2025-12-05 | 3 | 2025-12-10 | 2026-02-21 | 2 | 2026-02-24 | 0% | 0%
Formulas:
Planned Start = MIN([Planned Start, row below]:E18)
Planned Start = WORKDAY.INTL([Planned End, row above],0,1,Data!$C3:C60)
Planned End = MAX([Planned End, row below]:G18)
Planned End = WORKDAY.INTL([Planned Start],[Duration],1,Data!$C3:C60)
Actual Start = MIN([Actual Start, row below]:I18)
Actual Start = WORKDAY.INTL([Actual End, row above],0,1,Data!$C3:C60)
Actual End = MAX([Actual End, row below]:K18)
Actual End = WORKDAY.INTL([Actual Start],[Duration],1,Data!$C3:C60)
Expected Status = LET( _xlpm.s,VALUE([Actual Start]), _xlpm.e,VALUE([Actual End]), IF(OR(_xlpm.s="",_xlpm.e=""),"", IF(_xlpm.e<=_xlpm.s, IF(TODAY()>=_xlpm.e,1,0), MAX(0,MIN(1,(TODAY()-_xlpm.s)/(_xlpm.e-_xlpm.s))))) )

## BOQ
Item | Supplier | Description | Quantity | PO Generated Y/N | Comments
PV Module | Menlo | Jinko 590W - JKM590N-72HL4-BDV | 424
DC Cable Red & Black | Menlo | Enco 6mm PV Cable | 6000
Inverters | Menlo | Huawei String inverter 50kW 3PH | 4
Mounting Structure | Schletter | Kliplock Mounting structures |  | Yes | PO4401-MBE-20251023
Current Transformers (Production)
Current Transformers (Consumption)
Solar Production Meter (Techistter)
Grid Consumption Meter
Wi-Fi Router & Sim
Switch
Back Up Battery
PVDB
Supplier List
Accuenergy
Krannich
Menlo
Red Pole
Schletter
Switchboard
Techsitter

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  | FINANCIAL REVIEW | TIMELINE REVIEW |  |  | 2025 Actual Revenue | 2025 Actual COS | 2026 Budget Revenue | 2026 Budget COS | 2026 Actual Revenue | 2026 Actual COS
1 | Planned Revenue | 2581531 |  | 2820054.9195 |  | 2581531 | Start Date |  |  | 0 | 0 | 2792653.976 | 2684846.6775 | 2727994.4234 | 2580748.466
2 | Planned Expenditure | 2278170.85 |  | 2684846.6775 |  | 2452512.1275 | 2025-10-29
3 | Planned Profit | 303360.15 |  | 135208.242 |  | 129018.8725 | End Date - PC
4 | Planned Margin | 11.75% |  | 4.795% |  | 4.998% | 2025-11-28
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Signature of Contract |  | 1% | 23233.779 | 2025-10-31 | 004874 | 2025-10-31 | 2025-11-03 | [7 empty] | 1900-01-06
2 | Design Sign Off |  | 1.5% | 34850.6685 | 2025-10-31 | 004874 | 2025-10-31 | 2025-11-03
3 | Site Establishment Completion |  | 2% | 46467.558 | 2025-11-04 | 004874 | 2025-10-31 | 2025-11-03
4 | Start of Rooftop Structure Installation |  | 8% | 185870.232 | 2025-11-10 | 004874 | 2025-10-31 | 2025-11-03
5 | Mounting Structure Delivery to Site |  | 10% | 232337.79 | 2025-11-03 | 004876 | 2025-11-10 | 2025-11-14
6 | Module Delivery to Site |  | 32.5% | 755097.8175 | 2025-11-25 | 004876 | 2025-11-10 | 2025-11-14
7 | Inverter Delivery to Site |  | 26.5% | 615695.11 | 2025-11-04 | 004876 | 2025-11-10 | 2025-11-14
8 | Practical Completion |  | 13.5% | 348506.685 | 2025-11-21 | 004896 | 2025-12-09 | 2025-12-10
9 | Works Completion & PV Output |  | 5% | 129076.55 | 2025-12-11 |  |  | 2026-03-06
| Retention Claimable |  | 0% | 147700.9095 | 2025-12-05 | 004896 | 2025-12-09 | 2025-12-10
10 | Retention |  | 0% | 62693.86 | 2026-03-10 |  |  | 2026-06-04 | Check contract regarding Retention Requirements - also check with PD
11 | VO - Roof Remedial Work |  | 0% | 23350 | 2025-11-21 | 004896 | 2025-12-09 | 2025-12-10
| VO - Walkways |  | 0% | 183223.96 | 2025-11-04 |  |  | 2026-03-06
| VO - Catladder Design, manufacture, supply & install |  | 0% | 26500 | 2025-11-21 | 004896 | 2025-12-09 | 2025-12-10
12 | VO - Waterpoint |  | 0% | 5450 | 2025-11-21 | 004896 | 2025-12-09 | 2025-12-10
|  |  | 100% | 2820054.9195
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 987019.2218
2 | Delivery of Panels |  | 30% | 846016.4758
3 | Delivery of Inverters |  | 20% | 564010.9839
4 | Practical Completion |  | 10% | 282005.4919
5 | Handover |  | 5% | 141002.746
| Total |  | 100% | 2820054.9195
|  |  | 100% | 2820054.9195
Formulas:
PLANNED PAYMENT DATE = [PLANNED PAYMENT DATE, row above]
PAYMENT RECEIVED DATE = [PAYMENT RECEIVED DATE, row below]
Note on R14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Thami Cambalele please invoice these for us

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from Costed
EXPENDITURE |  | 2278170.85 |  | 2684846.6775 | -406675.8275
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 561360.21 |  | 487812 | 73548.21
2 | 2. Inverters | 247000 |  | 174424.32 | 72575.68
3 | 3. Mounting Structures | 100040 |  | 48031 | 52009
4 | 4. DC Equipment | 161926 |  | 143126.92 | 18799.08
5 | 5. Monitoring | 148000 |  | 105182.45 | 42817.55
6 | 6. AC Equipment | 278660.6 |  | 389809.96 | -111149.36 | Request line item breakdown of Q
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 469833.45 |  | 533564.02 | -63730.57
9 | 9. AC & DC installation | 198850 |  | 361334 | -162484
10 | 10. Site Logistics | 56854.45 |  | 176150.51 | -119296.06
11 | 11. Due Dilligence | 29000 |  | 161123.5 | -132123.5
12 | 12. BDP Commission | 0 |  | 0 | 0
13 | 13. Engineering | 22271.14 |  | 32269.1375 | -9997.9975
14 | 14. General Expenses | 4375 |  | 33994.93 | -29619.93
15 | 15. Service Add On | 0 |  | 38023.93 | -38023.93
| check: | 0 | #REF! | 0

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 2278170.85 | 2581529 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 2684846.6775
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FORECASTED PAYMENT DATE | Total COS | ERROR on REV |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | Panels Budget |  |  | 561360.21 | 2026-01-17 | 561360.21 | 637909 |  | 1 | 1. Panels | Jinko 590W - Menlo | 424 | 1150.5 | 487812 |  | Menlo INV0003366 | 2025-10-31 | 637909 | 0 | 2025-12-28 | 487812
1 |  | Delivery Budget | [7 empty] | 1 | 1. Panels |  |  | 1.95 |  |  |  |  | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 278660.6
2 | Inverters | Inverter Budget | 4 |  | 247000 | 2025-12-27 | 247000 | 280682 |  | 2 | 2. Inverters | Huawei 50KTL (Menlo) | 4 | 43606.08 | 174424.32 |  | Menlo INV0003366 | 2025-10-31 | 280682 | 0 | 2025-12-28 | 174424.32 | DC Equipment | 103406
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | AC Labour | 62525 | 0.2501
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | DC Labour | 136325 | 0.5453
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Offloading | 8500
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Scaffolding | 17326.67
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Storage | 1027.78
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  | Telehandler | 0
3 | Mounting Structures | Structure Budget |  |  | 100040 | 2025-11-26 | 100040 | 113682 |  | 3 | 3. Mounting Structures | Schletter - Mounting Structure |  |  | 45051 | PO4401-MBE-20251023 - RV Approved | Schletter INV 2353 | 2025-10-31 | 106628.7977 | 0 | 2025-11-28 | 48031 | Other | 0
3 | [9 empty] | 3 | 3. Mounting Structures | Delivery |  |  | 2980 |  | Schletter INV 2353 | 2025-10-31 | 7053.2023 |  | 2025-11-28 |  | Total | 607771.05
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Less 15% | 516605.3925
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | R/Wp | 2.0664
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | ACTUAL - Greenway Solar | Installer Price |  |  |  |  | Revised Cost
[23 empty] | AC Equipment | 390053.47 | 200m AC cable |  |  |  |  | 389809.96
4 | DC Equipment | DC Cable Budget | 4807 |  | 58520 | 2025-12-26 | 161926 | 184007 |  | 4 | 4. DC Equipment | DC Cable - Menlo | 6000 | 13.65 | 81900 |  | Menlo INV0003366 | 2025-10-31 | 76217.1044 | -0.0023061 | 2025-12-28 | 143126.92 | DC Equipment | 115826.92 | [5 empty] | 115826.92
4 |  | DC Equipment Budget |  |  | 103406 | 2025-11-24 |  |  |  | 4 | 4. DC Equipment | DC Cable -Red Move to stock JHB) | -2000 | 13.65 | -27300 |  | Allocated to Joburg Storeroom | 2026-01-31 | 0 |  | 2026-01-31 |  | AC Labour | 138972.23 | 0.55589 | 75000 | "@0,30c/W | 36k of Walkway installation | 0,5/W | 109400.2 | 0,31/W for installation | 0,19/W for living out
4 | [9 empty] | 4 | 4. DC Equipment | DC Cable - BlackMove to stock JHB) | -2000 | 13.65 | -27300 |  | Allocated to Joburg Storeroom | 2026-01-31 | 0 |  | 2026-01-31 |  | DC Labour | 320601.87 | 1.2824 | 250000 | "@1/W |  | 1,15/W | 251933.8 | 0,72/W for installation | 0,43/W for living out
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  | Roof Access | 16041.03 | [5 empty] | 15879.25
4 | [9 empty] | 4 | 4. DC Equipment | Project Kick Off | 115826.92 | 10% | 11582.692 | PO4415-MBE-20251028 - RV Approved | The Greenway INV0001528 | 2025-10-31 | 10778.9896 |  | 2025-10-30 |  | Deliveries and Collections | 48180 | <----- | Doesn't include the forklift. Container delivery. AC & Equipment delivery |  | Total saving of R64 000 | 0.19 | 26180
4 | [9 empty] | 4 | 4. DC Equipment | Site Establishment |  | 15% | 17374.038 |  | The Greenway INV0001529 | 2025-10-31 | 16168.4843 |  | 2025-11-06 |  | Offloading and Rigging | 59410 | <----- | Forklift hire and Operator |  |  | 0.11 | 28490
4 | [9 empty] | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 23165.384 |  | The Greenway INV0001555 | 2025-12-31 | 21557.9791 |  | 2025-12-12 |  | P&G | 90051.25 |  | Greenway's time |  |  |  | 77601.25
4 | [9 empty] | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 28956.73 |  | The Greenway INV0001556 | 2025-12-31 | 26947.4739 |  | 2025-12-12 |  | HSE | 0
4 | [9 empty] | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 11582.692 |  | The Greenway INV0001557 | 2025-12-31 | 10778.9896 |  | 2025-12-12 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 11582.692 |  | The Greenway INV0001564 | 2025-12-31 | 10778.9896 |  | 2025-12-24 |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 5791.346 |  | The Greenway - INV0001565 | 2025-12-31 | 5389.4948 |  | 2026-01-29 |  | Total | 1179136.77 |  | 1044562.67 | 134574.1 |  |  | 1015121.38
4 | [9 empty] | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 5791.346 |  |  | 2026-02-28 | 5389.4971 |  | 2026-02-28 |  | R/Wp | 4.7165 |  | 4.1783 |  |  |  | 4.0605
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  |  | 218358.6611 | 0.30638
4 | [9 empty] | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  |  | 85106.3148
5 | Monitoring | Monitoring Budget |  |  | 133000 | 2025-12-27 | 148000 | 168182 |  | 5 | 5. Monitoring | Smartlogger |  |  | 8598.34 |  | Menlo INV0003366 | 2025-10-31 | 9890.213 | 0.0028336 | 2025-12-28 | 105182.45
5 |  | Revenue Metering |  |  | 15000 | 2025-12-27 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 14118 | PO4458-MBE-2025111 - RV Approved | Accuenergy Inv:ASAI-006830 | 2025-11-30 | 25155.7288 |  | 2026-01-07
5 | [9 empty] | 5 | 5. Monitoring | Techsitter |  |  | 11169 |  | Matriarch Inv: 6200 | 2026-01-31 | 23141.4579 |  | 2026-01-29
[10 empty] | 5 | 5. Monitoring | Delivery of Techsitter |  |  | 307.94 |  | DSV Inv: 180156930 | 2025-11-30 | 475.0787 |  | 2025-12-30
5 | [9 empty] | 5 | 5. Monitoring | Meteocontrol Data manager + Station |  |  | 70989.17 | PO4451-MBE-20251107 - RV Approved | IBC Solar - ZA12502620 | 2025-11-30 | 109519.5188 |  | 2025-11-18
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
5 | [9 empty] | 5 | 5. Monitoring | [7 empty] | 0
6 | AC Equipment | AC Equipment Budget |  |  | 278660.6 | 2025-12-14 | 278660.6 | 316660 |  | 6 | 6. AC Equipment | [7 empty] | 0 | 0 |  | 389809.96
6 | [9 empty] | 6 | 6. AC Equipment | PVDB |  |  | 0 |  |  |  | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | Project Kick Off | 389809.96 | 10% | 38980.996 | PO4415-MBE-20251028 - RV Approved | The Greenway INV0001528 | 2025-10-31 | 31666 |  | 2025-10-30
6 | [9 empty] | 6 | 6. AC Equipment | Site Establishment |  | 15% | 58471.494 |  | The Greenway INV0001529 | 2025-10-31 | 47499 |  | 2025-11-06
6 | [9 empty] | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 77961.992 |  | The Greenway INV0001555 | 2025-12-31 | 63332 |  | 2025-12-12
6 | [9 empty] | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 97452.49 |  | The Greenway INV0001556 | 2025-12-31 | 79165 |  | 2025-12-12
6 | [9 empty] | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 38980.996 |  | The Greenway INV0001557 | 2025-12-31 | 31666 |  | 2025-12-12
6 | [9 empty] | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 38980.996 |  | The Greenway INV0001564 | 2025-12-31 | 31666 |  | 2025-12-24
6 | [9 empty] | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 19490.498 |  | The Greenway - INV0001565 | 2025-12-31 | 15833 |  | 2026-01-29
6 | [9 empty] | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 19490.498 |  |  | 2026-02-28 | 15833 |  | 2026-02-28
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 | 0 |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | Walkways |  |  | 97500 | 2025-11-27 | 469833.45 | 533901 |  | 8 | 8. Product Add On | Walkways - 300m |  |  | 213097.85 | PO4451-MBE-20251107 - RV Approved | Onvlee - Inv01051750 | 2025-11-30 | 197924.5226 | -182487.3067 | 2025-12-01 | 533564.02
8 |  | Lightning Protection |  |  | 121333.45 | 2025-11-27 |  |  |  | 8 | 8. Product Add On | Walkways - 20m |  |  | 19795.6 | PO4505-MBE-20251128 - RV Approved | Onvlee - PO-4505-MBE-20251128 | 2025-11-30 | 201610.0426 |  | 2025-12-01
8 |  | Tie-in Panel |  |  | 131000 | 2025-11-27 |  |  |  | 8 | 8. Product Add On | Installation of additional 170m Walkway |  |  | 23510 | PO4529-MBE-20251209 - RV Approved | The Greenway - INV0001563 | 2025-12-31 | 23797.9452 |  | 2025-12-24
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | Catladder |  |  | 26500 | PO4499-MBE-20251126 - RV Approved | Boukon -25/11/2025 | 2025-11-30 | 51113.1054 |  | 2025-11-27
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 |  | Temporary Fencing for storage Container |  |  | 10000 | 2025-11-27 |  |  |  | 8 | 8. Product Add On | Lightning Protection |  |  | 21014.75 | PO4482-MBE-20251124 - RV Approved | LPS - IN307595 | 2025-12-31 | 21272.134 |  | 2026-02-05
8 |  | Inverter Cage |  |  | 50000 | 2025-11-27 |  |  |  | 8 | 8. Product Add On | Lightning Risk Assessment |  |  | 7250 | PO4406-MBE-20251024 - RV Approved | LPS - IN307444 | 2025-11-30 | 6733.7741 |  | 1//2026
8 |  | Safety Life Lines (Temporary) |  |  | 60000 | 2025-11-27 |  |  |  | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | Tie-in Panel |  |  | 0 |  |  |  | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | Temporary Fencing for storage Container |  |  | 0 |  |  |  | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | Inverter Cage | 50% | 59734.19 | 29867.095 |  | JJL Steel & Construction INV251112 | 2025-11-30 | 27740.4513 |  | 2025-11-13
8 | [9 empty] | 8 | 8. Product Add On |  | 50% |  | 29867.095 |  | JJL Steel & Construction INV251112 | 2025-11-30 | 27740.4513 |  | 2025-12-04
8 | [9 empty] | 8 | 8. Product Add On | Enclosure Modification |  |  | 6123 | PO4583-MBE-20260127 - RV Approved |  | 2026-02-28 | 0 |  | 2026-02-20
8 | [9 empty] | 8 | 8. Product Add On | Safety Life Lines - 140m - Deposit | 111075 | 50% | 55537.5 | PO4552-MBE-20260116 - RV Approved | ATS Africa - INV-0468 | 2026-01-31 | 56217.7109 |  | 2026-01-23
8 | [9 empty] | 8 | 8. Product Add On | Safety Life Lines - 140m - Balance |  | 50% | 55537.5 |  | ATS Africa - INV-0468 | 2026-01-31 | 56217.7109 |  | 2026-02-05
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | DC Gantry - Greenway |  |  | 19063 | PO4508-MBE-20251201 - RV Approved | The Greenway - INV0001558 | 2025-12-31 | 19296.4794 |  | 2025-12-12
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [9 empty] | 8 | 8. Product Add On | Mains Comms Equipment & Installation |  |  | 9574.73 | PO4509-MBE-20251201 - RV Approved | The Greenway - INV0001559 | 2025-12-31 | 9691.9992 |  | 2025-12-18
8 | [9 empty] | 8 | 8. Product Add On | Cable Trays |  |  | 16825.9 |  | The Greenway - INV0001559 | 2025-12-31 | 17031.9799 |  | 2025-12-12
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation Budget |  |  | 62525 | 2025-11-27 | 198850 | 220944 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0 |  | 361334
9 |  | DC Installation Budget |  |  | 136325 | 2025-12-01 |  |  |  | 9 | 9. AC & DC installation | Project Kick Off | 361334 | 10% | 36133.4 | PO4415-MBE-20251028 - RV Approved | The Greenway INV0001528 | 2025-10-31 | 22094.4 |  | 2025-10-30
9 | [9 empty] | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 54200.1 |  | The Greenway INV0001529 | 2025-10-31 | 33141.6 |  | 2025-11-06
9 | [9 empty] | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 72266.8 |  | The Greenway INV0001555 | 2025-12-31 | 44188.8 |  | 2025-12-12
9 | [9 empty] | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 90333.5 |  | The Greenway INV0001556 | 2025-12-31 | 55236 |  | 2025-12-12
9 | [9 empty] | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 36133.4 |  | The Greenway INV0001557 | 2025-12-31 | 22094.4 |  | 2025-12-12
9 | [9 empty] | 9 | 9. AC & DC installation | Site De-establisment | 101512.138 | 10% | 36133.4 |  | The Greenway INV0001564 | 2025-12-31 | 22094.4 |  | 2025-12-24
9 | [9 empty] | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 18066.7 |  | The Greenway - INV0001565 | 2025-12-31 | 11047.2 |  | 2026-01-29
9 | [9 empty] | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 18066.7 |  |  | 2026-02-28 | 11047.2 |  | 2026-02-28
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | Offloading |  |  | 8500 | 2025-11-27 | 56854.45 | 63171 |  | 10 | 10. Site Logistics | Security |  |  | 28000 | PO4409-MBE-20251027 - RV Approved | Setso Security - SET001551 | 2025-12-31 | 10041.3448 | -0.00075404 | 2025-12-12 | 176150.51
10 |  | Scaffolding |  |  | 17326.67 | 2025-11-27 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Security |  |  | 30000 | 2025-11-27 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 |  | Storage |  |  | 1027.78 | 2025-11-27 |  |  |  | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | Project Kick Off | 148150.5 | 10% | 14815.05 | PO4415-MBE-20251028 - RV Approved | The Greenway INV0001528 | 2025-10-31 | 5312.9655 |  | 2025-10-30
10 | [9 empty] | 10 | 10. Site Logistics | Site Establishment |  | 15% | 22222.575 |  | The Greenway INV0001529 | 2025-10-31 | 7969.4482 |  | 2025-11-06
10 | [9 empty] | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 29630.1 |  | The Greenway INV0001555 | 2025-12-31 | 10625.9303 |  | 2025-12-12
10 | [9 empty] | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 37037.625 |  | The Greenway INV0001556 | 2025-12-31 | 13282.4129 |  | 2025-12-12
10 | [9 empty] | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 14815.05 |  | The Greenway INV0001557 | 2025-12-31 | 5312.9652 |  | 2025-12-12
10 | [9 empty] | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 14815.05 |  | The Greenway INV0001564 | 2025-12-31 | 5312.9652 |  | 2025-12-24
10 | [9 empty] | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 7407.53 |  | The Greenway - INV0001565 | 2025-12-31 | 2656.4844 |  | 2026-01-29
10 | [9 empty] | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 7407.53 |  |  | 2026-02-28 | 2656.4844 |  | 2026-02-28
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [7 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11000 | 2025-12-04 | 29000 | 32222 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 17750 |  | SunSpot - E035 | 2025-12-31 | 3664.321 | 162.3263 | 2026-01-23 | 161123.5
11 |  | Structural sign off |  |  | 18000 | 2025-12-04 |  |  |  | 11 | 11. Due Dilligence | Structural Sign Off - LnB Consulting |  |  | 11373.5 | PO4385-MBE-20251021 - RV Approved | L&B Consulting IN-2113 | 2025-10-31 | 2679.8847 |  | 2025-10-30
11 | [9 empty] | 11 | 11. Due Dilligence | Roof Report - Cosmic Sun |  |  | 6000 | PO4386-MBE-20251021 - RV Approved | Cosmic Sun - CS_MHK_001 | 2025-10-31 | 1413.752 |  | 2025-10-24
11 | [9 empty] | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 |  |  | 2026-02-28 | 1199.8995 |  | 2026-02-27
[10 empty] | 11 | 11. Due Dilligence | Safety Officer | 100800 | 25% | 25200 | PO4422-MBE-20251029 - RV Approved | WAGMA - INV-000001 | 2025-10-31 | 5937.7584 |  | 2025-11-06
[10 empty] | 11 | 11. Due Dilligence | Safety Officer |  | 75% | 75600 |  | WAGMA - INV-000010 | 2025-12-31 | 17164.0581 |  | 2026-01-15
11 | [9 empty] | 11 | 11. Due Dilligence | Safety Officer |  |  | 19200 |  | WAGMA - INV-000023 | 2026-02-28 |  |  | 2026-02-13
12 | BDP Commission | PD Fee |  |  |  |  | 0 | 0 |  | 12 | 12. BDP Commission | PD Fee |  |  | 0 | [6 empty] | 0
12 | BDP Commission | [8 empty] | 12 | 12. BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 22271.14 | 2025-12-10 | 22271.14 | 25308 |  | 13 | 13. Engineering | Matriarch Defects Period - 1.25% |  |  | 32269.1375 |  |  | 2026-02-28 | 25308 | 0 | 2026-02-26 | 32269.1375
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Travel & Accommodation Budget |  |  | 4375 | 2025-12-10 | 4375 | 4861 |  | 14 | 14. General Expenses | Travel |  |  | 8016.46 |  | Expense Claim | 2025-10-31 | 1536.8081 | 0.0047425 | 2025-11-06 | 33994.93
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 10490.93 |  | Expense Claim | 2025-11-30 | 1455.2804 |  | 2025-12-05
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 8655.54 |  | Expense Claim | 2025-12-31 | 1016.026 |  | 2026-01-08
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 3332 |  | Expense Claim | 2026-01-31 | 352.409 |  | 2026-02-05
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 3500 |  |  | 2026-02-28 | 500.4717 |  | 2026-03-05
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | Travel | [6 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
14 | [9 empty] | 14 | 14. General Expenses | [7 empty] | 0
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | [8 empty] | 0 |  | 38023.93
15 | [9 empty] | 15 | 15. Service Add On | Roof Remedial Work Deposit - Client Cost | 23350 | 80% | 18680 | PO4436-MBE-20251102 - RV Approved | Evolution Coatings - INV0000122 | 2025-11-30 | 23350 |  | 2025-11-04
15 | [9 empty] | 15 | 15. Service Add On | Roof Remedial Work Balance - Client Cost |  | 20% | 4670 |  | Evolution Coatings - INV0000122 | 2025-11-30 | 0 |  | 2025-11-27
15 | [9 empty] | 15 | 15. Service Add On | Waterpoints |  |  | 5450 |  | Evolution Coatings - INV0000138 | 2025-12-31 | 2725 |  | 2025-12-18
15 | [9 empty] | 15 | 15. Service Add On | Waterproofing - Client Cost |  |  | 5450 | PO4519-MBE-20251203 - RV Approved |  | 2026-02-28 | 2725 |  | 2026-02-19
15 | [9 empty] | 15 | 15. Service Add On | Cable support signoff |  |  | 3500 | PO4543-MBE-20251217 - RV Approved | L&B Consulting IN-2175 | 2025-12-31 | 0 |  | 2025-12-18
15 | [9 empty] | 15 | 15. Service Add On | Delivery of Sonel Meter |  |  | 273.93 |  | DSV Inv: 180158820 | 2025-12-31 | 0 |  | 2026-01-29
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
| Panel Procurement Budget | 561360.21 |  | 637909
| Inverter Procurement Budget | 247000 |  | 280682
| Mounting Structure Budget | 100040 |  | 113682
| DC Equipment Budget | 161926 |  | 184007
| AC Equipment Budget | 278660.6 |  | 316660
| Monitoring Budget | 148000 |  | 168182
| Optional Extras Budget | 97500 |  | 110795
MV Equipment Budget
| ADD ON | 372333.45 |  | 423106
Battery System
Generator
Services
| AC Installer Budget | 62525 |  | 69472
| DC Installer Budget | 136325 |  | 151472
| In-House Expense Budget | 22271.14 |  | 25308
| Compliance Budget | 29000 |  | 32222
| Offloading Budget | 8500 |  | 9444
Roof Access Budget for Equipment
| Site storage | 1027.78 |  | 1142
| On Site Security | 30000 |  | 33333
| Roof Access Budget for Installers | 17326.67 |  | 19252
EPC Management Fee
ADD ON
Expenses
| Total EE Expense Budget | 4375 |  | 4861

## Sheet1 (hidden)
Scope | Cost
Walkways - 190m - Additional | 159713.9613
Walkways - 190m - Additional Labour | 23510
Gravity Lifelines Equipment - Additional | 304738.28
Gravity Lifelines Labour - Additional | 113035
Sub-Total of Additional Scope | 600997.2413
Emergent Energy Contribution
Walkways - 130m - Costed | 97500
Walkways - 130m - Labour Costed | 14000
Lifelines Equipment - Costed | 60000
Lifelines Labour - Costed | 22000
Sub-Total of EE contribution | 193500
Sub-Total (Netting off EE Contribution) | 407497.2413
Vat | 61124.5862
Total | 468621.8274

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-09-01 to 2031-02-24
PLANNED |  | CHECK | CHECK
| Planned Revenue | 2581531 | 2820054.9195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58084.4475 | 1077724.418 | 185870.232 | 403806.685 | 755097.8175 | 147700.9095 | 129076.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62693.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58084.4475 | 1135808.8655 | 1321679.0975 | 1725485.7825 | 2480583.6 | 2628284.5095 | 2757361.0595 | 2757361.0595 | 2757361.0595 | 2757361.0595 | 2757361.0595 | 2757361.0595 | 2757361.0595 | 2757361.0595 | 2757361.0595 | 2757361.0595 | 2757361.0595 | 2757361.0595 | 2757361.0595 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195
| Planned Expenditure | 2278170.85 | 2278170.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 792658.9 | 165325 | 305306.74 | 0 | 453520 | 0 | 0 | 561360.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 792658.9 | 957983.9 | 1263290.64 | 1263290.64 | 1716810.64 | 1716810.64 | 1716810.64 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85 | 2278170.85
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58084.4475 | 1135808.8655 | 1321679.0975 | 1725485.7825 | 1687924.7 | 1670300.6095 | 1494070.4195 | 1494070.4195 | 1040550.4195 | 1040550.4195 | 1040550.4195 | 479190.2095 | 479190.2095 | 479190.2095 | 479190.2095 | 479190.2095 | 479190.2095 | 479190.2095 | 479190.2095 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695 | 541884.0695
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 2820054.9195 | 2820054.9195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290422.2375 | 1603130.7175 | 0 | 0 | 0 | 551507.5945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 312300.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62693.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290422.2375 | 1893552.955 | 1893552.955 | 1893552.955 | 1893552.955 | 2445060.5495 | 2445060.5495 | 2445060.5495 | 2445060.5495 | 2445060.5495 | 2445060.5495 | 2445060.5495 | 2445060.5495 | 2445060.5495 | 2445060.5495 | 2445060.5495 | 2445060.5495 | 2757361.0595 | 2757361.0595 | 2757361.0595 | 2757361.0595 | 2757361.0595 | 2757361.0595 | 2757361.0595 | 2757361.0595 | 2757361.0595 | 2757361.0595 | 2757361.0595 | 2757361.0595 | 2757361.0595 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195 | 2820054.9195
| Actual + Planned Expenditure | 2684846.6775 | 2677596.6775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 112885.638 | 204164.667 | 29867.095 | 70989.17 | 79201 | 273251.475 | 622205.659 | 18524.73 | 877756.798 | 307.94 | 22773.54 | 75600 | 73287.5 | 7599.004 | 79884.25 | 19200 | 11573 | 89025.2115 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 118885.638 | 323050.305 | 352917.4 | 423906.57 | 503107.57 | 776359.045 | 1398564.704 | 1417089.434 | 2294846.232 | 2295154.172 | 2317927.712 | 2393527.712 | 2466815.212 | 2474414.216 | 2554298.466 | 2573498.466 | 2585071.466 | 2674096.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775 | 2677596.6775
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6000 | -118885.638 | -32628.0675 | 1540635.555 | 1469646.385 | 1390445.385 | 1117193.91 | 1046495.8455 | 1027971.1155 | 150214.3175 | 149906.3775 | 127132.8375 | 51532.8375 | -21754.6625 | -29353.6665 | -109237.9165 | -128437.9165 | -140010.9165 | -229036.128 | 79764.382 | 79764.382 | 79764.382 | 79764.382 | 79764.382 | 79764.382 | 79764.382 | 79764.382 | 79764.382 | 79764.382 | 79764.382 | 79764.382 | 79764.382 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242 | 142458.242
|  | CHECK | CHECK
| Revenue Recognition | -211122.976 | 2792653.976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1304579.4081 | 0 | 0 | 0 | 672817.954 | 0 | 0 | 0 | 0 | 614667.7725 | 0 | 0 | 0 | 135929.2888 | 0 | 0 | 0 | 64659.5526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 2792653.976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1304579.4081 | 1304579.4081 | 1304579.4081 | 1304579.4081 | 1977397.3621 | 1977397.3621 | 1977397.3621 | 1977397.3621 | 1977397.3621 | 2592065.1346 | 2592065.1346 | 2592065.1346 | 2592065.1346 | 2727994.4234 | 2727994.4234 | 2727994.4234 | 2727994.4234 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976 | 2792653.976

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-10-31 | 2025-11-30 | 2025-12-31 |  | 2026-01-31 | 2026-02-28 | Grand Total
(blank)
1. Panels |  | 637909 |  |  | 0 |  |  | 637909
2. Inverters |  | 280682 |  |  | 0 |  |  | 280682
3. Mounting Structures |  | 113682 |  |  | 0 |  |  | 113682
4. DC Equipment |  | 103164.5783 |  | 75452.9269 | 0 | 0 | 5389.4971 | 184007.0023
5. Monitoring |  | 9890.213 | 135150.3263 |  | 0 | 23141.4579 |  | 168181.9972
6. AC Equipment | 0 | 79165 |  | 221662 | 0 |  | 15833 | 316660
8. Product Add On | 0 |  | 512862.3473 | 91090.5376 | 0 | 112435.4218 |  | 716388.3067
9. AC & DC installation | 0 | 55236 |  | 154660.8 | 0 |  | 11047.2 | 220944
10. Site Logistics |  | 13282.4137 |  | 47232.1027 | 0 |  | 2656.4844 | 63171.0008
11. Due Dilligence |  | 10031.3951 |  | 20828.3792 |  |  | 1362.2268 | 32222.0011
13. Engineering | 0 | [5 empty] | 25308 | 25308
14. General Expenses |  | 1536.8081 | 1455.2804 | 1016.026 | 0 | 352.409 | 500.4717 | 4860.9953
15. Service Add On |  |  | 23350 | 2725 |  |  | 2725 | 28800
12. BDP Commission
7.BESS
Grand Total | 0 | 1304579.4081 | 672817.954 | 614667.7725 | 0 | 135929.2888 | 64821.88 | 2792816.3034

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | Grand Total
(blank)
1. Panels |  | 487812 |  |  |  |  | 487812
2. Inverters |  | 174424.32 |  |  |  |  | 174424.32
3. Mounting Structures |  | 48031 |  |  |  |  | 48031
4. DC Equipment |  | 110856.73 |  | 81078.844 | -54600 | 5791.346 | 143126.92
5. Monitoring |  | 8598.34 | 85415.11 |  | 11169 |  | 105182.45
6. AC Equipment | 0 | 97452.49 |  | 272866.972 |  | 19490.498 | 389809.96
8. Product Add On | 0 |  | 326377.64 | 89988.38 | 111075 |  | 527441.02
9. AC & DC installation |  | 90333.5 |  | 252933.8 |  | 18066.7 | 361334
10. Site Logistics |  | 37037.625 |  | 131705.355 |  | 7407.53 | 176150.51
11. Due Dilligence |  | 42573.5 |  | 93350 |  | 6000 | 141923.5
13. Engineering | [5 empty] | 32269.1375 | 32269.1375
14. General Expenses |  | 8016.46 | 10490.93 | 8655.54 | 3332 | 3500 | 33994.93
15. Service Add On |  |  | 23350 | 9223.93 |  | 11573 | 44146.93
12. BDP Commission | 0 | [5 empty] | 0
7.BESS
Grand Total | 0 | 1105135.965 | 445633.68 | 939802.821 | 70976 | 104098.2115 | 2665646.6775

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill
2025-12-15 | Builders Break
2025-12-16 | Builders Break
2025-12-17 | Builders Break
2025-12-18 | Builders Break
2025-12-19 | Builders Break
2025-12-20 | Builders Break
2025-12-21 | Builders Break
2025-12-22 | Builders Break
2025-12-23 | Builders Break
2025-12-24 | Builders Break
2025-12-25 | Builders Break
2025-12-26 | Builders Break
2025-12-27 | Builders Break
2025-12-28 | Builders Break
2025-12-29 | Builders Break
2025-12-30 | Builders Break
2025-12-31 | Builders Break
2026-01-01 | Builders Break
2026-01-02 | Builders Break
2026-01-03 | Builders Break
2026-01-04 | Builders Break
2026-01-05 | Builders Break
2026-01-06 | Builders Break
2026-01-07 | Builders Break
2026-01-08 | Builders Break
2026-01-09 | Builders Break
2026-01-10 | Builders Break
2026-01-11 | Builders Break
2026-01-12 | Builders Break
2026-01-13 | Builders Break
2026-01-14 | Builders Break
2026-01-15 | Builders Break
2026-01-16 | Builders Break
2026-03-21 | Human Rights day
2026-04-03 | Good Friday
2026-04-06 | Family Day
2026-04-27 | Freedom Day
2026-05-01 | Workers day
2026-06-16 | Youth Day Holiday
2026-08-09 | Womens Day
2026-08-10 | Womens Day Observerd
2026-09-24 | Heritage Day
2026-12-16 | Day of Reconciliation
2026-12-25 | Christmas Day
2026-12-26 | Day of Goodwill