## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate | [5 empty] | FINANCIAL CLOSE CERTIFICATE
Project Name: | Lynridge Mall
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion: |  |  |  | 1. Financial Close | 1. Financial Close
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Project Plan
[9 empty] | 2026-01-28 | 2026-01-28
| PROJECT PLAN | Lynridge Mall | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 700
| PROJECT DEVELOPER | Peet Verenney
| PROJECT MANAGERS | Eon Van Rensburg
| CONTRACT VALUE | 5818787.2101
| Phase: | Compliance Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status | Expected Status | Comment
|  |  | 53 |  |  | 90 |  | 100% | 100%
1 | Project Initiation | 2025-01-28 | 140 | 2025-06-17 | 2025-01-28 | 140 | 2025-06-17 | 100% | 100%
1.1 | BD Handover | 2025-01-28 | 1 | 2025-01-29 | 2025-01-28 | 1 | 2025-01-29 | 100% | 100%
1.2 | Project Introduction | 2025-03-05 | 1 | 2025-03-06 | 2025-03-05 | 1 | 2025-03-06 | 100% | 100%
1.3 | HSE | 2025-02-11 | 126 | 2025-06-17 | 2025-02-11 | 126 | 2025-06-17 | 100% | 100%
1.4 | Installer Kick Off | 2025-06-10 | 1 | 2025-06-11 | 2025-06-10 | 1 | 2025-06-11 | 100% | 100%
1.5 | Project Review | 2025-06-10 | 1 | 2025-06-11 | 2025-06-10 | 1 | 2025-06-11 | 100% | 100%
2 | Site Establishment | 2025-06-19 | 1 | 2025-06-20 | 2025-06-18 | 1 | 2025-06-19 | 100% | 100%
2.1 | Installer on site & Roof Assessment | 2025-06-19 | 1 | 2025-06-20 | 2025-06-18 | 1 | 2025-06-19 | 100% | 100% |  | 65 | Net Work Days
3 | AC Installation | 2025-06-19 | 49 | 2025-08-07 | 2025-06-17 | 59 | 2025-08-15 | 100% | 100% |  | 13 | Total Weeks
3.1 | Inverters delivered | 2025-06-19 | 1 | 2025-06-20 | 2025-06-17 | 1 | 2025-06-18 | 100% | 100% |  | 53.8462 | kW/Week Installation Rate
3.2 | Inverters Mounted | 2025-06-20 | 5 | 2025-06-27 | 2025-06-19 | 5 | 2025-06-26 | 100% | 100%
3.3 | Solar DB Lead Time | 2025-06-19 | 20 | 2025-07-17 | 2025-06-18 | 30 | 2025-07-31 | 100% | 100%
3.4 | AC Works | 2025-07-17 | 15 | 2025-08-07 | 2025-07-22 | 17 | 2025-08-14 | 100% | 100%
3.5 | AC Tie-In | 2025-07-17 | 3 | 2025-07-22 | 2025-08-13 | 2 | 2025-08-15 | 100% | 100%
4 | DC Works | 2025-06-19 | 46 | 2025-08-04 | 2025-06-17 | 72 | 2025-08-28 | 100% | 100%
4.1 | Lifeline Installation (If Applicable) | [6 empty] | 0% | 0%
4.1 | Mounting Structure delivered | 2025-06-19 | 1 | 2025-06-20 | 2025-06-17 | 1 | 2025-06-18 | 100% | 100%
4.2 | Mounting Structure installation | 2025-06-19 | 10 | 2025-07-03 | 2025-06-18 | 35 | 2025-08-06 | 100% | 100%
4.3 | DC Cable delivered | 2025-06-26 | 1 | 2025-06-27 | 2025-07-23 | 1 | 2025-07-24 | 100% | 100%
4.4 | Trunking installation |  |  |  | 2025-07-18 | 9 | 2025-07-31 | 100% | 100%
4.5 | DC Stringing | 2025-07-21 | 10 | 2025-08-04 | 2025-07-29 | 22 | 2025-08-28 | 100% | 100%
5 | Module installation | 2025-06-26 | 28 | 2025-07-24 | 2025-07-23 | 22 | 2025-08-14 | 100% | 100%
5.1 | Module delivery | 2025-06-26 | 1 | 2025-06-27 | 2025-07-23 | 1 | 2025-07-24 | 100% | 100%
5.2 | Module mounting | 2025-07-03 | 15 | 2025-07-24 | 2025-07-24 | 15 | 2025-08-14 | 100% | 100%
6 | Commissioning | 2025-08-07 | 4 | 2025-08-11 | 2025-08-28 | 19 | 2025-09-16 | 100% | 100%
6.1 | Commissioning | 2025-08-07 | 1 | 2025-08-08 | 2025-08-28 | 3 | 2025-09-02 | 100% | 100%
6.2 | Practical Completion | 2025-08-08 | 1 | 2025-08-11 | 2025-09-02 | 10 | 2025-09-16 | 100% | 100% | Engineering to assist with technical issues, APEX and SMA data manager coms
7 | QA Inspections | 2025-08-11 | 1 | 2025-08-12 | 2025-09-11 | 1 | 2025-09-12 | 100% | 100%
7.1 | Red-Team Inspection | 2025-08-11 | 1 | 2025-08-12 | 2025-09-11 | 1 | 2025-09-12 | 100% | 100%
8 | Project Closure | 2025-08-12 | 24 | 2025-09-05 | 2025-09-12 | 41 | 2025-10-23 | 100% | 100%
8.1 | Equipment serial numbers | 2025-08-12 | 2 | 2025-08-14 | 2025-09-12 | 2 | 2025-09-16 | 100% | 100%
8.2 | Snags completion | 2025-08-12 | 2 | 2025-08-14 | 2025-09-12 | 2 | 2025-09-16 | 100% | 100%
8.3 | System Performance Monitoring | 2025-08-14 | 5 | 2025-08-21 | 2025-09-16 | 5 | 2025-09-23 | 100% | 100%
8.4 | Handover documentation | 2025-08-21 | 10 | 2025-09-04 | 2025-09-23 | 10 | 2025-10-08 | 100% | 100%
8.5 | Handover to Client | 2025-09-04 | 1 | 2025-09-05 | 2025-10-17 | 0 | 2025-10-17 | 100% | 100%
8.6 | Handover to Matriarch | 2025-08-16 | 5 | 2025-08-22 | 2025-10-16 | 5 | 2025-10-23 | 100% | 100%
Formulas:
Planned Start = MIN([Planned Start, row below]:E16)
Planned Start = [Planned Start, row below]
Planned End = MAX([Planned End, row below]:G16)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I16)
Actual Start = [Actual Start, row below]
Actual End = MAX([Actual End, row below]:K16)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C14)

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | PLANNED |  | ACTUAL |  | FINANCIAL REVIEW | TIMELINE REVIEW
1 | Planned Revenue | 5818787.2101 |  | 5818787.2101 |  |  | Start Date
2 | Planned Expenditure | 4908792.2029 |  | 4056639.2401
3 | Planned Profit | 909995.0072 |  | 1762147.97 |  |  | End Date - PC
4 | Planned Margin | 15.64% |  | 30.28%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Acceptance and initial Deposit |  | 35% | 2036575.5235 | 2025-05-31 | 004766 | 2025-06-11 | 2025-06-06
2 | Delivery of Panels |  | 20% | 1163757.442 | 2025-07-26 | 004766 | 2025-06-11 | 2025-07-17
3 | Delivery of Inverters |  | 30% | 1745636.163 | 2025-07-19 | 004766 | 2025-06-11 | 2025-07-17
4 | Practical Completion |  | 10% | 581878.721 | 2025-09-10 | 004766 | 2025-06-11 | 2025-09-26
5 | Handover |  | 5% | 290939.3605 | 2025-10-05 | 004766 | 2025-06-11 | 2025-10-17
6 |  |  | 0%
7 | - |  | 0% | 0
|  |  | 100% | 5818787.2101
KEY: | contains an error (in result or a check has failed) |  |  |  |  | 1338321.0583
| Red Font - IF TEXT : content not yet confirmed |  |  |  |  | 2007481.5875
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 2036575.5235
2 | Delivery of Panels |  | 30% | 1745636.163
3 | Delivery of Inverters |  | 20% | 1163757.442
4 | Practical Completion |  | 10% | 581878.721
5 | Handover |  | 5% | 290939.3605
| Total |  | 100% | 5818787.2101
|  |  | 100% | 5818787.2101

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  |  | COSTED |  | ACTUAL | Difference from costed
| EXPENDITURE |  | 4908792.2029 |  | 4056639.2401 | 852152.9628
| No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
| 1 | Panels | 1743145.3875 |  | 1387821.6 | 355323.7875
| 2 | Inverters | 400000 |  | 272034.43 | 127965.57
| 3 | Mounting Structures | 280164 |  | 161872.3 | 118291.7
| 4 | DC Equipment | 540581.7 |  | 612357.56 | -71775.86
| 5 | Monitoring | 174000 |  | 159713.84 | 14286.16
| 6 | AC Equipment | 644291.8913 |  | 372881.45 | 271410.4413
| 7 | Battery Systems | 0 |  | 0 | 0
| 8 | Product Add On | 50000 |  | 109213.4 | -59213.4
| 9 | AC & DC Installation | 594717.5 |  | 515836.3 | 78881.2
| 10 | Site Logistics | 82411.5 |  | 150323.9 | -67912.4
| 11 | Due Dilligence | 139530.75 |  | 108250 | 31280.75
| 12 | BDP Commission | 0 |  | 45499.75 | -45499.75
| 13 | Engineering | 247699.4741 |  | 72734.8401 | 174964.634 | RV: Matriarch defects percentage 1.25%
| 14 | General Expenses | 12250 |  | 9057.37 | 3192.63
| 15 | Service Add On | 0 |  | 79042.5 | -79042.5
|  | check: | 0 | #REF! | 0
Copy amounts in column H and paste as values at Project review.

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 4908792.2029 | 5818787.2101 |  | ACTUAL EXPENDITURE BREAKDOWN | [6 empty] | FINANCE ONLY |  |  |  |  | 4056639.2401
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | Project Related date | Total COS | ERROR on REV |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS | COMMENTS
1 | Panels | Longi 555W | 1262 | 1381.2562 | 1743145.3875 | 2025-07-26 | 1743145.3875 | 2075173.0804 |  | 1 | 1. Panels | Jinko 590 - Menlo | 1187 | 1168.2 | 1386653.4 |  | Menlo Inv0003034 | 2025-06-30 | 2075173.0804 | 0 | 2025-07-29 | 1387821.6 |  | 19
1 | [9 empty] | 1 | 1. Panels | Jinko 590 - Menlo (additional panel) |  | 1.98 | 1168.2 |  | Menlo - INV0003138 | 2025-08-31 | 0 |  | 2025-10-09 |  |  | BUDGET | Installer Allocation
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  |  | AC Equipment | 494291.8913
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  |  | DC Equipment | 238331.7
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  |  | AC Labour | 175102.5
1 | [9 empty] | 1 | 1. Panels | [7 empty] | 0 |  |  |  |  | DC Labour | 369615
[24 empty] | Offloading | 8500
2 | Inverters | SMA Core 2 | 5 | 80000 | 400000 | 2025-07-19 | 400000 | 476190.4762 |  | 2 | 2. Inverters | SMA Core 2 - Krannich | 5 | 54000 | 269428.85 | PO4001-LYNN-20250617 - RV Approved | Krannich - Inv 15-10012990 | 2025-06-30 | 471629.4639 | 0 | 2025-06-19 | 272034.43 |  | Roof Access/Scaffolding | 60961.5
2 | [9 empty] | 2 | 2. Inverters | Delivery |  |  | 2110.03 |  | Krannich - Inv 15-10012990 | 2025-06-30 | 3693.5626 |  | 2025-06-19 |  |  | Storage | 12950
2 | [9 empty] | 2 | 2. Inverters | EPR Fees |  |  | 495.55 |  | Krannich - Inv 15-10012990 | 2025-06-30 | 867.4497 |  | 2025-06-19 |  |  | Telehandler | 0
2 | [9 empty] | 2 | 2. Inverters |  |  |  | 0 |  |  | 2025-06-30 | 0 |  | 2025-08-24
2 | [9 empty] | 2 | 2. Inverters | [7 empty] | 0 |  |  |  |  | Other | 0
[24 empty] | Total | 1359752.5913
3 | Mounting Structures | Lumax Pitch Roof |  |  | 280164 | 2025-07-19 | 280164 | 333528.5714 |  | 3 | 3. Mounting Structures | [7 empty] | 0 | 0 |  | 161872.3 |  | Less 15% | 1155789.7026
[10 empty] | 3 | 3. Mounting Structures | Kliplok order |  |  | 145483.3 | PO4011-LYNN-20250619 - RV Approved | Schletter - INV1888 | 2025-06-30 | 303206.5228 |  | 2025-07-29
[10 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
[10 empty] | 3 | 3. Mounting Structures | Additional Clamps |  |  | 14549 | PO4043-LYNN-20250627 - RV Approved | Schletter - INV1909 | 2025-06-30 | 30322.0486 |  | 2025-07-29
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  | Stock in storeroom couldn't be used onsite. | R/Wp | 1.6511
[10 empty] | 3 | 3. Mounting Structures | Replacement Clamps |  |  | 1840 | PO4223-LYNN-20250814 - RV Approved | Schletter - INV2069 | 2025-08-31 | 0 |  | 2025-09-30
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
[10 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
[10 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
[10 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
[10 empty] | 3 | 3. Mounting Structures | [7 empty] | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [7 empty] | 0 |  |  |  |  | ACTUAL | Installer Price
[24 empty] | AC Equipment | 372881.45
4 | DC Equipment | DC Cabling (Total Cable Length) | 15875 | 14 | 222250 | 2025-07-26 | 540581.7 | 643549.6429 |  | 4 | 4. DC Equipment | [7 empty] | 0 | 0 |  | 612357.56 |  | DC Equipment | 131480.3
[10 empty] | 4 | 4. DC Equipment | DC Cable | 22400 | 13.5 | 333360 |  | Krannich - Inv 15-10013067 | 2025-06-30 | 460007.228 |  | 2025-07-29 |  |  | AC Labour | 87718.86 | 0.12531
[10 empty] | 4 | 4. DC Equipment | Delivery |  |  | 1530 |  | Krannich - Inv 15-10013067 | 2025-06-30 | 2111.2643 |  | 2025-07-29
[10 empty] | 4 | 4. DC Equipment | DC Cable - Cape Town Store (3 red, 4 black) | 7000 | 13.5 | 94500 |  | Allocated from Cpt Storage | 2025-08-31 | 0 |  | 2025-08-31
[10 empty] | 4 | 4. DC Equipment | DC Cable - JHB store (red) | 300 | 13.3 | 3990 |  | Allocated from Jhb Storage | 2025-08-31 | 0 |  | 2025-08-31 |  |  | DC Labour | 428117.44 | 0.6116
[10 empty] | 4 | 4. DC Equipment | DC Cable - Red (Check stock count) | 100 | 13.3 | 1330 |  | Allocated from Jhb Storage | 2025-08-31 | 0 |  | 2025-08-31
[10 empty] | 4 | 4. DC Equipment | DC Cable - Red |  |  | 27000 |  | Rubicon - INVWCRE-0070295 | 2025-08-31 | 0 |  | 2025-09-30
[10 empty] | 4 | 4. DC Equipment | Delivery of Cable |  |  | 19167.26 |  | DSV Inv: 180144108 | 2025-08-31 | 0 |  | 2025-09-30
4 |  | Project Kick Off |  | 10% | 31833.17 | 2025-06-12 |  |  |  | 4 | 4. DC Equipment | [7 empty] | 0 |  |  |  |  | Offloading | 36930
4 | 318331.7 | Site Establishment |  | 15% | 47749.755 | 2025-06-26 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 131480.3 | 10% | 13148.03 | PO3998-LYNN-20260613 - RV Approved | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 18143.1151 |  | 2025-06-26 |  |  | Roof Access/Scaffolding | 61062.4
4 |  | AC Installation Complete |  | 20% | 63666.34 | 2025-08-14 |  |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 19722.045 |  | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 27214.6726 |  | 2025-06-26 |  |  | Storage | 10730
4 |  | DC Installation Complete |  | 25% | 79582.925 | 2025-08-11 |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 20% | 26296.06 |  | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 36286.2301 |  | 2025-06-26 |  |  | Site Ablutions | 4476
[10 empty] | 4 | 4. DC Equipment | DC Installation Complete |  |  | 831.95 |  | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 0 |  | 2025-06-26
4 |  | Commissioning Complete |  | 10% | 31833.17 | 2025-08-18 |  |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 25% | 32038.125 |  | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 45357.7876 |  | 2025-09-04 |  |  | Return Of Excess Material | 7220.5
4 |  | Site De-establisment |  | 10% | 31833.17 | 2025-09-23 |  |  |  | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 13148.03 |  | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 18143.1151 |  | 2025-09-18 |  |  | Waste Skip | 15855
4 |  | Handover Document Complete |  | 5% | 15916.585 | 2025-08-21 |  |  |  | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 13148.03 |  | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 18143.1151 |  | 2025-09-16 |  |  | Other | 0
4 |  | End of Defects Period |  | 5% | 15916.585 | 2025-09-20 |  |  |  | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 6574.015 |  | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 9071.5575 |  | 2025-09-16 |  |  | Total | 1156471.95
4 | [9 empty] | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 6574.015 |  | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 9071.5575 |  | 2025-09-18 |  |  | R/Wp | 1.6521
5 | Monitoring | SMA Datamanager |  |  | 26000 | 2025-07-19 | 174000 | 207142.8571 |  | 5 | 5. Monitoring | SMA Data Manager |  |  | 29966.34 | PO4277-LYNN-20250826 - RV Approved | IBC Inv ZA22502201 | 2025-08-31 | 0 | -0.0025724 | 2025-08-27 | 159713.84
5 |  | Comms DB |  |  | 8000 | 2025-07-19 |  |  |  | 5 | 5. Monitoring | CTs & Meters |  |  | 25135 | PO4067-LYNN-20250630 - RV Approved | AccuEnergy ASAI-005849 | 2025-06-30 | 38986.104 |  | 2025-07-29
[10 empty] | 5 | 5. Monitoring |  |  |  | -3960 |  | Accuenergy - CN-00224 | 2025-08-31 | 0 |  | 2025-08-31
[10 empty] | 5 | 5. Monitoring |  |  |  | 7690 |  | Accuenergy - ASAI-006153 | 2025-08-31 | 0 |  | 2025-09-30
5 | [9 empty] | 5 | 5. Monitoring | SMA Power Supply |  |  | 838 | PO4001-LYNN-20250617 - RV Approved | Krannich - Inv 15-10012990 | 2025-06-30 | 1299.7953 |  | 2025-06-19
5 |  | Generator Integration |  |  | 125000 | 2025-08-21 |  |  |  | 5 | 5. Monitoring | Apex Controller |  |  | 85000 | PO4121-LYNN-20250714 - RV Approved | Rubicon - INVWCRE-0069678 | 2025-07-31 | 142127.3735 |  | 2025-09-01
5 |  | Revenue Grade Meter |  |  | 15000 | 2025-09-20 |  |  |  | 5 | 5. Monitoring | Revenue Grade Meter | 1 | 15000 | 11169 |  | Matriarch - INV-4742 | 2025-07-31 | 18359.1848 |  | 2025-07-31
5 | [9 empty] | 5 | 5. Monitoring | Anntenna |  |  | 300 | PO4082-LYNN-20250702 - RV Approved | Accuenergy Inv: ASAI-005952 | 2025-07-31 | 493.1288 |  | 2025-08-29
5 | [9 empty] | 5 | 5. Monitoring | UPS |  |  | 3575.5 | PO4082-LYNN-20250702 - RV Approved | Frontline INV733385 | 2025-07-31 | 5877.2733 |  | 2025-07-31
6 | AC Equipment | [5 empty] | 644291.8913 | 767014.1563 |  | 6 | 6. AC Equipment | [8 empty] | 0 |  | 372881.45
6 |  | Project Kick Off |  | 10% | 64429.1891 | 2025-06-12 |  |  |  | 6 | 6. AC Equipment | Project Kick Off | 372881.45 | 10% | 37288.145 | PO3998-LYNN-20260613 - RV Approved | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 76701.4156 |  | 2025-06-26
6 | 644291.8913 | Site Establishment |  | 15% | 96643.7837 | 2025-06-26 |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 55932.2175 |  | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 115052.1234 |  | 2025-06-26
6 |  | AC Installation Complete |  | 20% | 128858.3783 | 2025-08-14 |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 20% | 74576.29 |  | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 153402.8313 |  | 2025-06-26
6 |  | DC Installation Complete |  | 25% | 161072.9728 | 2025-08-11 |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 25% | 93220.3625 |  | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 191753.5391 |  | 2025-09-04
6 |  | Commissioning Complete |  | 10% | 64429.1891 | 2025-08-18 |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 37288.145 |  | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 76701.4156 |  | 2025-09-18
6 |  | Site De-establisment |  | 10% | 64429.1891 | 2025-09-23 |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 37288.145 |  | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 76701.4156 |  | 2025-09-16
6 |  | Handover Document Complete |  | 5% | 32214.5946 | 2025-08-21 |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 18644.0725 |  | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 38350.7078 |  | 2025-09-16
6 |  | End of Defects Period |  | 5% | 32214.5946 | 2025-09-20 |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 18644.0725 |  | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 38350.7078 |  | 2025-09-18
7 | Battery Systems | [5 empty] | 0 | 0 |  | 7 | Battery Systems | [8 empty] | 0 |  | 0
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
8 | Product Add On | [5 empty] | 50000 | 59523.8095 |  | 8 | 8. Product Add On | Catladder |  |  | 4900 | PO4145-LYNN-20250722 - RV Approved | JRL Engineering | 2025-07-31 | 2757.7278 | 0 | 2025-07-31 | 109213.4
8 |  | Inverter Cage |  |  | 50000 | 2025-08-18 |  |  |  | 8 | 8. Product Add On | Inverter Cage/Awning Deposit | 80% | 11800 | 9440 | PO4102-LYNN-20250709 -MI Approved | JRL Engineering INV00343 | 2025-07-31 | 5312.847 |  | 2025-07-11
8 | [9 empty] | 8 | 8. Product Add On |  | 20% |  | 2360 | PO4103LYNN-20250709 - MI Approved | JRL Engineering INV00343 | 2025-07-31 | 1328.2117 |  | 2025-07-31
8 | [9 empty] | 8 | 8. Product Add On | DB box |  |  | 1900 |  | JRL Engineering INV00344 | 2025-07-31 | 1069.323 |  | 2025-07-11
[10 empty] | 8 | 8. Product Add On | Additional Work |  |  | 3450 | PO4237-LYNN-20250819 - RV Approved | JRL Engineering INV00349 | 2025-08-31 | 0 |  | 2025-08-21
8 | [9 empty] | 8 | 8. Product Add On | Cable Route VO |  |  | 87163.4 | PO4152-LYNN-20250723 - RV Approved | JA Electrical - Inv 1087 | 2025-08-31 | 0 |  | 2025-09-04
Only services to be capture below, products above
9 | AC & DC Installation | Project Kick Off |  | 10% | 59471.75 | 2025-06-12 | 594717.5 | 699667.6471 |  | 9 | 9. AC & DC installation | Project Kick Off | 515836.3 | 10% | 51583.63 | PO3998-LYNN-20260613 - RV Approved | JA ELECTRICAL - Inv 1079 | 2025-07-31 | 69966.7647 | 0 | 2025-07-31 | 515836.3
9 | 175102.5 | Site Establishment |  | 15% | 89207.625 | 2025-06-26 |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 77375.445 |  | JA ELECTRICAL - Inv 1079 | 2025-07-31 | 104950.1471 |  | 2025-07-31
9 | 419615 | AC Installation Complete |  | 20% | 118943.5 | 2025-08-14 |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 20% | 103167.26 |  | JA ELECTRICAL - Inv 1079 | 2025-07-31 | 139933.5294 |  | 2025-08-29
9 |  | DC Installation Complete |  | 25% | 148679.375 | 2025-08-11 |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 25% | 128959.075 |  | JA ELECTRICAL - Inv 1079 | 2025-07-31 | 174916.9118 |  | 2025-09-04
9 |  | Commissioning Complete |  | 10% | 59471.75 | 2025-08-18 |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 51583.63 |  | JA ELECTRICAL - Inv 1079 | 2025-08-31 | 69966.7647 |  | 2025-09-18
9 |  | Site De-establisment |  | 10% | 59471.75 | 2025-09-23 |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 51583.63 |  | JA ELECTRICAL - Inv 1079 | 2025-08-31 | 69966.7647 |  | 2025-09-16
9 |  | Handover Document Complete |  | 5% | 29735.875 | 2025-08-21 |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 25791.815 |  | JA ELECTRICAL - Inv 1079 | 2025-08-31 | 34983.3824 |  | 2025-09-16
9 |  | End of Defects Period |  | 5% | 29735.875 | 2025-09-20 |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 25791.815 |  | JA ELECTRICAL - Inv 1079 | 2025-08-31 | 34983.3824 |  | 2025-09-18
10 | Site Logistics | [5 empty] | 82411.5 | 96954.7059 |  | 10 | 10. Site Logistics | Security |  |  | 14050 | PO4285-LYNN-20250827 - RV Approved | Nightguard Security | 2025-08-31 | 0 | 0 | 2025-08-30 | 150323.9
10 |  | Scaffolding |  |  | 60961.5 | 2025-08-18 |  |  |  | 10 | 10. Site Logistics | Project Kick Off | 136273.9 | 10% | 13627.39 | PO3998-LYNN-20260613 - RV Approved | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 9695.4706 |  | 2025-06-26
10 |  | Site Storage |  |  | 12950 | 2025-08-18 |  |  |  | 10 | 10. Site Logistics | Site Establishment |  | 15% | 20441.085 |  | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 14543.2059 |  | 2025-06-26
10 | [9 empty] | 10 | 10. Site Logistics | AC Installation Complete |  | 20% | 27254.78 |  | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 19390.9412 |  | 2025-06-26
10 | [9 empty] | 10 | 10. Site Logistics | DC Installation Complete |  | 25% | 34068.475 |  | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 24238.6765 |  | 2025-09-04
10 |  | Offloading |  |  | 8500 | 2025-08-18 |  |  |  | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 13627.39 |  | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 9695.4706 |  | 2025-09-18
10 | [9 empty] | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 13627.39 |  | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 9695.4706 |  | 2025-09-16
10 | [9 empty] | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 6813.695 |  | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 4847.7353 |  | 2025-09-16
10 | [9 empty] | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 6813.695 |  | JA ELECTRICAL - Inv 1070 | 2025-06-30 | 4847.7353 |  | 2025-09-18
11 | Due Dilligence | Electrical PrEng sign off |  |  | 17510.25 | 2025-08-25 | 139530.75 | 164153.8235 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 10500 |  | Sunspot E029 | 2025-07-31 | 24200.2818 | -0.0027104 | 2025-09-11 | 108250
11 |  | Structural sign off |  |  | 35020.5 | 2025-06-05 |  |  |  | 11 | 11. Due Dilligence | Structural sign off |  |  | 7500 |  | L&B - INV-1872 | 2025-06-30 | 14900.9814 |  | 2025-07-24
11 | [9 empty] | 11 | 11. Due Dilligence | Red Team |  |  | 8000 |  | Matriarch - INV-4987 | 2025-08-31 | 12131.4604 |  | 2025-08-31
11 |  | Grid Study - Outside of CoCT |  |  | 80000 | 2025-09-05 |  |  |  | 11 | 11. Due Dilligence | Grid Study - Outside of CoCT |  |  | 79700 | PO3688-LYNN-20250220 - RV Approved | Okusha Engineering Inv EE11 | 2025-05-31 | 109289.3888 |  | 2026-02-28
11 |  | Lightning Risk Assessment |  |  | 7000 | 2025-09-05 |  |  |  | 11 | 11. Due Dilligence | Lightning Risk Assessment |  |  | 2550 | PO4008-LYNN-20250618 - RV Approved | LPS IN307022 | 2025-06-30 | 3631.7139 |  | 2025-07-24
12 | BDP Commission | [5 empty] | 0 | 0 |  | 12 | BDP Commission |  |  |  | 22749.875 |  | Auxilio Dei - INV 032 | 2025-07-31 |  |  | 2025-07-29 | 45499.75
[10 empty] | 12 | BDP Commission |  |  |  | 22749.875 |  | Auxilio Dei - INV 032 | 2025-07-31 |  |  | 2025-09-04
12 | BDP Commission | [8 empty] | 12 | BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 57485.5341 | 2025-09-05 | 247699.4741 | 281476.6751 |  | 13 | 13. Engineering | Matriarch Defects Period |  |  | 72734.8401 |  | Matriarch - INV-4986 | 2025-08-31 | 281476.6751 | 0 | 2025-08-31 | 72734.8401
13 |  | Management |  |  | 28000 | 2025-09-05 |  |  |  | 13 | 13. Engineering | Management |  |  | 0 |  |  |  | 0
13 |  | Project manager |  |  | 95200 | 2025-09-05 |  |  |  | 13 | 13. Engineering | Project manager |  |  | 0 |  |  |  | 0
13 |  | Planner time |  |  | 36400 | 2025-09-05 |  |  |  | 13 | 13. Engineering | Planner time |  |  | 0 |  |  |  | 0
13 |  | De Snagging |  |  | 30613.94 | 2025-09-05 |  |  |  | 13 | 13. Engineering | De Snagging |  |  | 0 |  |  |  | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
13 | [9 empty] | 13 | 13. Engineering | [7 empty] | 0
14 | General Expenses | Car travel to site |  |  | 12250 | 2025-09-05 | 12250 | 14411.7647 |  | 14 | 14. General Expenses | Car travel to site |  |  | 994.52 |  | Expense Claim | 2025-05-31 | 739.9661 | 0 | 2025-06-09 | 9057.37
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 952 |  | Expense Claim | 2025-06-30 | 1236.064 |  | 2025-07-04
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 4268.89 |  | Expense Claim | 2025-07-31 | 5282.649 |  | 2025-08-07
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 2841.96 |  | Expense Claim | 2025-08-31 | 7153.0855 |  | 2025-09-05
14 | [9 empty] | 14 | 14. General Expenses
14 | [9 empty] | 14 | 14. General Expenses
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | [8 empty] | 0 |  | 79042.5
15 | [9 empty] | 15 | 15. Service Add On | Additional labour |  |  | 79042.5 | PO4296-LYNN-20250903 - RV Approved | JA Electrical - INV1092 | 2025-09-30 |  |  | 2025-09-25
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
5769731.5154

## Finance - Revenue
REVENUE RECOGNITION AMOUNT | (All)
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels |  | (blank) | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | Grand Total
(blank)
Battery Systems
BDP Commission
1. Panels | 0 |  |  | 2075173.0804 |  | 0 |  | 2075173.0804
2. Inverters | 0 |  |  | 476190.4762 |  |  |  | 476190.4762
3. Mounting Structures |  | 0 |  | 333528.5714 |  | 0 |  | 333528.5714
4. DC Equipment | 0 |  |  | 643549.6429 |  | 0 |  | 643549.6429
5. Monitoring |  |  |  | 40285.8993 | 166856.9604 | 0 |  | 207142.8597
6. AC Equipment |  |  |  | 767014.1563 |  |  |  | 767014.1563
8. Product Add On |  |  |  |  | 10468.1095 | 0 |  | 10468.1095 | 4513066.8964
9. AC & DC installation |  |  |  |  | 489767.3529 | 209900.2941 |  | 699667.6471
10. Site Logistics |  |  |  | 96954.7059 |  | 0 |  | 96954.7059
11. Due Dilligence |  |  | 109289.3888 | 18532.6953 | 24200.2818 | 12131.4604 |  | 164153.8262
13. Engineering | 0 | 0 |  |  |  | 281476.6751 |  | 281476.6751
14. General Expenses |  |  | 739.9661 | 1236.064 | 5282.649 | 7153.0855 |  | 14411.7647
15. Service Add On
Grand Total | 0 | 0 | 110029.3549 | 4452465.2917 | 696575.3537 | 510661.5152 |  | 5769731.5154
|  |  | 117855.98 | 4452465.29 | 696575.35 | 551890.59 |  | 5818787.21
|  |  | -7826.6251 | 0.0017028 | 0.0036606 | -41229.0748
5818787.2101
5818787.21
0.00011623

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | Grand Total
Battery Systems
BDP Commission |  |  |  | 45499.75 |  |  | 45499.75 | 45499.75
(blank) | [7 empty] | 0
1. Panels |  |  | 1386653.4 |  | 1168.2 |  | 1387821.6 | 1387821.6
2. Inverters |  |  | 272034.43 |  |  |  | 272034.43 | 272034.43
3. Mounting Structures |  |  | 160032.3 |  | 1840 |  | 161872.3 | 161872.3
4. DC Equipment |  |  | 466370.3 |  | 145987.26 |  | 612357.56 | 612357.56
5. Monitoring |  |  | 25973 | 100044.5 | 33696.34 |  | 159713.84 | 159713.84
6. AC Equipment |  |  | 372881.45 |  |  |  | 372881.45 | 372881.45
8. Product Add On |  |  |  | 18600 | 90613.4 |  | 109213.4 | 109213.4 | 3075894.58
9. AC & DC installation |  |  |  | 361085.41 | 154750.89 |  | 515836.3 | 515836.3
10. Site Logistics |  |  | 136273.9 |  | 14050 |  | 150323.9 | 150323.9
11. Due Dilligence |  | 79700 | 10050 | 10500 | 8000 |  | 108250 | 108250
13. Engineering | 0 |  |  |  | 72734.8401 |  | 72734.8401 | 72734.8401
14. General Expenses |  | 994.52 | 952 | 4268.89 | 2841.96 |  | 9057.37 | 9057.37
15. Service Add On | [5 empty] | 79042.5 | 79042.5 | 0
Grand Total | 0 | 80694.52 | 2831220.78 | 539998.55 | 525682.8901 | 79042.5 | 4056639.2401 | 3977596.7401

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2026-09-28
PLANNED |  | CHECK | CHECK
| Planned Revenue | 5818787.2101 | 5818787.2101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2036575.5235 | 0 | 0 | 0 | 0 | 0 | 0 | 1745636.163 | 1163757.442 | 0 | 0 | 0 | 0 | 0 | 0 | 581878.721 | 0 | 0 | 290939.3605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2036575.5235 | 2036575.5235 | 2036575.5235 | 2036575.5235 | 2036575.5235 | 2036575.5235 | 2036575.5235 | 3782211.6866 | 4945969.1286 | 4945969.1286 | 4945969.1286 | 4945969.1286 | 4945969.1286 | 4945969.1286 | 4945969.1286 | 5527847.8496 | 5527847.8496 | 5527847.8496 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101
| Planned Expenditure | 4908792.2029 | 4908792.2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35020.5 | 155734.1091 | 0 | 233601.1637 | 0 | 0 | 714164 | 1965395.3875 | 0 | 0 | 700803.4911 | 491012.6637 | 17510.25 | 346949.4741 | 0 | 92867.0546 | 155734.1091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35020.5 | 190754.6091 | 190754.6091 | 424355.7728 | 424355.7728 | 424355.7728 | 1138519.7728 | 3103915.1603 | 3103915.1603 | 3103915.1603 | 3804718.6514 | 4295731.3151 | 4313241.5651 | 4660191.0392 | 4660191.0392 | 4753058.0938 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029 | 4908792.2029
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2036575.5235 | 2001555.0235 | 1845820.9144 | 1845820.9144 | 1612219.7507 | 1612219.7507 | 1612219.7507 | 2643691.9137 | 1842053.9683 | 1842053.9683 | 1842053.9683 | 1141250.4772 | 650237.8135 | 632727.5635 | 285778.0894 | 867656.8104 | 774789.7558 | 619055.6467 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072 | 909995.0072
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 5818787.2101 | 5818787.2101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2036575.5235 | 0 | 0 | 0 | 0 | 0 | 2909393.6051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 581878.721 | 0 | 0 | 290939.3605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2036575.5235 | 2036575.5235 | 2036575.5235 | 2036575.5235 | 2036575.5235 | 2036575.5235 | 4945969.1286 | 4945969.1286 | 4945969.1286 | 4945969.1286 | 4945969.1286 | 4945969.1286 | 4945969.1286 | 4945969.1286 | 4945969.1286 | 4945969.1286 | 5527847.8496 | 5527847.8496 | 5527847.8496 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101 | 5818787.2101
| Actual + Planned Expenditure | 4056639.2401 | 4056639.2401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 994.52 | 272872.43 | 289117.9925 | 952 | 11340 | 0 | 10050 | 2080424.15 | 4268.89 | 0 | 3450 | 324078.4401 | 486041.2725 | 10500 | 346941.585 | 79042.5 | 55697.26 | 1168.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 994.52 | 273866.95 | 562984.9425 | 563936.9425 | 575276.9425 | 575276.9425 | 585326.9425 | 2665751.0925 | 2670019.9825 | 2670019.9825 | 2673469.9825 | 2997548.4226 | 3483589.6951 | 3494089.6951 | 3841031.2801 | 3920073.7801 | 3975771.0401 | 3976939.2401 | 3976939.2401 | 3976939.2401 | 3976939.2401 | 3976939.2401 | 3976939.2401 | 3976939.2401 | 3976939.2401 | 3976939.2401 | 3976939.2401 | 3976939.2401 | 3976939.2401 | 3976939.2401 | 3976939.2401 | 3976939.2401 | 3976939.2401 | 3976939.2401 | 3976939.2401 | 3976939.2401 | 3976939.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401 | 4056639.2401
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2036575.5235 | 2035581.0035 | 1762708.5735 | 1473590.581 | 1472638.581 | 1461298.581 | 4370692.1861 | 4360642.1861 | 2280218.0361 | 2275949.1461 | 2275949.1461 | 2272499.1461 | 1948420.706 | 1462379.4335 | 1451879.4335 | 1104937.8485 | 1607774.0695 | 1552076.8095 | 1550908.6095 | 1841847.97 | 1841847.97 | 1841847.97 | 1841847.97 | 1841847.97 | 1841847.97 | 1841847.97 | 1841847.97 | 1841847.97 | 1841847.97 | 1841847.97 | 1841847.97 | 1841847.97 | 1841847.97 | 1841847.97 | 1841847.97 | 1841847.97 | 1841847.97 | 1841847.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97 | 1762147.97
|  | CHECK | CHECK
| Revenue Recognition | 49055.6947 | 5769731.5154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110029.3549 | 0 | 0 | 0 | 0 | 4452465.2917 | 0 | 0 | 0 | 696575.3537 | 0 | 0 | 0 | 510661.5152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 5769731.5154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110029.3549 | 110029.3549 | 110029.3549 | 110029.3549 | 110029.3549 | 4562494.6466 | 4562494.6466 | 4562494.6466 | 4562494.6466 | 5259070.0002 | 5259070.0002 | 5259070.0002 | 5259070.0002 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154 | 5769731.5154
| Installer Expenditure |  | 1020198.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227794.7375 | 0 | 0 | 0 | 0 | 128959.075 | 0 | 0 | 0 | 103167.26 | 254217.5625 | 0 | 306059.415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Installer Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227794.7375 | 227794.7375 | 227794.7375 | 227794.7375 | 227794.7375 | 356753.8125 | 356753.8125 | 356753.8125 | 356753.8125 | 459921.0725 | 714138.635 | 714138.635 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05 | 1020198.05

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | 400000 | 0 | 400000 | 0 | 400000
Inverters | 400000
Optimizers | 0
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | 280164 | 0 | 280164 | 0 | 280164
Mounting Structure | 280164
Delivery fee
|  | >Name< |  | >Name<
DC Cable | 222250 | 0 | 222250 | 0 | 222250
DC Cable | 222250
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
SMA Datamanager | 26000
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | 0 | 0 | #REF! | 0 | #REF!
SCADA | 0
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | 494291.8913 | 0.70613 | 277892.91 | 0.39699 | 216398.9813 |  | 0 | 494291.8913
DC Equipment | 238331.7 | 0.34047 | 142158.25 | 0.20308 | 96173.45 |  | 0 | 238331.7
AC Labour | 175102.5 | 0.25015 | 96174 | 0.13739 | 78928.5 |  | 0 | 175102.5
DC Labour | 369615 | 0.52802 | 230160 | 0.3288 | 139455 |  | 0 | 369615
Offloading | 8500 |  | 0 |  | 8500 |  |  | 8500
Roof Access/Scaffolding | 60961.5 |  | 29257.61 |  | 31703.89 |  |  | 60961.5
Storage | 12950 |  |  |  | 12950 |  |  | 12950
Telehandler | 0
HSE | 0
Totals | 1359752.5913 |  | 775642.77 |  | 584109.8213 | 0 |  | 1359752.5913
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | 494291.8913
AC equipment | 0 | 0 |  |  | 0 |  | 0 | 238331.7
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | 175102.5
DC equipment | 31833.17 | 0.045476 |  |  | 31833.17 |  |  | 369615
Storage | 7000 |  |  |  | 7000 |  |  | 8500
Panel lifting equipment | 82411.5 |  |  |  | 82411.5 |  |  | 60961.5
Offloading | 0 |  |  |  | 0 |  |  | 12950
Totals | #REF! |  | 0 |  | #REF! | 0 |  | 1359752.5913
Budget Summary
Budget | 1359752.5913
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
Loss | 1359752.5913
All amounts are exc VAT

## Decision Register (hidden)
Lynridge Mall |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Lynridge Mall | 0 | 0 | 0