🧾 COS Realisation Rule Book

Purpose: Ensure consistency, accuracy, and accountability in how Cost of Sales (COS) is recognised across projects.

Applies To: Project Managers (PMs), Project Finance Manager (PFM), Construction Manager (CM), and Program Manager (PrM).

1. 🎯 COS Realisation Principle

COS is only recognised when physical work or value has been delivered to site and accepted by Emergent as installed or fully assigned.

2. ✅ COS Recognition Criteria

A cost may be recognised under COS if all the following conditions are met:

| # | Condition | Description |
| --- | --- | --- |
| 1 | Goods Delivered | Goods have been delivered to site and signed off by the PM or Installer. |
| 2 | Work Executed | Installation or work completed on site, validated through photo evidence, installer signoff, or QA inspection. |
| 3 | No Duplicate | Expense not previously recorded or claimed under COS. |
| 4 | Scope-Aligned | Cost is part of project scope (main BOQ or approved VO). |
| 5 | Timing Matched | Cost relates to work done within the current reporting period. |

3. 🔄 COS Recognition Triggers by Category

| Cost Type | COS Trigger | Supporting Evidence | Owner |
| --- | --- | --- | --- |
| Equipment | On delivery to site | Delivery note, PM/installer signoff | PM |
| Subcontractor Labour | Verified work done on site | Signed subcontractor sheet, QA report | PM / CM |
| Installer Cost | Based on % of milestone completed | Installer invoice, milestone progress photo | PM |
| VOs | After formal VO approval + delivery/work | VO approval + site evidence | PM / PFM |
| Transport | On equipment movement to site | Delivery record | PM |
| Commissioning | When commissioning completed or booked | Commissioning form, QA report | CM |
| SSEG/Municipal Fees | On payment AND submission to municipality | Proof of payment, submission confirmation | PFM |
| Design/Engineering | Recognised upfront (if internal) or per contract delivery (if 3rd party) | Timesheets or invoice | Engineering Lead / PFM |

4. 📊 COS Reporting Cadence

- PMs update COS realisation every Friday via Project Tracker.

- PFM reviews entries weekly for finalisation in the Monday COS meeting.

- Disputes or delays in evidence → flagged for escalation.

5. ⚠️ Common Errors to Avoid

- Recognising COS based on invoice date instead of actual work.

- Capturing the same cost across multiple months.

- Recognising costs for undelivered or unused stock.

- Missing VO approvals before inclusion.

6. 🧭 Responsibility Matrix

| Task | Responsible | Accountable | Support |
| --- | --- | --- | --- |
| Log COS-eligible items weekly | PM | PM | Installer / CM |
| Validate work or delivery | PM / CM | PM | QA / Engineering |
| VO tracking & approval | PM | PrM | PFM |
| Upload to Tracker | PM | PM | - |
| Review & Final COS decision | PFM | Finance Manager | COO |

7. 🔐 COS Lock-in Protocol (Month-End)

- Final COS for the month is locked on the 3rd working day of the new month.

- No changes post-lock unless approved by COO and Finance Manager.

- COS vs Revenue GP% checks done at project and portfolio level.