## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | PLANNED |  | ACTUAL |  | FINANCIAL REVIEW | TIMELINE REVIEW |  | Allocated in 2024 | Budgeted | Acutal
1 | Planned Revenue | 5531086.4512 |  | 5630723.7612 |  | 5531086.4512 | Start Date | Sales | 2657720.9077 | 2873365.5436 | 2973002.8536
2 | Planned Expenditure | 4800198.66 |  | 4032944.1306 |  | 4211805.5106 | 2024-10-14 | COS | 1892484.48 | 2276451.4806 | 2140459.6506
3 | Planned Profit | 730887.7912 |  | 1597779.6306 |  | 1319280.9406 | End Date - PC | GP | 765236.4277 | 596914.0629 | 832543.2029
4 | Planned Margin | 13.21% |  | 28.38% |  | 23.85% | 2024-12-05
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Acceptance and Initial Deposit |  | 35% | 1935880.2579 | 2024-07-18 | 004467 | 2024-07-15 | 2024-07-17
2 | Delivery of Inverters |  | 20% | 1106217.2902 | 2024-10-21 | 004552 | 2024-10-02 | 2024-10-08
3 | Delivery of Panels |  | 30% | 1659325.9354 | 2024-12-19 | 004632 | 2024-12-12 | 2025-01-27
4 | Practical Completion |  | 10% | 553108.6451 | 2025-01-23 | 004678 | 2025-02-13 | 2026-01-31
5 | Handover |  | 5% | 276554.3226 | 2025-02-14 | 004690 | 2025-02-26 | 2025-10-16
6 | VO - Walkways |  | 0% | 120546.32 | 2025-01-23 | 004678 | 2025-02-13 | 2025-02-21
7 | Credit Note Walkways |  | 0% | -20909.01 | 2025-12-10 | 004898 | 2025-12-10 | 2026-01-31
8 | Credit Note Walkways |  |  | -17220.75 |  | 004931 | 2026-01-23 | 2026-01-31
|  |  | 100% | 5630723.7612
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 1970753.3164
2 | Delivery of Panels |  | 30% | 1689217.1284
3 | Delivery of Inverters |  | 20% | 1126144.7522
4 | Practical Completion |  | 10% | 563072.3761
5 | Handover |  | 5% | 281536.1881
| Total |  | 100% | 5630723.7612
|  |  | 100% | 5630723.7612
Formulas:
PAYMENT RECEIVED DATE = [TIMELINE REVIEW]+6

## Project Plan
[9 empty] | 2025-10-13 | 2025-10-13
| PROJECT PLAN | SA Metal - 14 Christiaan_A | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 595
| BUSINESS DEVELOPER | Peet
| PROJECT MANAGER | Lloyd
| CONTRACT VALUE | 5531086.4512
| Phase: | Hold
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status |  | Comment
|  |  | 100 |  |  | 121 |  | 100% | 100%
1 | Project Initiation | 2024-08-14 | 37 | 2024-09-20 | 2024-08-14 | 37 | 2024-09-20 | 100% | 100%
1.1 | BD Handover | 2024-08-14 | 1 | 2024-08-15 | 2024-08-14 | 1 | 2024-08-15 | 100% | 100%
1.2 | Project Introduction | 2024-09-05 | 1 | 2024-09-06 | 2024-09-05 | 1 | 2024-09-06 | 100% | 100%
1.3 | HSE | 2024-09-05 | 15 | 2024-09-20 | 2024-09-05 | 15 | 2024-09-20 | 100% | 100%
1.4 | Installer Kick Off | 2024-09-13 | 1 | 2024-09-16 | 2024-09-13 | 1 | 2024-09-16 | 100% | 100%
1.5 | Project Review | 2024-09-12 | 1 | 2024-09-13 | 2024-09-12 | 1 | 2024-09-13 | 100% | 100%
2 | Site Establishment | 2024-10-14 | 1 | 2024-10-15 | 2024-10-14 | 1 | 2024-10-15 | 100% | 100%
2.1 | Installer on site & Roof Assessment | 2024-10-14 | 1 | 2024-10-15 | 2024-10-14 | 1 | 2024-10-15 | 100% | 100% |  | 91 | Net working Days
3 | AC Installation | 2024-11-18 | 29 | 2024-12-17 | 2024-11-18 | 29 | 2024-12-17 | 100% | 100% |  | 18.2 | Net Working Weeks
3.1 | Inverters delivered | 2024-10-14 | 1 | 2024-10-15 | 2024-09-30 | 1 | 2024-10-01 | 100% | 100% |  | 32.6923 | kW/Week Installationn Speed
3.2 | Inverters Mounted | 2024-10-15 | 1 | 2024-10-16 | 2024-10-01 | 1 | 2024-10-02 | 100% | 100%
3.3 | Solar DB lead time | 2024-09-12 | 30 | 2024-10-25 | 2024-09-12 | 30 | 2024-10-25 | 100% | 100%
3.4 | AC Works | 2024-10-15 | 10 | 2024-10-29 | 2024-11-20 | 45 | 2025-01-27 | 100% | 100%
3.5 | AC Tie - in | 2024-10-23 | 1 | 2024-10-24 | 2024-10-09 | 1 | 2024-10-10 | 100% | 100%
4 | DC Works | 2024-11-18 | 59 | 2025-01-16 | 2024-11-18 | 59 | 2025-01-16 | 100% | 100%
4.1 | Mounting Structure delivered | 2024-10-14 | 1 | 2024-10-15 | 2024-10-14 | 1 | 2024-10-15 | 100% | 100%
4.2 | Mounting Structure installation | 2024-10-14 | 8 | 2024-10-24 | 2024-10-14 | 8 | 2024-10-24 | 100% | 100%
4.3 | DC Cable delivered | 2024-10-14 | 1 | 2024-10-15 | 2024-10-14 | 1 | 2024-10-15 | 100% | 100%
4.3 | DC Stringing | 2025-01-07 | 5 | 2025-01-14 | 2025-01-27 | 5 | 2025-02-03 | 100% | 100%
5 | Module installation | 2024-12-12 | 35 | 2025-01-16 | 2024-12-12 | 60 | 2025-02-10 | 100% | 100%
5.1 | Module delivery | 2024-12-12 | 1 | 2024-12-13 | 2024-12-12 | 1 | 2024-12-13 | 100% | 100%
5.2 | Module mounting | 2024-12-12 | 15 | 2025-01-07 | 2025-01-13 | 20 | 2025-02-10 | 100% | 100%
6 | Commissioning | 2025-01-06 | 18 | 2025-01-24 | 2025-01-06 | 37 | 2025-02-12 | 100% | 100%
6.1 | Commissioning | 2025-01-16 | 1 | 2025-01-17 | 2025-02-10 | 1 | 2025-02-11 | 100% | 100%
6.2 | Practical Completion | 2025-01-16 | 4 | 2025-01-22 | 2025-02-11 | 1 | 2025-02-12 | 100% | 100%
7 | QA Inspections | 2025-01-20 | 4 | 2025-01-24 | 2025-01-20 | 4 | 2025-01-24 | 100% | 100%
7.1 | Red-Team Inspection | 2025-01-20 | 3 | 2025-01-23 | 2025-02-12 | 1 | 2025-02-13 | 100% | 100%
8 | Project Closure | 2025-01-17 | 12 | 2025-01-29 | 2025-01-17 | 224 | 2025-08-29 | 100% | 100%
8.1 | Equipment serial numbers | 2025-01-23 | 1 | 2025-01-24 | 2025-02-13 | 1 | 2025-02-14 | 100% | 100%
8.2 | Snags completion | 2025-01-24 | 5 | 2025-01-31 | 2025-02-13 | 2 | 2025-02-17 | 100% | 100%
8.3 | System Performance Monitoring | 2025-01-31 | 5 | 2025-02-07 | 2025-02-17 | 1 | 2025-02-18 | 100% | 100%
8.4 | Handover documentation | 2025-01-31 | 5 | 2025-02-07 | 2025-02-17 | 1 | 2025-02-18 | 100% | 100%
8.5 | Handover to Client | 2025-02-07 | 1 | 2025-02-10 | 2025-02-20 | 1 | 2025-08-29 | 100% | 100%
8.6 | Handover to Matriarch | 2025-01-24 | 1 | 2025-01-27 | 2025-04-29 | 1 | 2025-04-30 | 100% | 100%

## Data (hidden)
Public holidays |  | Drop down list
2024-01-01 | New Years Day | Approved
2024-03-21 | Human Rights day | Pending
2024-03-29 | Good Friday | Declined
2024-04-01 | Family Day | Abanded
2024-05-01 | Workers day
2024-06-17 | Youth Day Holiday
2024-08-09 | Womens Day
2024-09-24 | Heritage Day
2024-12-16 | Day of Reconciliation
2024-12-25 | Christmas Day
2024-12-26 | Day of Goodwill |  | Manual dates

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  |  | COSTED |  | PLANNED |  | ACTUAL | Difference from costed | Difference from planned
| EXPENDITURE |  | 4800198.66 |  | 4211805.5106 |  | 4032944.1306 | 767254.5294 | 178861.38
| No. | Item | Costed Expenditure |  | Planned Expenditure |  | Actual Expenditure | Saving / Overrun | Saving / Overrun | Comments on variations from planned expenditure
| 1 | Panels | 1642699.21 |  | 1618563.25 |  | 1520595.14 | 122104.07 | 97968.11
| 2 | Inverters | 394490 |  | 361567.5 |  | 345455.23 | 49034.77 | 16112.27
| 3 | Mounting Structures | 238032 |  | 114681.4 |  | 73364.1 | 164667.9 | 41317.3
| 4 | DC Equipment | 419782.9 |  | 527842.4 |  | 550887.4 | -131104.5 | -23045
| 5 | Monitoring | 49000 |  | 80490.5 |  | 109045.78 | -60045.78 | -28555.28
| 6 | AC Equipment | 840770.37 |  | 362257.91 |  | 395469.19 | 445301.18 | -33211.28
| 7 | Battery Systems | 0 |  | 0 |  | 0 | 0 | 0
| 8 | Product Add On | 30000 |  | 0 |  | 121265.17 | -91265.17 | -121265.17
| 9 | AC & DC Installation | 495900 |  | 513333.33 |  | 513333.33 | -17433.33 | 0
| 10 | Site Logistics | 69299.97 |  | 78500 |  | 63500 | 5799.97 | 15000
| 11 | Due Dilligence | 104631 |  | 23020 |  | 21978.33 | 82652.67 | 1041.67
| 12 | BDP Commission | 128980.2 |  | 128980.2 |  | 128980.2 | 0 | 0
| 13 | Engineering | 376288.01 |  | 392244.0206 |  | 155538.5806 | 220749.4294 | 236705.44 | RV: Matriarch defects percentage 1.25%
| 14 | General Expenses | 10325 |  | 10325 |  | 8729.38 | 1595.62 | 1595.62
| 15 | Service Add On | 0 |  | 0 |  | 24802.3 | -24802.3 | -24802.3
|  | check: | 0 | #REF! | 0 | #REF! | 0
Copy amounts in column H and paste as values at Project review.

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 4800198.66 | 5630032.772 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY |  |  |  |  | 4032944.1306
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | Project Related date | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS | PO NUMBER | COMMENTS
1 | Panels | Longi 570W - Costing Sheet | 1044 | 1535.1525 | 1602699.21 | 2025-02-10 | 1642699.21 | 1955594.298 |  | 1 | 1. Panels | Canadian Solar 555W - Deposit - Herholdts | 1073 | 1415.25 | 759281.625 | Herholdts Inv: INV875402 | 2024-07-31 | 940631.8159 | 0.0013203 | 2024-09-27 | 1520595.14 | PO3244-SAM-20240719 - RV Approved |  | 19
1 |  | Jinko Solar 575W | [7 empty] | 1 | 1. Panels |  |  |  | 618186.63 | Herholdts Inv: INV875402 | 2024-07-31 | 940631.8159 |  | 2024-10-17 |  |  |  | BUDGET | Installer Allocation
[10 empty] | 1 | 1. Panels |  |  |  | 141094.995 | Herholdts Inv: INV875402 | 2024-07-31 | 0 |  | 2024-10-31
[10 empty] | 1 | 1. Panels | Canadian Solar 555W - moved to stock | 15 | -1415.25 | -21228.75 | Allocated to Stock | 2025-02-28 |  |  | 2025-02-28
[10 empty] | 1 | 1. Panels | 2 x Canadian Solar 555W - Stock | 2 | 1415.25 | 2830.5 | Stock | 2025-08-31 |  |  | 2025-08-31 |  | PO3713-SAM14A-20250304 - RV Approved
1 | [9 empty] | 1 | 1. Panels | Delivery |  |  | 2600 | Supply Chain Inv:SCO04658 | 2025-01-31 |  |  | 2025-01-16 |  |  |  | AC Equipment | 840770.37
1 |  | Delivery |  |  | 40000 | 2025-02-10 |  |  |  | 1 | 1. Panels | Delivery |  |  | 9050 | Supply Chain Inv:SCO04658 | 2024-12-31 | 63458.2488 |  | 2025-01-16 |  |  |  | DC Equipment | 208422.9
1 | [9 empty] | 1 | 1. Panels | Storage |  |  | 4860 | Supply Chain: Inv SCO04502 | 2024-10-31 | 5882.6761 |  | 2024-11-29 |  |  |  | AC Labour | 347130
1 | [9 empty] | 1 | 1. Panels | Storage |  |  | 3920.14 | Supply Chain: Inv SCO04610 | 2024-11-30 | 4989.7399 |  | 2024-12-19 |  |  |  | DC Labour | 148770
[24 empty] | Offloading | 8500
2 | Inverters | Huawei 100KTL | 5 | 78898 | 394490 | 2024-11-13 | 394490 | 469630.9524 |  | 2 | 2. Inverters | Huawei 100KTL | 5 | 68870 | 344350 | Kathea Inv 518635 | 2024-09-30 | 468128.4416 | 0 | 2024-10-30 | 345455.23 |  | MI: Kathea Quote | Telehandler | 0
2 | [9 empty] | 2 | 2. Inverters | [6 empty] | 0 | [5 empty] | Storage | 7276.67
2 | [9 empty] | 2 | 2. Inverters | Delivery |  |  | 1105.23 | Kathea Inv 518635 | 2024-09-30 | 1502.5108 |  | 2024-10-30 |  |  |  | Scaffolding | 53523.3
2 | [9 empty] | 2 | 2. Inverters | [6 empty] | 0 | [5 empty] | Other | 0
[24 empty] | Total | 1614393.24
3 | Mounting Structures | KlipLok Roof | 595000 | 0.45 | 238032 | 2024-11-13 | 238032 | 283371.4286 |  | 3 | 3. Mounting Structures | KlipLok Roof |  |  | 112831.4 | Schletter Inv0892 | 2024-09-30 | 278800.1804 | 0 | 2024-09-23 | 73364.1 | PO3363-SAM20-20240918 - RV Approved |  | Less 15% | 1372234.254
3 | [9 empty] | 3 | 3. Mounting Structures | IBR Clampfit brackets used from Colcab PH2 | 500 | 24.13 | 12065 | Allocated from colcab - Phase 2 | 2025-01-31 | 0 |  | 2025-01-31 |  | PO3419-SAM-20241024 - RV Approved |  | R/Wp | 2.3063
3 | [9 empty] | 3 | 3. Mounting Structures | Delivery |  |  | 1850 | Schletter Inv0893 | 2024-09-30 | 4571.2482 |  | 2024-09-23
[11 empty] | 3. Mounting Structures |  |  |  | -58094.8 | Schletter Credit: CRN0157 | 2024-11-30 | 0 |  | 2024-11-30
3 | [9 empty] | 3 | 3. Mounting Structures |  |  |  | 4712.5 | Schletter - INV1717 | 2025-04-30 | 0 |  | 2025-05-29 |  |  |  | ACTUAL - Cosmic Sun | Installer Price
[24 empty] | AC Equipment | 114860
4 | DC Equipment | DC Cable | 11835 | 16 | 189360 | 2024-11-13 | 419782.9 | 499741.5476 |  | 4 | 4. DC Equipment | DC Cable | 9000 | 13.5 | 121500 | Herholdts Inv: INV8954316 | 2024-11-30 | 116715.4481 | -0.0027933 | 2024-12-19 | 550887.4 | PO3315-MUL-20240823 - RV Approved |  | DC Equipment | 309687.4
4 |  | DC Surge Arrestor | 4 | 5500 | 22000 | 2025-01-11 |  |  |  | 4 | 4. DC Equipment | DC Cable | 6000 |  | 79800 | Menlo Inv0002268 | 2024-11-30 | 78043.7551 |  | 2025-01-23 |  | PO3470-SAM-20241121 - RV Approved | TC | AC Labour | 124583.33
[10 empty] | 4 | 4. DC Equipment | DC Cable | 3000 | 13.3 | 39900 | Menlo: INV0002444 | 2025-01-31 | 10968.2878 |  | 2025-03-28
4 |  | DC Cable Tray | 180 | 261 | 46980 | 2025-01-11 |  |  |  | 4 | 4. DC Equipment | Deposit | 309687.4 | 30% | 92906.22 | Cosmic Sun CS_SAM14A_001 | 2024-10-31 | 92972.1058 |  | 2024-11-07 |  | PO3374-SAM14A-20240930 - RV Approved |  | DC Labour | 388750
4 |  | Earth Cable | 11835 | 13.5 | 159772.5 | 2024-11-13 |  |  |  | 4 | 4. DC Equipment | All DC and AC Equipment on site |  | 20% | 61937.48 | Cosmic Sun CS_SAM14A_002 | 2024-11-30 | 60574.3549 |  | 2024-12-12 |  |  |  | Offloading | 8500
4 |  | Earth clamp | 104.4 | 16 | 1670.4 | 2024-12-12 |  |  |  | 4 | 4. DC Equipment | Practical completion |  | 30% | 92906.22 | Cosmic Sun CS_SAM14A_005 | 2025-02-28 | 84280.5593 |  | 2025-02-20 |  |  |  | Telehandler | 0
4 | [9 empty] | 4 | 4. DC Equipment | Site fully Commissioned |  | 15% | 46453.11 | Cosmic Sun CS_SAM14A_005 | 2025-02-28 | 42140.2796 |  | 2025-03-06 |  |  |  | Storage | 0
4 | [9 empty] | 4 | 4. DC Equipment | Retention |  | 5% | 15484.37 | Cosmic Sun CS_SAM14A_006 | 2025-02-28 | 14046.7599 |  | 2025-03-28 |  |  |  | Roof Access | 55000
4 | [9 empty] | 4 | 4. DC Equipment | [6 empty] | 0 | [5 empty] | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | [6 empty] | 0 | [5 empty] | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | [6 empty] | 0 | [5 empty] | Other | 0
[24 empty] | Total | 1001380.73
5 | Monitoring | Smartlogger 3000 | 1 | 26000 | 26000 | 2024-11-13 | 49000 | 58333.3333 |  | 5 | 5. Monitoring | Smartlogger 3000 | 1 | 8000 | 8000 | Solarworld SASIV-24-00517 | 2024-08-31 | 5797.7857 | -0.00089977 | 2024-09-26 | 109045.78 |  | MI: Kathea quote 14/08 | R/Wp | 1.683
5 |  | Comms DB |  |  | 8000 | 2024-11-13 |  |  |  | 5 | 5. Monitoring | CTs |  |  | 13740.5 | AccuEnergy ASAI-003743 | 2024-08-31 | 9958.0592 |  | 2024-09-27
5 |  | Revenue Grade Meter | 1 | 15000 | 15000 | 2025-01-27 |  |  |  | 5 | 5. Monitoring | Revenue Grade Meter | 1 | 11169 | 11169 | MATRIARCH - INV-3278 | 2024-11-30 | 14579.8347 |  | 2024-11-30
[10 empty] | 5 | 5. Monitoring | Delivery of Techsitter Meter |  |  | 129.63 | DSV Inv: 180102912 | 2024-10-31 | 100.5784 |  | 2024-11-29
5 | [9 empty] | 5 | 5. Monitoring | SCADA |  |  | 35750 | Rubicon INVWCRE-0060133 | 2024-08-31 | 25908.8547 |  | 2024-09-27
[10 empty] | 5 | 5. Monitoring | SCADA |  |  | -35750 | Allocated to Stock | 2025-05-31 |  |  | 2025-05-31
[10 empty] | 5 | 5. Monitoring | [10 empty] | PO3821-SAM14A-20250424 - RV Approved
[10 empty] | 5 | 5. Monitoring | Janitza - UMG 604 |  |  | 20383.2 | Harmonious - QU100593 | 2025-04-30 |  |  | 2025-05-08 |  | PO3824-SA-M-20250425 - RV Approved
[10 empty] | 5 | 5. Monitoring | Delivery |  |  | 110.44 | DV Inv: 1801311355 | 2025-05-31 |  |  | 2025-06-27
[10 empty] | 5 | 5. Monitoring | Apex MCS-G2 Hardware & License |  |  | 50000 | Rubicon - INVWCRE-0067407 | 2025-05-31 |  |  | 2025-06-05 |  | PO3841-SAM14A-20250429 - RV Approved
[10 empty] | 5 | 5. Monitoring
[10 empty] | 5 | 5. Monitoring
[10 empty] | 5 | 5. Monitoring
[10 empty] | 5 | 5. Monitoring
5 | [9 empty] | 5 | 5. Monitoring | Frontline Comms Equipment |  |  | 2562.51 | Frontline Electrical: INV697940 | 2024-10-31 | 1988.2216 |  | 2024-10-10 |  | PO3387-SAM-20241007 - RV Approved | PO split across the portfolio
5 | [9 empty] | 5 | 5. Monitoring | Router |  |  | 2950.5 | Accuenergy - Inv ASAI-004773 | 2025-02-28 | 0 |  | 2025-03-28 |  | PO3639-SAM14A-20250211 - RV Approved
6 | AC Equipment | [5 empty] | 840770.37 | 1000917.107 |  | 6 | 6. AC Equipment | [6 empty] | 0 | -0.0047397 |  | 395469.19
[10 empty] | 6 | 6. AC Equipment | PVDB |  |  | 24166.67 | Cosmic Sun: CS_SAM_001 | 2024-07-31 | 33846.8767 |  | 2024-08-01 |  | RV Approved without PO
[10 empty] | 6 | 6. AC Equipment | Installation and Supply of equipment |  |  | 218731.24 | Cosmic Sun: CS_SAM_001 | 2024-07-31 | 306346.2745 |  | 2024-08-01 |  | PO3261-SAM-20240726 - RV Approved
[10 empty] | 6 | 6. AC Equipment | HSE |  |  | 4500 | Cosmic Sun: CS_SAM_001 | 2024-07-31 | 6302.521 |  | 2024-08-01
[10 empty] | 6 | 6. AC Equipment | [5 empty] | 2024-08-31 | 337063.73
[10 empty] | 6 | 6. AC Equipment | [6 empty] | 0
6 |  | Project Kick Off |  | 10% | 84077.037 | 2025-02-07 |  |  |  | 6 | 6. AC Equipment | Deposit | 114860 | 30% | 34458 | Cosmic Sun CS_SAM14A_001 | 2024-10-31 | 95207.3115 |  | 2024-11-07 |  | PO3374-SAM14A-20240930 - RV Approved
6 | 840770.37 | Site Establishment |  | 15% | 126115.5555 | 2024-10-14 |  |  |  | 6 | 6. AC Equipment | All DC and AC Equipment on site |  | 20% | 22972 | Cosmic Sun CS_SAM14A_002 | 2024-11-30 | 63471.541 |  | 2024-12-12
6 |  | AC Installation Complete |  | 20% | 168154.074 | 2024-12-17 |  |  |  | 6 | 6. AC Equipment | Practical completion |  | 30% | 34458 | Cosmic Sun CS_SAM14A_005 | 2025-02-28 | 87211.855 |  | 2025-02-20
6 |  | DC Installation Complete |  | 25% | 210192.5925 | 2025-01-16 |  |  |  | 6 | 6. AC Equipment | Site fully Commissioned |  | 15% | 17229 | Cosmic Sun CS_SAM14A_005 | 2025-02-28 | 43605.9275 |  | 2025-03-06
6 |  | Commissioning Complete |  | 10% | 84077.037 | 2025-01-24 |  |  |  | 6 | 6. AC Equipment | Retention |  | 5% | 5743 | Cosmic Sun CS_SAM14A_006 | 2025-02-28 | 14535.3092 |  | 2025-03-28
6 |  | Site De-establisment |  | 10% | 84077.037 | 2025-01-31 |  |  |  | 6 | 6. AC Equipment | [6 empty] | 0
6 |  | Handover Document Complete |  | 5% | 42038.5185 | 2025-02-07 |  |  |  | 6 | 6. AC Equipment | Additional AC Cable |  |  | 33211.28 | CS_SAM14A_003 | 2025-02-28 | 13325.7653 |  | 2025-02-13 |  | PO3626-SAM14A-20250205 - RV Approved
6 |  | End of Defects Period |  | 5% | 42038.5185 | 2025-03-09 |  |  |  | 6 | 6. AC Equipment | [6 empty] | 0
7 | Battery Systems | [5 empty] | 0 | 0 |  | 7 | Battery Systems | [7 empty] | 0 |  | 0
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
8 | Product Add On | [5 empty] | 30000 | 134660.6057 |  | 8 | 8. Product Add On | Switch Disconnectors |  |  | 16916.75 | All Electrical Inv IN142421 | 2024-11-30 | 19385.2463 | -0.0015993 | 2024-11-07 | 121265.17 | PO3452-SAM-20241105 - RV Approved
8 |  | Comms Cable Run |  |  | 30000 | 2025-01-24 |  |  |  | 8 | 8. Product Add On | Delivery |  |  | 1650 | All Electrical SO049152 | 2024-11-30 | 35714.29 |  | 2024-11-07
8 | [9 empty] | 8 | 8. Product Add On | Mounting Structure for Walkways | Splice Kit | 568.8 | 4244.32 | Schletter INV0951 | 2024-10-31 | 4863.6522 |  | 2024-11-29 |  | PO3389-SAM-20241008 - RV Approved
[10 empty] | 8 | 8. Product Add On | Walkway Installation | Labour | 2492.3077 | 21600 | Cosmic Sun - CS_SAM14A_004 | 2025-02-28 | 0 |  | 2025-02-13
8 | [9 empty] | 8 | 8. Product Add On | Walkways | Walkways | 17847.9 | 89239.5 | Onvlee Engineering: Inv 0148938 | 2024-11-30 | 68437.8295 |  | 2024-11-07 |  | PO3390-SAM-20241008 - RV Approved
[10 empty] | 8 | 8. Product Add On | Walkways transport |  |  | 5462.5 | Onvlee Engineering: Inv 0148938 | 2024-11-30 | 6259.5893 |  | 2024-11-07
8 | [9 empty] | 8 | 8. Product Add On | WAlkways Allocated to Trident Steel - PE |  |  | -17847.9 | Allocated to Trident Steel - PE | 2025-03-31 | 0 |  | 2025-03-31
Only services to be capture below, products above
9 | AC & DC Installation | Project Kick Off |  | 10% | 49590 | 2024-10-07 | 495900 | 583411.7647 |  | 9 | 9. AC & DC installation | Deposit | 513333.33 | 30% | 153999.999 | Cosmic Sun CS_SAM14A_001 | 2024-10-31 | 175023.5294 | 0 | 2024-11-07 | 513333.33 | PO3374-SAM14A-20240930 - RV Approved
9 | 148770 | Site Establishment |  | 15% | 74385 | 2024-10-14 |  |  |  | 9 | 9. AC & DC installation | All DC and AC Equipment on site |  | 20% | 102666.666 | Cosmic Sun CS_SAM14A_002 | 2024-11-30 | 116682.3529 |  | 2024-12-12
9 | 347130 | AC Installation Complete |  | 20% | 99180 | 2024-12-17 |  |  |  | 9 | 9. AC & DC installation | Practical completion |  | 30% | 153999.999 | Cosmic Sun CS_SAM14A_005 | 2025-02-28 | 175023.5294 |  | 2025-02-20
9 |  | DC Installation Complete |  | 25% | 123975 | 2025-01-16 |  |  |  | 9 | 9. AC & DC installation | Site fully Commissioned |  | 15% | 76999.9995 | Cosmic Sun CS_SAM14A_005 | 2025-02-28 | 87511.7647 |  | 2025-03-06
9 |  | Commissioning Complete |  | 10% | 49590 | 2025-01-24 |  |  |  | 9 | 9. AC & DC installation | Retention |  | 5% | 25666.6665 | Cosmic Sun CS_SAM14A_006 | 2025-02-28 | 29170.5882 |  | 2025-03-28
9 |  | Site De-establisment |  | 10% | 49590 | 2025-01-31 |  |  |  | 9 | 9. AC & DC installation | [6 empty] | 0
9 |  | Handover Document Complete |  | 5% | 24795 | 2025-02-07 |  |  |  | 9 | 9. AC & DC installation | [6 empty] | 0
9 |  | End of Defects Period |  | 5% | 24795 | 2025-03-09 |  |  |  | 9 | 9. AC & DC installation | [6 empty] | 0
10 | Site Logistics | [5 empty] | 69299.97 | 81529.3726 |  | 10 | 10. Site Logistics | Security | [5 empty] | 0 | 0.001044 |  | 63500
[10 empty] | 10 | 10. Site Logistics | [6 empty] | 0
[10 empty] | 10 | 10. Site Logistics | Deposit | 63500 | 30% | 19050 | Cosmic Sun CS_SAM14A_001 | 2024-10-31 | 19785.1535 |  | 2024-11-07 |  | PO3374-SAM14A-20240930 - RV Approved
[10 empty] | 10 | 10. Site Logistics | All DC and AC Equipment on site |  | 20% | 12700 | Cosmic Sun CS_SAM14A_002 | 2024-11-30 | 24458.8118 |  | 2024-12-12
[10 empty] | 10 | 10. Site Logistics | Practical completion |  | 30% | 19050 | Cosmic Sun CS_SAM14A_005 | 2025-02-28 | 24458.8118 |  | 2025-02-20
[10 empty] | 10 | 10. Site Logistics | Site fully Commissioned |  | 15% | 9525 | Cosmic Sun CS_SAM14A_005 | 2025-02-28 | 8750.1259 |  | 2025-03-06
[10 empty] | 10 | 10. Site Logistics | Retention |  | 5% | 3175 | Cosmic Sun CS_SAM14A_006 | 2025-02-28 | 4076.4686 |  | 2025-03-28
10 |  | Offloading |  |  | 8500 | 2025-01-24 |  |  |  | 10 | 10. Site Logistics | [6 empty] | 0
10 |  | Site Storage |  |  | 7276.67 | 2025-02-07 |  |  |  | 10 | 10. Site Logistics | [6 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [6 empty] | 0
10 |  | Scaffolding |  |  | 53523.3 | 2025-02-07 |  |  |  | 10 | 10. Site Logistics | [6 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 14877 | 2025-01-24 | 104631 | 123095.2941 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 13458.33 | Sun Spot Inv E005 | 2024-11-30 | 68551.201 | 0.0037013 | 2025-01-16 | 21978.33
11 |  | Structural sign off |  |  | 29754 | 2024-10-14 |  |  |  | 11 | 11. Due Dilligence | Structural sign off |  |  | 2520 | L&B Consulting Inv1742 | 2024-08-31 | 13475.2451 |  | 2024-09-02
11 |  | SCADA - COCT |  |  | 60000 | 2024-11-13 |  |  |  | 11 | 11. Due Dilligence | [6 empty] | 0
11 | [9 empty] | 11 | 11. Due Dilligence | [6 empty] | 0
11 | [9 empty] | 11 | 11. Due Dilligence | Red Team Inspection |  |  | 6000 | Matriarch - INV-3458 | 2024-12-31 | 41068.8443 |  | 2024-12-31
12 | BDP Commission | Referral Fee |  |  | 128980.2 | 2025-02-10 | 128980.2 | 0 |  | 12 | BDP Commission | Referral Fee |  |  | 64490.1 | Green Co Inv: INV0000518 | 2024-08-31 |  |  | 2024-09-02 | 128980.2
[10 empty] | 12 | BDP Commission | Referral Fee |  |  | 64490.1 | Green Co Inv: INV0000527 | 2024-11-30 |  |  | 2024-12-12
12 | BDP Commission | [8 empty] | 12 | BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 53182.57 | 2025-02-27 | 376288.01 | 427600.0092 |  | 13 | 13. Engineering | Matriarch Defects Period |  |  | 69138.5806 | Matriarch Inv: 3459 | 2024-12-31 | 427600.0092 | 0 | 2024-12-31 | 155538.5806
13 |  | Management |  |  | 47200 | 2025-02-27 |  |  |  | 13 | 13. Engineering | Performance Guarantee |  |  | 86400 | Matriarch - INV-5021 | 2025-08-31 | 0 |  | 2025-08-31
13 |  | Project manager |  |  | 160480 | 2025-02-27 |  |  |  | 13 | 13. Engineering |  |  |  | 0 |  |  | 0
13 |  | Planner time |  |  | 61360 | 2025-02-27 |  |  |  | 13 | 13. Engineering |  |  |  | 0 |  |  | 0
13 |  | De Snagging |  |  | 54065.44 | 2025-02-27 |  |  |  | 13 | 13. Engineering |  |  |  | 0 |  |  | 0
13 | [9 empty] | 13 | 13. Engineering
13 | [9 empty] | 13 | 13. Engineering
14 | General Expenses | Car travel to site |  |  | 10325 | 2025-02-27 | 10325 | 12147.0588 |  | 14 | 14. General Expenses | Car travel to site |  |  | 2022.72 | Expense Claim | 2024-08-31 | 2043.6389 | 0.0041805 | 2024-09-05 | 8729.38
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 1570.98 | Expense Claim | 2024-09-30 | 1891.2863 |  | 2024-10-04
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 1671 | Expense Claim | 2024-10-31 | 2295.2209 |  | 2024-11-08
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 0 | Expense Claim | 2024-11-30 | 0 |  | 2024-12-06
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 1634.56 | Expense Claim | 2025-01-31 | 2112.4106 |  | 2025-02-07
[10 empty] | 14 | 14. General Expenses |  |  |  | 423.22 | Expense Claim | 2025-02-28 | 3804.4979 |  | 2025-03-07
[10 empty] | 14 | 14. General Expenses |  |  |  | 318.92 | Expense Claim | 2025-03-31 | 0 |  | 2025-04-04
[10 empty] | 14 | 14. General Expenses |  |  |  | 1087.98 | Expense Claim | 2025-04-30 |  |  | 2025-05-08
14 | [9 empty] | 14 | 14. General Expenses
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | [7 empty] | 0 |  | 24802.3
15 | [9 empty] | 15 | 15. Service Add On | Rework of AC Installation |  |  | 16214.8 | Cosmic Sun Inv: CS_SAM14A_007 | 2025-05-31 |  |  | 2025-05-15 |  | PO3853-SAM14A-20250507 - RV Approved
15 | [9 empty] | 15 | 15. Service Add On | Replacement of broken panels |  |  | 8587.5 | Cosmic Sun Inv: CS_SAM14A_008 | 2025-08-31 |  |  | 2025-12-10 |  | PO4289-SAM14-20250828 - JP Approved
15 | [9 empty] | 15 | 15. Service Add On
5630032.7718

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2024-07-15 to 2026-01-19
PLANNED |  | CHECK | CHECK
| Planned Revenue | 5531086.4512 | 5651632.7712 | 1935880.2579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1106217.2902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1659325.9354 | 0 | 0 | 0 | 0 | 673654.9651 | 0 | 0 | 276554.3226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 3042097.5482 | 3042097.5482 | 3042097.5482 | 3042097.5482 | 3042097.5482 | 3042097.5482 | 3042097.5482 | 3042097.5482 | 4701423.4836 | 4701423.4836 | 4701423.4836 | 4701423.4836 | 4701423.4836 | 5375078.4487 | 5375078.4487 | 5375078.4487 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712 | 5651632.7712
| Planned Expenditure | 4800198.66 | 4800198.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49590 | 230254.5555 | 0 | 0 | 0 | 1075654.5 | 0 | 0 | 0 | 1670.4 | 267334.074 | 0 | 0 | 68980 | 334167.5925 | 187044.037 | 148667.037 | 211710.5255 | 1771679.41 | 0 | 386613.01 | 66833.5185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49590 | 279844.5555 | 279844.5555 | 279844.5555 | 279844.5555 | 1355499.0555 | 1355499.0555 | 1355499.0555 | 1355499.0555 | 1357169.4555 | 1624503.5295 | 1624503.5295 | 1624503.5295 | 1693483.5295 | 2027651.122 | 2214695.159 | 2363362.196 | 2575072.7215 | 4346752.1315 | 4346752.1315 | 4733365.1415 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66 | 4800198.66
| PLANNED CashFlow |  |  | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1886290.2579 | 1656035.7024 | 2762252.9927 | 2762252.9927 | 2762252.9927 | 1686598.4927 | 1686598.4927 | 1686598.4927 | 1686598.4927 | 1684928.0927 | 3076919.9541 | 3076919.9541 | 3076919.9541 | 3007939.9541 | 2673772.3616 | 3160383.2897 | 3011716.2527 | 2800005.7272 | 1304880.6397 | 1304880.6397 | 918267.6297 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112 | 851434.1112
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 5630723.7612 | 4821969.8036 | 1935880.2579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1106217.2902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1659325.9354 | 0 | 0 | 120546.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276554.3226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 1935880.2579 | 3042097.5482 | 3042097.5482 | 3042097.5482 | 3042097.5482 | 3042097.5482 | 3042097.5482 | 3042097.5482 | 3042097.5482 | 3042097.5482 | 3042097.5482 | 3042097.5482 | 3042097.5482 | 3042097.5482 | 3042097.5482 | 3042097.5482 | 3042097.5482 | 4701423.4836 | 4701423.4836 | 4701423.4836 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 4821969.8036 | 5098524.1261 | 5098524.1261 | 5098524.1261 | 5098524.1261 | 5098524.1261 | 5098524.1261 | 5098524.1261 | 5098524.1261 | 5098524.1261 | 5098524.1261 | 5098524.1261 | 5098524.1261 | 5098524.1261 | 5098524.1261 | 5098524.1261
| Actual + Planned Expenditure | 4032944.1306 | 4024356.6306 | 0 | 0 | 247397.91 | 0 | 0 | 0 | 0 | 69032.82 | 0 | 0 | 931453.525 | 1570.98 | 2562.51 | 618186.63 | 0 | 486550.225 | 415353.969 | 0 | 0 | -37691.85 | 0 | 264766.246 | 125420.14 | 0 | 75138.5806 | 0 | 25108.33 | 79800 | 12065 | 1634.56 | 54811.28 | 300414.219 | -21228.75 | 150630.3295 | 0 | 0 | 92919.5365 | -17528.98 | 0 | 0 | 0 | 0 | 21471.18 | 16214.8 | 0 | -31037.5 | 50000 | 0 | 0 | 110.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89230.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 247397.91 | 247397.91 | 247397.91 | 247397.91 | 247397.91 | 316430.73 | 316430.73 | 316430.73 | 1247884.255 | 1249455.235 | 1252017.745 | 1870204.375 | 1870204.375 | 2356754.6 | 2772108.569 | 2772108.569 | 2772108.569 | 2734416.719 | 2734416.719 | 2999182.965 | 3124603.105 | 3124603.105 | 3199741.6856 | 3199741.6856 | 3224850.0156 | 3304650.0156 | 3316715.0156 | 3318349.5756 | 3373160.8556 | 3673575.0746 | 3652346.3246 | 3802976.6541 | 3802976.6541 | 3802976.6541 | 3895896.1906 | 3878367.2106 | 3878367.2106 | 3878367.2106 | 3878367.2106 | 3878367.2106 | 3899838.3906 | 3916053.1906 | 3916053.1906 | 3885015.6906 | 3935015.6906 | 3935015.6906 | 3935015.6906 | 3935126.1306 | 3935126.1306 | 3935126.1306 | 3935126.1306 | 3935126.1306 | 3935126.1306 | 3935126.1306 | 3935126.1306 | 3935126.1306 | 4024356.6306 | 4024356.6306 | 4024356.6306 | 4024356.6306 | 4024356.6306 | 4024356.6306 | 4024356.6306 | 4024356.6306 | 4024356.6306 | 4024356.6306 | 4024356.6306 | 4024356.6306 | 4024356.6306 | 4024356.6306 | 4024356.6306 | 4024356.6306 | 4024356.6306 | 4024356.6306 | 4024356.6306 | 4024356.6306 | 4024356.6306 | 4024356.6306
| ACTUAL CashFlow |  |  | 1935880.2579 | 1935880.2579 | 1688482.3479 | 1688482.3479 | 1688482.3479 | 1688482.3479 | 1688482.3479 | 1619449.5279 | 1619449.5279 | 1619449.5279 | 687996.0029 | 686425.0229 | 1790079.8032 | 1171893.1732 | 1171893.1732 | 685342.9482 | 269988.9792 | 269988.9792 | 269988.9792 | 307680.8292 | 307680.8292 | 42914.5832 | -82505.5568 | -82505.5568 | -157644.1375 | -157644.1375 | -182752.4675 | -262552.4675 | 1384708.4679 | 1383073.9079 | 1328262.6279 | 1148394.7289 | 1169623.4789 | 1018993.1494 | 1018993.1494 | 1018993.1494 | 926073.6129 | 943602.5929 | 943602.5929 | 943602.5929 | 943602.5929 | 943602.5929 | 922131.4129 | 905916.6129 | 905916.6129 | 936954.1129 | 886954.1129 | 886954.1129 | 886954.1129 | 886843.6729 | 886843.6729 | 886843.6729 | 886843.6729 | 886843.6729 | 886843.6729 | 886843.6729 | 886843.6729 | 886843.6729 | 797613.1729 | 797613.1729 | 797613.1729 | 797613.1729 | 797613.1729 | 797613.1729 | 797613.1729 | 1074167.4955 | 1074167.4955 | 1074167.4955 | 1074167.4955 | 1074167.4955 | 1074167.4955 | 1074167.4955 | 1074167.4955 | 1074167.4955 | 1074167.4955 | 1074167.4955 | 1074167.4955 | 1074167.4955 | 1074167.4955 | 1074167.4955
|  | CHECK | CHECK
| Revenue Recognition | -98946.3206 | 5630032.7718 | 0 | 0 | 2227759.3041 | 0 | 0 | 0 | 394247.3136 | 0 | 0 | 0 | 0 | 754893.6673 | 0 | 0 | 0 | 398118.4494 | 0 | 0 | 0 | 677863.9944 | 0 | 0 | 0 | 0 | 532127.1023 | 0 | 0 | 0 | 13080.6984 | 0 | 0 | 0 | 631942.2424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 5630032.7718 | 0 | 0 | 2227759.3041 | 2227759.3041 | 2227759.3041 | 2227759.3041 | 2622006.6177 | 2622006.6177 | 2622006.6177 | 2622006.6177 | 2622006.6177 | 3376900.2849 | 3376900.2849 | 3376900.2849 | 3376900.2849 | 3775018.7343 | 3775018.7343 | 3775018.7343 | 3775018.7343 | 4452882.7287 | 4452882.7287 | 4452882.7287 | 4452882.7287 | 4452882.7287 | 4985009.831 | 4985009.831 | 4985009.831 | 4985009.831 | 4998090.5294 | 4998090.5294 | 4998090.5294 | 4998090.5294 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718 | 5630032.7718
| Installer Expenditure |  | 971092.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281364.219 | 0 | 0 | 0 | 0 | 187576.146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33211.28 | 281364.219 | 0 | 140682.1095 | 0 | 0 | 46894.0365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Installer Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281364.219 | 281364.219 | 281364.219 | 281364.219 | 281364.219 | 468940.365 | 468940.365 | 468940.365 | 468940.365 | 468940.365 | 468940.365 | 468940.365 | 468940.365 | 468940.365 | 502151.645 | 783515.864 | 783515.864 | 924197.9735 | 924197.9735 | 924197.9735 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01 | 971092.01

## Finance - Revenue
REVENUE RECOGNITION AMOUNT | (All)
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels |  | (blank) | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-08-31 | Grand Total
(blank)
Battery Systems
BDP Commission
1. Panels |  |  | 1881263.6319 |  |  | 5882.6761 | 4989.7399 | 63458.2488 | [6 empty] | 1955594.2967
2. Inverters | 0 |  |  |  | 469630.9524 | [9 empty] | 469630.9524
3. Mounting Structures |  |  |  |  | 283371.4286 |  | 0 |  | 0 |  |  | 0 |  |  | 283371.4286
4. DC Equipment |  | 0 |  |  |  | 92972.1058 | 255333.5581 |  | 10968.2878 | 140467.5988 |  |  |  |  | 499741.5504
5. Monitoring |  |  |  | 41664.6996 |  | 2088.8 | 14579.8347 |  |  | 0 |  |  |  |  | 58333.3342
6. AC Equipment | 0 | 0 | 346495.6722 | 337063.73 |  | 95207.3115 | 63471.541 |  |  | 158678.8571 |  |  |  |  | 1000917.1117
8. Product Add On | [5 empty] | 4863.6522 | 129796.9551 |  |  | 0 | 0 |  |  |  | 134660.6073
9. AC & DC installation |  | 0 |  |  |  | 175023.5294 | 116682.3529 |  |  | 291705.8824 |  |  |  |  | 583411.7647
10. Site Logistics | 0 | 0 |  |  |  | 19785.1535 | 24458.8118 |  |  | 37285.4063 |  |  |  |  | 81529.3715
11. Due Dilligence | 0 | 0 |  | 13475.2451 |  |  | 68551.201 | 41068.8443 | [6 empty] | 123095.2904
13. Engineering |  | 0 | [5 empty] | 427600.0092 | [5 empty] | 0 | 427600.0092
14. General Expenses |  |  |  | 2043.6389 | 1891.2863 | 2295.2209 | 0 |  | 2112.4106 | 3804.4979 | 0 |  |  |  | 12147.0546
15. Service Add On
Grand Total | 0 | 0 | 2227759.3041 | 394247.3136 | 754893.6673 | 398118.4494 | 677863.9944 | 532127.1023 | 13080.6984 | 631942.2424 | 0 | 0 |  | 0 | 5630032.7718
|  |  | 2227759.3 | 429961.6 | 754893.67 | 398118.45 | 677863.99 | 532127.1 | 13080.7 | 631942.24 | 5665747.05
|  |  | 0.0041027 | -35714.2864 | -0.002749 | -0.00062907 | 0.0044474 | 0.0022923 | -0.0015927 | 0.0023675

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-08-31 | Grand Total
Battery Systems
BDP Commission |  | 2024-08-31: 64490.1; 2024-11-30: 64490.1 | 128980.2 | 64490.1
(blank) | [14 empty] | 0
1. Panels |  | 2024-07-31: 1518563.25; 2024-10-31: 4860; 2024-11-30: 3920.14; 2024-12-31: 9050; 2025-01-31: 2600; 2025-02-28: -21228.75; 2025-08-31: 2830.5 | 1520595.14 | 2031.89
2. Inverters |  | 2024-09-30: 345455.23 | 345455.23 | 345455.23
3. Mounting Structures |  | 2024-09-30: 114681.4; 2024-11-30: -58094.8; 2025-01-31: 12065; 2025-04-30: 4712.5 | 73364.1 | 73364.1
4. DC Equipment |  | 2024-10-31: 92906.22; 2024-11-30: 263237.48; 2025-01-31: 39900; 2025-02-28: 154843.7 | 550887.4 | 550887.4
5. Monitoring |  | 2024-08-31: 57490.5; 2024-10-31: 2692.14; 2024-11-30: 11169; 2025-02-28: 2950.5; 2025-04-30: 20383.2; 2025-05-31: 14360.44 | 109045.78 | 51555.28
6. AC Equipment |  | 2024-07-31: 247397.91; 2024-10-31: 34458; 2024-11-30: 22972; 2025-02-28: 90641.28 | 395469.19 | 148071.28
8. Product Add On |  | 2024-10-31: 4244.32; 2024-11-30: 113268.75; 2025-02-28: 21600; 2025-03-31: -17847.9 | 121265.17 | 121265.17 | 1292630.35
9. AC & DC installation |  | 2024-10-31: 153999.999; 2024-11-30: 102666.666; 2025-02-28: 256666.665 | 513333.33 | 513333.33
10. Site Logistics |  | 2024-10-31: 19050; 2024-11-30: 12700; 2025-02-28: 31750 | 63500 | 63500
11. Due Dilligence |  | 2024-08-31: 2520; 2024-11-30: 13458.33; 2024-12-31: 6000 | 21978.33 | 19458.33
13. Engineering | 0 | 2024-12-31: 69138.5806; 2025-08-31: 86400 | 155538.5806 | 155538.5806
14. General Expenses |  |  | 2022.72 | 1570.98 | 1671 | 0 |  | 1634.56 | 423.22 | 318.92 | 1087.98 |  |  | 8729.38 | 6706.66
15. Service Add On |  | 2025-05-31: 16214.8; 2025-08-31: 8587.5 | 24802.3 | 24802.3
Grand Total | 0 | 1765961.16 | 126523.32 | 461707.61 | 313881.679 | 549787.666 | 84188.5806 | 56199.56 | 537646.615 | -17528.98 | 26183.68 | 30575.24 | 97818 | 4032944.1306 | 2140459.6506

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | 394490 | 0 | 394490 | 0 | 394490
Inverters | 394490
Optimizers | 0
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | 238032 | 0 | 238032 | 0 | 238032
Mounting Structure | 238032
Delivery fee
|  | >Name< |  | >Name<
DC Cable | 189360 | 0 | 189360 | 0 | 189360
DC Cable | 189360
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
Smartlogger 3000 | 26000
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | 0 | 0 | #REF! | 0 | #REF!
SCADA | 0
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | 840770.37 | 1.4131 | 277892.91 | 0.46705 | 562877.46 |  | 0 | 840770.37
DC Equipment | 208422.9 | 0.35029 | 142158.25 | 0.23892 | 66264.65 |  | 0 | 208422.9
AC Labour | 347130 | 0.58341 | 96174 | 0.16164 | 250956 |  | 0 | 347130
DC Labour | 148770 | 0.25003 | 230160 | 0.38682 | -81390 |  | 0 | 148770
Offloading | 8500 |  | 0 |  | 8500 |  |  | 8500
Roof Access/Scaffolding | 0 |  | 29257.61 |  | -29257.61 |  |  | 0
Storage | 7276.67 |  |  |  | 7276.67 |  |  | 7276.67
Telehandler | 53523.3
HSE | 0
Totals | 1614393.24 |  | 775642.77 |  | 785227.17 | 0 |  | 1560869.94
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | 840770.37
AC equipment | 0 | 0 |  |  | 0 |  | 0 | 208422.9
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | 347130
DC equipment | 0 | 0 |  |  | 0 |  |  | 148770
Storage | 0 |  |  |  | 0 |  |  | 8500
Panel lifting equipment | 15776.67 |  |  |  | 15776.67 |  |  | 0
Offloading | 53523.3 |  |  |  | 53523.3 |  |  | 7276.67
Totals | #REF! |  | 0 |  | #REF! | 0 |  | 1560869.94
Budget Summary
Budget | 1614393.24
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
Loss | 1614393.24
All amounts are exc VAT

## Decision Register (hidden)
SA Metal - 14 Christiaan_A |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | SA Metal - 14 Christiaan_A | 0 | 0 | 0