## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Certificate - Financial Close
Emergent Energy – Financial Close Completion Certificate |  |  |  | FINANCIAL CLOSE CERTIFICATE
Project Name: | Trident Steel PE
COO: | Johannes Potgieter
Programme Manager: | Roedolph Venter
HoPD: | Natasha Watkins-Baker
Date of Phase Completion:
Phase Deliverables Checklist: (Y/N)
Product Agreement | NA
EPC Agreement | NA
O&M Agreeement | NA
Cost Proposal | Signed
Deposit Received | Yes
Risks / Notes | None
Acknowledgement and Acceptance:
Role | Name | Signature | Date
COO | Johannes | JTP | 2025-10-23

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | PLANNED |  | ACTUAL |  | FINANCIAL REVIEW | TIMELINE REVIEW
1 | Planned Revenue | 3878819.44 |  | 3878819.44 |  | 3878819.44 | Start Date
2 | Planned Expenditure | 3622274.3004 |  | 3227541.703 |  | 3239868.3498 | 2025-01-29
3 | Planned Profit | 256545.1396 |  | 651277.737 |  | 638951.0902 | End Date - PC
4 | Planned Margin | 6.614% |  | 16.79% |  | 16.47% | 2025-03-20
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Acceptance and initial Deposit |  | 35% | 1357586.804 | 2024-11-18 | 004606 | 2024-11-13 | 2024-12-17
2 | Delivery of Inverters |  | 20% | 775763.888 | 2025-02-06 | 004667 | 2025-02-07 | 2025-02-14 | Receipt of inverters of site
3 | Delivery of Panels |  | 30% | 1163645.832 | 2025-02-07 | 004667 | 2025-02-07 | 2025-02-14 | Receipt of solar panels on site
4 | Practical Completion |  | 10% | 387881.944 | 2025-03-06 | 004688 | 2025-02-26 | 2025-03-20 | All provisional test successfully finalised
5 | Handover |  | 5% | 193940.972 | 2025-04-25 | 004688 | 2025-02-26 | 2026-02-28 | All documentation provided - What else is required.
6 | - |  | 0% | 0
7 | - |  | 0% | 0
|  |  | 100% | 3878819.44
KEY: | contains an error (in result or a check has failed)
| Red Font - IF TEXT : content not yet confirmed |  |  |  |  | 446064.2356
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 1357586.804
2 | Delivery of Panels |  | 30% | 1163645.832
3 | Delivery of Inverters |  | 20% | 775763.888
4 | Practical Completion |  | 10% | 387881.944
5 | Handover |  | 5% | 193940.972
| Total |  | 100% | 3878819.44
|  |  | 100% | 3878819.44

## Project Plan
[9 empty] | 2026-02-11 | 2026-02-11
| PROJECT PLAN | Trident Steel PE | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 440
| PROJECT DEVELOPER | Natasha
| PROJECT MANAGERS | Lloyd Brown
| CONTRACT VALUE | 3878819.44
| Phase: | Handover
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status |  | Comment
|  |  | 33 |  |  | 34 |  | 100% | 100%
1 | Project Initiation | 2024-10-29 | 25 | 2024-11-23 | 2024-10-29 | 91 | 2025-01-28 | 100% | 100%
1.1 | BD Handover | 2024-10-29 | 1 | 2024-10-30 | 2024-10-29 | 1 | 2024-10-30 | 100% | 100%
1.2 | Project Introduction | 2025-01-27 | 1 | 2025-01-28 | 2025-01-27 | 1 | 2025-01-28 | 100% | 100%
1.3 | HSE | 2025-01-13 | 15 | 2025-01-28 | 2025-01-13 | 15 | 2025-01-28 | 100% | 100%
1.4 | Installer Kick Off | 2025-01-27 | 1 | 2025-01-28 | 2025-01-27 | 1 | 2025-01-28 | 100% | 100%
1.5 | Project Review | 2025-01-27 | 1 | 2025-01-28 | 2025-01-27 | 1 | 2025-01-28 | 100% | 100%
2 | Site Establishment | 2025-01-29 | 1 | 2025-01-30 | 2025-01-31 | 5 | 2025-02-05 | 100% | 100%
2.1 | Installer on site & Roof Assessment | 2025-01-29 | 1 | 2025-01-30 | 2025-01-31 | 3 | 2025-02-05 | 100% | 100% |  | 42
3 | AC Installation | 2025-01-22 | 35 | 2025-02-26 | 2025-01-24 | 35 | 2025-02-28 | 100% | 100% |  | 8.4
3.1 | Inverters delivered | 2025-01-30 | 1 | 2025-01-31 | 2025-02-06 | 1 | 2025-02-07 | 100% | 100%
3.2 | Inverters Mounted | 2025-01-31 | 2 | 2025-02-04 | 2025-02-21 | 2 | 2025-02-25 | 100% | 100% |  | 52.381
3.3 | Solar DB Lead Time | 2025-01-22 | 25 | 2025-02-26 | 2025-01-24 | 20 | 2025-02-21 | 100% | 100%
3.4 | AC Works | 2025-01-28 | 18 | 2025-02-21 | 2025-02-21 | 5 | 2025-02-28 | 100% | 100%
3.5 | AC Tie-In | 2025-02-19 | 1 | 2025-02-20 | 2025-02-14 | 1 | 2025-02-17 | 100% | 100%
4 | DC Works | 2025-01-29 | 29 | 2025-02-27 | 2025-02-06 | 22 | 2025-02-28 | 100% | 100%
4.1 | Mounting Structure delivered | 2025-01-29 | 1 | 2025-01-30 | 2025-02-06 | 1 | 2025-02-07 | 100% | 100%
4.2 | Mounting Structure installation | 2025-01-30 | 10 | 2025-02-13 | 2025-02-07 | 4 | 2025-02-13 | 100% | 100%
4.3 | DC Cable delivered | 2025-01-29 | 1 | 2025-01-30 | 2025-02-06 | 1 | 2025-02-07 | 100% | 100%
4.4 | DC Stringing | 2025-02-13 | 10 | 2025-02-27 | 2025-02-21 | 5 | 2025-02-28 | 100% | 100%
5 | Module installation | 2025-01-31 | 21 | 2025-02-21 | 2025-02-06 | 18 | 2025-02-24 | 100% | 100%
5.1 | Module delivery | 2025-01-31 | 1 | 2025-02-03 | 2025-02-06 | 1 | 2025-02-07 | 100% | 100%
5.2 | Module mounting | 2025-01-31 | 15 | 2025-02-21 | 2025-02-06 | 12 | 2025-02-24 | 100% | 100%
6 | Commissioning | 2025-02-27 | 4 | 2025-03-03 | 2025-02-28 | 6 | 2025-03-06 | 100% | 100%
6.1 | Commissioning | 2025-02-27 | 1 | 2025-02-28 | 2025-02-28 | 1 | 2025-03-03 | 100% | 100%
6.2 | Practical Completion | 2025-02-27 | 2 | 2025-03-03 | 2025-02-28 | 4 | 2025-03-06 | 100% | 100%
7 | QA Inspections | 2025-02-27 | 21 | 2025-03-20 | 2025-02-28 | 17 | 2025-03-17 | 100% | 100%
7.1 | Red-Team Inspection | 2025-02-27 | 15 | 2025-03-20 | 2025-02-28 | 11 | 2025-03-17 | 100% | 100%
8 | Project Closure | 2025-02-27 | 50 | 2025-04-18 | 2025-02-28 | 171 | 2025-08-18 | 100% | 100%
8.1 | Equipment serial numbers | 2025-03-20 | 2 | 2025-03-24 | 2025-02-28 | 2 | 2025-03-04 | 100% | 100%
8.2 | Snags completion | 2025-03-20 | 10 | 2025-04-03 | 2025-03-17 | 10 | 2025-03-31 | 100% | 100%
8.3 | System Performance Monitoring | 2025-02-27 | 5 | 2025-03-06 | 2025-02-28 | 10 | 2025-03-14 | 100% | 100%
8.4 | Handover documentation | 2025-04-03 | 10 | 2025-04-17 | 2025-03-31 | 10 | 2025-04-14 | 100% | 100%
8.5 | Handover to Client | 2025-04-17 | 1 | 2025-04-18 | 2025-08-15 | 1 | 2025-08-18 | 100% | 100%
8.6 | Handover to Matriarch | 2025-03-03 | 5 | 2025-03-10 | 2025-03-06 | 5 | 2025-03-13 | 100% | 100%
Formulas:
Actual End = MAX([Actual End, row below]:K16)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C14)
Planned Start = [Planned Start, row below]-14
Planned Start = [Planned Start, row below]
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Planned End = [Planned Start]+[Duration (days)]
Actual Start = [Actual Start, row below]-14
Actual Start = [Actual Start, row below]

## Data (hidden)
Public holidays |  | Drop down list
2024-01-01 | New Years Day | Approved
2024-03-21 | Human Rights day | Pending
2024-03-29 | Good Friday | Declined
2024-04-01 | Family Day | Abanded
2024-05-01 | Workers day
2024-06-17 | Youth Day Holiday
2024-08-09 | Womens Day
2024-09-24 | Heritage Day
2024-12-16 | Day of Reconciliation
2024-12-25 | Christmas Day
2024-12-26 | Day of Goodwill |  | Manual dates

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  |  | COSTED |  | PLANNED |  | ACTUAL | Difference from costed | Difference from planned
| EXPENDITURE |  | 3622274.3004 |  | 3239868.3498 |  | 3227541.703 | 394732.5974 | 12326.6468
| No. | Item | Costed Expenditure |  | Planned Expenditure |  | Actual Expenditure | Saving / Overrun | Saving / Overrun | Comments on variations from planned expenditure
| 1 | Panels | 1054280.8 |  | 1041274.3 |  | 1012492 | 41788.8 | 28782.3
| 2 | Inverters | 280000 |  | 275480 |  | 275481.41 | 4518.59 | -1.41
| 3 | Mounting Structures | 154280 |  | 63162.4 |  | 75626.92 | 78653.08 | -12464.52
| 4 | DC Equipment | 356516 |  | 329400 |  | 349560 | 6956 | -20160
| 5 | Monitoring | 174000 |  | 141800 |  | 178926.29 | -4926.29 | -37126.29
| 6 | AC Equipment | 675293.2 |  | 418694 |  | 401539 | 273754.2 | 17155
| 7 | Battery Systems | 0 |  | 0 |  | 0 | 0 | 0
| 8 | Product Add On | 179212 |  | 199664.2368 |  | 277324.06 | -98112.06 | -77659.8232
| 9 | AC & DC Installation | 362900 |  | 438750 |  | 351000 | 11900 | 87750
| 10 | Site Logistics | 57306.9667 |  | 55000 |  | 55000 | 2306.9667 | 0
| 11 | Due Dilligence | 113060 |  | 99875 |  | 108556.38 | 4503.62 | -8681.38
| 12 | BDP Commission | 45272.6717 |  | 0 |  | 0 | 45272.6717 | 0
| 13 | Engineering | 162452.6621 |  | 170592.443 |  | 134885.243 | 27567.4191 | 35707.2 | RV: Matriarch defects percentage 1.25%
| 14 | General Expenses | 7700 |  | 6175.97 |  | 7150.4 | 549.6 | -974.43
| 15 | Service Add On | 0 |  | 0 |  | 0 | 0 | 0
|  | check: | 0 | #REF! | 0 | #REF! | 0
Copy amounts in column H and paste as values at Project review.

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 3622274.3004 | 3878819.44 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY |  |  |  |  | 3227541.703
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | Project Related date | Total COS | Total Revenue |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS | PO NUMBER | COMMENTS
1 | Panels | Jinko 580W | 760 | 1334.58 | 1014280.8 | 2025-04-07 | 1054280.8 | 1121861.5973 |  | 1 | 1. Panels | Jinko 585W | 754 | 1327.95 | 1001274.3 | Menlo Inv0002484 | 2025-01-31 | 1109432.159 | 0 | 2025-04-17 | 1012492 |  |  | 19
1 | [9 empty] | 1 | 1. Panels | Jinko 585W | 6 | 1327.95 | 7967.7 | Menlo Inv0002539 | 2025-02-28 | 8828.3726 |  | 2025-04-24 |  |  |  | BUDGET - Solar | Installer Allocation
1 |  | Module delivery to site |  |  | 40000 | 2025-04-07 |  |  |  | 1 | 1. Panels | Delivery |  | 3250 | 3250 | Menlo Inv0002539 | 2025-02-28 | 3601.0657 |  | 2025-04-24 |  |  |  | AC Equipment | 675293.2
1 | [9 empty] | 1 | 1. Panels | [6 empty] | 0 | [5 empty] | DC Equipment | 208676
1 | [9 empty] | 1 | 1. Panels | [6 empty] | 0 | [5 empty] | AC Labour | 252700 | 0.57302
1 | [9 empty] | 1 | 1. Panels | [6 empty] | 0 | [5 empty] | DC Labour | 110200 | 0.24989
[24 empty] | Offloading | 8500
2 | Inverters | Huawei 100KTL | 4 | 70000 | 280000 | 2025-03-01 | 280000 | 297948.3713 |  | 2 | 2. Inverters | Huawei 100kTL | 4 | 68870.35 | 275481.41 | Menlo Inv0002366 | 2025-01-31 | 297948.3713 | 0 | 2025-02-20 | 275481.41 |  |  | Roof Access/Scaffolding | 43380.3
2 | [9 empty] | 2 | 2. Inverters | [6 empty] | 0 | [5 empty] | Storage | 5426.6667
2 | [9 empty] | 2 | 2. Inverters | [6 empty] | 0 | [5 empty] | Telehandler | 0
2 | [9 empty] | 2 | 2. Inverters | [6 empty] | 0 | [5 empty] | Other | 0
[24 empty] | Total | 1304176.1667
3 | Mounting Structures | IBR Roof |  |  | 154280 | 2025-02-28 | 154280 | 164169.5526 |  | 3 | 3. Mounting Structures | Kliplok Roof |  |  | 63211.8 | Schletter Inv1326 | 2025-01-31 | 164169.5526 | 0 | 2025-02-26 | 75626.92 | PO3575-TRIPE-20250128 - RV Approved |  | Less 15% | 1108549.7417 | [SM: Target Installation Price]
3 | [9 empty] | 3 | 3. Mounting Structures |  | 499 | 24.88 | 12415.12 | Allocated from PE Stockroom | 2025-08-31 | 0 |  | 2025-08-31 |  |  |  | R/Wp | 2.5194
3 | [9 empty] | 3 | 3. Mounting Structures
3 | [9 empty] | 3 | 3. Mounting Structures | [12 empty] | ACTUAL - Luken Solar | Installer Price
[24 empty] | AC Equipment | 264600
4 | DC Equipment | DC Cable | 10560 | 14 | 147840 | 2025-02-28 | 356516 | 379369.1484 |  | 4 | 4. DC Equipment | DC Cable | 10000 | 13.3 | 133000 | Menlo Inv0002366 | 2025-01-31 | 153175.7642 | -0.0018569 | 2025-02-20 | 349560 |  |  | DC Equipment | 90000
4 |  | Project Kick Off |  | 10% | 20867.6 | 2025-01-22 |  |  |  | 4 | 4. DC Equipment | DC Cable | 8000 | 13.3 | 106400 | Menlo Inv0002484 | 2025-01-31 | 122540.6114 |  | 2024-04-17 |  |  |  | AC Labour | 100000 | 0.22676
[10 empty] | 4 | 4. DC Equipment | DC Cable | 2005 | 14.7 | 29473.5 | Rubicon INVWCRE-0065460 | 2025-02-28 | 11014.67 |  | 2025-03-28
4 | [9 empty] | 4 | 4. DC Equipment | Additional Cable | 995 | 14.7 | 14626.5 | Rubicon INVWCRE-0065461 | 2025-02-28 |  |  | 2025-03-28 |  | PO3707-TRIPE-20250228 - RV Approved
[10 empty] | 4 | 4. DC Equipment | DC Cable Blck | 1000 | 13.3 | -13300 | Allocated to Stock | 2025-08-31 |  |  | 2025-08-31
[10 empty] | 4 | 4. DC Equipment | Dc Cable Red | 800 | 13.3 | -10640 | Allocated to Stock | 2025-08-31 |  |  | 2025-08-31
4 | 208676 | Site Establishment |  | 15% | 31301.4 | 2025-01-31 |  |  |  | 4 | 4. DC Equipment | Project Kick Off | 90000 | 10% | 9000 | Luken Solar INV-0615 | 2025-01-31 | 10365.2773 |  | 2025-01-30 |  | PO3580-TRIPE-2020129 - RV Approved |  | DC Labour | 251000 | 0.56916
4 |  | AC Installation Complete |  | 20% | 41735.2 | 2025-02-26 |  |  |  | 4 | 4. DC Equipment | Site Establishment |  | 15% | 13500 | Luken Solar INV-0619 | 2025-02-28 | 13712.1379 |  | 2025-02-20 |  |  |  | Offloading | 55000
4 |  | DC Installation Complete |  | 25% | 52169 | 2025-02-27 |  |  |  | 4 | 4. DC Equipment | AC Installation Complete |  | 25% | 22500 | Luken Solar INV-0625 | 2025-02-28 | 22853.5632 |  | 2025-03-13 |  |  |  | Roof Access/Scaffolding | 0
4 |  | Commissioning Complete |  | 10% | 20867.6 | 2025-03-03 |  |  |  | 4 | 4. DC Equipment | DC Installation Complete |  | 20% | 18000 | Luken Solar INV-0625 | 2025-02-28 | 18282.8505 |  | 2025-03-13 |  |  |  | Storage | 0
4 |  | Site De-establisment |  | 10% | 20867.6 | 2025-04-03 |  |  |  | 4 | 4. DC Equipment | Commissioning Complete |  | 10% | 9000 | Luken Solar INV-0627 | 2025-03-31 | 9141.4253 |  | 2025-03-28 |  |  |  | Telehandler | 0
4 |  | Handover Document Complete |  | 5% | 10433.8 | 2025-04-17 |  |  |  | 4 | 4. DC Equipment | Site De-establisment |  | 10% | 9000 | Luken Solar INV-0634 | 2025-03-31 | 9141.4253 |  | 2025-04-10 |  |  |  | Other | 0
4 |  | End of Defects Period |  | 5% | 10433.8 | 2025-07-16 |  |  |  | 4 | 4. DC Equipment | Handover Document Complete |  | 5% | 4500 | Luken Solar INV-0635 | 2025-04-30 | 4570.7126 |  | 2025-05-08 |  |  |  | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | End of Defects Period |  | 5% | 4500 | Luken Solar INV-0636 | 2025-04-30 | 4570.7126 |  | 2025-05-08 |  |  |  | Other | 760600
[24 empty] | Total | 760600
5 | Monitoring | Smartlogger 3000 |  |  | 26000 | 2025-03-01 | 174000 | 185153.6307 |  | 5 | 5. Monitoring | Smartlogger 3000 |  |  | 7639.54 | Menlo Inv0002484 | 2025-01-31 | 9161.231 | 0.0038239 | 2024-04-17 | 178926.29 |  |  | R/Wp | 1.7286
5 |  | Comms DB |  |  | 8000 | 2025-04-03 |  |  |  | 5 | 5. Monitoring | CTs |  |  | 16850.5 | AccuEnergy ASAI-004688 | 2025-01-31 | 20206.8872 |  | 2025-02-27 |  | PO3610-TRIPE-20250131 - RV Approved
5 |  | Generator Integration |  |  | 125000 | 2025-03-10 |  |  |  | 5 | 5. Monitoring | Revenue Grade Meter | 2 | 11169 | 22338 | Matriach INV-3706 | 2025-01-31 | 26787.4215 |  | 2025-01-31
[10 empty] | 5 | 5. Monitoring | Delivery of Techsitter Meter |  |  | 508.25 | DSV Inv: 180117109 | 2025-02-28 | 502.3284 |  | 2025-03-31
5 |  | Revenue Grade Meter |  |  | 15000 | 2025-03-01 |  |  |  | 5 | 5. Monitoring | Generator Integration - Apex |  |  | 85000 | Rubicon INVWCRE-0064864 | 2025-02-28 | 74136.5731 |  | 2025-03-28 |  | PO3640-TRIPE-20250211 - RV Approved |  |  | 87469
5 | [9 empty] | 5 | 5. Monitoring | Janitza |  |  | 0 | 0 |  | 0 |  |  |  | PO3612-TRIPE-20250203 - RV Approved |  |  | 74348.65
[10 empty] | 5 | 5. Monitoring | Janitza (Move to Trident Steel GP) |  |  | 0
[10 empty] | 5 | 5. Monitoring | LV Metering CTs |  |  | 14060 | Accuenergy - Inv ASAI-004984 | 2025-03-31 | 14549.3435 |  | 2025-04-30 |  | PO3720-TRIPE-20250305 - RV Approved
5 | [9 empty] | 5 | 5. Monitoring | Fibre installation |  |  | 32530 | Luken INV-0633 | 2025-03-31 | 39809.8423 |  | 2025-04-03 |  | PO3764-TRIPE-20250325 - RV Approved | Added in cost for MV Metering
6 | AC Equipment | Project Kick Off |  | 10% | 67529.32 | 2025-01-22 | 675293.2 | 718580.3896 |  | 6 | 6. AC Equipment | AC Board 1 - Eastern SwitchGear - Deposit | 55805 | 50% | 27902.5 | Eastern Switchgear INV16739 | 2025-01-31 | 46462.0563 | 0.004705 | 2025-01-30 | 401539 | PO3572-TRPE-20250128 - RV Approved |  |  | 84835
6 | [9 empty] | 6 | 6. AC Equipment | AC Board 1- Eastern SwitchGear - Balance |  | 50% | 27902.5 | Eastern Switchgear INV16754 | 2025-02-28 | 49933.3547 |  | 2025-02-27
[10 empty] | 6 | 6. AC Equipment | AC Board 2 - Eastern SwitchGear - Deposit | 54738 | 50% | 27369 | Eastern Switchgear INV16739 | 2025-01-31 | 45573.6948 |  | 2025-01-30
[10 empty] | 6 | 6. AC Equipment | AC Board 2 - Eastern SwitchGear - Deposit |  | 50% | 27369 | Eastern Switchgear INV16754 | 2025-02-28 | 48978.6215 |  | 2025-02-27
[10 empty] | 6 | 6. AC Equipment | Bus Bar Stubs - Eastern SwitchGear - Deposit | 26396 | 50% | 13198 | Eastern Switchgear INV16752 | 2025-02-28 | 23618.6871 |  | 2025-02-27 |  | PO3625-TRIPE-20250205 - RV Approved
[10 empty] | 6 | 6. AC Equipment | Bus Bar Stubs - Eastern SwitchGear - Balance |  | 50% | 13198 | Eastern Switchgear INV16752 | 2025-02-28 | 23618.6871 |  | 2025-02-27
6 | [9 empty] | 6 | 6. AC Equipment | 400A Tie In Breaker | 30000 |  | 0 |  |  | 0
6 | [9 empty] | 6 | 6. AC Equipment | [6 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | Project Kick Off | 264600 | 10% | 26460 | Luken Solar INV-0615 | 2025-01-31 | 44060.0667 |  | 2025-01-30 |  | PO3580-TRIPE-2020129 - RV Approved
6 | 675293.2 | Site Establishment |  | 15% | 101293.98 | 2025-01-31 |  |  |  | 6 | 6. AC Equipment | Site Establishment |  | 15% | 39690 | Luken Solar INV-0619 | 2025-02-28 | 81195.9195 |  | 2025-02-20
6 |  | AC Installation Complete |  | 20% | 135058.64 | 2025-02-26 |  |  |  | 6 | 6. AC Equipment | AC Installation Complete |  | 25% | 66150 | Luken Solar INV-0625 | 2025-02-28 | 118379.7658 |  | 2025-03-13
6 |  | DC Installation Complete |  | 25% | 168823.3 | 2025-02-27 |  |  |  | 6 | 6. AC Equipment | DC Installation Complete |  | 20% | 52920 | Luken Solar INV-0625 | 2025-02-28 | 94703.8126 |  | 2025-03-13
6 |  | Commissioning Complete |  | 10% | 67529.32 | 2025-03-03 |  |  |  | 6 | 6. AC Equipment | Commissioning Complete |  | 10% | 26460 | Luken Solar INV-0627 | 2025-03-31 | 47351.9063 |  | 2025-03-28
6 |  | Site De-establisment |  | 10% | 67529.32 | 2025-04-03 |  |  |  | 6 | 6. AC Equipment | Site De-establisment |  | 10% | 26460 | Luken Solar INV-0634 | 2025-03-31 | 47351.9063 |  | 2025-04-10
6 |  | Handover Document Complete |  | 5% | 33764.66 | 2025-04-17 |  |  |  | 6 | 6. AC Equipment | Handover Document Complete |  | 5% | 13230 | Luken Solar INV-0635 | 2025-04-30 | 23675.9532 |  | 2025-05-08
6 |  | End of Defects Period |  | 5% | 33764.66 | 2025-07-16 |  |  |  | 6 | 6. AC Equipment | End of Defects Period |  | 5% | 13230 | Luken Solar INV-0636 | 2025-04-30 | 23675.9532 |  | 2025-05-08
7 | Battery Systems | [5 empty] | 0 | 0 |  | 7 | Battery Systems | [7 empty] | 0 |  | 0
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
7 | [9 empty] | 7
8 | Product Add On | Warranty Extension - Huawei to 10 years |  |  | 50212 | 2025-03-20 | 179212 | 190699.7268 |  | 8 | 8. Product Add On | Warranty Extension |  |  | 47930.48 | Menlo INV0002647 | 2025-02-28 | 47216.7916 | -0.0037583 | 2025-04-30 | 277324.06 | PO3706-TRIPE-20250227 - RV Approved
8 | [9 empty] | 8 | 8. Product Add On | [6 empty] | 0
8 |  | Walkways | 100 | 750 | 75000 | 2025-03-20 |  |  |  | 8 | 8. Product Add On | EZI Systems - Fall Protection |  |  | 8220 | Ezi Systems: VIN-2725 | 2025-05-31 | 5652.4189 |  | 2025-06-05 |  | PO3897-TRI-PE-20250514 - RV Approved
8 |  | Water Points | 2 | 12000 | 24000 | 2025-03-20 |  |  |  | 8 | 8. Product Add On | Walkways | 12 | 2974.66 | 35695.92 | Onvlee Eng Inv PO3723-TRID-20250306 | 2025-03-31 | 23598.3821 |  | 2025-03-13 |  | PO3723-TRIPE-20250306 - RV Approved
8 |  | Cat Ladders | 1 | 30000 | 30000 | 2025-03-20 |  |  |  | 8 | 8. Product Add On | Delivery |  |  | 500 | Onvlee Eng Inv PO3723-TRID-20250306 | 2025-03-31 | 371.2039 |  | 2025-03-13
[10 empty] | 8 | 8. Product Add On | Delivery from Cpt to PE |  |  | 2250 | Supply Chain Inv: SCO04875 | 2025-03-31 | 1670.4177 |  | 2025-04-17
8 | [9 empty] | 8 | 8. Product Add On | Walkways Fastners |  |  | 0 |  |  | 0
8 | [9 empty] | 8 | 8. Product Add On | Waterpoints | 2 |  | 25255 | BOOS NETWORK - INV QU503444 | 2025-05-31 | 4913.7038 |  | 2025-05-22 |  | PO3856-TRID-20250508 - RV Approved
8 | [9 empty] | 8 | 8. Product Add On | Walkways (moved from 14 A Christiaan) | 6 | 2974.65 | 17847.9 | Allocated from 14A Christian Ave | 2025-03-31 | 4520.1415 |  | 2025-03-31
8 | [9 empty] | 8 | 8. Product Add On | CatLadder - Supply and Install - Deposit | 50% | 67608 | 33804 | THE ENGINEERING HUB - INV/2025/02/0322 | 2025-02-28 | 25096.3558 |  | 2025-02-20 |  | PO3671-TRIPE-20250218 - RV Approved
8 | [9 empty] | 8 | 8. Product Add On | CatLadder - Supply and Install - Balance | 50% |  | 33804 | THE ENGINEERING HUB - INV/2025/03/0336 | 2025-03-31 | 25096.3558 |  | 2025-04-10
8 | [9 empty] | 8 | 8. Product Add On | Boom Lift - Waterpoints |  |  | 6982.54 | Eazi Access: CO117945 | 2025-05-31 | 4801.4892 |  | 2025-05-29
8 | [9 empty] | 8 | 8. Product Add On | Anchor Points - Deposit | 50% | 57450 | 28725 | Ezi Systems: VIN2618 | 2025-03-31 | 21325.6662 |  | 2025-04-10 |  | PO3757-TRIPE-20250319 - RV Approved
8 | [9 empty] | 8 | 8. Product Add On | Anchor Points - Balance | 50% |  | 28725 | Ezi Systems: VIN2650 | 2025-04-30 | 20898.1302 |  | 2025-05-02
8 | [9 empty] | 8 | 8. Product Add On | Stitching Screws |  |  | 1409 | Luken Inv0630 | 2025-03-31 | 1046.0527 |  | 2025-04-03
8 | [9 empty] | 8 | 8. Product Add On | Cherry Picker for additional days |  |  | 6175.22 | Luken Inv-0633 | 2025-03-31 | 4492.6215 |  | 2025-04-03
Only services to be capture below, products above
9 | AC & DC Installation | Project Kick Off |  | 10% | 36290 | 2025-01-22 | 362900 | 426941.1765 |  | 9 | 9. AC & DC installation | Project Kick Off | 351000 | 10% | 35100 | Luken Solar INV-0615 | 2025-01-31 | 42694.1176 | 0 | 2025-01-30 | 351000 | PO3580-TRIPE-2020129 - RV Approved
9 | 110200 | Site Establishment |  | 15% | 54435 | 2025-01-31 |  |  |  | 9 | 9. AC & DC installation | Site Establishment |  | 15% | 52650 | Luken Solar INV-0619 | 2025-02-28 | 64041.1765 |  | 2025-02-20
9 | 252700 | AC Installation Complete |  | 20% | 72580 | 2025-02-26 |  |  |  | 9 | 9. AC & DC installation | AC Installation Complete |  | 25% | 87750 | Luken Solar INV-0625 | 2025-02-28 | 106735.2941 |  | 2025-03-13
9 |  | DC Installation Complete |  | 25% | 90725 | 2025-02-27 |  |  |  | 9 | 9. AC & DC installation | DC Installation Complete |  | 20% | 70200 | Luken Solar INV-0625 | 2025-02-28 | 85388.2353 |  | 2025-03-13
9 |  | Commissioning Complete |  | 10% | 36290 | 2025-03-03 |  |  |  | 9 | 9. AC & DC installation | Commissioning Complete |  | 10% | 35100 | Luken Solar INV-0627 | 2025-03-31 | 42694.1176 |  | 2025-03-28
9 |  | Site De-establisment |  | 10% | 36290 | 2025-04-03 |  |  |  | 9 | 9. AC & DC installation | Site De-establisment |  | 10% | 35100 | Luken Solar INV-0634 | 2025-03-31 | 42694.1176 |  | 2025-04-10
9 |  | Handover Document Complete |  | 5% | 18145 | 2025-04-17 |  |  |  | 9 | 9. AC & DC installation | Handover Document Complete |  | 5% | 17550 | Luken Solar INV-0635 | 2025-04-30 | 21347.0588 |  | 2025-05-22
9 |  | End of Defects Period |  | 5% | 18145 | 2025-07-16 |  |  |  | 9 | 9. AC & DC installation | End of Defects Period |  | 5% | 17550 | Luken Solar INV-0636 | 2025-04-30 | 21347.0588 |  | 2025-05-08
10 | Site Logistics | [5 empty] | 57306.9667 | 67419.9608 |  | 10 | 10. Site Logistics | [6 empty] | 0 | 0 |  | 55000
10 |  | Offloading |  |  | 8500 | 2025-03-03 |  |  |  | 10 | 10. Site Logistics | [6 empty] | 0
10 |  | Storage |  |  | 5426.6667 | 2025-03-03 |  |  |  | 10 | 10. Site Logistics | Project Kick Off | 55000 | 10% | 5500 | Luken Solar INV-0615 | 2025-01-31 | 6741.9961 |  | 2025-01-30 |  | PO3580-TRIPE-2020129 - RV Approved
10 |  | Scaffolding |  |  | 43380.3 | 2025-03-03 |  |  |  | 10 | 10. Site Logistics | Site Establishment |  | 15% | 8250 | Luken Solar INV-0619 | 2025-02-28 | 10112.9941 |  | 2025-02-20
10 | [9 empty] | 10 | 10. Site Logistics | AC Installation Complete |  | 25% | 13750 | Luken Solar INV-0625 | 2025-02-28 | 16854.9902 |  | 2025-03-13
10 | [9 empty] | 10 | 10. Site Logistics | DC Installation Complete |  | 20% | 11000 | Luken Solar INV-0625 | 2025-02-28 | 13483.9922 |  | 2025-03-13
10 | [9 empty] | 10 | 10. Site Logistics | Commissioning Complete |  | 10% | 5500 | Luken Solar INV-0627 | 2025-03-31 | 6741.9961 |  | 2025-03-28
10 | [9 empty] | 10 | 10. Site Logistics | Site De-establisment |  | 10% | 5500 | Luken Solar INV-0634 | 2025-03-31 | 6741.9961 |  | 2025-04-10
10 | [9 empty] | 10 | 10. Site Logistics | Handover Document Complete |  | 5% | 2750 | Luken Solar INV-0635 | 2025-04-30 | 3370.998 |  | 2025-05-08
10 | [9 empty] | 10 | 10. Site Logistics | End of Defects Period |  | 5% | 2750 | Luken Solar INV-0636 | 2025-04-30 | 3370.998 |  | 2025-05-08
10 | [9 empty] | 10 | 10. Site Logistics | [6 empty] | 0
10 | [9 empty] | 10 | 10. Site Logistics | [6 empty] | 0
11 | Due Dilligence | Electrical PrEng sign off |  |  | 11020 | 2025-03-03 | 113060 | 133011.7647 |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 15051.69 | Sunspot Investments - E020 | 2025-04-30 | 17565.9675 | -0.0034959 | 2025-05-08 | 108556.38 | PO3805-TSP-20250415 - RV Approved
11 |  | Structural sign off |  |  | 22040 | 2025-01-29 |  |  |  | 11 | 11. Due Dilligence | Structural sign off |  |  | 8875 | L&B Inv-1845 | 2024-12-31 | 11819.5686 |  | 2025-01-16 |  | PO3480-TRID-20241122 - RV Approved
11 |  |  |  |  | 0 |  |  |  |  | 11 | 11. Due Dilligence | Grid Study - Outside of CoCT |  |  | 79700 | Okusha Electrical: Inv EE09 | 2025-04-30 | 97654.6717 |  | 2025-07-29 |  | PO3685-TSP-20250220 - RV Approved
11 |  | Grid Study - Outside of CoCT |  |  | 80000 | 2025-03-03 |  |  |  | 11 | 11. Due Dilligence | Red Team inspection |  |  | 3020.73 | Gerhard's travel Pd with TVH CC | 2025-02-28 | 3627.2634 |  | 2025-03-06
11 | [9 empty] | 11 | 11. Due Dilligence |  |  |  | 1908.96 | Gerhard's travel Pd with TVH CC | 2025-03-31 | 2344.2971 |  | 2025-03-31
12 | BDP Commission | Referral Fee |  |  | 45272.6717 | 2025-04-10 | 45272.6717 | 0 |  | 12 | BDP Commission | Referral Fee |  |  | 0 | [5 empty] | 0
12 | BDP Commission | [8 empty] | 12 | BDP Commission
13 | Engineering | Matriarch Defects Period |  |  | 40345.4621 | 2025-04-10 | 162452.6621 | 184605.2978 |  | 13 | 13. Engineering | Matriarch Defects Period |  |  | 48485.243 | Matriarch - INV-4067 | 2025-03-31 | 184605.2978 | 0 | 2025-03-31 | 134885.243
13 |  | Management |  |  | 17600 | 2025-04-10 |  |  |  | 13 | 13. Engineering | MAM Performance Gaurantee |  |  | 86400 | Matriarch - INV-4997 | 2025-08-31 |  |  | 221216
13 |  | Project manager |  |  | 59840 | 2025-04-10 |  |  |  | 13 | 13. Engineering | Project manager |  |  | 0 |  | 2025-03-31 | 0 |  | 2025-03-31
13 |  | Planner time |  |  | 22880 | 2025-04-10 |  |  |  | 13 | 13. Engineering | Planner time |  |  | 0 |  | 2025-03-31 | 0 |  | 2025-03-31
13 |  | De Snagging |  |  | 21787.2 | 2025-04-10 |  |  |  | 13 | 13. Engineering | De Snagging |  |  | 0 |  | 2025-03-31 | 0 |  | 2025-03-31
13 | [9 empty] | 13 | 13. Engineering
13 | [9 empty] | 13 | 13. Engineering
14 | General Expenses | Car travel to site |  |  | 7700 | 2025-04-10 | 7700 | 9058.8235 |  | 14 | 14. General Expenses | Travel to site |  |  | 400.97 | Expense Claims | 2024-12-31 | 588.137 | 0.00038103 | 2025-01-09 | 7150.4
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 2128.93 | Expense Claims | 2025-01-31 | 3022.8689 |  | 2025-02-07
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 736.33 | Expense Claims | 2025-02-28 | 1284.9139 |  | 2025-03-07
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 2532.89 | Expense Claims | 2025-03-31 | 1905.2654 |  | 2025-04-04
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 1179.92 | Expense Claims | 2025-04-30 | 892.2824 |  | 2025-05-07
14 | [9 empty] | 14 | 14. General Expenses |  |  |  | 171.36 | Expense Claims | 2025-05-31 | 1365.3555 |  | 2025-06-09
15 | Service Add On | [5 empty] | 0 | 0 |  | 15 | 15. Service Add On | [7 empty] | 0 |  | 0
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
3878819.4402
Note on W116: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update payment date
Note on W117: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mizelda Isaacs please update the payment date

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2024-11-04 to 2026-07-13
PLANNED |  | CHECK | CHECK
| Planned Revenue | 3878819.44 | 3878819.44 | 0 | 0 | 1357586.804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1939409.72 | 0 | 0 | 0 | 387881.944 | 0 | 0 | 0 | 0 | 0 | 0 | 193940.972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 1357586.804 | 1357586.804 | 1357586.804 | 1357586.804 | 1357586.804 | 1357586.804 | 1357586.804 | 1357586.804 | 1357586.804 | 1357586.804 | 1357586.804 | 3296996.524 | 3296996.524 | 3296996.524 | 3296996.524 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44
| Planned Expenditure | 3622274.3004 | 3622274.3004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124686.92 | 209070.38 | 0 | 0 | 0 | 1184211.14 | 273013.8867 | 125000 | 179212 | 0 | 132686.92 | 1269706.1338 | 62343.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62343.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124686.92 | 333757.3 | 333757.3 | 333757.3 | 333757.3 | 1517968.44 | 1790982.3267 | 1915982.3267 | 2095194.3267 | 2095194.3267 | 2227881.2467 | 3497587.3804 | 3559930.8404 | 3559930.8404 | 3559930.8404 | 3559930.8404 | 3559930.8404 | 3559930.8404 | 3559930.8404 | 3559930.8404 | 3559930.8404 | 3559930.8404 | 3559930.8404 | 3559930.8404 | 3559930.8404 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004 | 3622274.3004
| PLANNED CashFlow |  |  | 0 | 0 | 1357586.804 | 1357586.804 | 1357586.804 | 1357586.804 | 1357586.804 | 1357586.804 | 1357586.804 | 1357586.804 | 1357586.804 | 1232899.884 | 1023829.504 | 2963239.224 | 2963239.224 | 2963239.224 | 1779028.084 | 1893896.1413 | 1768896.1413 | 1589684.1413 | 1589684.1413 | 1456997.2213 | 187291.0876 | 124947.6276 | 318888.5996 | 318888.5996 | 318888.5996 | 318888.5996 | 318888.5996 | 318888.5996 | 318888.5996 | 318888.5996 | 318888.5996 | 318888.5996 | 318888.5996 | 318888.5996 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396 | 256545.1396
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 3878819.44 | 3878819.44 | 0 | 0 | 0 | 0 | 0 | 0 | 1357586.804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1939409.72 | 0 | 0 | 0 | 0 | 387881.944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193940.972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1357586.804 | 1357586.804 | 1357586.804 | 1357586.804 | 1357586.804 | 1357586.804 | 1357586.804 | 1357586.804 | 3296996.524 | 3296996.524 | 3296996.524 | 3296996.524 | 3296996.524 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3684878.468 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44 | 3878819.44
| Actual + Planned Expenditure | 3227541.703 | 3027102.163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400.97 | 8875 | 0 | 153669.5 | 2128.93 | 0 | 556375.41 | 161729.8 | 3757.06 | 378465.92 | 0 | 205160 | 111397.463 | 138589 | 1003524.3 | 11217.7 | 90715.48 | 74741.61 | 0 | 42805 | 6982.54 | 8220 | 171.36 | 0 | 0 | 0 | 0 | 0 | 0 | 79700 | 0 | 0 | 0 | -11524.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400.97 | 9275.97 | 9275.97 | 162945.47 | 165074.4 | 165074.4 | 721449.81 | 883179.61 | 886936.67 | 1265402.59 | 1265402.59 | 1470562.59 | 1581960.053 | 1720549.053 | 2724073.353 | 2735291.053 | 2826006.533 | 2900748.143 | 2900748.143 | 2943553.143 | 2950535.683 | 2958755.683 | 2958927.043 | 2958927.043 | 2958927.043 | 2958927.043 | 2958927.043 | 2958927.043 | 2958927.043 | 3038627.043 | 3038627.043 | 3038627.043 | 3038627.043 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163 | 3027102.163
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1357586.804 | 1357586.804 | 1357586.804 | 1357185.834 | 1348310.834 | 1348310.834 | 1194641.334 | 1192512.404 | 3131922.124 | 2575546.714 | 2413816.914 | 2410059.854 | 2031593.934 | 2419475.878 | 2214315.878 | 2102918.415 | 1964329.415 | 960805.115 | 949587.415 | 858871.935 | 784130.325 | 784130.325 | 741325.325 | 734342.785 | 726122.785 | 725951.425 | 725951.425 | 725951.425 | 725951.425 | 725951.425 | 725951.425 | 725951.425 | 646251.425 | 646251.425 | 646251.425 | 646251.425 | 657776.305 | 657776.305 | 657776.305 | 657776.305 | 657776.305 | 657776.305 | 657776.305 | 657776.305 | 657776.305 | 657776.305 | 657776.305 | 657776.305 | 657776.305 | 657776.305 | 657776.305 | 657776.305 | 657776.305 | 657776.305 | 657776.305 | 657776.305 | 657776.305 | 657776.305 | 657776.305 | 657776.305 | 657776.305 | 657776.305 | 851717.277 | 851717.277 | 851717.277 | 851717.277 | 851717.277 | 851717.277 | 851717.277 | 851717.277 | 851717.277 | 851717.277 | 851717.277 | 851717.277 | 851717.277 | 851717.277 | 851717.277 | 851717.277 | 851717.277 | 851717.277 | 851717.277 | 851717.277 | 851717.277
|  | CHECK | CHECK
| Revenue Recognition | -0.00020125 | 3878819.4402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12407.7056 | 0 | 0 | 0 | 2102342.0758 | 0 | 0 | 0 | 967202.4165 | 0 | 0 | 0 | 0 | 537193.7779 | 0 | 0 | 0 | 242940.4971 | 0 | 0 | 0 | 16732.9674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 3878819.4402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12407.7056 | 12407.7056 | 12407.7056 | 12407.7056 | 2114749.7813 | 2114749.7813 | 2114749.7813 | 2114749.7813 | 3081952.1978 | 3081952.1978 | 3081952.1978 | 3081952.1978 | 3081952.1978 | 3619145.9758 | 3619145.9758 | 3619145.9758 | 3619145.9758 | 3862086.4728 | 3862086.4728 | 3862086.4728 | 3862086.4728 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402 | 3878819.4402
| Installer Expenditure |  | 705600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70560 | 0 | 0 | 105840 | 0 | 0 | 317520 | 0 | 70560 | 0 | 70560 | 0 | 0 | 0 | 53010 | 0 | 17550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Installer Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70560 | 70560 | 70560 | 176400 | 176400 | 176400 | 493920 | 493920 | 564480 | 564480 | 635040 | 635040 | 635040 | 635040 | 688050 | 688050 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600 | 705600

## Finance - Revenue
REVENUE RECOGNITION AMOUNT | (All)
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels |  | (blank) | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-08-31 | Grand Total
(blank)
Battery Systems
BDP Commission
1. Panels | 0 |  |  | 1109432.159 | 12429.4383 |  |  |  |  | 1121861.5973
2. Inverters | 0 | 0 |  | 297948.3713 | [5 empty] | 297948.3713
3. Mounting Structures |  |  |  | 164169.5526 |  |  |  |  | 0 | 164169.5526
4. DC Equipment |  |  |  | 286081.6529 | 65863.2216 | 18282.8505 | 9141.4253 |  |  | 379369.1502
5. Monitoring |  | 0 |  | 56155.5396 | 74638.9015 | 54359.1858 |  |  |  | 185153.6269
6. AC Equipment | 0 |  |  | 136095.8178 | 440428.8482 | 94703.8126 | 47351.9063 |  |  | 718580.3849
8. Product Add On | 0 | 0 |  |  | 72313.1473 | 82120.8413 | 20898.1302 | 15367.6118 |  | 190699.7306
9. AC & DC installation |  |  |  | 42694.1176 | 256164.7059 | 85388.2353 | 42694.1176 |  |  | 426941.1765
10. Site Logistics | 0 |  |  | 6741.9961 | 40451.9765 | 13483.9922 | 6741.9961 |  |  | 67419.9608
11. Due Dilligence |  |  | 11819.5686 |  | 3627.2634 | 2344.2971 | 115220.6391 |  |  | 133011.7682
13. Engineering | [5 empty] | 184605.2978 |  |  |  | 184605.2978
14. General Expenses |  |  | 588.137 | 3022.8689 | 1284.9139 | 1905.2654 | 892.2824 | 1365.3555 |  | 9058.8231
15. Service Add On
Grand Total | 0 | 0 | 12407.7056 | 2102342.0758 | 967202.4165 | 537193.7779 | 242940.4971 | 16732.9674 | 0 | 3878819.4402
|  |  | 12407.71 | 2102342.08 | 975406.72 | 537285.69 | 242940.5 | 16732.97 | 3887115.67
3878819.44
-3887115.67
-8296.23

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) |  | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-08-31 | Grand Total
Battery Systems
BDP Commission | 0 | [8 empty] | 0
(blank)
1. Panels |  |  |  | 1001274.3 | 11217.7 |  |  |  |  | 1012492
2. Inverters |  |  |  | 275481.41 | [5 empty] | 275481.41
3. Mounting Structures |  |  |  | 63211.8 |  |  |  |  | 12415.12 | 75626.92
4. DC Equipment |  |  |  | 248400 | 98100 | 18000 | 9000 |  | -23940 | 349560
5. Monitoring | 0 |  |  | 46828.04 | 85508.25 | 46590 |  |  |  | 178926.29
6. AC Equipment |  | 0 |  | 81731.5 | 240427.5 | 52920 | 26460 |  |  | 401539
8. Product Add On | 0 |  |  |  | 81734.48 | 126407.04 | 28725 | 40457.54 |  | 277324.06
9. AC & DC installation |  |  |  | 35100 | 210600 | 70200 | 35100 |  |  | 351000
10. Site Logistics |  |  |  | 5500 | 33000 | 11000 | 5500 |  |  | 55000
11. Due Dilligence |  |  | 8875 |  | 3020.73 | 1908.96 | 94751.69 |  |  | 108556.38
13. Engineering | [5 empty] | 48485.243 |  |  | 86400 | 134885.243
14. General Expenses |  |  | 400.97 | 2128.93 | 736.33 | 2532.89 | 1179.92 | 171.36 |  | 7150.4
15. Service Add On
Grand Total | 0 | 0 | 9275.97 | 1759655.98 | 764344.99 | 378044.133 | 200716.61 | 40628.9 | 74875.12 | 3227541.703

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | 280000 | 0 | 280000 | 0 | 280000
Inverters | 280000
Optimizers | 0
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | 154280 | 0 | 154280 | 0 | 154280
Mounting Structure | 154280
Delivery fee
|  | >Name< |  | >Name<
DC Cable | 147840 | 0 | 147840 | 0 | 147840
DC Cable | 147840
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
Smartlogger 3000 | 26000
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | 50212 | 0 | #REF! | 0 | #REF!
SCADA | 50212
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | 675293.2 | 1.5348 | 277892.91 | 0.63157 | 397400.29 |  | 0 | 675293.2
DC Equipment | 208676 | 0.47426 | 142158.25 | 0.32309 | 66517.75 |  | 0 | 208676
AC Labour | 252700 | 0.57432 | 96174 | 0.21858 | 156526 |  | 0 | 252700
DC Labour | 110200 | 0.25045 | 230160 | 0.52309 | -119960 |  | 0 | 110200
Offloading | 8500 |  | 0 |  | 8500 |  |  | 8500
Roof Access/Scaffolding | 43380.3 |  | 29257.61 |  | 14122.69 |  |  | 43380.3
Storage | 5426.6667 |  |  |  | 5426.6667 |  |  | 5426.6667
Telehandler | 0
HSE | 0
Totals | 1304176.1667 |  | 775642.77 |  | 528533.3967 | 0 |  | 1304176.1667
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | 675293.2
AC equipment | 0 | 0 |  |  | 0 |  | 0 | 208676
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | 252700
DC equipment | 20867.6 | 0.047426 |  |  | 20867.6 |  |  | 110200
Storage | 0 |  |  |  | 0 |  |  | 8500
Panel lifting equipment | 13926.6667 |  |  |  | 13926.6667 |  |  | 43380.3
Offloading | 0 |  |  |  | 0 |  |  | 5426.6667
Totals | #REF! |  | 0 |  | #REF! | 0 |  | 1304176.1667
Budget Summary
Budget | 1304176.1667
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
Loss | 1304176.1667
All amounts are exc VAT

## Decision Register (hidden)
Trident Steel PE |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Trident Steel PE | 0 | 0 | 0