## Sheet1 (hidden)
PROJECT PLAN
# | Project Milestone | Planned Start Date | Duration (Work Days) | Planned End Date | Actual Start Date |  | Actual End Date | Comments | time axis 2020-01-01 to 2020-09-30
1 | Contract Signature | 2020-01-01 | 1 | 2020-01-02 | 2020-01-01 | 1 | 2020-01-02 |  | 2020-01-01: 3
A | PAYMENT MILESTONE 1: DEPOSIT | 2020-01-02 | 1 | 2020-01-03 | 2020-01-02 | 1 | 2020-01-03 | bar: 2020-01-01
2 | Structural and Electrical Due Diligences | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
3 | Design Confirmation | 2020-01-11 | 2 | 2020-01-14 | 2020-01-11 | 2 | 2020-01-14 |  | 2020-01-11: 3
4 | Equipment Procurement | 2020-01-03 |  | 2020-04-28 | 2020-01-03 |  | 2020-04-28 |  | 2020-01-01: 1; 2020-01-04: 2; 2020-01-11: 2; 2020-01-18: 2; 2020-01-25: 2; 2020-01-31: 2; 2020-02-01: 2; 2020-02-08: 2; 2020-02-15: 2; 2020-02-22: 2; 2020-02-28: 2; 2020-03-06: 2; 2020-03-13: 2; 2020-03-20: 2; 2020-03-27: 2; 2020-03-30: 2; 2020-04-03: 2; 2020-04-10: 2; 2020-04-17: 2; 2020-04-24: 3
| Panel Procurement | 2020-01-03 | 5 | 2020-01-10 | 2020-01-03 | 5 | 2020-01-10 |  | 2020-01-01: 1; 2020-01-04: 3
| Inverter Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| Mounting Structure Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
| BOS Procurement | 2020-04-20 | 5 | 2020-04-28 | 2020-04-20 | 5 | 2020-04-28 |  | 2020-04-17: 1; 2020-04-24: 3
5 | Internal Project Kick off | 2020-04-15 | 5 | 2020-04-22 | 2020-04-15 | 5 | 2020-04-22
6 | Client Project Kick-off | 2020-05-12 | 5 | 2020-05-19 | 2020-05-12 | 5 | 2020-05-19 |  | 2020-05-09: 1; 2020-05-16: 3
7 | Equipment Delivery | 2020-06-01 | 9 | 2020-06-12 | 2020-06-01 | 9 | 2020-06-12 |  | 2020-05-30: 1; 2020-05-31: 1; 2020-06-06: 3
| Mounting Structure Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
| Panel Delivery | 2020-06-08 | 2 | 2020-06-10 | 2020-06-08 | 2 | 2020-06-10 | bar: 2020-06-06
| Generator Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03
B | PAYMENT MILESTONE 2: DELIVERY OF PV PANELS | 2020-06-10 | 2 | 2020-06-12 | 2020-06-10 | 2 | 2020-06-12
| Inverter Delivery | 2020-06-01 | 2 | 2020-06-03 | 2020-06-01 | 2 | 2020-06-03 | bar: 2020-05-30 to 2020-05-31
| BOS Delivery | 2020-06-01 | 1 | 2020-06-02 | 2020-06-01 | 1 | 2020-06-02 | bar: 2020-05-30 to 2020-05-31
C | PAYMENT MILESTONE 3: DELIVERY OF INVERTERS AND BOS | 2020-06-03 | 2 | 2020-06-05 | 2020-06-03 | 2 | 2020-06-05
8 | Installation | 2020-06-08 | 22 | 2020-06-30 | 2020-06-08 | 22 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Site Establishment | 2020-06-08 | 1 | 2020-06-09 | 2020-06-08 | 1 | 2020-06-09 | Installation placed on hold due to Covid-19 case | bar: 2020-06-06
9 | DC Works | 2020-06-09 | 16 | 2020-06-30 | 2020-06-09 | 16 | 2020-06-30 |  | 2020-06-06: 1; 2020-06-13: 2; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 2
| Mounting structure Installation | 2020-06-09 | 4 | 2020-06-15 | 2020-06-09 | 4 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Cable tray Installation | 2020-06-15 | 3 | 2020-06-22 | 2020-06-15 | 3 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
| DC Cable Installation | 2020-06-22 | 2 | 2020-06-24 | 2020-06-22 | 2 | 2020-06-24 | bar: 2020-06-20
| Module Installation | 2020-06-24 | 4 | 2020-06-30 | 2020-06-24 | 4 | 2020-06-30 |  | 2020-06-20: 1; 2020-06-27: 3; 2020-06-30: 2
| Earth Cable Installation | 2020-06-22 | 1 | 2020-06-23 | 2020-06-22 | 1 | 2020-06-23 | bar: 2020-06-20
10 | AC Works | 2020-06-09 | 8 | 2020-06-18 | 2020-06-09 | 8 | 2020-06-18
| Inverters Installation | 2020-06-09 | 2 | 2020-06-11 | 2020-06-09 | 2 | 2020-06-11 | bar: 2020-06-06
| AC BOS Installation | 2020-06-11 | 3 | 2020-06-18 | 2020-06-11 | 3 | 2020-06-18 |  | 2020-06-06: 1; 2020-06-13: 3
| AC Cable/Tie-In | 2020-06-10 | 3 | 2020-06-15 | 2020-06-10 | 3 | 2020-06-15 |  | 2020-06-06: 1; 2020-06-13: 3
| Monitoring Platform Installation | 2020-06-15 | 1 | 2020-06-18 | 2020-06-15 | 1 | 2020-06-18
11 | Completion | 2020-06-18 | 14 | 2020-07-02 | 2020-06-18 | 14 | 2020-07-02 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 3; 2020-06-30: 3
| DC Works | 2020-06-30 | 2 | 2020-07-02 | 2020-06-30 | 2 | 2020-07-02 |  | 2020-06-27: 1; 2020-06-30: 3
| AC Works | 2020-06-18 | 2 | 2020-06-22 | 2020-06-18 | 2 | 2020-06-22 |  | 2020-06-13: 1; 2020-06-20: 3
D | PAYMENT MILESTONE 4: PRACTICAL COMPLETION | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
12 | Commissioning | 2020-06-15 | 22 | 2020-07-07 | 2020-06-15 | 22 | 2020-07-07 |  | 2020-06-13: 1; 2020-06-20: 2; 2020-06-27: 2; 2020-06-30: 2
| Snag List | 2020-07-02 | 3 | 2020-07-07 | 2020-07-02 | 3 | 2020-07-07
| Pre-Commissioning Checks | 2020-06-28 | 2 | 2020-06-30 | 2020-06-28 | 2 | 2020-06-30
| Issue CoC | 2020-06-15 | 2 | 2020-06-19 | 2020-06-15 | 2 | 2020-06-19 | bar: 2020-06-13
| Cold Commissioning | 2020-06-30 | 1 | 2020-07-01 | 2020-06-30 | 1 | 2020-07-01 |  | 2020-06-27: 1; 2020-06-30: 3
| Hot Commissioning | 2020-07-01 | 2 | 2020-07-03 | 2020-07-01 | 2 | 2020-07-03 | bar: 2020-06-27 to 2020-06-30
13 | Handover | 2020-07-08 | 1 | 2020-07-09 | 2020-07-08 | 1 | 2020-07-09
E | PAYMENT MILESTONE 6: HANDOVER COMPLETE | 2020-07-10 | 1 | 2020-07-13 | 2020-07-10 | 1 | 2020-07-13
|  | 43831 | These numbers are used to set the start and end dates on the Gantt Chart
44014
Note on B2: Robert: taken directly from the contract
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These will calculate based on the start date and duration of the event
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually during the course of the project
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be entered manually
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The AC tie-in and Monitoring Platform installation must be completed wihin 7 days of project start date

## Compliance
HSE
Description | Status | Approved By | Date | Results / Comments
NOC
7.1 Agreement
13.2 Agreement
EE File
Subbie File
SSEG
Description | Status | Approved By | Date | Results / Comments
SSEG Application
PTI
Commissioning Approval

## Project Plan
[9 empty] | 2026-03-06 | 2026-03-06
| PROJECT PLAN | Cassia | [6 empty] | 0 | 1
| PROJECT SIZE (kWp) | 50
| PROJECT DEVELOPER | Dayne Sage
| PROJECT MANAGERS | Amanda Gadla
| CONTRACT VALUE | 261790.45
| Phase: | Commercial Close Out
No. | HIGH LEVEL PROGRAMME | Planned Start | Duration (days) | Planned End | Actual Start | Duration (days) | Actual End | Status |  | Comment
100%
1 | Project Activities | 2025-03-28 | 46 | 2025-05-13 | 2025-03-28 | 48 | 2025-05-15 | 100% | 48
1.1 | PD Handover | 2025-03-28 | 1 | 2025-03-31 | 2025-03-28 | 1 | 2025-03-31 | 100%
1.2 | HSE | 2025-03-31 | 2 | 2025-04-02 | 2025-03-31 | 2 | 2025-04-02 | 100%
1.3 | Material Procurement | 2025-03-28 | 1 | 2025-03-31 | 2025-03-28 | 1 | 2025-03-31 | 100%
1.4 | Site Establishment | 2025-03-31 | 1 | 2025-04-01 | 2025-03-31 | 1 | 2025-04-01 | 100%
1.5 | Material Delivery | 2025-04-01 | 1 | 2025-04-02 | 2025-04-01 | 1 | 2025-04-02 | 100%
1.6 | Construction | 2025-04-02 | 10 | 2025-04-16 | 2025-04-02 | 10 | 2025-04-16 | 100%
1.7 | System Energised | 2025-04-16 | 1 | 2025-04-17 | 2025-04-16 | 1 | 2025-04-17 | 100%
1.8 | O&M Monitoring | 2025-04-17 | 5 | 2025-04-28 | 2025-04-17 | 5 | 2025-04-28 | 100%
1.9 | Red Team Inspection | 2025-04-17 | 2 | 2025-04-23 | 2025-04-17 | 2 | 2025-04-23 | 100%
1.10 | Snag Completion | 2025-04-23 | 3 | 2025-04-28 | 2025-04-23 | 3 | 2025-04-28 | 100%
1.11 | PrEng Sign off | 2025-04-28 | 2 | 2025-04-30 | 2025-04-28 | 2 | 2025-04-30 | 100%
1.18 | Handover Documentation | 2025-04-30 | 5 | 2025-05-08 | 2025-04-30 | 5 | 2025-05-08 | 100%
1.19 | O&M Handover | 2025-05-08 | 2 | 2025-05-12 | 2025-05-08 | 2 | 2025-05-12 | 100%
1.20 | Client Handover | 2025-05-12 | 1 | 2025-05-13 | 2025-05-14 | 1 | 2025-05-15 | 100%
Formulas:
Planned Start = MIN([Planned Start, row below]:E25)
Planned Start = WORKDAY.INTL([Planned End, row above],0,1,Data!$C3:C14)
Planned End = MAX([Planned End, row below]:G25)
Planned End = WORKDAY.INTL([Planned Start],[Duration (days)],1,Data!$C3:C14)
Actual Start = MIN([Actual Start, row below]:I25)
Actual Start = WORKDAY.INTL([Actual End, row above],0,1,Data!$C3:C14)
Actual End = MAX([Actual End, row below]:K25)
Actual End = WORKDAY.INTL([Actual Start],[Duration (days)],1,Data!$C3:C14)

## Revenue Tracking
HIGH LEVEL PROJECT REVENUE TRACKING
|  | COSTED |  | ACTUAL |  | FINANCIAL REVIEW | TIMELINE REVIEW
1 | Planned Revenue | 261790.45 |  | 261790.45 |  |  | Start Date
2 | Planned Expenditure | 210304.07 |  | 183007.37
3 | Planned Profit | 51486.38 |  | 78783.08 |  |  | End Date - PC
4 | Planned Margin | 19.67% |  | 30.09%
CONTRACT
No. | PAYMENT MILESTONE |  | % | VALUE | PLANNED PAYMENT DATE | INVOICE NUMBER | INVOICE RAISED DATE | PAYMENT RECEIVED DATE | MILESTONE NOTES & COMMENTS
1 | Deposit |  |  | 21815.8708 | 2025-06-17 | 004744 | 2025-05-19 | 2025-06-17
2 | Hanodver |  |  | 21815.8708 | 2025-07-14 | 004744 | 2025-05-19 | 2025-07-14
3 | - |  |  | 21815.8708 | 2025-08-18 | 004744 | 2025-05-19 | 2025-08-18
4 | - |  |  | 21815.8708 | 2025-09-16 | 004744 | 2025-05-19 | 2025-09-16
5 | - |  |  | 21815.8708 | 2025-10-15 | 004744 | 2025-05-19 | 2025-10-17
6 | - |  |  | 21815.8708 | 2025-11-15 | 004744 | 2025-05-19 | 2025-12-01
7 | - |  |  | 21815.8708 | 2025-12-15 | 004744 | 2025-05-19 | 2025-12-17
8 | - |  |  | 21815.8708 | 2026-01-15 | 004744 | 2025-05-19 | 2026-01-15
9 | - |  |  | 21815.8708 | 2026-02-15 | 004744 | 2025-05-19 | 2026-02-23
10 | - |  |  | 21815.8708 | 2026-03-15 | 004744 | 2025-05-19 | 2026-03-15
11 | - |  |  | 21815.8708 | 2026-04-15 | 004744 | 2025-05-19 | 2026-04-15
12 | - |  | 0% | 21815.8708 | 2026-05-15 | 004744 | 2025-05-19 | 2026-05-15
|  |  | 0% | 261790.45
KEY: | contains an error (in result or a check has failed)
Red Font - IF TEXT : content not yet confirmed
Red Font - IF NUMBER: Negative value
Anything in yellow is a concern or risk for noting or action
confirmed
[ADD INITIALS: comment for noting in square brackets, use colour or red to draw attention if important]
[RT: When adding rows into sheet, ensure you insert between first and last row of each category]
end of sheet - do not insert information below/beyond this
No. | PAYMENT MILESTONE |  | % | VALUE
1 | Deposit - Project commencement |  | 35% | 91626.6575
2 | Delivery of Panels |  | 30% | 78537.135
3 | Delivery of Inverters |  | 20% | 52358.09
4 | Practical Completion |  | 10% | 26179.045
5 | Handover |  | 5% | 13089.5225
| Total |  | 100% | 261790.45
|  |  | 100% | 261790.45

## Expenditure Tracking
HIGH LEVEL PROJECT EXPENDITURE TRACKING
|  | COSTED |  | ACTUAL | Difference from costed
EXPENDITURE |  | 210304.07 |  | 183007.37 | 27296.7
No. | Item | Costed Expenditure |  | Actual Expenditure | Saving / Overrun | Comments on variations from planned expenditure
1 | 1. Panels | 0 |  | 0 | 0
2 | 2. Inverters | 0 |  | 0 | 0
3 | 3. Mounting Structures | 0 |  | 0 | 0
4 | 4. DC Equipment | 0 |  | 0 | 0
5 | 5. Monitoring | 0 |  | 0 | 0
6 | 6. AC Equipment | 23485.1 |  | 44635.5 | -21150.4
7 | 7.BESS | 0 |  | 0 | 0
8 | 8. Product Add On | 172000 |  | 73999.62 | 98000.38
9 | 9. AC & DC installation | 14818.97 |  | 64015.25 | -49196.28
10 | 10. Site Logistics | 0 |  | 0 | 0
11 | 11. Due Dilligence | 0 |  | 0 | 0
12 | 12. BDP Commission | 0 |  | 0 | 0
13 | 13. Engineering | 0 |  | 0 | 0
14 | 14. General Expenses | 0 |  | 357 | -357
15 | 15. Service Add On | 0 |  | 0 | 0
| check: | 0 | #REF! | 0

## Data (hidden)
Public holidays |  | Drop down list
2025-01-01 | New Years Day | Approved
2025-03-21 | Human Rights day | Pending
2025-04-18 | Good Friday | Declined
2025-04-21 | Family Day | Abanded
2025-04-27 | Freedom Day
2025-04-18 | Freedom DayObserved
2025-05-01 | Workers day
2025-06-16 | Youth Day Holiday
2025-08-09 | Womens Day
2025-09-24 | Heritage Day
2025-12-16 | Day of Reconciliation |  | Manual dates
2025-12-25 | Christmas Day
2025-12-26 | Day of Goodwill

## Expenditure Breakdown
COSTED EXPENDITURE BREAKDOWN | [6 empty] | 210304.07 | 261790.45 |  | ACTUAL EXPENDITURE BREAKDOWN | [5 empty] | FINANCE ONLY | [5 empty] | 183007.37
No. | Product / Service | Description of Work | QTY | Rate / Unit | Budget Total | FINANCE PAYMENT DATE | Total COS | ERROR on REV |  | No. | Product/ Service | Description of Work | QTY | Rate / Unit | Actual Total | PO NUMBER | INVOICE NUMBER | INVOICE RAISED DATE | REVENUE RECOGNITION AMOUNT | CHECK | FINANCE PAYMENT DATE | Total COS
1 | Panels | [5 empty] | 0 |  |  | 1 | 1. Panels | [10 empty] | 0
1 | [9 empty] | 1 | 1. Panels
1 | [9 empty] | 1 | 1. Panels
1 | [9 empty] | 1 | 1. Panels
1 | [9 empty] | 1 | 1. Panels
1 | [9 empty] | 1 | 1. Panels | [11 empty] | BUDGET | Installer Allocation
[23 empty] | AC Equipment | 23485.1
2 | Inverters | [5 empty] | 0 |  |  | 2 | 2. Inverters | [8 empty] | 0 |  | 0 | DC Equipment | 0
2 | [9 empty] | 2 | 2. Inverters | [11 empty] | AC Labour | 4500
2 | [9 empty] | 2 | 2. Inverters | [11 empty] | DC Labour | 10318.97
2 | [9 empty] | 2 | 2. Inverters | [11 empty] | Offloading | 0
2 | [9 empty] | 2 | 2. Inverters | [11 empty] | Scaffolding | 0
2 | [9 empty] | 2 | 2. Inverters | [11 empty] | Storage | #REF!
2 | [9 empty] | 2 | 2. Inverters | [11 empty] | Telehandler | 0
3 | Mounting Structures | [5 empty] | 0 |  |  | 3 | 3. Mounting Structures | [8 empty] | 0 |  | 0 | Other | 0
3 | [9 empty] | 3 | 3. Mounting Structures | [11 empty] | Total | #REF!
3 | [9 empty] | 3 | 3. Mounting Structures | [11 empty] | Less 15% | #REF!
3 | [9 empty] | 3 | 3. Mounting Structures | [11 empty] | R/Wp | 0
3 | [9 empty] | 3 | 3. Mounting Structures
3 | [9 empty] | 3 | 3. Mounting Structures | [11 empty] | ACTUAL | Installer Price
[23 empty] | AC Equipment | 137643.8957
4 | DC Equipment | [5 empty] | 0 |  |  | 4 | 4. DC Equipment | [8 empty] | 0 |  | 0 | DC Equipment | 68844.4
4 | [9 empty] | 4 | 4. DC Equipment | [11 empty] | AC Labour | 11655
4 | [9 empty] | 4 | 4. DC Equipment | [11 empty] | DC Labour | 27930
4 | [9 empty] | 4 | 4. DC Equipment | [11 empty] | Offloading | 8500
4 | [9 empty] | 4 | 4. DC Equipment | [11 empty] | Scaffolding | 17008.5
4 | [9 empty] | 4 | 4. DC Equipment | [11 empty] | Storage | #REF!
4 | [9 empty] | 4 | 4. DC Equipment | [11 empty] | Telehandler | 0
4 | [9 empty] | 4 | 4. DC Equipment | [11 empty] | HSE | 0
4 | [9 empty] | 4 | 4. DC Equipment | [11 empty] | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | [11 empty] | Other | 0
4 | [9 empty] | 4 | 4. DC Equipment | [11 empty] | Total | #REF!
4 | [9 empty] | 4 | 4. DC Equipment | [11 empty] | R/Wp | 0
4 | [9 empty] | 4 | 4. DC Equipment
4 | [9 empty] | 4 | 4. DC Equipment
4 | [9 empty] | 4 | 4. DC Equipment
5 | Monitoring | [5 empty] | 0 |  |  | 5 | 5. Monitoring | [8 empty] | 0 |  | 0
5 | [9 empty] | 5 | 5. Monitoring
5 | [9 empty] | 5 | 5. Monitoring
5 | [9 empty] | 5 | 5. Monitoring
5 | [9 empty] | 5 | 5. Monitoring
5 | [9 empty] | 5 | 5. Monitoring
5 | [9 empty] | 5 | 5. Monitoring
6 | AC Equipment | AC Equipment Budget |  |  | 23485.1 | 2025-04-03 | 23485.1 | 29356.37 |  | 6 | 6. AC Equipment | Inverter Upgrade - Deposit | 44635.5 | 50% | 22317.75 | PO3777-CASS-20250331 - RV Approved | HappySolar - INV-0300 | 2025-04-30 | 14678.185 | 0 | 2025-04-03 | 44635.5
6 | [5 empty] | 2025-04-17 |  |  |  | 6 | 6. AC Equipment | Equipment Onsite |  | 25% | 11158.875 |  | HappySolar - INV-0303 | 2025-04-30 | 7339.0925 |  | 2025-04-17
6 | [5 empty] | 2025-04-17 |  |  |  | 6 | 6. AC Equipment | AC & DC Complete |  | 20% | 8927.1 |  | HappySolar - INV-0304 | 2025-04-30 | 5871.274 |  | 2025-04-17
6 | [5 empty] | 2025-06-05 |  |  |  | 6 | 6. AC Equipment | Retention |  | 5% | 2231.775 |  | HappySolar - INV-0312 | 2025-05-31 | 1467.8185 |  | 2025-06-05
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
6 | [9 empty] | 6 | 6. AC Equipment | [7 empty] | 0
7 | BESS | [5 empty] | 0 |  |  | 7 | 7.BESS | [8 empty] | 0 |  | 0
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
7 | [9 empty] | 7 | 7.BESS
8 | Product Add On | Installation of 2 new inverters and some AC wiring at Cassia Restaurant |  |  | 150000 | 2025-04-03 | 172000 | 215000 |  | 8 | 8. Product Add On | Inverter Upgrade - Deposit | 19440.5 | 50% | 9720.25 | PO3777-CASS-20250331 - RV Approved | HappySolar - INV-0300 | 2025-04-30 | 28241.4119 | 0 | 2025-04-03 | 73999.62
8 |  | Smart Logger and Commissioning at Cassia |  |  | 22000 | 2025-04-17 |  |  |  | 8 | 8. Product Add On | Equipment Onsite |  | 25% | 4860.125 |  | HappySolar - INV-0303 | 2025-04-30 | 14120.706 |  | 2025-04-17
8 | [5 empty] | 2025-04-17 |  |  |  | 8 | 8. Product Add On | AC & DC Complete |  | 20% | 3888.1 |  | HappySolar - INV-0304 | 2025-04-30 | 11296.5648 |  | 2025-04-17
8 | [5 empty] | 2025-06-05 |  |  |  | 8 | 8. Product Add On | Retention |  | 5% | 972.025 |  | HappySolar - INV-0312 | 2025-05-31 | 2824.1412 |  | 2025-06-05
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
8 | [5 empty] | 2025-05-29 |  |  |  | 8 | 8. Product Add On | Huawei 50KTL |  |  | 43190.78 | PO3775-CASS-20250328 - RV Approved | Menlo Inv0002791 | 2025-04-30 | 125487.3701 |  | 2025-05-29
8 | [5 empty] | 2025-05-29 |  |  |  | 8 | 8. Product Add On | Smartlogger |  |  | 8598.34 | PO3775-CASS-20250328 - RV Approved | Menlo Inv0002791 | 2025-04-30 | 24981.7918 |  | 2025-05-29
8 | [5 empty] | 2025-04-30 |  |  |  | 8 | 8. Product Add On | Router |  |  | 2770 | PO3778-CASS-20250331 - RV Approved | ACCUENERGY - INV ASAI-005156 | 2025-04-30 | 8048.0143 |  | 2025-04-30
8 | [9 empty] | 8 | 8. Product Add On | [7 empty] | 0
Only services to be capture below, products above
9 | AC & DC Installation | AC Installation |  |  | 4500 | 2025-04-17 | 14818.97 | 17434.08 |  | 9 | 9. AC & DC installation | [7 empty] | 0 | 0 |  | 64015.25
9 |  | DC Installation |  |  | 10318.97 | 2025-04-03 |  |  |  | 9 | 9. AC & DC installation | Inverter Upgrade - Deposit | 64015.5 | 50% | 32007.5 | PO3777-CASS-20250331 - RV Approved | HappySolar - INV-0300 | 2025-04-30 | 8717.006 |  | 2025-04-03
9 | [5 empty] | 2025-04-17 |  |  |  | 9 | 9. AC & DC installation | Equipment Onsite |  | 25% | 16003.875 |  | HappySolar - INV-0303 | 2025-04-30 | 4358.537 |  | 2025-04-17
9 | [5 empty] | 2025-04-17 |  |  |  | 9 | 9. AC & DC installation | AC & DC Complete |  | 20% | 12803.1 |  | HappySolar - INV-0304 | 2025-04-30 | 3486.8296 |  | 2025-04-17
9 | [5 empty] | 2025-06-05 |  |  |  | 9 | 9. AC & DC installation | Retention |  | 5% | 3200.775 |  | HappySolar - INV-0312 | 2025-05-31 | 871.7074 |  | 2025-06-05
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
9 | [9 empty] | 9 | 9. AC & DC installation | [7 empty] | 0
10 | Site Logistics | [5 empty] | 0 |  |  | 10 | 10. Site Logistics | [8 empty] | 0 |  | 0
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
10 | [9 empty] | 10 | 10. Site Logistics
11 | Due Dilligence | [5 empty] | 0 |  |  | 11 | 11. Due Dilligence | Electrical PrEng sign off |  |  | 0 | MI - Cost removed as per AG - 12 May | [5 empty] | 0
11 | [9 empty] | 11 | 11. Due Dilligence
11 | [9 empty] | 11 | 11. Due Dilligence
11 | [9 empty] | 11 | 11. Due Dilligence
11 | [9 empty] | 11 | 11. Due Dilligence
12 | BDP Commission | [5 empty] | 0 |  |  | 12 | 12. BDP Commission | [10 empty] | 0
12 | BDP Commission | [8 empty] | 12 | 12. BDP Commission
13 | Engineering | [5 empty] | 0 |  |  | 13 | 13. Engineering | [8 empty] | 0 |  | 0
13 | [9 empty] | 13 | 13. Engineering
13 | [9 empty] | 13 | 13. Engineering
13 | [9 empty] | 13 | 13. Engineering
13 | [9 empty] | 13 | 13. Engineering
13 | [9 empty] | 13 | 13. Engineering
14 | General Expenses | [5 empty] | 0 |  |  | 14 | 14. General Expenses | Travel |  |  | 357 |  | Expense Claim | 2025-04-30 |  | 0 | 2025-05-08 | 357
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-05-31 |  |  | 2025-06-07
14 | [9 empty] | 14 | 14. General Expenses | Travel |  |  | 0 |  | Expense Claim | 2025-06-30 |  |  | 2025-07-07
14 | [9 empty] | 14 | 14. General Expenses
14 | [9 empty] | 14 | 14. General Expenses
14 | [9 empty] | 14 | 14. General Expenses
14 | [9 empty] | 14 | 14. General Expenses
14 | [9 empty] | 14 | 14. General Expenses
14 | [9 empty] | 14 | 14. General Expenses
14 | [9 empty] | 14 | 14. General Expenses
14 | [9 empty] | 14 | 14. General Expenses
14 | [9 empty] | 14 | 14. General Expenses
15 | Service Add On | [5 empty] | 0 |  |  | 15 | 15. Service Add On | [8 empty] | 0 |  | 0
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
15 | [9 empty] | 15 | 15. Service Add On
| Panel Procurement Budget | 136107.277
| Inverter Procurement Budget | 51963.0691
| Mounting Structure Budget | 70380.5311
| DC Equipment Budget | 96448.2696
| AC Equipment Budget | 150576.8264
| Monitoring Budget | 44852.3333
| Optional Extras Budget | 0
| MV Metering Budget | 0
| ADD ON | 0
| Battery System | 0
| Generator | 0
Services
| AC Installer Budget | 13711.7647
| DC Installer Budget | 32858.8235
| In-House Expense Budget | 50016.3994
| Compliance Budget | 34117.6471
| Offloading Budget | 10000
| Roof Access Budget for Equipment | 0
| Site storage | 0
| On Site Security | 14117.6471
| Roof Access Budget for Installers | 20010
| EPC Management Fee | 0
| ADD ON | 0
Expenses
| Total EE Expense Budget | 1029.4118

## Cashflow
[RT: Double Check the first date is always a MONDAY] | time axis 2025-01-20 to 2030-12-30
PLANNED |  | CHECK | CHECK
| Planned Revenue | 261790.45 | 261790.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21815.8708 | 0 | 0 | 0 | 21815.8708 | 0 | 0 | 0 | 0 | 21815.8708 | 0 | 0 | 0 | 21815.8708 | 0 | 0 | 0 | 21815.8708 | 0 | 0 | 0 | 21815.8708 | 0 | 0 | 0 | 0 | 21815.8708 | 0 | 0 | 0 | 21815.8708 | 0 | 0 | 0 | 21815.8708 | 0 | 0 | 0 | 21815.8708 | 0 | 0 | 0 | 0 | 21815.8708 | 0 | 0 | 0 | 21815.8708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21815.8708 | 21815.8708 | 21815.8708 | 21815.8708 | 43631.7417 | 43631.7417 | 43631.7417 | 43631.7417 | 43631.7417 | 65447.6125 | 65447.6125 | 65447.6125 | 65447.6125 | 87263.4833 | 87263.4833 | 87263.4833 | 87263.4833 | 109079.3542 | 109079.3542 | 109079.3542 | 109079.3542 | 130895.225 | 130895.225 | 130895.225 | 130895.225 | 130895.225 | 152711.0958 | 152711.0958 | 152711.0958 | 152711.0958 | 174526.9667 | 174526.9667 | 174526.9667 | 174526.9667 | 196342.8375 | 196342.8375 | 196342.8375 | 196342.8375 | 218158.7083 | 218158.7083 | 218158.7083 | 218158.7083 | 218158.7083 | 239974.5792 | 239974.5792 | 239974.5792 | 239974.5792 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45
| Planned Expenditure | 210304.07 | 210304.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183804.07 | 0 | 26500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183804.07 | 183804.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07 | 210304.07
| PLANNED CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -183804.07 | -183804.07 | -210304.07 | -210304.07 | -210304.07 | -210304.07 | -210304.07 | -210304.07 | -210304.07 | -210304.07 | -210304.07 | -188488.1992 | -188488.1992 | -188488.1992 | -188488.1992 | -166672.3283 | -166672.3283 | -166672.3283 | -166672.3283 | -166672.3283 | -144856.4575 | -144856.4575 | -144856.4575 | -144856.4575 | -123040.5867 | -123040.5867 | -123040.5867 | -123040.5867 | -101224.7158 | -101224.7158 | -101224.7158 | -101224.7158 | -79408.845 | -79408.845 | -79408.845 | -79408.845 | -79408.845 | -57592.9742 | -57592.9742 | -57592.9742 | -57592.9742 | -35777.1033 | -35777.1033 | -35777.1033 | -35777.1033 | -13961.2325 | -13961.2325 | -13961.2325 | -13961.2325 | 7854.6383 | 7854.6383 | 7854.6383 | 7854.6383 | 7854.6383 | 29670.5092 | 29670.5092 | 29670.5092 | 29670.5092 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38 | 51486.38
ACTUAL |  | CHECK | CHECK
| Actual + Planned Revenue | 261790.45 | 261790.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21815.8708 | 0 | 0 | 0 | 21815.8708 | 0 | 0 | 0 | 0 | 21815.8708 | 0 | 0 | 0 | 21815.8708 | 0 | 0 | 0 | 21815.8708 | 0 | 0 | 0 | 0 | 0 | 0 | 21815.8708 | 0 | 21815.8708 | 0 | 0 | 0 | 21815.8708 | 0 | 0 | 0 | 0 | 0 | 21815.8708 | 0 | 21815.8708 | 0 | 0 | 0 | 0 | 21815.8708 | 0 | 0 | 0 | 21815.8708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Revenue - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21815.8708 | 21815.8708 | 21815.8708 | 21815.8708 | 43631.7417 | 43631.7417 | 43631.7417 | 43631.7417 | 43631.7417 | 65447.6125 | 65447.6125 | 65447.6125 | 65447.6125 | 87263.4833 | 87263.4833 | 87263.4833 | 87263.4833 | 109079.3542 | 109079.3542 | 109079.3542 | 109079.3542 | 109079.3542 | 109079.3542 | 109079.3542 | 130895.225 | 130895.225 | 152711.0958 | 152711.0958 | 152711.0958 | 152711.0958 | 174526.9667 | 174526.9667 | 174526.9667 | 174526.9667 | 174526.9667 | 174526.9667 | 196342.8375 | 196342.8375 | 218158.7083 | 218158.7083 | 218158.7083 | 218158.7083 | 218158.7083 | 239974.5792 | 239974.5792 | 239974.5792 | 239974.5792 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45
| Actual + Planned Expenditure | 183007.37 | 183007.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64045.5 | 0 | 57641.175 | 0 | 2770 | 357 | 0 | 0 | 51789.12 | 6404.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual + Planned Expenditure - Cumulative |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64045.5 | 64045.5 | 121686.675 | 121686.675 | 124456.675 | 124813.675 | 124813.675 | 124813.675 | 176602.795 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37 | 183007.37
| ACTUAL CashFlow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -64045.5 | -64045.5 | -121686.675 | -121686.675 | -124456.675 | -124813.675 | -124813.675 | -124813.675 | -176602.795 | -183007.37 | -183007.37 | -161191.4992 | -161191.4992 | -161191.4992 | -161191.4992 | -139375.6283 | -139375.6283 | -139375.6283 | -139375.6283 | -139375.6283 | -117559.7575 | -117559.7575 | -117559.7575 | -117559.7575 | -95743.8867 | -95743.8867 | -95743.8867 | -95743.8867 | -73928.0158 | -73928.0158 | -73928.0158 | -73928.0158 | -73928.0158 | -73928.0158 | -73928.0158 | -52112.145 | -52112.145 | -30296.2742 | -30296.2742 | -30296.2742 | -30296.2742 | -8480.4033 | -8480.4033 | -8480.4033 | -8480.4033 | -8480.4033 | -8480.4033 | 13335.4675 | 13335.4675 | 35151.3383 | 35151.3383 | 35151.3383 | 35151.3383 | 35151.3383 | 56967.2092 | 56967.2092 | 56967.2092 | 56967.2092 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08 | 78783.08
|  | CHECK | CHECK
| Revenue Recognition | 0 | 261790.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256626.7829 | 0 | 0 | 0 | 5163.6671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Recognition Cumulative | 0 | 261790.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256626.7829 | 256626.7829 | 256626.7829 | 256626.7829 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45 | 261790.45

## Finance - Revenue
Sum of REVENUE RECOGNITION AMOUNT | Column Labels
Row Labels | (blank) | 2025-06-30 |  | 2025-04-30 | 2025-05-31 | Grand Total
(blank)
1. Panels
2. Inverters
3. Mounting Structures
4. DC Equipment
5. Monitoring
6. AC Equipment | 0 |  |  | 27888.5515 | 1467.8185 | 29356.37
8. Product Add On |  |  | 0 | 212175.8588 | 2824.1412 | 215000
9. AC & DC installation | 0 |  |  | 16562.3726 | 871.7074 | 17434.08
10. Site Logistics
11. Due Dilligence
13. Engineering
14. General Expenses
15. Service Add On
12. BDP Commission
7.BESS
Grand Total | 0 |  | 0 | 256626.7829 | 5163.6671 | 261790.45

## Finance - COS
Sum of Actual Total | Column Labels
Row Labels | (blank) | 2025-04-30 | 2025-05-31 | 2025-06-30 | Grand Total
(blank)
1. Panels
2. Inverters
3. Mounting Structures
4. DC Equipment
5. Monitoring
6. AC Equipment |  | 42403.725 | 2231.775 |  | 44635.5
8. Product Add On |  | 73027.595 | 972.025 |  | 73999.62 | 118635.12
9. AC & DC installation |  | 60814.475 | 3200.775 |  | 64015.25
10. Site Logistics
11. Due Dilligence | 0 |  |  |  | 0
13. Engineering
14. General Expenses |  | 357 | 0 | 0 | 357
15. Service Add On
12. BDP Commission
7.BESS
Grand Total | 0 | 176602.795 | 6404.575 | 0 | 183007.37

## Project Margins (hidden)
[capture project margins from costing sheet]
Products | 32%
Services | 50%
Expenses | 15%
Subcontractors | 20%

## Equipment Quotes (hidden)
Equipment Quote and Budget comparision
Description | Budget | Supplier 1 | Variance | Supplier 2 | Variance | Comments / Notes
|  | >Name< |  | >Name<
Inverters | #REF! | 0 | #REF! | 0 | #REF!
Inverters | #REF!
Optimizers | #REF!
Warranty
Delivery fee
|  | >Name< |  | >Name<
Mounting Structure | #REF! | 0 | #REF! | 0 | #REF!
Mounting Structure | #REF!
Delivery fee
|  | >Name< |  | >Name<
DC Cable | #REF! | 0 | #REF! | 0 | #REF!
DC Cable | #REF!
Delivery fee
|  | >Name< |  | >Name<
Monitoring system | #REF! | 0 | #REF! | 0 | #REF!
#REF! | #REF!
#REF! | #REF!
Delivery fee
|  | >Name< |  | >Name<
Additional Scope | #REF! | 0 | #REF! | 0 | #REF!
SCADA | #REF!
Inverter cage
Cat ladders
Gen Integration
Lifelines
Totals | #REF! |  | #REF! |  | #REF!
All amounts are incl VAT

## Installer Quotes (hidden)
Installer Quote and Budget comparision
Description | Budget |  | Cosmic Sun |  | Variance | Matthews Group |  | Variance
AC Equipment | #REF! | #REF! | 277892.91 | 5.5579 | #REF! |  | 0 | #REF!
DC Equipment | #REF! | #REF! | 142158.25 | 2.8432 | #REF! |  | 0 | #REF!
AC Labour | #REF! | #REF! | 96174 | 1.9235 | #REF! |  | 0 | #REF!
DC Labour | #REF! | #REF! | 230160 | 4.6032 | #REF! |  | 0 | #REF!
Offloading | #REF! |  | 0 |  | #REF! |  |  | #REF!
Roof Access/Scaffolding | #REF! |  | 29257.61 |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Telehandler | #REF!
HSE | 0
Totals | #REF! |  | 775642.77 |  | #REF! | 0 |  | #REF!
Description | Budget |  | >Installer Name 3< |  | Variance | >Installer Name 4< |  | Variance
AC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
AC equipment | #REF! | #REF! |  |  | #REF! |  | 0 | #REF!
DC installation | #REF! | #REF! |  | 0 | #REF! |  | 0 | #REF!
DC equipment | #REF! | #REF! |  |  | #REF! |  |  | #REF!
Storage | #REF! |  |  |  | #REF! |  |  | #REF!
Panel lifting equipment | #REF! |  |  |  | #REF! |  |  | #REF!
Offloading | #REF! |  |  |  | #REF! |  |  | #REF!
Totals | #REF! |  | 0 |  | #REF! | 0 |  | #REF!
Budget Summary
Budget | #REF!
Cosmic Sun | 775642.77
Matthews Group | 0
>Installer Name 3< | 0
>Installer Name 4< | 0
#REF! | #REF!
All amounts are exc VAT

## Decision Register (hidden)
Cassia |  |  | Decision Register
ID | Decision Description | Decision Impact | Proposed Date | Proposed By | Status | Approved By | Date | Results / Comments
DEC001
DEC002
DEC003
DEC004
DEC005
DEC006
DEC007
DEC008
DEC009
DEC010
|  | Cassia | 0 | 0 | 0